## Sheet1
1.01 | Field | Scala Penetrometer Cohesive soils only | RITS Table 3-20 | NZS 4402.6.5.2:1988 | 1m inside of edge of seal and along centerline, Both lanes, at 10m spacing Minimum of 10 tests and/or at a frequency of 2 test per 10m chainage, whichever qty is greater | Confirm design assumptions - Scalar reaches minimum 2 blows/100mm | Test Record | QA / SE | 1.01 - Field | Material Test Method Requirement - Scala Penetrometer Cohesive soils only | Reference Documents - RITS Table 3-20 | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988 | Material Test Frequency - 1m inside of edge of seal and along centerline, Both lanes, at 10m spacing Minimum of 10 tests and/or at a frequency of 2 test per 10m chainage, whichever qty is greater | Target Criteria - Confirm design assumptions - Scalar reaches minimum 2 blows/100mm | Action Point Records required - Test Record | Responsibility - QA / SE | 1.01 - Field
1.02 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | +0mm/-30m from design or nominated level No more than 15mm deviation from a 3m straight edge | Survey record | QA / SE | 1.02 - Field | Material Test Method Requirement - Surface Level, Shape, and crossfall | Reference Documents - RITS Table 3.24 | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1 | Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | Target Criteria - +0mm/-30m from design or nominated level No more than 15mm deviation from a 3m straight edge | Action Point Records required - Survey record | Responsibility - QA / SE | Material Test Method Requirement - Scala Penetrometer Cohesive soils only
1.03 | Field | Geogrid and Geofabric (cloth) installation | ISO:G 032 Version 2 | Manufracture installation instructions | 100% of Surface | Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints. Geogrid and Geofabric shall be neatly installed without creases or folds. | Site Record | QA / SE | 1.03 - Field | Material Test Method Requirement - Geogrid and Geofabric (cloth) installation | Reference Documents - ISO:G 032 Version 2 | Material Acceptance Criteria (Method) - Manufracture installation instructions | Material Test Frequency - 100% of Surface | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints. Geogrid and Geofabric shall be neatly installed without creases or folds. | Action Point Records required - Site Record | Responsibility - QA / SE | Reference Documents - RITS Table 3-20
1.04 | PE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to placement of material | PQE Approval All testing record CHAR(AMP) reviewed as comliant. Available Documents: Test records Survey records Hold Point Records | Hold Point | PM | 1.04 - PE | Material Test Method Requirement - Is the layer closed out ? | Reference Documents - See PQE | Material Acceptance Criteria (Method) - See PQE | Material Test Frequency - 100% of Surface Prior to placement of material | Target Criteria - PQE Approval All testing record CHAR(AMP) reviewed as comliant. Available Documents: Test records Survey records Hold Point Records | Action Point Records required - Hold Point | Responsibility - PM | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
2.01 | PE | Has the material used in this layer been formally accepted for use? | Insert Material Testing link | See PQE | Prior to construction commencing | Material meets project requirements | Hold Point | QA / SE | 2.01 - PE | Material Test Method Requirement - Has the material used in this layer been formally accepted for use? | Reference Documents - Insert Material Testing link | Material Acceptance Criteria (Method) - See PQE | Material Test Frequency - Prior to construction commencing | Target Criteria - Material meets project requirements | Action Point Records required - Hold Point | Responsibility - QA / SE | Material Test Frequency - 1m inside of edge of seal and along centerline, Both lanes, at 10m spacing Minimum of 10 tests and/or at a frequency of 2 test per 10m chainage, whichever qty is greater
2.02 | Field | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer | N/A | Hold Point Test Record | QA / SE | 2.02 - Field | Material Test Method Requirement - Plateau Density Test | Reference Documents - TNZ B/02: 2005 | Material Acceptance Criteria (Method) - TNZ B/02: 2005 | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer | Target Criteria - N/A | Action Point Records required - Hold Point Test Record | Responsibility - QA / SE | Target Criteria - Confirm design assumptions - Scalar reaches minimum 2 blows/100mm
2.03 | Field | Clegg Hammer | RITS Table 3-21 | RITS 3.8.3.3 ASTM D5874-16 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | CIV ≥ 35 | Test Record | QA / SE | 2.03 - Field | Material Test Method Requirement - Clegg Hammer | Reference Documents - RITS Table 3-21 | Material Acceptance Criteria (Method) - RITS 3.8.3.3 ASTM D5874-16 | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | Target Criteria - CIV ≥ 35 | Action Point Records required - Test Record | Responsibility - QA / SE | Action Point Records required - Test Record
2.04 | Field | Compaction NDM Back Scatter | RITS Table 3-22 | RITS 3.8.3.4 4407:2015 test 4.3 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | Mean ≥ 95 % MDD Minimum ≥ 92% MDD | Test Record | QA / SE | 2.04 - Field | Material Test Method Requirement - Compaction NDM Back Scatter | Reference Documents - RITS Table 3-22 | Material Acceptance Criteria (Method) - RITS 3.8.3.4 4407:2015 test 4.3 | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | Target Criteria - Mean ≥ 95 % MDD Minimum ≥ 92% MDD | Action Point Records required - Test Record | Responsibility - QA / SE | Responsibility - QA / SE
2.05 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | +5mm/-25m from design or nominated level No more than 15mm deviation from a 3m straight edge | Survey record | QA / SE | 2.05 - Field | Material Test Method Requirement - Surface Level, Shape, and crossfall | Reference Documents - RITS Table 3.24 | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1 | Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | Target Criteria - +5mm/-25m from design or nominated level No more than 15mm deviation from a 3m straight edge | Action Point Records required - Survey record | Responsibility - QA / SE | 1.02 - Field
2.06 | PE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to placement of material | PQE Approval All testing record CHAR(AMP) reviewed as comliant. Available Documents: Test records Survey records Hold Point Records | Hold Point | PM | 2.06 - PE | Material Test Method Requirement - Is the layer closed out ? | Reference Documents - See PQE | Material Acceptance Criteria (Method) - See PQE | Material Test Frequency - 100% of Surface Prior to placement of material | Target Criteria - PQE Approval All testing record CHAR(AMP) reviewed as comliant. Available Documents: Test records Survey records Hold Point Records | Action Point Records required - Hold Point | Responsibility - PM | Material Test Method Requirement - Surface Level, Shape, and crossfall
3.01 | PE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements | Hold Point | QA / SE | 3.01 - PE | Material Test Method Requirement - Seal Design | Reference Documents - INSERT SEAL DESIGN | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application) | Target Criteria - Meets project requirements | Action Point Records required - Hold Point | Responsibility - QA / SE | Reference Documents - RITS Table 3.24
3.02 | PE | Bitumen Sprayer | TNZ P3 | Certification provided | Prior to starting | Current E/2 Certificate | Certificate Sheet | QA / SE | 3.02 - PE | Material Test Method Requirement - Bitumen Sprayer | Reference Documents - TNZ P3 | Material Acceptance Criteria (Method) - Certification provided | Material Test Frequency - Prior to starting | Target Criteria - Current E/2 Certificate | Action Point Records required - Certificate Sheet | Responsibility - QA / SE | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
3.03 | PE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements | Hold Point | QA / SE | 3.03 - PE | Material Test Method Requirement - Has the material used in this layer been formally accepted for use? | Reference Documents - Insert Material Testing | Material Acceptance Criteria (Method) - See PQE | Material Test Frequency - Prior to construction commencing | Target Criteria - Material meets project requirements | Action Point Records required - Hold Point | Responsibility - QA / SE | Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
3.04 | Field | Preseal Inspection | TNZ B/02: 2005 | TNZ B/02: 2005 | 100% of Surface Prior to sealing of surface | All loose aggregate, dirt, dust, silt and deleterious matter has been removed. | Test Record | QA / SE | 3.04 - Field | Material Test Method Requirement - Preseal Inspection | Reference Documents - TNZ B/02: 2005 | Material Acceptance Criteria (Method) - TNZ B/02: 2005 | Material Test Frequency - 100% of Surface Prior to sealing of surface | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed. | Action Point Records required - Test Record | Responsibility - QA / SE | Target Criteria - +0mm/-30m from design or nominated level No more than 15mm deviation from a 3m straight edge
3.05 | Field | GO/NO GO Survey | Downers processes | Downer survey sealing GO/NO GO,Road science Zeus app CHAR(AMP) Downer Iris app | Prior to sealing on each site | Pass on GO/NO GO ,Marginal CHAR(AMP) discussion with contract Manager or Written approval from Rehab manager | Survey record | QA / SE | 3.05 - Field | Material Test Method Requirement - GO/NO GO Survey | Reference Documents - Downers processes | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app CHAR(AMP) Downer Iris app | Material Test Frequency - Prior to sealing on each site | Target Criteria - Pass on GO/NO GO ,Marginal CHAR(AMP) discussion with contract Manager or Written approval from Rehab manager | Action Point Records required - Survey record | Responsibility - QA / SE | Action Point Records required - Survey record
3.06 | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate | Spray Sheet | QA / SE | 3.06 - Field | Material Test Method Requirement - Application Rate | Reference Documents - TNZ P/3 : 1995.18 | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate | Action Point Records required - Spray Sheet | Responsibility - QA / SE | Responsibility - QA / SE
3.07 | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose | Witness Point | QA / SE | 3.07 - Field | Material Test Method Requirement - Post Seal Inspection | Reference Documents - TNZ P3: 1995 | Material Acceptance Criteria (Method) - Engineers Inspection | Material Test Frequency - After sealing | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose | Action Point Records required - Witness Point | Responsibility - QA / SE | 1.03 - Field
4.01 | PE | Has the material used in this layer been formally accepted for use? | Insert Asphalt Design CHAR(AMP) Material Records NZTA -M32 Specification for high modulus asphalt EME 2) | Approved Treatment Design | Prior to paving works commencing | Treatment Design validation | Hold Point | QA / SE | 4.01 - PE | Material Test Method Requirement - Has the material used in this layer been formally accepted for use? | Reference Documents - Insert Asphalt Design CHAR(AMP) Material Records NZTA -M32 Specification for high modulus asphalt EME 2) | Material Acceptance Criteria (Method) - Approved Treatment Design | Material Test Frequency - Prior to paving works commencing | Target Criteria - Treatment Design validation | Action Point Records required - Hold Point | Responsibility - QA / SE | Material Test Method Requirement - Geogrid and Geofabric (cloth) installation
4.02 | Lab | In-situ mat density calibration cores | NZTA M32: 2021, 9.8.1 | ASTM D5361 | 1 test per 300m² per layer (Min 8 / Construction lot) 1 test per 100m per layer length (min 3 / Construction lot) | Characteristic value - mix design air void +3% -2% | Hold Point | QA / SE | 4.02 - Lab | Material Test Method Requirement - In-situ mat density calibration cores | Reference Documents - NZTA M32: 2021, 9.8.1 | Material Acceptance Criteria (Method) - ASTM D5361 | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot) 1 test per 100m per layer length (min 3 / Construction lot) | Target Criteria - Characteristic value - mix design air void +3% -2% | Action Point Records required - Hold Point | Responsibility - QA / SE | Reference Documents - ISO:G 032 Version 2
4.03 | Lab | Grading (Particle Size Distribution) | NZTA M32: 2021, 5.3 | NZS 4407:2015 test 3.8 | One test per 200 tonnes of production | Tolerance from nominated JMF grading as per NZTA M32: 2021, Table 5.3 | Test record | QA / SE | 4.03 - Lab | Material Test Method Requirement - Grading (Particle Size Distribution) | Reference Documents - NZTA M32: 2021, 5.3 | Material Acceptance Criteria (Method) - NZS 4407:2015 test 3.8 | Material Test Frequency - One test per 200 tonnes of production | Target Criteria - Tolerance from nominated JMF grading as per NZTA M32: 2021, Table 5.3 | Action Point Records required - Test record | Responsibility - QA / SE | Material Acceptance Criteria (Method) - Manufracture installation instructions
4.04 | Lab | Binder content | NZTA M32: 2021, 5.3 | ASTM D2172 | One test per 200 tonnes of production | Tolerance on JMF Individual ±0.5 Rolling Average of 3 ±0.3% |  | QA / SE | 4.04 - Lab | Material Test Method Requirement - Binder content | Reference Documents - NZTA M32: 2021, 5.3 | Material Acceptance Criteria (Method) - ASTM D2172 | Material Test Frequency - One test per 200 tonnes of production | Target Criteria - Tolerance on JMF Individual ±0.5 Rolling Average of 3 ±0.3% | Action Point Records required - | Responsibility - QA / SE | Material Test Frequency - 100% of Surface
4.05 | Lab | Maximum Theoratical Specific Gravity | NZTA M32: 2021, 5.3 | ASTM D2041 | One test per 200 tonnes of production | Report Value |  | QA / SE | 4.05 - Lab | Material Test Method Requirement - Maximum Theoratical Specific Gravity | Reference Documents - NZTA M32: 2021, 5.3 | Material Acceptance Criteria (Method) - ASTM D2041 | Material Test Frequency - One test per 200 tonnes of production | Target Criteria - Report Value | Action Point Records required - | Responsibility - QA / SE | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints. Geogrid and Geofabric shall be neatly installed without creases or folds.
4.06 | Lab | Air Voids | NZTA M32: 2021, 5.3 | ASTM D3203-22 | One test per 600 tonnes of production | As specified for each mix type |  | QA / SE | 4.06 - Lab | Material Test Method Requirement - Air Voids | Reference Documents - NZTA M32: 2021, 5.3 | Material Acceptance Criteria (Method) - ASTM D3203-22 | Material Test Frequency - One test per 600 tonnes of production | Target Criteria - As specified for each mix type | Action Point Records required - | Responsibility - QA / SE | Action Point Records required - Site Record
4.07 | Field | Load Locate | Downer Procedures | Each load can be indentified to a location. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | Every Load | All data is collected | QA Sheet | QA / SE | 4.07 - Field | Material Test Method Requirement - Load Locate | Reference Documents - Downer Procedures | Material Acceptance Criteria (Method) - Each load can be indentified to a location. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | Material Test Frequency - Every Load | Target Criteria - All data is collected | Action Point Records required - QA Sheet | Responsibility - QA / SE | Responsibility - QA / SE
4.08 | Field | NDM Density Testing On-Site Mat and Joint | NZTA M32: 2021, 9.8 Table 9.2 | ASTM D2950 ASTM D5361 | 1 test per 300m² per layer (Min 8 / Construction lot) 1 test per 100m per layer length (min 3 / Construction lot) | Mat: Mean air voids JMF +3,-2 Join: Mean air voids JMF +5,-2 | Test record | QA / SE | 4.08 - Field | Material Test Method Requirement - NDM Density Testing On-Site Mat and Joint | Reference Documents - NZTA M32: 2021, 9.8 Table 9.2 | Material Acceptance Criteria (Method) - ASTM D2950 ASTM D5361 | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot) 1 test per 100m per layer length (min 3 / Construction lot) | Target Criteria - Mat: Mean air voids JMF +3,-2 Join: Mean air voids JMF +5,-2 | Action Point Records required - Test record | Responsibility - QA / SE | 1.04 - PE
4.09 | Field | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | 1 test per site | N/A | Test Record | QA / SE | 4.09 - Field | Material Test Method Requirement - Plateau Density Test | Reference Documents - TNZ B/02: 2005 | Material Acceptance Criteria (Method) - TNZ B/02: 2005 | Material Test Frequency - 1 test per site | Target Criteria - N/A | Action Point Records required - Test Record | Responsibility - QA / SE | Material Test Method Requirement - Is the layer closed out ?
4.1 | Field | Surface Level- Stringline checks for validation | NZTA M32:2021 10.2 and 10.3 Downer Procedures | Contract Specifications | 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | +15mm/-5mm from design or nominated level No more than 8mm deviaton from a 3m straight edge | Survey record | QA / SE | 4.1 - Field | Material Test Method Requirement - Surface Level- Stringline checks for validation | Reference Documents - NZTA M32:2021 10.2 and 10.3 Downer Procedures | Material Acceptance Criteria (Method) - Contract Specifications | Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | Target Criteria - +15mm/-5mm from design or nominated level No more than 8mm deviaton from a 3m straight edge | Action Point Records required - Survey record | Responsibility - QA / SE | Reference Documents - See PQE
4.11 | Field | Post Surfacing Inspection | CCA Procedures | Contract Specifications | 100% of site After surfacing (within 5 days) | Line marking has been reinstated All excess material has been removed from site All CPs are clear from filter fabric and any excess material removed from on top service covers | Survey record | PM | 4.11 - Field | Material Test Method Requirement - Post Surfacing Inspection | Reference Documents - CCA Procedures | Material Acceptance Criteria (Method) - Contract Specifications | Material Test Frequency - 100% of site After surfacing (within 5 days) | Target Criteria - Line marking has been reinstated All excess material has been removed from site All CPs are clear from filter fabric and any excess material removed from on top service covers | Action Point Records required - Survey record | Responsibility - PM | Material Acceptance Criteria (Method) - See PQE
5.01 | PE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements | Hold Point | QA / SE | 5.01 - PE | Material Test Method Requirement - Seal Design | Reference Documents - INSERT SEAL DESIGN | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application) | Target Criteria - Meets project requirements | Action Point Records required - Hold Point | Responsibility - QA / SE | Material Test Frequency - 100% of Surface Prior to placement of material
5.02 | PE | Bitumen Sprayer | TNZ P3 | Certification provided | Prior to starting | Current E/2 Certificate | Certificate Sheet | QA / SE | 5.02 - PE | Material Test Method Requirement - Bitumen Sprayer | Reference Documents - TNZ P3 | Material Acceptance Criteria (Method) - Certification provided | Material Test Frequency - Prior to starting | Target Criteria - Current E/2 Certificate | Action Point Records required - Certificate Sheet | Responsibility - QA / SE | Target Criteria - PQE Approval All testing record CHAR(AMP) reviewed as comliant. Available Documents: Test records Survey records Hold Point Records
5.03 | PE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements | Hold Point | QA / SE | 5.03 - PE | Material Test Method Requirement - Has the material used in this layer been formally accepted for use? | Reference Documents - Insert Material Testing | Material Acceptance Criteria (Method) - See PQE | Material Test Frequency - Prior to construction commencing | Target Criteria - Material meets project requirements | Action Point Records required - Hold Point | Responsibility - QA / SE | Action Point Records required - Hold Point
5.04 | Field | Preseal Inspection | TNZ B/02: 2005 | TNZ B/02: 2005 | 100% of Surface Prior to sealing of surface | All loose aggregate, dirt, dust, silt and deleterious matter has been removed. | Test Record | QA / SE | 5.04 - Field | Material Test Method Requirement - Preseal Inspection | Reference Documents - TNZ B/02: 2005 | Material Acceptance Criteria (Method) - TNZ B/02: 2005 | Material Test Frequency - 100% of Surface Prior to sealing of surface | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed. | Action Point Records required - Test Record | Responsibility - QA / SE | Responsibility - PM
5.05 | Field | Degree of Saturaton | TNZ B/02: 2005 | TNZ B/02: 2005 | 1 set of 5 per 1000m² - then 1 per 200m² | CHAR(LESS) 80 % Completed Max 48hrs before sealing | Test Record | QA / SE | 5.05 - Field | Material Test Method Requirement - Degree of Saturaton | Reference Documents - TNZ B/02: 2005 | Material Acceptance Criteria (Method) - TNZ B/02: 2005 | Material Test Frequency - 1 set of 5 per 1000m² - then 1 per 200m² | Target Criteria - CHAR(LESS) 80 % Completed Max 48hrs before sealing | Action Point Records required - Test Record | Responsibility - QA / SE | 2.01 - PE
5.06 | Field | GO/NO GO Survey | Downers processes | Downer survey sealing GO/NO GO,Road science Zeus app CHAR(AMP) Downer Iris app | Prior to sealing on each site | Pass on GO/NO GO ,Marginal CHAR(AMP) discussion with contract Manager or Written approval from Rehab manager | Survey record | QA / SE | 5.06 - Field | Material Test Method Requirement - GO/NO GO Survey | Reference Documents - Downers processes | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app CHAR(AMP) Downer Iris app | Material Test Frequency - Prior to sealing on each site | Target Criteria - Pass on GO/NO GO ,Marginal CHAR(AMP) discussion with contract Manager or Written approval from Rehab manager | Action Point Records required - Survey record | Responsibility - QA / SE | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
5.07 | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C | Spray sheet | QA / SE | 5.07 - Field | Material Test Method Requirement - Road temp | Reference Documents - TNZ P3:1995.18 | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing | Material Test Frequency - Once per day of sealing prior to sealing commencing | Target Criteria - Air temp >10°C | Action Point Records required - Spray sheet | Responsibility - QA / SE | Reference Documents - Insert Material Testing link
5.08 | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate | Spray Sheet | QA / SE | 5.08 - Field | Material Test Method Requirement - Application Rate | Reference Documents - TNZ P/3 : 1995.18 | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate | Action Point Records required - Spray Sheet | Responsibility - QA / SE | Material Acceptance Criteria (Method) - See PQE
5.09 | Field | Chip spread rate | TNZ P3: 1995.21 | area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Total amount of chip used to be calculated at end of days sealing | Visual checks meets seal design requirements | Witness Point/Spray sheet | QA / SE | 5.09 - Field | Material Test Method Requirement - Chip spread rate | Reference Documents - TNZ P3: 1995.21 | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing | Target Criteria - Visual checks meets seal design requirements | Action Point Records required - Witness Point/Spray sheet | Responsibility - QA / SE | Material Test Frequency - Prior to construction commencing
5.1 | Field | Rolling Checks | TNZ P3: 1995.22 | Sealing Record | for each sealing site per day | As per rolling requirements defined in TNZ P3: 1995.22. | Witness Point/Spray sheet | QA / SE | 5.1 - Field | Material Test Method Requirement - Rolling Checks | Reference Documents - TNZ P3: 1995.22 | Material Acceptance Criteria (Method) - Sealing Record | Material Test Frequency - for each sealing site per day | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22. | Action Point Records required - Witness Point/Spray sheet | Responsibility - QA / SE | Target Criteria - Material meets project requirements
5.11 | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose | Witness Point | QA / SE | 5.11 - Field | Material Test Method Requirement - Post Seal Inspection | Reference Documents - TNZ P3: 1995 | Material Acceptance Criteria (Method) - Engineers Inspection | Material Test Frequency - After sealing | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose | Action Point Records required - Witness Point | Responsibility - QA / SE | Action Point Records required - Hold Point
6.01 | PE | Asbuilt and RAMM Data | RAMM Update sheet | Asset Management Information Plan | After works complete | RAMM sheet 100% complete and accurate . | RAMM Asset Update sheet | PM | 6.01 - PE | Material Test Method Requirement - Asbuilt and RAMM Data | Reference Documents - RAMM Update sheet | Material Acceptance Criteria (Method) - Asset Management Information Plan | Material Test Frequency - After works complete | Target Criteria - RAMM sheet 100% complete and accurate . | Action Point Records required - RAMM Asset Update sheet | Responsibility - PM | Responsibility - QA / SE
6.02 | Field | Site Safety Audit |  |  |  |  | Test Record | PM | 6.02 - Field | Material Test Method Requirement - Site Safety Audit | Reference Documents - | Material Acceptance Criteria (Method) - | Material Test Frequency - | Target Criteria - | Action Point Records required - Test Record | Responsibility - PM | 2.02 - Field
Material Test Method Requirement - Plateau Density Test
Reference Documents - TNZ B/02: 2005
Material Acceptance Criteria (Method) - TNZ B/02: 2005
Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer
Target Criteria - N/A
Action Point Records required - Hold Point Test Record
Responsibility - QA / SE
2.03 - Field
Material Test Method Requirement - Clegg Hammer
Reference Documents - RITS Table 3-21
Material Acceptance Criteria (Method) - RITS 3.8.3.3 ASTM D5874-16
Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
Target Criteria - CIV ≥ 35
Action Point Records required - Test Record
Responsibility - QA / SE
2.04 - Field
Material Test Method Requirement - Compaction NDM Back Scatter
Reference Documents - RITS Table 3-22
Material Acceptance Criteria (Method) - RITS 3.8.3.4 4407:2015 test 4.3
Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
Target Criteria - Mean ≥ 95 % MDD Minimum ≥ 92% MDD
Action Point Records required - Test Record
Responsibility - QA / SE
2.05 - Field
Material Test Method Requirement - Surface Level, Shape, and crossfall
Reference Documents - RITS Table 3.24
Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
Target Criteria - +5mm/-25m from design or nominated level No more than 15mm deviation from a 3m straight edge
Action Point Records required - Survey record
Responsibility - QA / SE
2.06 - PE
Material Test Method Requirement - Is the layer closed out ?
Reference Documents - See PQE
Material Acceptance Criteria (Method) - See PQE
Material Test Frequency - 100% of Surface Prior to placement of material
Target Criteria - PQE Approval All testing record CHAR(AMP) reviewed as comliant. Available Documents: Test records Survey records Hold Point Records
Action Point Records required - Hold Point
Responsibility - PM
3.01 - PE
Material Test Method Requirement - Seal Design
Reference Documents - INSERT SEAL DESIGN
Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
Target Criteria - Meets project requirements
Action Point Records required - Hold Point
Responsibility - QA / SE
3.02 - PE
Material Test Method Requirement - Bitumen Sprayer
Reference Documents - TNZ P3
Material Acceptance Criteria (Method) - Certification provided
Material Test Frequency - Prior to starting
Target Criteria - Current E/2 Certificate
Action Point Records required - Certificate Sheet
Responsibility - QA / SE
3.03 - PE
Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
Reference Documents - Insert Material Testing
Material Acceptance Criteria (Method) - See PQE
Material Test Frequency - Prior to construction commencing
Target Criteria - Material meets project requirements
Action Point Records required - Hold Point
Responsibility - QA / SE
3.04 - Field
Material Test Method Requirement - Preseal Inspection
Reference Documents - TNZ B/02: 2005
Material Acceptance Criteria (Method) - TNZ B/02: 2005
Material Test Frequency - 100% of Surface Prior to sealing of surface
Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
Action Point Records required - Test Record
Responsibility - QA / SE
3.05 - Field
Material Test Method Requirement - GO/NO GO Survey
Reference Documents - Downers processes
Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app CHAR(AMP) Downer Iris app
Material Test Frequency - Prior to sealing on each site
Target Criteria - Pass on GO/NO GO ,Marginal CHAR(AMP) discussion with contract Manager or Written approval from Rehab manager
Action Point Records required - Survey record
Responsibility - QA / SE
3.06 - Field
Material Test Method Requirement - Application Rate
Reference Documents - TNZ P/3 : 1995.18
Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
Action Point Records required - Spray Sheet
Responsibility - QA / SE
3.07 - Field
Material Test Method Requirement - Post Seal Inspection
Reference Documents - TNZ P3: 1995
Material Acceptance Criteria (Method) - Engineers Inspection
Material Test Frequency - After sealing
Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
Action Point Records required - Witness Point
Responsibility - QA / SE
4.01 - PE
Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
Reference Documents - Insert Asphalt Design CHAR(AMP) Material Records NZTA -M32 Specification for high modulus asphalt EME 2)
Material Acceptance Criteria (Method) - Approved Treatment Design
Material Test Frequency - Prior to paving works commencing
Target Criteria - Treatment Design validation
Action Point Records required - Hold Point
Responsibility - QA / SE
4.02 - Lab
Material Test Method Requirement - In-situ mat density calibration cores
Reference Documents - NZTA M32: 2021, 9.8.1
Material Acceptance Criteria (Method) - ASTM D5361
Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot) 1 test per 100m per layer length (min 3 / Construction lot)
Target Criteria - Characteristic value - mix design air void +3% -2%
Action Point Records required - Hold Point
Responsibility - QA / SE
4.03 - Lab
Material Test Method Requirement - Grading (Particle Size Distribution)
Reference Documents - NZTA M32: 2021, 5.3
Material Acceptance Criteria (Method) - NZS 4407:2015 test 3.8
Material Test Frequency - One test per 200 tonnes of production
Target Criteria - Tolerance from nominated JMF grading as per NZTA M32: 2021, Table 5.3
Action Point Records required - Test record
Responsibility - QA / SE
4.04 - Lab
Material Test Method Requirement - Binder content
Reference Documents - NZTA M32: 2021, 5.3
Material Acceptance Criteria (Method) - ASTM D2172
Material Test Frequency - One test per 200 tonnes of production
Target Criteria - Tolerance on JMF Individual ±0.5 Rolling Average of 3 ±0.3%
Action Point Records required -
Responsibility - QA / SE
4.05 - Lab
Material Test Method Requirement - Maximum Theoratical Specific Gravity
Reference Documents - NZTA M32: 2021, 5.3
Material Acceptance Criteria (Method) - ASTM D2041
Material Test Frequency - One test per 200 tonnes of production
Target Criteria - Report Value
Action Point Records required -
Responsibility - QA / SE
4.06 - Lab
Material Test Method Requirement - Air Voids
Reference Documents - NZTA M32: 2021, 5.3
Material Acceptance Criteria (Method) - ASTM D3203-22
Material Test Frequency - One test per 600 tonnes of production
Target Criteria - As specified for each mix type
Action Point Records required -
Responsibility - QA / SE
4.07 - Field
Material Test Method Requirement - Load Locate
Reference Documents - Downer Procedures
Material Acceptance Criteria (Method) - Each load can be indentified to a location. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth
Material Test Frequency - Every Load
Target Criteria - All data is collected
Action Point Records required - QA Sheet
Responsibility - QA / SE
4.08 - Field
Material Test Method Requirement - NDM Density Testing On-Site Mat and Joint
Reference Documents - NZTA M32: 2021, 9.8 Table 9.2
Material Acceptance Criteria (Method) - ASTM D2950 ASTM D5361
Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot) 1 test per 100m per layer length (min 3 / Construction lot)
Target Criteria - Mat: Mean air voids JMF +3,-2 Join: Mean air voids JMF +5,-2
Action Point Records required - Test record
Responsibility - QA / SE
4.09 - Field
Material Test Method Requirement - Plateau Density Test
Reference Documents - TNZ B/02: 2005
Material Acceptance Criteria (Method) - TNZ B/02: 2005
Material Test Frequency - 1 test per site
Target Criteria - N/A
Action Point Records required - Test Record
Responsibility - QA / SE
4.1 - Field
Material Test Method Requirement - Surface Level- Stringline checks for validation
Reference Documents - NZTA M32:2021 10.2 and 10.3 Downer Procedures
Material Acceptance Criteria (Method) - Contract Specifications
Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
Target Criteria - +15mm/-5mm from design or nominated level No more than 8mm deviaton from a 3m straight edge
Action Point Records required - Survey record
Responsibility - QA / SE
4.11 - Field
Material Test Method Requirement - Post Surfacing Inspection
Reference Documents - CCA Procedures
Material Acceptance Criteria (Method) - Contract Specifications
Material Test Frequency - 100% of site After surfacing (within 5 days)
Target Criteria - Line marking has been reinstated All excess material has been removed from site All CPs are clear from filter fabric and any excess material removed from on top service covers
Action Point Records required - Survey record
Responsibility - PM
5.01 - PE
Material Test Method Requirement - Seal Design
Reference Documents - INSERT SEAL DESIGN
Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
Target Criteria - Meets project requirements
Action Point Records required - Hold Point
Responsibility - QA / SE
5.02 - PE
Material Test Method Requirement - Bitumen Sprayer
Reference Documents - TNZ P3
Material Acceptance Criteria (Method) - Certification provided
Material Test Frequency - Prior to starting
Target Criteria - Current E/2 Certificate
Action Point Records required - Certificate Sheet
Responsibility - QA / SE
5.03 - PE
Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
Reference Documents - Insert Material Testing
Material Acceptance Criteria (Method) - See PQE
Material Test Frequency - Prior to construction commencing
Target Criteria - Material meets project requirements
Action Point Records required - Hold Point
Responsibility - QA / SE
5.04 - Field
Material Test Method Requirement - Preseal Inspection
Reference Documents - TNZ B/02: 2005
Material Acceptance Criteria (Method) - TNZ B/02: 2005
Material Test Frequency - 100% of Surface Prior to sealing of surface
Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
Action Point Records required - Test Record
Responsibility - QA / SE
5.05 - Field
Material Test Method Requirement - Degree of Saturaton
Reference Documents - TNZ B/02: 2005
Material Acceptance Criteria (Method) - TNZ B/02: 2005
Material Test Frequency - 1 set of 5 per 1000m² - then 1 per 200m²
Target Criteria - CHAR(LESS) 80 % Completed Max 48hrs before sealing
Action Point Records required - Test Record
Responsibility - QA / SE
5.06 - Field
Material Test Method Requirement - GO/NO GO Survey
Reference Documents - Downers processes
Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app CHAR(AMP) Downer Iris app
Material Test Frequency - Prior to sealing on each site
Target Criteria - Pass on GO/NO GO ,Marginal CHAR(AMP) discussion with contract Manager or Written approval from Rehab manager
Action Point Records required - Survey record
Responsibility - QA / SE
5.07 - Field
Material Test Method Requirement - Road temp
Reference Documents - TNZ P3:1995.18
Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
Material Test Frequency - Once per day of sealing prior to sealing commencing
Target Criteria - Air temp >10°C
Action Point Records required - Spray sheet
Responsibility - QA / SE
5.08 - Field
Material Test Method Requirement - Application Rate
Reference Documents - TNZ P/3 : 1995.18
Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
Action Point Records required - Spray Sheet
Responsibility - QA / SE
5.09 - Field
Material Test Method Requirement - Chip spread rate
Reference Documents - TNZ P3: 1995.21
Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435)
Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
Target Criteria - Visual checks meets seal design requirements
Action Point Records required - Witness Point/Spray sheet
Responsibility - QA / SE
5.1 - Field
Material Test Method Requirement - Rolling Checks
Reference Documents - TNZ P3: 1995.22
Material Acceptance Criteria (Method) - Sealing Record
Material Test Frequency - for each sealing site per day
Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
Action Point Records required - Witness Point/Spray sheet
Responsibility - QA / SE
5.11 - Field
Material Test Method Requirement - Post Seal Inspection
Reference Documents - TNZ P3: 1995
Material Acceptance Criteria (Method) - Engineers Inspection
Material Test Frequency - After sealing
Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
Action Point Records required - Witness Point
Responsibility - QA / SE
6.01 - PE
Material Test Method Requirement - Asbuilt and RAMM Data
Reference Documents - RAMM Update sheet
Material Acceptance Criteria (Method) - Asset Management Information Plan
Material Test Frequency - After works complete
Target Criteria - RAMM sheet 100% complete and accurate .
Action Point Records required - RAMM Asset Update sheet
Responsibility - PM
6.02 - Field
Material Test Method Requirement - Site Safety Audit
Reference Documents -
Material Acceptance Criteria (Method) -
Material Test Frequency -
Target Criteria -
Action Point Records required - Test Record
Responsibility - PM