## Sheet1
Review of approved construction drawings and specifications | All drawings and specifications approved and up to date | WBS-SS-CI-SPC-007 | Review of approved construction drawings and specifications | All drawings and specifications approved and up to date | WBS-SS-CI-SPC-007 | Review of approved construction drawings and specifications
Verification of permits | All relevant permits (GDA/GDP) in place | GDA/GDP | Verification of permits | All relevant permits (GDA/GDP) in place | GDA/GDP | All drawings and specifications approved and up to date
Site access and safety preparation | Site access cleared and made safe | WBS-SS-CI-SPC-007 | Site access and safety preparation | Site access cleared and made safe | WBS-SS-CI-SPC-007 | WBS-SS-CI-SPC-007
Safety inductions and toolbox talks | All personnel inducted; safety briefings completed | Induction record | Safety inductions and toolbox talks | All personnel inducted; safety briefings completed | Induction record | Verification of permits
Environmental controls in place | Dust, noise, and sediment barriers installed and functioning | SEPD environmental requirements | Environmental controls in place | Dust, noise, and sediment barriers installed and functioning | SEPD environmental requirements | All relevant permits (GDA/GDP) in place
GDA/GDP
Set-out of slab location | Slab set-out conforms to approved design coordinates | Site Layout Drawings, Survey Plan | Set-out of slab location | Slab set-out conforms to approved design coordinates | Site Layout Drawings, Survey Plan | Site access and safety preparation
Level and alignment check | Levels and alignment of formwork and slab position verified | WBS-SS-CI-SPC-0007, Survey Report | Level and alignment check | Levels and alignment of formwork and slab position verified | WBS-SS-CI-SPC-0007, Survey Report | Site access cleared and made safe
As-built survey after formwork and reinforcement | Survey to confirm reinforcement cover and formwork position | As-Built Drawings, Survey Report | As-built survey after formwork and reinforcement | Survey to confirm reinforcement cover and formwork position | As-Built Drawings, Survey Report | WBS-SS-CI-SPC-007
Safety inductions and toolbox talks
Review of approved concrete mix design | Mix design approved P3220100 | AS 1379 WBS-SS-CI-SPC-0007 | Review of approved concrete mix design | Mix design approved P3220100 | AS 1379 WBS-SS-CI-SPC-0007 | All personnel inducted; safety briefings completed
Formwork installation | Formwork aligned, clean, and secure; dimensions correct | AS 3610 WBS-SS-CI-SPC-0007 | Formwork installation | Formwork aligned, clean, and secure; dimensions correct | AS 3610 WBS-SS-CI-SPC-0007 | Induction record
Reinforcement placement | Reinforcement size, placement, spacing and cover as per drawings | AS 4671 WBS-SS-CI-SPC-0007 | Reinforcement placement | Reinforcement size, placement, spacing and cover as per drawings | AS 4671 WBS-SS-CI-SPC-0007 | Environmental controls in place
Reinforcement ties | Reinforcement securely tied in place, no loose bars | AS 4671 | Reinforcement ties | Reinforcement securely tied in place, no loose bars | AS 4671 | Dust, noise, and sediment barriers installed and functioning
Installation of dowels | Correct placement of all embedded items, dowels aligned | WBS-SS-CI-SPC-0007 | Installation of dowels | Correct placement of all embedded items, dowels aligned | WBS-SS-CI-SPC-0007 | SEPD environmental requirements
Waterproofing membrane | Membrane installed per design; overlaps secured | WBS-SS-CI-SPC-0007 | Waterproofing membrane | Membrane installed per design; overlaps secured | WBS-SS-CI-SPC-0007 | Set-out of slab location
Crack control joints | Joints placed and cut as per drawings and specifications | AS 3600 WBS-SS-CI-SPC-0007 | Crack control joints | Joints placed and cut as per drawings and specifications | AS 3600 WBS-SS-CI-SPC-0007 | Slab set-out conforms to approved design coordinates
Construction joints | Joints placed and prepared as per drawings and specifications | AS 3600 WBS-SS-CI-SPC-0007 | Construction joints | Joints placed and prepared as per drawings and specifications | AS 3600 WBS-SS-CI-SPC-0007 | Site Layout Drawings, Survey Plan
Site safety inspection prior to pour | Site clear, access routes checked, and emergency plans in place | Safety Plan WBS-SS-CI-SPC-0007 | Site safety inspection prior to pour | Site clear, access routes checked, and emergency plans in place | Safety Plan WBS-SS-CI-SPC-0007 | Level and alignment check
Levels and alignment of formwork and slab position verified
Concrete delivery | Delivery in line with approved mix design | AS 1379 Delivery dockets | Concrete delivery | Delivery in line with approved mix design | AS 1379 Delivery dockets | WBS-SS-CI-SPC-0007, Survey Report
Slump test | Slump within specified range (e.g., 100mm +/- 20mm) | AS 1012 Slump Test Results | Slump test | Slump within specified range (e.g., 100mm +/- 20mm) | AS 1012 Slump Test Results | As-built survey after formwork and reinforcement
Concrete placement | Concrete placed within formwork without segregation or delays | WBS-SS-CI-SPC-0007 | Concrete placement | Concrete placed within formwork without segregation or delays | WBS-SS-CI-SPC-0007 | Survey to confirm reinforcement cover and formwork position
Compaction of concrete | Concrete compacted using vibrators, no visible voids or honeycombing | AS 3600 WBS-SS-CI-SPC-0007 | Compaction of concrete | Concrete compacted using vibrators, no visible voids or honeycombing | AS 3600 WBS-SS-CI-SPC-0007 | As-Built Drawings, Survey Report
Cylinder sampling for compressive strength | Cylinder samples taken for 7, 14, 28-day tests | AS 1012 Sample Register | Cylinder sampling for compressive strength | Cylinder samples taken for 7, 14, 28-day tests | AS 1012 Sample Register | Review of approved concrete mix design
Concrete temperature monitoring (if required) | Temperature recorded during pouring | WBS-SS-CI-SPC-0007 Pour record | Concrete temperature monitoring (if required) | Temperature recorded during pouring | WBS-SS-CI-SPC-0007 Pour record | Mix design approved P3220100
AS 1379 WBS-SS-CI-SPC-0007
Surface finish | Class 5 | AS 3610 WBS-SS-CI-SPC-0007 | Surface finish | Class 5 | AS 3610 WBS-SS-CI-SPC-0007 | Formwork installation
Curing method | Curing compound or wet curing applied as per requirements | AS 3799 WBS-SS-CI-SPC-0007 | Curing method | Curing compound or wet curing applied as per requirements | AS 3799 WBS-SS-CI-SPC-0007 | Formwork aligned, clean, and secure; dimensions correct
Formwork stripping | Formwork removed after concrete reaches required strength | WBS-SS-CI-SPC-0007 | Formwork stripping | Formwork removed after concrete reaches required strength | WBS-SS-CI-SPC-0007 | AS 3610 WBS-SS-CI-SPC-0007
Compressive strength testing | Compressive strength results meet >32 MPa at 28 days | AS 1012 Test Results | Compressive strength testing | Compressive strength results meet >32 MPa at 28 days | AS 1012 Test Results | Reinforcement placement
Inspection of surface cracks and defects | No major cracks or surface defects observed | WBS-SS-CI-SPC-0007 | Inspection of surface cracks and defects | No major cracks or surface defects observed | WBS-SS-CI-SPC-0007 | Reinforcement size, placement, spacing and cover as per drawings
AS 4671 WBS-SS-CI-SPC-0007
As-built survey verification | As-built levels and layout match design | As-Built Drawings, Survey Report | As-built survey verification | As-built levels and layout match design | As-Built Drawings, Survey Report | Reinforcement ties
Final inspection sign-off | Final approval of the slab surface, dimensions, and finish | FIC sign-off | Final inspection sign-off | Final approval of the slab surface, dimensions, and finish | FIC sign-off | Reinforcement securely tied in place, no loose bars
AS 4671
Installation of dowels
Correct placement of all embedded items, dowels aligned
WBS-SS-CI-SPC-0007
Waterproofing membrane
Membrane installed per design; overlaps secured
WBS-SS-CI-SPC-0007
Crack control joints
Joints placed and cut as per drawings and specifications
AS 3600 WBS-SS-CI-SPC-0007
Construction joints
Joints placed and prepared as per drawings and specifications
AS 3600 WBS-SS-CI-SPC-0007
Site safety inspection prior to pour
Site clear, access routes checked, and emergency plans in place
Safety Plan WBS-SS-CI-SPC-0007
Concrete delivery
Delivery in line with approved mix design
AS 1379 Delivery dockets
Slump test
Slump within specified range (e.g., 100mm +/- 20mm)
AS 1012 Slump Test Results
Concrete placement
Concrete placed within formwork without segregation or delays
WBS-SS-CI-SPC-0007
Compaction of concrete
Concrete compacted using vibrators, no visible voids or honeycombing
AS 3600 WBS-SS-CI-SPC-0007
Cylinder sampling for compressive strength
Cylinder samples taken for 7, 14, 28-day tests
AS 1012 Sample Register
Concrete temperature monitoring (if required)
Temperature recorded during pouring
WBS-SS-CI-SPC-0007 Pour record
Surface finish
Class 5
AS 3610 WBS-SS-CI-SPC-0007
Curing method
Curing compound or wet curing applied as per requirements
AS 3799 WBS-SS-CI-SPC-0007
Formwork stripping
Formwork removed after concrete reaches required strength
WBS-SS-CI-SPC-0007
Compressive strength testing
Compressive strength results meet >32 MPa at 28 days
AS 1012 Test Results
Inspection of surface cracks and defects
No major cracks or surface defects observed
WBS-SS-CI-SPC-0007
As-built survey verification
As-built levels and layout match design
As-Built Drawings, Survey Report
Final inspection sign-off
Final approval of the slab surface, dimensions, and finish
FIC sign-off