## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Asphalt Placement | itp |  |  |  |  | ITP - Asphalt Placement
section | PRELIMINARY
checkpoint | 1.1 - Dot approved mix registration letter
label | FREQUENCY - Prior to commencing works
label | ACCEPTANCE CRITERIA - HP missing: "All asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport as ‘General’, unless otherwise approved by the Department of Transport. The registration for all mixes incorporated into the works shall be current at the time of their use. The Contractor shall submit documentation to the Superintendent nominating the asphalt mixes to be supplied no less than 7 days prior to their use."
label | REFERENCE DOCUMENTS - 407.09
label | INSPECTION / TEST METHOD - Verbal communication / inspection on site
label | HP
label | RESPONSIBILITY - Engineer
holdpoint | HOLD POINT
checkpoint | 1.2 - Submission of RAP Management plan
label | FREQUENCY - Prior to commencing works
label | ACCEPTANCE CRITERIA - No asphalt containing RAP shall be supplied until the Department of Transport approved RAP Management Plan has been submitted at least 14 days prior to the asphalt works commencing and approval to proceed is given by the Superintendent. Onetime sign off Hold Point - Not repeated
label | REFERENCE DOCUMENTS - 407.13(f)
label | INSPECTION / TEST METHOD - Verbal communication / inspection on site
label | HP
label | RESPONSIBILITY - Engineer
holdpoint | HOLD POINT
checkpoint | 1.3 - Cold Temperature Requirement: Asphalt Plant Supply
label | FREQUENCY - Prior to commencing paving
label | ACCEPTANCE CRITERIA - If surface temperatures are likely to drop below DOT minimum pavement temperature requirements, Evotherm to be added to asphalt mix. (See ‘Table 407.171 Minimum Pavement Temperatures Prior to Laying Asphalt’ at end of document).
label | REFERENCE DOCUMENTS - Approval to Lay Asphalt
label | INSPECTION / TEST METHOD - Verbal Communication n & Delivery Dockets
label | HP
label | RESPONSIBILITY - Asphalt Supervisor/ Engineer
holdpoint | HOLD POINT
checkpoint | 1.4 - Site Inspection and Base Condition
label | FREQUENCY - Prior to commencing paving
label | ACCEPTANCE CRITERIA - The surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material, and edge irregularities)
label | REFERENCE DOCUMENTS - 407.18, AS2150 10.1
label | INSPECTION / TEST METHOD - Visual Inspection
label | WP
label | RESPONSIBILITY - Foreman/ Engineer
section | PLACEMENT OF ASPHALT
checkpoint | 2.1 - Ambient Conditions for Placing
label | FREQUENCY - Prior to commencing paving
label | ACCEPTANCE CRITERIA - The majority of the surface area to be paved has a temperature greater than or equal to those specified in Table 407.171.
label | ○ Where approved by the Superintendent, placement of dense graded asphalt in layers 35 mm or greater may take place at pavement temperatures up to 5ºC below those specified in Table 407.171.
label | REFERENCE DOCUMENTS - 407.17
label | INSPECTION / TEST METHOD - Infrared Thermometer
label | IP
label | RESPONSIBILITY - Foreman/ Engineer
checkpoint | 2.2 - Cold Temperature Requirement: Site Inspection
label | FREQUENCY - Prior to commencing paving
label | ACCEPTANCE CRITERIA - Wind Speed is to be checked at the beginning of the shift. If speeds exceeds 30kmph the client is to be contacted and conditions assessed.
label | REFERENCE DOCUMENTS - 407.17
label | INSPECTION / TEST METHOD - Anemometer
label | IP
label | RESPONSIBILITY - Asphalt Supervisor/ Engineer
checkpoint | 2.3 - Surface Preparation
label | FREQUENCY - Prior to commencing paving
label | ACCEPTANCE CRITERIA - The area to be paved is free of all loose and deleterious material
label | REFERENCE DOCUMENTS - 407.18, AS2150 10.3
label | INSPECTION / TEST METHOD - Sweep Clean and Inspect
label | WP
label | RESPONSIBILITY - Foreman/ Engineer
checkpoint | 2.4 - Tack Coat
label | FREQUENCY - Prior to commencing paving
label | ACCEPTANCE CRITERIA - Cationic Rapid Set Bitumen emulsion (60% bitumen) to be applied at an application rate of no less than 0.5l/m2. The applied rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving.
label | ○ The Contractor shall submit the details of the trackless tack coat proposed to be used in the works, as per 407.08d
label | ○ The application rate for the tack coat shall be 0.15 to 0.30 L/m2 of residual bitumen (except for joints and chases where rates shall be doubled).
label | REFERENCE DOCUMENTS - 407.19, AS2150 11, HP
label | INSPECTION / TEST METHOD - Records
label | WP
label | RESPONSIBILITY - Foreman/ Engineer
checkpoint | 2.5 - Planning of Joints
label | FREQUENCY - Prior to commencing paving
label | ACCEPTANCE CRITERIA - a) Joints against a granular pavement', 'junctions at limits of work' and 'treatment of exposed edges against traffic'
label | b) Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or Centre of the lane. Wearing course shall be on lane lines.
label | REFERENCE DOCUMENTS - 407.21 d,e,f) 407.21
label | INSPECTION / TEST METHOD - Measure and mark out runs and submit Paving Plan to Client if requested
label | WP
label | RESPONSIBILITY - Foreman/ Engineer
checkpoint | 2.6 - Commencement of Placing
label | FREQUENCY - Prior to commencing Paving
label | ACCEPTANCE CRITERIA - The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | REFERENCE DOCUMENTS - 407.23
label | INSPECTION / TEST METHOD - Review ITP & Site Conditions
label | HP
label | RESPONSIBILITY - Supervisor / VicRoads Superint endent
holdpoint | HOLD POINT
checkpoint | 2.7 - Delivery of Mix
label | FREQUENCY - Each load
label | ACCEPTANCE CRITERIA - Asphalt is not segregated; the binder is not separated or does not contain uncoated particles and the temperature from the mixing plant is not more than 175°C. Mix delivery temperature no lower than 135°C
label | REFERENCE DOCUMENTS - 407.2
label | INSPECTION / TEST METHOD - Visual Inspection & Delivery Docket
label | WP
label | RESPONSIBILITY - Tipman
checkpoint | 2.8 - Traceability
label | FREQUENCY - Each lot
label | ACCEPTANCE CRITERIA - Ability to locate asphalt test results placed in three dimensions. Cold weather records to be collected in addition to the ITP with hourly temperature and wind speed checks
label | ○ Asphalt temperature is recorded in attached template
label | REFERENCE DOCUMENTS - BARS Doc 5.2.05, 5.2.06 407.17(a)
label | INSPECTION / TEST METHOD - Measure and Record on Daily Lot Record
label | IP
label | RESPONSIBILITY - Foreman/ Engineer
checkpoint | 2.9 - Layer Thickness and Level Control
label | FREQUENCY - Regularly during paving
label | ACCEPTANCE CRITERIA - The thickness of the asphalt layer conforms to asphalt thickness on drawings or specifications. To be checked at 10m to 20m intervals.
label | REFERENCE DOCUMENTS - 407.25 (a) & (b)
label | INSPECTION / TEST METHOD - Dips
label | WP
label | RESPONSIBILITY - Foreman / Level hands
checkpoint | 2.10 - Paver Stoppages
label | FREQUENCY - If paver stops
label | ACCEPTANCE CRITERIA - A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
label | REFERENCE DOCUMENTS - 407.25 (c)
label | INSPECTION / TEST METHOD - Temp gun
label | WP
label | RESPONSIBILITY - Foreman/ Engineer
checkpoint | 2.11 - Surface Finish of Wearing Course
label | FREQUENCY - During paving and after the final roll
label | ACCEPTANCE CRITERIA - (a) The finished surface of the asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open- textured patches, and roller marks.
label | (b) The temperature of each load of asphalt must be checked at the completion of initial rolling. The minimum required temperature of 110°C
label | REFERENCE DOCUMENTS - 407.29 (a)(i)
label | INSPECTION / TEST METHOD - (a) Visual Inspection Temp gun
label | WP
label | RESPONSIBILITY - Foreman/ Engineer
checkpoint | 2.12 - Kerb and Channel
label | FREQUENCY - During paving and after the final roll
label | ACCEPTANCE CRITERIA - The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | REFERENCE DOCUMENTS - 407.29 (a)(ii)
label | INSPECTION / TEST METHOD - Visual Inspection & Measurement
label | WP
label | RESPONSIBILITY - Foreman/ Engineer
checkpoint | 2.13 - Compaction
label | FREQUENCY - Per Lot (6 shot test)
label | ○ For lots greater than 2000m2 split into two equal sublots (ie firsts and last 50% of the lot laid).
label | ACCEPTANCE CRITERIA - Dense Grade Asphalt
label | ○ For layers <50mm, if characteristic density ratio is: 95.0% or greater Accept lot
label | ○ 93.0% to 94.9% - Lot may be accepted at a reduced rate For layers ≥50mm if characteristic thickness is: 96.0% or greater Accept lot
label | ○ 94.0% to 95.9% - Lot may be accepted at a reduced rate
label | Stone Mastic Asphalt
label | ○ For layers <50mm if characteristic density ratio is: 96.0% or greater Accept lot 93.0% to 95.9% Lot may be accepted at reduced rate
label | ○ Compaction reports are to be submitted to the Client to demonstrate conformance with these requirements.
label | ○ For OGA Layers not less than 5 passes with a static steel- drum roller with a minimum overall mass of 6 tonnes
label | REFERENCE DOCUMENTS - Table 407.271, Table 404.141
label | INSPECTION / TEST METHOD - VicRoads Code of Practice 500.05 and 500.16
label | TP
label | RESPONSIBILITY - Laborato ry Technicia n
checkpoint | 2.14 - Open Road After Asphalt
label | FREQUENCY - Completion of paving asphalt
label | ACCEPTANCE CRITERIA - The Contractor shall not place traffic on the Finished Surface until the Superintendent has agreed the temperature of the asphalt is less than 50oC and is trafficable.
label | REFERENCE DOCUMENTS - 404.14
label | INSPECTION / TEST METHOD - Temp gun
label | HP
label | RESPONSIBILITY - Supervisor / VicRoads Superintendent
holdpoint | HOLD POINT
checkpoint | 2.15 - Level Conformance
label | FREQUENCY - Each Lot
label | ACCEPTANCE CRITERIA - The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b)
label | – – – – – – – – – – – – – –
label | Table 407.292: Minimum Number of Level Measurements per Lot
label | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements Per Lot
label | – – – – – – – – – – – – – –
label | Scale A ¦¦ 80
label | Scale B ¦¦ 40
label | – – – – – – – – – – – – – –
label
label | – – – – – – – – – – – – – –
label | Table 407.293 Mean Surface Level Tolerances for the Sub-base and Pavement Courses
label | Scale of Surface Level Measurement ¦¦ Granular or Cement Treated Subbase (x̄ Range (mm) / Max. S (mm)) ¦¦ Asphalt Layers (x̄ Range (mm) / Max. S (mm))
label | – – – – – – – – – – – – – –
label | Scale A ¦¦ + 4 to - 8 / 8 ¦¦ ± 5 / 8
label | Scale B ¦¦ + 6 to - 12 / 13 ¦¦ ± 8 / 10
label | – – – – – – – – – – – – – –
label | REFERENCE DOCUMENTS - Table 407.292 and Table 407.293
label | INSPECTION / TEST METHOD - Survey Results
label | WP
label | RESPONSIBILITY - Surveyor
checkpoint | FINAL INSPECTION: (HOLD POINT)
label | This is to verify that the final inspection has been carried out in accordance with the B.A Roads Service’s Quality Procedures and Project Quality Plan and the product are hereby certified to confirm contract specifications:
label | BA Road Services
textbox | Print Name:
textbox | Position:
date | Date:
textbox | HOLD POINT