## Russley - New Checklists
checklist-flat | Asbestos Removal Works | Purpose
checkpoint | Air Monitoring Results | I want to be able to upload a document
checkpoint | Attach Photos | I want to be able to upload and take photos.
checkpoint | Attach Clearance Certificate | I want to be able to upload a document
Checklist | Compliance Documentation - Russley School | Purpose
checkpoint | Structural PS4 | I want to be able to upload a document
checkpoint | Geotechnical PS4 | I want to be able to upload a document
checkpoint | Hydraulic PS4 | I want to be able to upload a document
checkpoint | Mechanical PS4 | I want to be able to upload a document
checkpoint | Fire PS4 | I want to be able to upload a document
checkpoint | Civil PS4 | I want to be able to upload a document
checkpoint | Seismic PS4 | I want to be able to upload a document
checkpoint | Building Location Certificate | I want to be able to upload a document
checkpoint | Certificate of Title | I want to be able to upload a document
checkpoint | CPU Application Form | I want to be able to upload a document
checkpoint | CoC Application Form | I want to be able to upload a document
checkpoint | CPU Certificate | I want to be able to upload a document
checkpoint | CoC Certificate | I want to be able to upload a document
Checklist | Excavation Works | Purpose
checkpoint | Foundation Beams | I want to be able to upload and take photos.
checkpoint | Sub Grade Inspection | I want to be able to upload and take photos.
checkpoint | Backfill Layers | I want to be able to upload and take photos.
checkpoint | NDM Testing | I want to be able to upload a document
Checklist | Roofing & Spouting
| Pre Roof | Section Header?
checkpoint | Roofing Type | I want to be able to comment and take photos.
checkpoint | Confirm Roofing Colour | Comment + Photo
checkpoint | Confirm Sample Provided | Yes, no, N/A
checkpoint | Confirm alignment of structure | Yes, no, N/A + ability to comment and take photos
checkpoint | Confirm batten / purlin spacing | Yes, no, N/A + ability to comment and take photos
checkpoint | Confirm building paper / netting required | Yes, no, N/A + ability to comment and take photos
checkpoint | Confirm insulation | Yes, no, N/A + ability to comment and take photos
checkpoint | Framing / Substructure | I want to be able to comment and take photos.
checkpoint | Confirm Council Pre-Roof Inspection Required? | Yes, no, N/A + ability to upload documents
| HOLD POINT | All of the above signed off
| Roof Installation | Section Header?
checkpoint | Safety Mesh / Safety Nets | Yes, No, N/A + add photos.
checkpoint | Confirm Fixing types | Yes, no, N/A + ability to comment and take photos
checkpoint | Confirm Expansion joints, laps | Yes, no, N/A + ability to comment and take photos
checkpoint | Confirm Alignment of ridges, hips valley, falls | Yes, no, N/A + ability to comment and take photos
checkpoint | Confirm compliance with Weathering details – E2 | Yes, no, N/A + ability to comment and take photos
checkpoint | Confirm Air passages | Yes, no, N/A + ability to comment and take photos
checkpoint | Skylights, correct postion, sealed, flashed | Yes, No, N/A + add photos.
checkpoint | Ridge Flashings | I want to be able to comment and take photos.
checkpoint | Apron Flashings | I want to be able to comment and take photos.
checkpoint | Barge Flashings including correct laps | I want to be able to comment and take photos.
checkpoint | Penetrations sealed and complete | Yes, No, N/A + add photos.
checkpoint | Gutters | I want to be able to comment and take photos.
checkpoint | Fascia lines straight & true | Yes, no, N/A + ability to comment and take photos
checkpoint | Brackets even spacing | Yes, no, N/A + ability to comment and take photos
checkpoint | Brackets correct fall | Yes, no, N/A + ability to comment and take photos
checkpoint | Correct downpipe position | Yes, no, N/A + ability to comment and take photos
checkpoint | Spout expansion joins @ 15m | Yes, no, N/A + ability to comment and take photos
checkpoint | Spouting straightness | Yes, no, N/A + ability to comment and take photos
checkpoint | Snowstraps | Yes, no, N/A + ability to comment and take photos
checkpoint | Rainwater Heads | Yes, no, N/A + ability to comment and take photos
checkpoint | Fall Arrest System | Yes, no, N/A + ability to comment, take photos and upload documents
checkpoint | Roof Access Platforms / Monkey Toe | Yes, no, N/A + ability to comment, take photos and upload documents
checkpoint | Roof Ladder Brackets | Yes, no, N/A + ability to comment and take photos
checkpoint | Consultant Inspections - Structural | Yes, no, N/A + ability to comment, take photos and upload documents
checkpoint | Consultant Inspections - Architectural | Yes, no, N/A + ability to comment, take photos and upload documents
checkpoint | Trades QA received, attached, reviewed and approved | Yes, no, N/A + ability to comment, take photos and upload documents
checkpoint | Roof Clean + Roof Works Complete | Everything above needs to be signed off first.
Checklist | Timber Framing
checkpoint | Confirm Wall Type Plan (Drawing Numbers and Reference) | Ability to comment, take photos and upload documents (MUST HAVE A COMMENT)
checkpoint | Confirm Wall Type Schedule (Drawing Numbers and Reference) | Ability to comment, take photos and upload documents (MUST HAVE A COMMENT)
checkpoint | Confirm Timber Treatment Type | Ability to comment, take photos and upload documents (MUST HAVE A COMMENT)
checkpoint | Damp Proof Course Installed | Yes, no, N/A + ability to comment, take photos and upload documents
checkpoint | Confirm Set Out of all openings | Yes, no, N/A + ability to comment, take photos and upload documents
checkpoint | Confirm Stud Centres | Yes, no, N/A + ability to comment, take photos and upload documents
checkpoint | Confirm Dwang Centres | Yes, no, N/A + ability to comment, take photos and upload documents
checkpoint | Confirm Lintels | Yes, no, N/A + ability to comment, take photos and upload documents
checkpoint | Dimensions / locations checked and accurate
checkpoint | All frames are square
checkpoint | Frames are straight and level
checkpoint | Fixings are correct
checkpoint | Any bracing requirements installed
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Raise Remedial / Request trades QA / Sign Off
checkpoint | All framing completed correctly within tolerance in respective area
Checklist | Block A - Seismic Bracing QA Required | Unique List for my project only
| Report dated 4/7/23 | Subheading
| Item 7 - Photo required of control joint between bulkhead and full height wall | Must Upload Photo
| Report dated 4/9/23 | Subheading
| Item 13 - No photos provided for fixed ceiling hangers at seismic joint | Must Upload Photo
| Item 17 - Ensure mechanical brace indicated below is installed within 600mm of corner. | Must Upload Photo
| Item 18 - Mechanical duct dropper has no clearance with above cable tray. Fix cable tray to bottom flange of steel beam with EA bracket on either side of cable tray. | Must Upload Photo
| Item 19 - Ensure GIB Negative detail is provided underneath structural elements for all walls with deflection track. No photos provided showing negative detail in full height walls (at DHT Level). | Must Upload Photo
| Item 20 - Install additional lateral brace (transverse) to highlighted ducts on following page. Additional brace is due to fleixble connections to units. | Must Upload Photo
| Item 21 - Some braces fixed to underside of purlin with timber block and one - two screws. Not okay. Must be installed to bridging or direct to web of purlin with CPC 80. | Must Upload Photo
| Item 22 - plasterboard ceiling above reception braced incorrectly. Braced with GRIPLOK braces. Not okay. Braces required to furring channel as per design. Stengthen as per attached detail. | Must Upload Photo
| Report dated 4/9/23: Timber Bulkheads above reception require strengthening: | Subheading
| Item 14 - Bridging members required for timber braces as per KCL Details. Can use CPC 80 brackets instead of EA on detail. Bridging for braces for timber bulkheads not installed as per design. Remediate as per design. | Must Upload Photo
| Item 15 - Add additional 90x45TS to make 90x90TS bridge above droppers with braces on them. - Minimum 2x screws required per connection required for timber to timber connections. - Braces cannot fix to open face of purlins. Must go to back side of purlins. Timber bridging not strengthened at brace locations as required in last site report. Timber to be added. | Must Upload Photo
| Item 16 - Move / extend brace arm to achieve required clearances for timber brace to dropper connection. Timber braces not moved / extended to achieve required clearances for timber brace to dropper connection. | Must Upload Photo
Checklist | Service Trenching (non-drainage)
| Confirm filter cloth required? | Yes, no, N/A + ability to comment, take photos and upload documents
| Services specifications reviewed | Yes, no, N/A + ability to comment, take photos and upload documents
| Confirm bedding material required | Yes, no, N/A + ability to comment, take photos and upload documents
| Draw wires required? | Yes, no, N/A + ability to comment, take photos and upload documents
| Electrical Ducts / Cabling complete. All joints sealed incl. Mag Slab & Danger Tape | Yes, no, N/A + ability to comment, take photos and upload documents
| Fire Ducts / Cabling complete. All joints sealed incl. Mag Slab & Danger Tape | Yes, no, N/A + ability to comment, take photos and upload documents
| Comms Ducts / Cabling complete. All joints sealed incl. Mag Slab & Danger Tape | Yes, no, N/A + ability to comment, take photos and upload documents
| Security Ducts / Cabling complete. All joints sealed incl. Mag Slab & Danger Tape | Yes, no, N/A + ability to comment, take photos and upload documents
| Water Piping complete | Yes, no, N/A + ability to comment, take photos and upload documents
| Separation from other services acceptable | Yes, no, N/A + ability to comment, take photos and upload documents
| Pits installed and penetrations sealed | Yes, no, N/A + ability to comment, take photos and upload documents
| Confirm fill requirements | Yes, no, N/A + ability to comment, take photos and upload documents
| Information uploaded to as builts | Yes, no, N/A + ability to comment, take photos and upload documents
Checklist | First Fix Services - Pre-Line Inspection | NOT READY FOR CONQA TO IMPLEMENT YET
| Carpentry - Set Out | Yes, no, N/A + ability to comment, take photos and upload documents
| Carpentry - Alignment | Yes, no, N/A + ability to comment, take photos and upload documents
| Carpentry - Moisture Content (specify) | Yes, no, N/A + ability to comment, take photos and upload documents
| Carpentry - specify stud spacings | Yes, no, N/A + ability to comment, take photos and upload documents
| Carpentry - specify dwang spacings | Yes, no, N/A + ability to comment, take photos and upload documents
| Carpentry - services blocking | Yes, no, N/A + ability to comment, take photos and upload documents
Accessible Bathroom Blocking?
| Carpentry - Timber Doors Installed | Yes, no, N/A + ability to comment, take photos and upload documents
| Passive Fire - Back Blocking Complete | Yes, no, N/A + ability to comment, take photos and upload documents
First Fix Services & Seismic Bracing Installed?
| · Comms | Yes, no, N/A + ability to comment, take photos and upload documents
| · Electrical | Yes, no, N/A + ability to comment, take photos and upload documents
| · Security cables | Yes, no, N/A + ability to comment, take photos and upload documents
| · Fire systems | Yes, no, N/A + ability to comment, take photos and upload documents
| · Plumbing | Yes, no, N/A + ability to comment, take photos and upload documents
| · HVAC | Yes, no, N/A + ability to comment, take photos and upload documents
| Wall Insulation Complete | Yes, no, N/A + ability to comment, take photos and upload documents
| Ceiling Insulation Complete | Yes, no, N/A + ability to comment, take photos and upload documents
External Pre-Lining
Checklist | Accessible Bathroom
Check Opening Sizes - Confirm Compliance with NZS4121 - Section 10

## Russley - Breakdown Structure
Dilapidation Survey
| Existing Site Photos | Existing Buildings + Fences + Site Entrances + Street Connections + Trees
| Existing Services | Power, Water, Gas, Telecommunications, Fire, Drainage, Other
Site Set Up | Offices Onsite | Photo + Plant Numbers
| Containers Onsite | Photo + Plant Numbers
| Toilets Onsite | Photo + Plant Numbers
| Council Inspection | Sediment Control
Demolition | Services Disconnections
Asbestos Removal
Asbestos Removal Survey
| Block 2 | Checklist | E.g. air monitoring results, clearance survey, services isolated.
| Block 3 | Checklist | E.g. air monitoring results, clearance survey, services isolated.
| Block 4 | Checklist | E.g. air monitoring results, clearance survey, services isolated.
| Block 5 | Checklist | E.g. air monitoring results, clearance survey, services isolated.
| Block 6 | Checklist | E.g. air monitoring results, clearance survey, services isolated.
| Block 7 | Checklist | E.g. air monitoring results, clearance survey, services isolated.
| Block 8 | Checklist | E.g. air monitoring results, clearance survey, services isolated.
| Block 9 | Checklist | E.g. air monitoring results, clearance survey, services isolated.
| Block 10 | Checklist | E.g. air monitoring results, clearance survey, services isolated.
| Block 11 | Checklist | E.g. air monitoring results, clearance survey, services isolated.
| Block 12 | Checklist | E.g. air monitoring results, clearance survey, services isolated.
| Old Hall | Checklist | E.g. air monitoring results, clearance survey, services isolated.
Excavation | Building Footprint
Building Setout
HAIL Site
Contaminated Fill
Geotech Inspection
RL
| Underslab Services |  | Underslab Services Checklist (Audit) (AIAL)
Foundations & Floor Slab
| Block C Foundation Beams |  | Concrete Pour (AIAL)
| Reinforcing | Subs QA
Floor Rebates
| Floor Boxes | Checked Structural Drawings, Checked Services Drawings
Ducts
Hold Down Bolts Surveyed
BLC
| Nib | Waterproof - Sword Flashing
Structure + Exterior Windows & Cladding
| Structural Steel | Paint
Subs QA
|  | Level | Tolerance vs Actual
Plumb
Purlins Checked
Grouting
External Walls
| North Elevation | Framing | Timber Framing Checklist (AIAL)
| South | Cladding
| East | Pre-Clad Inspection | Council Inspection - ICL Weatherboards and sheet claddings (AIAL)
| West | Building Wrap + Tapes
Cavity Battens
|  | Brick Veneer | Cavity Size, Waterproofing
Window Lintels
|  | Flashings | Window Head, Jamb, Brick Capping, Soffit / Window Closure, Sill Flashing
Threshold Drains
Nib
Insulation
Hold Down Bolts
Soffits
Framing
|  | Services | Mechanical Vents
Lighting
Vents
Fire
Security
|  |  | Cladding | Orientation, shadow gaps?, fixings
Stopping?
Paint
Roofing
Roofing Type
Framing
Safety Mesh
Skylights
|  | Ridge Flashings | Ridge, apron, clerestorey,
Apron Flashings
Barge Flashings
Penetrations
Gutters
Downpipes
Rainwater Heads
External Windows & Doors
|  | Glazing Type | D01
|  | Subs QA | D02
D03
D04
D05
D06
D07
D08
D09
D10
D11
D12
D13
D14
D15
D16
D18
|  |  | FD01 | Approved Shop Drawing
Installation Sheet
Hardware
Fire Door Tags
FD02
Approved Shop Drawing
Installation Sheet
Hardware
Fire Door Tags
Internal Fitout + Services
GLA 1
|  | Timber Framing | Timber Framing Checklist (AIAL)
Electrical
Fire
Data / Comms
Water
Mechanical
Ceiling Framing
Internal Doors & Windows
Glazed Partitions
Painting
Plasterboard Lining
Insulation
Final Sign Off (AIAL)
Breakout 1
GLA 2
Art 1
Staff 01
Breakout 2
| WC Area 01 | WC Lobby 01
ACC 01
WC 01A
WC 01B
WC 01C
GLA 3
GLA 4
Art 2
Breakout 3
GLA 5
GLA 6
Staff 02
Breakout 4
Art 3
| WC Area 02 | WC Lobby 02
WC 02A
WC 02B
USB
Breakout 3
Breakout 4
First Fix Services
Second Fix Services
Siteworks
Block C East
Block C North
Block C West
Hard Courts
Driveway
Car Park
Council Inspections | Erosion / Sediment Control
Drainage
Foundations
Pre Roof
Pre Clad
Pre Line
CPU Inspection
Final Inspection
Council Documents
CoC Application
| Engineers + Consultant Documents | Structural PS4
Geotechnical PS4
Hydraulic PS4
Mechanical PS4
Fire PS4
Civil PS4
Seismic PS4
Building Location Certificate
Code Compliance Certificate
Consented Documents

## Breakdown Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Checklist Required
Site QA
Civils
Area 1
|  |  | Sub Soil |  |  |  | Sub Soil Checklist
Area 2
|  |  | Sub Soil |  |  |  | Sub Soil Checklist
Foundations
Zone 1
|  |  | Concrete Pour |  |  |  | Concrete Pour Checklist (Self Perform)
Zone 2
|  |  | Concrete Pour |  |  |  | Concrete Pour Checklist (Self Perform)
Zone 3
|  |  | Concrete Pour |  |  |  | Concrete Pour Checklist (Self Perform)
Zone 4
|  |  | Concrete Pour |  |  |  | Concrete Pour Checklist (Self Perform)
Foundations Services
Zone 1
|  |  | Watermain Pipeline Installation |  |  |  | Watermain - Pipeline Installation Checklist
Zone 2
|  |  | Watermain Pipeline Installation |  |  |  | Watermain - Pipeline Installation Checklist
Zone 3
|  |  | Watermain Pipeline Installation |  |  |  | Watermain - Pipeline Installation Checklist
Zone 4
|  |  | Watermain Pipeline Installation |  |  |  | Watermain - Pipeline Installation Checklist
Structure
Level 1
|  |  | Structural Steel |  |  |  | Structural Steel Checklist
|  |  | Intumescent Painting |  |  |  | Intumescent Painting Checklist
|  |  | Waterproofing |  |  |  | Waterproofing Checklist
Level 2
|  |  | Structural Steel |  |  |  | Structural Steel Checklist
|  |  | Intumescent Painting |  |  |  | Intumescent Painting Checklist
|  |  | Waterproofing |  |  |  | Waterproofing Checklist
Level 3
|  |  | Structural Steel |  |  |  | Structural Steel Checklist
|  |  | Intumescent Painting |  |  |  | Intumescent Painting Checklist
|  |  | Waterproofing |  |  |  | Waterproofing Checklist
Facade
North Elevation
Envelope
|  |  |  | Warm Roof |  |  | Envelope - Warm Roof Checklist
|  |  |  | Internal Gutter |  |  | Envelope - Internal Gutter Checklist
|  |  | Timber Framing |  |  |  | Timber Framing Checklist
|  |  | Curtain Wall |  |  |  | Curtain Wall Checklist
Fitout
Level 1
Room 1
|  |  |  | Ceiling Preline |  |  | Ceiling Preline incl High Level Services Checklist
|  |  |  | Walls Preline |  |  | Walls Preline Checklist
|  |  |  | Ceiling Postline |  |  | Ceiling Postline Checklist
|  |  |  | Walls Postline |  |  | Walls Postline Checklist
|  |  |  | Flooring |  |  | Flooring Checklist
|  |  |  | Final Sign Off |  |  | Final Sign Off Checklist

## Hawkins South Island Checklists
PLEASE PASTE YOUR DESIRED CHECKLISTS FROM OUR TEMPLATES HERE / CREATE YOUR OWN CUSTOM ONES (EXAMPLE BELOW) / SEND US A COPY TO DIGITISE
checklist-flat | Custom Checklist
checkpoint | This is a checkpoint
checkpoint | This is a checkpoint with a dropdown (you can select only one option)
dropdown | Select: | Option 1, Option 2, Option 3
checkpoint | This is a checkpoint with a textbox
textbox | Description:
checkpoint | This is a checkpoint with buttons (you can select only one option)
button | Select: | Option 1, Option 2, Option 3
checkpoint | This is a checkpoint with tickboxes (you can tick more than one box)
tickbox | Red
tickbox | Blue
checkpoint | This is a checkpoint with a signoff
signoff | Click here to signoff

## Hawkins AIAL Checklists
checklist-flat | Potable Water Checklist
checkpoint | Location details and relevant mark ups attached
textbox | Location
checkpoint | Consultant inspection
checkpoint | Council Inspection
checkpoint | Watercare Inspection
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Potable Water Installation completed
checklist-flat | Service Location / Isolation Checklist
checkpoint | Power located/Isolated
checkpoint | Hydraulic services located/isolated
checkpoint | Gas located/isolated
checkpoint | Telecommunication/Fibre located/isolated
checkpoint | Any other relevant services located/ isolated
checkpoint | All Services located/ isolated (Pass once all services are located/isolated)
checklist-flat | Stormwater (Main Line) - Pipeline Installation Checklist
checkpoint | Latest construction drawings referenced and followed
textbox | Drawing & Revision Number
checkpoint | Set Out & Excavation completed checked and accurate
checkpoint | Ground conditions checked & acceptable
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
textbox | Invert Level (upstream manhole)
textbox | Invert Level (downstream manhole)
textbox | Design length of pipe (m)
textbox | Length of pipe installed (m)
textbox | Grade of Pipe-Line %
checkpoint | Connections to manholes complete and approved (photo required)
checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
checkpoint | Relevant tests, photos & as-built information provided
checklist | Concrete Pour Checklist (Self Perform)
section | Pour Details
checkpoint | Pour Details
textbox | Area to be poured:
textbox | Date of pour:
checkpoint | Latest drawings available, checked and referenced
section | Formwork and Embedded Items
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
section | reinforcement
checkpoint | Trades QA received, attached, reviewed and approved
signoff | Raise Remedial / Request trades QA / Sign Off
checkpoint | Size and type correct to specification
checkpoint | reinforcement spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcement removed
checkpoint | Welding certificates sited and attached
checkpoint | Mill certificate reviewed, attached and approved
checkpoint | reinforcement installed correctly to specification and ready for concrete to be placed
section | Pre-Pour Completion (Approval to pour)
checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint | Any relevant service requirements completed (locations checked and accurate)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | All relevant inspections completed and attached
checkpoint | Main contractor inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
checkpoint | Concrete Supplier Specifics
textbox | Supplier Name:
textbox | Specified concrete strength:
textbox | Concrete strength ordered:
textbox | Concrete quantity ordered:
checkpoint | Test blocks booked
checkpoint | All concrete dockets photographed/ attached
checkpoint | Concrete strength test reports attached and required concrete strength achieved
section | Concrete Distribution
checkpoint | General distribution photos, documents and observations attached
checkpoint | All concrete distributed correctly (area left clean and tidy)
section | Placement Method
checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification | Yes, No
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint | Area left clean and tidy
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat | Council Inspection - ICA Cavity
checkpoint | Inspection Details: To check cavity has been formed; cavity battens; cavity closers and flashings all in place
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist-flat | Consultant - Site Visit Report
checkpoint | Purpose of visit
dropdown | Project name | SP2A - EBH South, SP2A - EBH South L1 Retail area/ L2 Lounge Extension & Fire Egress Stairs, SP2B - EBH South Balance of the Ground Floor, SP2C - EBH South Balance of Works, SP3 - Power Centre 69 (PC69), SP4 - Stage 1 Infill - Pre-Stitch, SP5 - Stage 2 Infill - Stitch, SP6 - Check-in Back of House
textbox | Area of site visited
textbox | Date/ Time of visit
textbox | Consultant personnel attending
textbox | Hawkins representative accompanying consultant
textbox | Comments made to/by contractor's representative
textbox | Follow-up action/s required by Hawkins
checklist-flat | Asbestos Removal Checklist
checkpoint | Initial Environment/Planning Asbestos report attached
checkpoint | Asbestos Removal approved to commence (all pre-commencement considerations allowed for)
checkpoint | Attach relevant asbestos removal photos (Label all photos with relevant location)
checkpoint | Independent asbestos report completed and attached
checkpoint | Trade contractor QA received, attached, reviewed and approved
checkpoint | Any remedial requirements actioned and completed / closed out
checkpoint | All asbestos removed and approval given to progress with work
checklist-flat | HV Ducts Checklist
checkpoint | Location details and relevant mark ups attached
textbox | Location
checkpoint | Separation to other services
checkpoint | Vector / North Power Review
checkpoint | Consultant inspection
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | Installation record photos
checkpoint | HV Ducts Installation completed
checklist-flat | Technical Submission item
checkpoint | Details
textbox | Closeout document type: (e.g. CoC for Security Systems or Commissioning results or PS3 for Security, O&M manual, Quality Assurance document etc.)
textbox | Mail reference (if submitted on Aconex):
checkpoint | Additional information (if applicable)
signoff | Signature
checklist-flat | Underground Services Checklist (Audit)
checkpoint | Electrical services/ conduits installed, fixed in correct location, backfilled and correct as per design
checkpoint | Hydraulic services installed, fixed in correct location, backfilled and correct as per design
checkpoint | Gas installed, fixed in correct location, backfilled and correct as per design
checkpoint | Telecommunication/Fibre installed, fixed in correct location, backfilled and correct as per design
checkpoint | Any other relevant services installed, fixed in correct location, backfilled and correct as per design
checkpoint | Any additional observations / attachments
checkpoint | Any relevant inspections carried out and attached - observations documented and closed out
checkpoint | All subfloor services correctly installed to respective area
checklist-flat | Timber Framing (Audit)
checkpoint | Approval given to install timber framing
checkpoint | Dimensions / locations checked and accurate
checkpoint | All frames are square
checkpoint | Frames are straight and level
checkpoint | Fixings are correct
checkpoint | Any bracing requirements installed
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received, attached, reviewed and approved
signoff | Raise Remedial / Request trades QA / Sign Off
checkpoint | All framing completed correctly within tolerance in respective area
checklist-flat | Tanking / Waterproofing Checklist (Audit)
checkpoint | Preparation / Substrate acceptable
checkpoint | Correct product delivered and checked - approval given to install
checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint | Trades QA received & attached as applicable
checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
checklist-flat | Foul Checklist
checkpoint | Location details and relevant mark ups attached
textbox | Location
checkpoint | Consultant inspection completed as required
checkpoint | Council Inspection completed as required
checkpoint | Watercare Inspection completed as required
checkpoint | Invert levels recorded
checkpoint | Invert levels as per design
textbox | Invert Levels
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | CCTV Survey
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Foul Installation completed
checklist-flat | Council Inspection - IPB Insulation
checkpoint | Inspection Details: To check the installation of all wall, ceiling and mid-floor insulation (thermal and acoustic) prior to installing interior linings
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | Note: This inspection may be included with the preline building inspection
checklist-flat | BCO10356437- New foundations across 6330m2 to South East of existing ITB for future the East Terminal Building - SP2 EBH South
checkpoint | PS3 - Foundation, Ground beam and pile cap
checkpoint | PS4 - All Structural elements
checkpoint | Engineers Observation Report
checklist-flat | Precast Panel Installation Checklist
checkpoint | Inspected on arrival and damage free
checkpoint | Installed in correct location
checkpoint | Adequately braced
checkpoint | Grout sleeves correctly grouted
checkpoint | Panel install complete (checked location & level)
checklist-flat | Council Inspection - ICL Roof framing
checkpoint | Inspection Details: To check roof framing, fixings and the installation of flashings; safe access must be provided to enable an inspection of the roof
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | Note: LBP must be on site if restricted building work involved
checklist-flat | Council Inspection - ICL Weatherboards and sheet claddings
checkpoint | Inspection Details: To check that the cladding has been correctly fixed; all soakers; scribers, box corners, and plugs have been fitted but only tacked in place to allow them to be removed at the request of the inspector to check correct cover has been achieved and all cuts have been primed.
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | Note: All control joints, apron, head and sill flashings to be installed
checklist-flat | Piling Pre-Start Checklist
checkpoint | Piles Set Out, surveyed and clearly marked
checkpoint | Accurate RL confirmed for piling reference
checkpoint | Acceptable site conditions and access for piling rig
checkpoint | Additional photos/ observations / reports attached
checkpoint | Approval given to commence piling
tickbox | approval given to dig
tickbox | relevant services identified and isolated / clearly marked
tickbox | relevant information communicated to piling trade
tickbox | any environmental requirements considered and enacted
checklist | Concrete Pour
section | Formwork and Embedded Items
checkpoint | Latest drawings available, checked and referenced
textbox | Grid Line
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Grids and RLs clearly marked for reference
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Formwork sufficiently fixed and braced (incl any propping)
checkpoint | Shear studs installed as-per shop drawings & check ring test
checkpoint | Any rebates/ nibs / cast in items are correctly positioned, sized and appropriately fixed in place
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint | Any additional formwork photos and observations
checkpoint | All formwork elements completed and ready for concrete pour ( excess debris removed )
section | reinforcement
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Size and type correct to specification
checkpoint | reinforcement spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcement removed
checkpoint | reinforcement installed correctly to specification and ready for concrete to be placed
section | Pre-Pour Completion (Approval to pour)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Council inspection completed and attached
checkpoint | All relevant inspections completed and attached
checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification | Yes, No
checkpoint | General photos and observations of concrete placement attached
section | Pour / Post-Pour Checks/Sign Off
checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete surface to specifications
checkpoint | Area left clean and tidy
checkpoint | Any remedial work completed
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat | QC 3.2.K Material Receiving Inspection
checkpoint | Material Receiving Inspection
note | Project number: HA0409
dropdown | Project name: | SP2 - Operational EBH South,SP3 - PC69,SP4 - Stage 1 Infill & Balance of EBH South,SP5 - Stage 2 Infill,SP6 - Check-in Back of House
textbox | MRI No:
date | Date:
textbox | Material Description:
textbox | Manufacturer:
textbox | Supplier:
textbox | Material Submittal (MAS) No.:
textbox | Material Requisition (MR) No.:
textbox | Local Purchase Order (LPO) No.:
date | Delivery Date:
textbox | Invoice No.:
textbox | Documents / specification / Drawings BOQ /etc. References:
textbox | Identification of the supplies:
textbox | Lot No.:
textbox | Quantity ordered:
textbox | Quantity Received:
date | Validity Date:
textbox | State of Packing:
textbox | Documents Received with the Delivery:
radio | Samples to be taken: | Yes,No
textbox | Handling, Transporting and Storage Instructions:
textbox | Comments:
radio | Result of the Inspection: | Material as per approved submittal,Material as per approved submittal with comments,Material rejected
textbox | Action to be taken:
checkpoint | Inspection made by:
note | Storekeeper/ Supplier
textbox | Storekeeper/ Supplier - Function:
textbox | Storekeeper/ Supplier - Name/ signature:
date | Storekeeper/ Supplier - Date:
note | Hawkins QA/QC / Site Supervisor
textbox | Hawkins QA/QC / Site Supervisor - Function:
textbox | Hawkins QA/QC / Site Supervisor - Name/ signature:
date | Hawkins QA/QC / Site Supervisor - Date:
note | Engineer Rep
textbox | Engineer Rep - Function:
textbox | Engineer Rep - Name/ signature:
date | Engineer Rep - Date:
checklist-flat | Lightning Protection Checklist
checkpoint | Location details and relevant mark ups attached
textbox | Location
checkpoint | Separation to other services
checkpoint | Consultant inspection
checkpoint | Received QA from Subcontractor?
checkpoint | Continuity test
checkpoint | As Built drawings received
checkpoint | Installation record photos
checkpoint | Lightning Installation completed
checklist-flat | Site Establishment Checklist
checkpoint | Any relevant dilapidation requirements captured
checkpoint | Attach relevant site establishment photos/ documents
checkpoint | Appropriate isolation of site (hoardings / fencing)
checkpoint | Sufficient & Appropriate site/H&S signage erected
checkpoint | Site establishment completed
checklist | Handover Documents
section | Close Out
checkpoint | Close Out - all required information captured
folder-normal | Handover Documents
checklist-flat | Council Inspection - IME Site Meeting
checkpoint | Inspection Details: To discuss any item of compliance relating to a building consent, Items recorded are: (1. Reason for meeting, What is being discussed, 3. Outcomes and responsibilities on various parties
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | Monitoring inspections to audit consultant’s inspections and uplift documentation.
checkpoint | Pre-construction meeting to discuss the project and proposed inspection regimes. For multi-unit developments of 4 or more units or complex commercial.
checkpoint | Pre-construction meeting to determine methodology for protecting excavations relating to any retaining walls proposed within 1m of the boundary.
checklist-flat | Detailed Excavation Checklist
checkpoint | Location accurate
checkpoint | Depth correct (allow for site concrete if required)
checkpoint | Width correct (allow for boxing if required)
checkpoint | Any relevant excavation for services is completed and accurate
checkpoint | Excess Material Cleaned up and removed as required
checkpoint | Detailed excavation completed, reviewed and approved
checklist-flat | BCO10350606 - New piling across 6330m2 of ground to become the new East Terminal Building at AIAL - SP2 - EBH South
checkpoint | PS3 - Pile driving
checkpoint | PS4 - Pile Driving
checkpoint | Pile driving log
checkpoint | Engineer Observation Report
checklist-flat | Council Inspection - IPB Preline Building
checkpoint | Inspection Details: To check the building is weathertight (refer to description of cladding from cladding inspection), proprietary connections for bracing elements installed and moisture content below 18%; prior to fixing any internal linings
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist-flat | Council Inspection - ITK Membrane roof, deck and wet areas
checkpoint | Inspection Details: To check the application of the membrane prior to completing decoration, floor coverings and roof claddings
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist-flat | Council Inspection - ISF Floor slab
checkpoint | Inspection Details: To check that hard fill has been compacted; DPM placed; reinforcement is tied and supported in chairs; and starter bars fitted
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | PS4 is required where hard fill exceeds 600m (select N/A if none)
checkpoint | Note: Siting is checked at this inspection for raft floors; boundaries must be defined and string lines in place. If you are unable to locate survey pegs a registered Land Surveyor’s certificate maybe required
checklist-flat | Council Inspection - IF2 Commercial Final
checkpoint | Inspection Details: To check that all construction covered within the scope of the consent has been completed in accordance with the building code. As-built plans showing the location of all specified systems have been provided.
textbox | Date of Inspection & Name of inspector
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist-flat | Underslab Services Checklist (Audit)
checkpoint | Electrical services/ conduits installed, fixed in correct location, backfilled and correct as per design
signoff | Raise Remedial / Request trades QA / Sign Off
checkpoint | Hydraulic services installed, fixed in correct location, backfilled and correct as per design
tickbox | Storm Water
tickbox | Sewer
tickbox | Water Supply
signoff | Raise Remedial / Request trades QA / Sign Off
checkpoint | Gas installed, fixed in correct location, backfilled and correct as per design
signoff | Raise Remedial / Request trades QA / Sign Off
checkpoint | Telecommunication/Fibre installed, fixed in correct location, backfilled and correct as per design
signoff | Raise Remedial / Request trades QA / Sign Off
checkpoint | Any other relevant services installed, fixed in correct location, backfilled and correct as per design
signoff | Raise Remedial / Request trades QA / Sign Off
checkpoint | Any additional observations / attachments
checkpoint | Any relevant inspections carried out and attached - observations documented and closed out
checkpoint | All subfloor services correctly installed to respective area
checklist-flat | Council Inspection - ICB Concrete reinforced columns and beams
checkpoint | Inspection Details: To check all reinforcing steel tied; stirrups at appropriate centres; reinforcing laps appropriate; spacers in place to achieve clearances from form work
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist | Sewer - Pipeline Installation Checklist
section | Pipe Laying
checkpoint | Latest consented drawings
textbox | Drawing Ref No.
checkpoint | Set Out completed checked and accurate
checkpoint | Excavation Accurate - Location & Depth
checkpoint | Ground Conditions Checked & Acceptable
checkpoint | Bedding depth and material correct
checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
textbox | Start Invert
textbox | Finish Invert
textbox | Grade of Pre-Line %
textbox | Product Type
checkpoint | Install Tests completed, reviewed & approved
textbox | Local Authority Inspection Passed
textbox | Name of inspector
textbox | Date
checkpoint | Pipe Laying Completed
tickbox | Bedding Sound
tickbox | Soil Removed
tickbox | Trench Compacted
tickbox | Hard Filled
checkpoint | Connections to manholes complete and approved
checkpoint | Air Test Complete
section | Backfill
checkpoint | Backfill methodology and material confirmed
checkpoint | Any formwork/ debris removed from area
checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint | General photos and observations during backfill
checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | Flushing Water Checklist
checkpoint | Location details and relevant mark ups attached
textbox | Location
checkpoint | Consultant inspection completed as required
checkpoint | Council Inspection completed as required
checkpoint | Watercare Inspection completed as required
checkpoint | Invert levels recorded
checkpoint | Invert levels as per design
textbox | Invert Levels
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | CCTV Survey
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Flushing Water Installation completed
checklist-flat | Council Inspection - IPP Plumbing Slab - Under slab plumbing
checkpoint | Inspection Details: To check all under slab drainage and plumbing; all pipes to be under test and exposed for inspection
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist | In Ground Water & Gas Mains Checklist
section | Water mains
checkpoint | All fittings scrapped correctly
checkpoint | Iso used on fittings
checkpoint | Valves fitted correctly
checkpoint | Fittings welded & weld indicator has popped out
checkpoint | Trace wire and ID tape installed
section | Gas main
checkpoint | All fittings scrapped correctly
checkpoint | Iso used on fittings
checkpoint | Valves fitted correctly
checkpoint | Fittings welded & weld indicator has popped out
checkpoint | Trace wire and ID tape installed
section | General
checkpoint | All open ends capped
checkpoint | Pipework bedded correctly
checkpoint | Tidy work areas
checkpoint | Pressure test pipework
checkpoint | Visual check (for leeks from valves, tees, saddles, etc)
checkpoint | Backfill around pipework with fines
checkpoint | as-built completed and photo
checkpoint | Installers name & date works completed
textbox | Installers name
textbox | Date:
checkpoint | Tested by & date
textbox | Tested by:
textbox | Date tested:
checkpoint | Council inspector sign off and date
checklist-flat | Council Inspection - ICB Concrete block or concrete reinforced walls - Precast fixings
checkpoint | Inspection Details: To check brackets, bolts, washers and inserts are in place
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist-flat | Council Inspection - ICA Wraps
checkpoint | Inspection Details: To check the wrap is correctly fixed; tapes, flashings, sealants, etc around all penetrations are installed, prior to the cladding or rigid backing being installed
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | Note: All control joints, apron, head and sill flashings to be installed
checklist-flat | Slab Penetration(s) Checklist
checkpoint | Area clear and ready for work (accessible & acceptable)
tickbox | Grid lines marked out available
note | Any issues "Fail" and send report to Kalmar
checkpoint | Slab Penetration(s) Completed
note | Select "PASS" once all slab penetrations are installed, double checked & mark up/photos attached
textbox | Drawing number used for set out
textbox | Penetration sizes
textbox | Total number of penetrations installed
tickbox | Measurements double checked
tickbox | Marked up drawing attached
checklist-flat | Gas Checklist
checkpoint | Location details and relevant mark ups attached
textbox | Location
checkpoint | Separation to other services
checkpoint | Consultant inspection completed as required
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Gas Installation completed
checklist-flat | AIAL - Hawkins Checklist
checkpoint | Trades QA approved and attached if applicable
checkpoint | On site inspection of works if applicable
checkpoint | General photos and observations if applicable
checklist-flat | Bulk Excavation Checklist
checkpoint | Excavation depth determined using appropriate RL's
checkpoint | Confirm location and isolation of relevant services
checkpoint | General excavation documentation and photos attached
checkpoint | Any batters formed correctly
checkpoint | Any trenches/ pits / hazardous areas appropriately isolated
checkpoint | Any soft spots identified and appropriate remedial completed
checkpoint | Any hardfill/ blinding installed correctly to required specification
checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-flat | Council Inspection - ISF Sub-grade before hard fill
checkpoint | Inspection Details: To check soil conditions for conventional and raft floors
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | Note: A PS4 may be required for cut, fill and compaction
checklist-flat | Profile Metal Checklist
checkpoint | Product checked and correct as per specification
checkpoint | All prestart checks completed and approval given to install
checkpoint | General photos, comments and observations during install
checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint | All cladding elements completed, checked and approved as per specifications
signoff | Request Sign Off
checklist | Structure - Concrete Pour - Modified (NB: Only to be used upon Approval by PM)
section | Formwork and Embedded Items
checkpoint | Latest drawings available, checked and referenced
checkpoint | Any additional formwork photos and observations
checkpoint | All formwork elements completed and ready for concrete pour ( excess debris removed )
section | reinforcement
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Verified Size and type correct to specification
checkpoint | Any additional photos and observations
section | Pre-Pour Completion (Approval to pour)
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification | Yes, No
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint | General photos and observations of concrete placement attached
section | Pour / Post-Pour Checks/Sign Off
checkpoint | Concrete checked on arrival & correct (slump, MPa, approved mix, etc)
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint | Concrete surface to specifications
checkpoint | Concrete results 7D & 28D Passed
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Any remedial work completed
checklist | BCO10355536-2 L2 Lounge Extension, Demo L2 roof & construction new L2 slab with egress route to replace fire egress stairs. Reconfig of L1 retail storage space to accom new egress route. Demo existing fire stair. Reinstate all services in the L1 retail and storage areas
section | Electrical works and certificates
checkpoint | Electrical Energy Works
checkpoint | Energy Works Certificate
section | Balustrades
checkpoint | PS3 for Balustrades installation
section | Structural Elements
checkpoint | PS4 Construction Review
checkpoint | Engineer Site Observation Report
section | Fire Protection – Interior Surface Finishes, floor coverings and suspended flexible fabrics
checkpoint | PS3 for Fire Protection – Interior Surface Finishes, floor coverings and suspended flexible fabrics
section | Fire Protection - Intumescent Coatings to Structural Steel
checkpoint | PS3 for Intumescent coatings to Structural Steel
checkpoint | Full compliance with manufacturer's criteria?
button | AS1530 Methods for fire tests on building materials and structures – Part 4: Fire resistance tests of elements of building construction; or | Yes, No
button | NZBS/BS 476 Fire tests on building materials and structures - Parts 21 and 2 | Yes, No
checkpoint | Supplier's material schedule
checkpoint | As-Built to identifying location of steel with intumescent coatings
section | Fire Safety Systems
checkpoint | PS4 Construction Review
checkpoint | Engineer Site Observation Report
section | Fire Stopping of Fire Rated Walls, Floors & Ceilings
checkpoint | PS3 for Passive Fire Protection Systems (e.g. fire stopping of penetrations and intersections or joints)
button | An inspection of each system has been carried out by the installer | Yes, No
button | Variations been approved by Council and certified in writing by an accredited fire protection specialist | Yes, No, N/A
checkpoint | Schedule for Passive Fire installed in accordance with the manufacturer’s installation instructions
tickbox | Project name and address
tickbox | Name, address and contact phone number of the installer / company
tickbox | Date installation inspected
tickbox | Description of service penetration or control joint
tickbox | Identification of the position of the installation (marked up plans)
tickbox | Description of the system used
tickbox | FRR for each installation
tickbox | A unique number for each fire protection measure installed
section | External Cladding
checkpoint | PS3 for Wall cladding installation
section | Soprema Duo membrane
checkpoint | PS3 for Soprema Duo membrane
section | CM of External Facade
checkpoint | PS4 Construction Review
checkpoint | Engineer Site Observation Report - CM of facade installation and certification that the work complies with the design
section | Structural works of SED/PS1 - all structural works
checkpoint | PS4 Construction Review
checkpoint | Engineer Site Observation Report for all related structural works
section | Structural Steel
checkpoint | PS4 Construction Review
checkpoint | Engineer Site Observation Report - Installation of the structural steel
section | Structural Steel: Manufacturers Report
checkpoint | Manufacturing data report to be submitted to council for comment before any on site erection can proceed
button | Amendments relating to Structural Steel | Yes, No
checkpoint | If yes, attach amended document
section | Geotechnical
checkpoint | PS4 Construction Review
checkpoint | Engineer Site Observation Report - e building platform, including site excavations, the installation of any sub-soil drainage and placement of compacted fill as necessary to form the building platform
section | Proprietary Product
checkpoint | PS3 for Proprietary Product Installation
section | Seismic Performance
checkpoint | PS4 Construction Review
checkpoint | Engineer Site Observation Report - Installation of the structural steel
section | Waterproof Membrane Warranty
checkpoint | A warranty certificate from the waterproof membrane supplier or manufacturer for roofs, decks tanking and wet areas membranes is required confirming that the work complies with the design as approved in this building consent and any relevant New Zealand Building Code clauses.
tickbox | Please note: this document is requested to validate the type of membrane that was installed only. It is not used for any other purpose.
section | SS1.1 Sprinkler Systems – Certification
checkpoint | PS3 - automatic sprinkler system from a fire protection contractor confirming compliance with NZS4541:2013
checkpoint | Accredited Inspection Company’s certification for automatic sprinkler system confirming compliance with NZS4541:2013 (altered, extended or new system).
checkpoint | Sprinkler System Certifiers (AON) Certificate of Compliance for the automatic sprinkler system confirming compliance with NZS4541:2013 (new or extended system)
checkpoint | As built plans
tickbox | Clear copy of sprinkler block plan
tickbox | Equipment manufacture register – if make of system not shown on plans
checkpoint | Electrical work certificate for any prescribed electrical work
section | SS2.1 Manual and automatic fire alarms – Certification
checkpoint | PS3 - Manual / automatic fire alarm from a fire alarm installer confirming compliance with NZS4512:2010
checkpoint | Accredited Inspection Bodies Certificate of Completion for manual / automatic fire alarm fire alarm confirming compliance with NZS4512:2010 (new system)
checkpoint | Accredited Inspection Bodies (BFS or Aon Inspections) certification for the alerted manual / automatic fire alarm fire alarm confirming compliance with NZS4512:2010 (altered systems)
checkpoint | As built plans
tickbox | Zone index plan
checkpoint | Operation and Maintenance manual
checkpoint | Electrical work certificate for any prescribed electrical work
section | SS4 Emergency lighting systems – Certification
checkpoint | PS3 - Emergency Lighting from the electrical contractor confirming compliance with NZBC F6
checkpoint | Duration test results for each emergency light fitting from the electrical contractor or IQP
checkpoint | Lux test results for the emergency lighting system (if required by design)
checkpoint | As Built plan including model of systems installed
checkpoint | Electrical work certificate for any prescribed electrical work
section | SS13.1 Mechanical smoke control systems – Certification
checkpoint | PS3 - Mechanical smoke control system
checkpoint | PS4 - Construction Review - Mechanical smoke control system (Mechanical Engineer)
checkpoint | Copies of test/commissioning results verifying measured airflow rates meets design (including interface test with fire alarm system)
checkpoint | As built plans
tickbox | Equipment schedules noting make of systems installed
checkpoint | Operation and Maintenance manual
checklist | SVR:
section | Site Visit Report
checkpoint | SVR Attached
section | Close-Out
checkpoint | SVR Closed-Out
folder-normal | Follow-Up Action(s)
checklist-flat | Council Inspection - IFG Pre-wrap and pre-cladding
checkpoint | Inspection Details: To check bracing; connecting plates; etc are in place
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist-flat | Council Inspection - IFO Bored piles
checkpoint | Inspection Details: To check soil conditions and the size and depth of footings; piles must be in place but prior to the placement of concrete
textbox | Date of Inspection & Name of inspector
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist-flat | Waste Water (Main Line) - Pipeline Installation Checklist
checkpoint | Latest construction drawings referenced and followed
textbox | Drawing & Revision Number
checkpoint | Set Out & Excavation completed checked and accurate
checkpoint | Ground Conditions Checked & Acceptable
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
textbox | Invert Level (upstream manhole)
textbox | Invert Level (downstream manhole)
textbox | Design length of pipe (m)
textbox | Length of pipe installed (m)
textbox | Grade of Pipe-Line %
checkpoint | Connections to manholes complete and approved (photo required)
checkpoint | Air/water test completed (photo of pressure gauge taken at START & FINISH)
checkpoint | Backfill completed & compacted as specified
checkpoint | Relevant tests, photos & as-built information attached
checklist-flat | Grouting Precast Panels
checkpoint | Dry pack completed?
checkpoint | Pumped used?
checkpoint | Grout Used: Mapei SP (If different add in comments)
textbox | Number of bags of grout used
checkpoint | Is the grout mixed properly? (3.0 to 3.4 Litres of Water per bag)
textbox | Number of grout tubes in panel
textbox | Duration of pumping the whole panel
checkpoint | Did grout came out of top of dross tube?
checkpoint | No blow outs
checklist-flat | Weekly QA Progress - All trades sitewide
checkpoint | Trades QA progress report, reviewed and approved
textbox | SP2 - EBH South - List subcontractors onsite
textbox | SP2 - EBH South Level 1 Retail area/ Level 2 Lounge Extension & Fire Egress Stairs - List subcontractors onsite
textbox | SP3 – PC69 - List subcontractors onsite
checkpoint | General photos and comments (if any)
checklist-flat | Council Inspection - ICB Concrete block or concrete reinforcing foundation walls
checkpoint | Inspection Details
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist-flat | Council Inspection - IFO Foundation - Strip Footings
checkpoint | Inspection Details: To check soil conditions and the size and depth of footings and reinforcing steel. All reinforcing steel in place tied and supported; prior to the placement of concrete
textbox | Date of Inspection & Name of inspector
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist-flat | Waterproofing Checklist
checkpoint | Preparation / Substrate acceptable
checkpoint | Correct product delivered and checked - approval given to install
checkpoint | General photos/comments during install
checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
checklist | Quality Control Checklist
section | Details
checkpoint | Details
dropdown | Separable Proportion: | SP2A - EBH South, SP2A - EBH South L1 Retail area/ L2 Lounge Extension & Fire Egress Stairs, SP2B - EBH South Balance of the Ground Floor, SP2C - EBH South Balance of Works, SP3 - Power Centre 69 (PC69), SP4 - Stage 1 Infill - Pre-Stitch, SP5 - Stage 2 Infill - Stitch, SP6 - Check-in Back of House, Check point Charlie (CPC), Honey Pot and Livestock (HPL), Operations Control Centre (OCC)
textbox | Date (--/--/----):
textbox | QA Trade name: (e.g. Structural Steel, Concrete etc.)
textbox | Activity: (e.g. Slab pour)
textbox | Subcontractor name:
textbox | Location/ Gridline/ Component references:
folder-normal | Work Items to be Inspected
folder-normal | Hold Points
section | Checklist Completion
checkpoint | Signature from Hawkins and subcontractor to confirm all items have been inspected and is as per specification, with no damage, or repairs remediated (add by clicking paper clip symbol, select signature)
tickbox | Subcontractor okay to proceed with inspected work: | Yes,No
textbox | Comment for subcontractor: (e.g. Concrete slump and spread tests carried out in accordance with NZS 3112: Part 1. Cubes/ cylinders also taken and sent off for testing after 28 days of curing etc.)
checkpoint | Signature from Hawkins and subcontractor to confirm that works have been completed to satisfaction (add by clicking paper clip symbol, select signature)
checkpoint | Noting in this document relieves the subcontractor of their contractual responsibilities
checklist-flat | Civil - Sanitary Sewer
checkpoint | Location details and relevant mark ups attached
checkpoint | Consultant inspection completed as required
checkpoint | Council Inspection completed as required
checkpoint | Watercare Inspection completed as required
checkpoint | Invert levels recorded
checkpoint | Invert levels as per design
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | CCTV Survey
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Foul Installation completed
checkpoint | Any onsite changes documented (Attach marked up drawings, etc)
checklist-flat | Water Main - Pipeline Installation Checklist
checkpoint | Latest construction drawings referenced and followed
textbox | Drawing & Revision Number
checkpoint | Set Out & Excavation completed checked and accurate
checkpoint | Ground Conditions Checked & Acceptable
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
textbox | Design length of pipe (m)
textbox | Length of pipe installed (m)
checkpoint | Connections complete and approved (photo required)
checkpoint | Relevant test completed (photos required)
checkpoint | Backfill completed & compacted as specified
checkpoint | Relevant tests, photos & as-built information attached
checklist-flat | Hold Point - Hawkins
checkpoint | Hold Point Detail
textbox | Hold Point Detail:
textbox | Contractor (Hawkins or name of subcontractor):
textbox | Contractor Manager:
textbox | Hold point comment: (N/A if no comment)
checkpoint | Sign off by Hawkins Site Manager/ Project Engineer (add by clicking paper clip symbol, select signature)
checklist-flat | Backfill Checklist
checkpoint | Backfill methodology and material confirmed
checkpoint | Any formwork/ debris removed from area
checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint | General photos and observations during backfill
checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | Earthing Protection Checklist
checkpoint | Location details and relevant mark ups attached
textbox | Location
checkpoint | Separation to other services
checkpoint | Consultant inspection
checkpoint | Received QA from Subcontractor?
checkpoint | Continuity test
checkpoint | As Built drawings received
checkpoint | Installation record photos
checkpoint | Earthing Protection Installation completed
checklist-flat | Items to be inspected:
checkpoint | Inspection Detail
textbox | Inspection Detail: (e.g. All dowel holes have been drilled to correct sizes/ centres as per design etc.)
textbox | Contractor (Hawkins or name of subcontractor):
textbox | Contractor Manager:
textbox | Comment: (NA/ of no comment)
textbox | Acceptable? (Yes or No)
checklist-flat | Council Inspection - ICB Concrete block or concrete reinforcing foundation walls and retaining walls
checkpoint | Inspection Details: To check all reinforcing steel is in place and tied; all cells to be clean; washouts to be open for viewing; tanking and sub-soil drain in place, if applicable
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist-flat | Flooring
checkpoint | Floor substrate clean, dry, ready for finishes
checkpoint | Finishes as per architectural plans
checkpoint | Trim thresholds junction as per detail
checkpoint | Any additional photos, comments and observations
checklist-flat | Structural Steel
checkpoint | Steel inspected on arrival, checked and correct and no significant damage
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Correct location and orientation
checkpoint | All drypacking and grouting completed , reviewed and approved to meet required specifications
checkpoint | General photos / comments / observations during install
checklist-flat | Walls Postline
checkpoint | Correct linings installed as per linings plan
checkpoint | Bracing fixings installed correctly as per requirements
checkpoint | Linings cut out for flush boxes neat and tidy
checkpoint | All screws installed flush
checkpoint | Wall approved for stopping
checkpoint | Stopping light check complete ready for paint
checklist-flat | IFG Subfloor Framing
checkpoint | Inspection Details
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist | BCO10355536-2 - QA/ Handover documents
section | Handover
checkpoint | Certificate for Public Use (CPU) inspection (attach)
checkpoint | Certificate for Public Use (CPU) application (attach)
textbox | Author and date applied: (e.g. full name and date --/--/----)
checkpoint | Council inspection outcome checklist (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
folder-normal | Structural
folder-normal | Waterproofing
folder-normal | Concrete
folder-normal | Balustrades and Walkways
folder-normal | Cladding
folder-normal | Carpentry
folder-normal | Aluminium Cassett panel
folder-normal | Door Supply
folder-normal | Intumensent Painting
folder-normal | Webnet
folder-normal | CCTV
folder-normal | Mechanical Services
folder-normal | PA Audio
folder-normal | Fire Protection
folder-normal | Passive Fire
folder-normal | Security Services
folder-normal | Communication Services
folder-normal | Electrical Services
checklist-flat | Description/Number:
checkpoint | Follow-Up Action completed
textbox | Specific Location:
textbox | Detail:
textbox | Action Required:
signoff | Request Review
checklist-flat | Council Inspection - IFO Siting
checkpoint | Inspection Details: To check the set-out of the building; boundaries defined and string lines in place
textbox | Date of Inspection & Name of inspector
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | Note: If you are unable to locate survey pegs a registered Land Surveyor’s certificate maybe required
checklist-flat | Final Sign Off
checkpoint | Doors Installed including drop down seals if applicable
checkpoint | Hardware as per approved schedule
checkpoint | Architraves and skirtings installed
checkpoint | Electrical Power/Lighting second fix installed
checkpoint | Sprinkler/Alarm second fix installed
checkpoint | Security second fix installed
checkpoint | Data second fix installed
checkpoint | HVAC second fix installed
checkpoint | Floor finishes installed as per architectural plan
checkpoint | Paint correct colour
checkpoint | Door signage installed
checkpoint | Manifestations on glazing
checkpoint | Joinery installed correctly
checklist-flat | Comms Checklist
checkpoint | Location details and relevant mark ups attached
textbox | Location
checkpoint | Consultant inspection
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Comms Installation completed
checklist | Demolition Checklist
section | Pre Demolition QA
checkpoint | Traffic management in place (attach TMP)
checkpoint | NVMP completed and attached
checkpoint | Attach any other relevant pre start documentation
checkpoint | All relevant services isolated
tickbox | Power isolated
tickbox | Waste/storm water isolated
tickbox | Gas isolated
tickbox | Telecommunication/Fibre isolated
tickbox | Any other relevant services isolated
textbox | Specify which other services were isolated
checkpoint | General Photos of controls (attach and label)
checkpoint | All pre demolition QA completed and approval given to commence demolition
section | Demolition QA
checkpoint | Prior to demolition, all pre start checks have been completed
checkpoint | General photos and observations of demo (attached and labelled)
section | Demolition Complete
checkpoint | All rubbish/debris removed and area left clean and tidy
checkpoint | Trade Contractor QA received, attached, reviewed and approved
checkpoint | All demolition works completed, checked and approved
checklist-flat | Daily Site Report
checkpoint | Weather Conditions Recorded
dropdown | Weather Conditions AM | Fine, Overcast, Wet
dropdown | Weather Conditions PM | Fine, Overcast, Wet
checkpoint | Site Instructions, Variations & Verbal Instructions.
textbox | SP2 - EBH South
tickbox | Completed
textbox | SP2 - EBH South Level 1 Retail area/ Level 2 Lounge Extension & Fire Egress Stairs
tickbox | Completed
textbox | SP3 – PC69
tickbox | Completed
textbox | SP4 - EBH Stage 1 infill (Pre-stitch)
tickbox | Completed
textbox | East Airfield Demolition
tickbox | Completed
checkpoint | Site Progress Photos
tickbox | Photo or PDF of "Daily Work Zones/ Pre Start" attached
tickbox | EBH South Photos Uploaded
tickbox | Level 1/ 2 & Fire Stairs Photos Uploaded
tickbox | PC69 Photos Uploaded
tickbox | SP4 - EBH Stage 1 infill (Pre-stitch) Photos Uploaded
tickbox | East Airfield Demolition Photos Uploaded
checkpoint | Progress on-site
textbox | SP2 - EBH South
tickbox | Completed
textbox | SP2 - EBH South Level 1 Retail area/ Level 2 Lounge Extension & Fire Egress Stairs
tickbox | Completed
textbox | SP3 – PC69
tickbox | Completed
textbox | SP4 - EBH Stage 1 infill (Pre-stitch)
tickbox | Completed
textbox | East Airfield Demolition
tickbox | Completed
checkpoint | Hawkins Site Management
textbox | Site Operations Team:
tickbox | Peter Hewitt - Project Manager
tickbox | Jack Stevenson - Site Manager
tickbox | Jamie Fazal - Site Manager
tickbox | Steve Smith - Project Manager
tickbox | Tom Wilson - Site Manager
tickbox | Nathan Aracena - Project Engineer
tickbox | Kimi Peraviri - Site Foreman
tickbox | Saul Wilson-Toalii - Site Foreman
tickbox | Sean Ritchie - Site Foreman
tickbox | Martin White - Sub-Foreman
tickbox | Zeed Abu Jwaid - Cadet
textbox | Site Commercial Team:
tickbox | David Harris - Quantity Surveyor
tickbox | Isalei Fuimaono - Quantity Surveyor
tickbox | John Foster - Senior Quantity Surveyor
tickbox | Adrian - Commercial Manager
tickbox | Wade Puklowski - Quantity Surveyor
tickbox | Liam Rikihana - Cadet
tickbox | Jarrod Skeen - Quantity Surveyor
textbox | Other Hawkins Staff, (ie Admin, BIM Manager etc.)
tickbox | Chintan Shah - Design Coordinator
tickbox | Hariete Susada - VDC/ BIM Manager
tickbox | Hassan Aldlimi - Services Engineer Lead
tickbox | James Edge - Construction Planner
tickbox | Jason Carnie - Project Director
tickbox | Jason Holding - Design Manager
tickbox | Darren Prinsloo - Senior Health & Safety Advisor
tickbox | Pam Framhein - Quality Assurance Manager
tickbox | Quintus Slabber - Project Lead
tickbox | Sasha Belcher - Site Administrator
checkpoint | Subcontractors on Site
textbox | SP2 - EBH South
tickbox | Completed
textbox | SP2 - EBH South Level 1 Retail area/ Level 2 Lounge Extension & Fire Egress Stairs
tickbox | Completed
textbox | SP3 – PC69
tickbox | Completed
textbox | SP4 - EBH Stage 1 infill (Pre-stitch)
tickbox | Completed
textbox | East Airfield Demolition
tickbox | Completed
checkpoint | Hawkins Hired Labour Recorded
textbox | Detail & Description of Hired Labour
checkpoint | Health & Safety
button | Accidents / Incidents | Yes , None
textbox | Details of Incident
checkpoint | Delays
textbox | SP2 - EBH South
tickbox | Completed
textbox | SP2 - EBH South Level 1 Retail area/ Level 2 Lounge Extension & Fire Egress Stairs
tickbox | Completed
textbox | SP3 – PC69
tickbox | Completed
textbox | SP4 - EBH Stage 1 infill (Pre-stitch)
tickbox | Completed
textbox | East Airfield Demolition
tickbox | Completed
checkpoint | Contra Charges / Non Conformance
textbox | SP2 - EBH South
tickbox | Completed
textbox | SP2 - EBH South Level 1 Retail area/ Level 2 Lounge Extension & Fire Egress Stairs
tickbox | Completed
textbox | SP3 – PC69
tickbox | Completed
textbox | SP4 - EBH Stage 1 infill (Pre-stitch)
tickbox | Completed
textbox | East Airfield Demolition
tickbox | Completed
checkpoint | Deliveries - Recorded & Photographed
tickbox | EBH Completed
tickbox | Level 1/ 2 & Fire Egress Stairs Completed
tickbox | PC69 Completed
tickbox | SP4 - EBH Stage 1 infill (Pre-stitch) Completed
tickbox | East Airfield Demolition Completed
checkpoint | Hired Plant Recorded
textbox | Description of hired plant on site
checkpoint | Vehicle/ Plant Breakdowns
textbox | SP2 - EBH South
tickbox | Completed
textbox | SP2 - EBH South Level 1 Retail area/ Level 2 Lounge Extension & Fire Egress Stairs
tickbox | Completed
textbox | SP3 – PC69
tickbox | Completed
textbox | SP4 - EBH Stage 1 infill (Pre-stitch)
tickbox | Completed
textbox | East Airfield Demolition
tickbox | Completed
checklist-flat | Daily Site Report
checkpoint | Weather report
checkpoint | Hawkins Personnel
textbox | Total number of Hawkins Personnel
checkpoint | Hawkins labour
textbox | Drive's hours for the day
textbox | Labourer's task for the day
textbox | Crane Crew hours for the day
textbox | Dogman hours for the day
checkpoint | Site Works
textbox | Daily Crew Briefing
checkpoint | SP2 - EBH South (SP2A, SPB, SP2C)
textbox | Subcontractors on site (Working hours)
textbox | Site Progress (Should be Subcontractor/ Work/ Location)
textbox | Constraints/Delays/No Shows
textbox | Out of Hours Works (Number of Subcontractors/ Works completed/ Hawkins Supervision)
textbox | Progress photos (one per area, with a description where and what)
checkpoint | SP3 - PC69
textbox | Subcontractors on site (Working hours)
textbox | Site Progress (Should be Subcontractor/ Work/ Location)
textbox | Constraints/Delays/No Shows
textbox | Out of Hours Works (Number of Subcontractors/ Works completed/ Hawkins Supervision)
textbox | Progress photos (one per area, with a description where and what)
checkpoint | SP4 - Stage 1 Infill & EBH South Balance of Works (PC68, L2 Plant, Shell space, Demo of OCC, Demo of Honey Pot, Demo of Livestock)
textbox | Subcontractors on site (Working hours)
textbox | Site Progress (Should be Subcontractor/ Work/ Location)
textbox | Constraints/Delays/No Shows
textbox | Out of Hours Works (Number of Subcontractors/ Works completed/ Hawkins Supervision)
textbox | Progress photos (one per area, with a description where and what)
checkpoint | Other
textbox | Subcontractors on site (Working hours)
textbox | Site Progress (Should be Subcontractor/ Work/ Location)
textbox | Constraints/Delays/No Shows
textbox | Out of Hours Works (Number of Subcontractors/ Works completed/ Hawkins Supervision)
textbox | Progress photos (one per area, with a description where and what)
checkpoint | Health & Safety
textbox | Accidents/ Incidents
textbox | Near misses
textbox | Site photos
checkpoint | Plant (Hawkins and subcontractors plant)
textbox | Machine (owner, type, usage) register (attach)
textbox | Breakdown/Servicing (attach)
checkpoint | Inspections (AKL council, clients, etc – excluding PCG consultants)
textbox | Purpose for visit
textbox | Vistor Details (Name and Company)
textbox | Comments
checklist-flat | Site Concrete Checklist
checkpoint | Excavation depth and location checked and correct
checkpoint | Ground conditions acceptable
checkpoint | Concrete specifications checked, correct and delivery docket photographed
checkpoint | Site concrete placed
textbox | Placed by:
checkpoint | Concrete placed to the correct height
checkpoint | Site concrete pour completed and finish acceptable
checklist-flat | Set Out / Surveying Checklist
checkpoint | Any RL's Set Out are correct, labelled and photographed
checkpoint | Any grid Set Out are correct, labelled and photographed
checkpoint | Any other relevant Set Out/ survey documentation attached
checkpoint | Survey work completed, checked and accurate
checklist | BCO10355536-1 - Temp enabling works to allow for separation of the Stage 2 construction area (358m2) from the public-facing L1 retail area in the ITP - SP2 - EBH South - L1 Retail
section | Energy Works Certificate - Electrical
checkpoint | Energy Works Certificate - Electrical
section | Structural elements
checkpoint | PS4 Construction Review
checkpoint | Engineer Site Observation Report
section | SS1.1 Sprinkler Systems – Certification
checkpoint | PS3 - automatic sprinkler system from a fire protection contractor confirming compliance with NZS4541:2013
checkpoint | Accredited Inspection Company’s certification for automatic sprinkler system confirming compliance with NZS4541:2013 (altered, extended or new system).
checkpoint | Sprinkler System Certifiers (AON) Certificate of Compliance for the automatic sprinkler system confirming compliance with NZS4541:2013 (new or extended system)
checkpoint | As built plans
checkpoint | Clear copy of sprinkler block plan
checkpoint | Equipment manufacture register – if make of system not shown on plans
checkpoint | Electrical work certificate for any prescribed electrical work
section | SS2.1 Manual and automatic fire alarms – Certification
checkpoint | PS3 - Manual / automatic fire alarm from a fire alarm installer confirming compliance with NZS4512:2010
checkpoint | Accredited Inspection Bodies Certificate of Completion for manual / automatic fire alarm fire alarm confirming compliance with NZS4512:2010 (new system)
checkpoint | Accredited Inspection Bodies (BFS or Aon Inspections) certification for the alerted manual / automatic fire alarm fire alarm confirming compliance with NZS4512:2010 (altered systems)
checkpoint | As built plans
checkpoint | Zone index plan
checkpoint | Operation and Maintenance manual
checkpoint | Electrical work certificate for any prescribed electrical work
section | SS4 Emergency lighting systems – Certification
checkpoint | PS3 - Emergency Lighting from the electrical contractor confirming compliance with NZBC F6
checkpoint | Duration test results for each emergency light fitting from the electrical contractor or IQP
checkpoint | Lux test results for the emergency lighting system (if required by design)
checkpoint | As Built plan including model of systems installed
checkpoint | Electrical work certificate for any prescribed electrical work
section | SS9 Mechanical ventilation or air-conditioning system – Certification
checkpoint | PS3 - Mechanical ventilation or air-conditioning system confirming compliance with NZBC G4
checkpoint | Copies of test/commissioning results verifying measured airflow rates meets design (including any interface test with fire alarm system)
checkpoint | As built plans
checkpoint | Equipment schedules noting make of systems installed
checkpoint | Operation and Maintenance manual
checkpoint | Electrical work certificate
checklist-flat | Intumescent Painting
checkpoint | Steel Erection completed and approval given to apply Intumescent Paint
checkpoint | Paint specifications and product checked
checkpoint | Paint applied using correct methodology
checkpoint | Positector readings uploaded
checkpoint | General photos, comments and observations during paint application
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Paint application complete - area inspected, checked and correct to required specification
checklist-flat | Council Inspection - IFG Subfloor Framing
checkpoint | Inspection Details: To check subfloor bracing, piles, connections, brackets, fastenings, beams, floor-framing members, and floor insulation
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist | BCO10354772 - New single storey 98m2 plant building to house electrical plan (HV Switchgear) - SP3 - PC69
section | Energy Works Certificate - Electrical
checkpoint | Energy Works Certificate - Electrical
section | Structural elements
checkpoint | PS4 Construction Review
checkpoint | Engineer Site Observation Report
section | Fire Stopping of Fire Rated Walls, Floors & Ceilings
checkpoint | Attach PS3
section | Building Platform, including site excavations, the installation of any sub-soil drainage and placement of compacted
checkpoint | PS4 - Building Platform, including site excavations, the installation of any sub-soil drainage and placement of compacted fill as necessary to form the building platform
checkpoint | Geotech Report
section | Masonry
checkpoint | PS4 - Type A or B Masonry
checkpoint | Engineer Observation Report
section | Waterproof Membrane
checkpoint | Product Warranty - Waterproof Membrane
section | Surveyor’s Certificates
checkpoint | Surveyor’s Certificate - Floor Level
checkpoint | Surveyor’s Certificate - Siting
section | SS2.1 Manual and automatic fire alarms – Certification
checkpoint | PS3 - Manual/ automatic fire alarm - NZ4512:2010
checkpoint | Accredited Inspection Bodies Certificate of Completion for manual / automatic fire alarm fire alarm confirming compliance with NZS4512:2010 (new system)
checkpoint | Accredited Inspection Bodies (BFS or Aon Inspections) certification for the alerted manual / automatic fire alarm fire alarm confirming compliance with NZS4512:2010 (altered systems)
checkpoint | As built plans
checkpoint | Zone index plan
checkpoint | Operation and Maintenance manual
checkpoint | Electrical work certificate for any prescribed electrical work
section | SS2.2 Automatic gas detection systems – Certification
checkpoint | PS3 - Fire Protection specialist for the automatic gas detection system confirming compliance with the approved design
checkpoint | As built plans showing location of all systems
checkpoint | Equipment schedules noting make of systems installed
checkpoint | Operation and Maintenance manual
checkpoint | Electrical work certificate
section | SS3.2 Access controlled doors – Certification
checkpoint | PS3 - Installation of access control to doors (confirming fail safe override)
checkpoint | As built plans showing location of all systems
checkpoint | Equipment schedules noting make of systems installed
checkpoint | Operation and Maintenance manual
checkpoint | Electrical work certificate
section | SS4 Emergency lighting systems – Certification
checkpoint | PS3 - Emergency Lighting from the electrical contractor confirming compliance with NZBC F6
checkpoint | Duration test results for each emergency light fitting from the electrical contractor or IQP
checkpoint | Lux test results for the emergency lighting system (if required by design)
checkpoint | As Built plan including model of systems installed
checkpoint | Electrical work certificate for any prescribed electrical work
section | SS9 Mechanical ventilation or air-conditioning system – Certification
checkpoint | PS3 - Mechanical ventilation or air-conditioning system confirming compliance with NZBC G4
checkpoint | Copies of test/commissioning results verifying measured airflow rates meets design (including any interface test with fire alarm system)
checkpoint | As built plans
checkpoint | Equipment schedules noting make of systems installed
checkpoint | Operation and Maintenance manual
checkpoint | Electrical work certificate
checklist | Water Pump Commissioning
section | Pumpset manifold
checkpoint | Connections welded correctly
checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint | Valves fitted correctly
checkpoint | Line strainer fitted between pump & tank
section | Pumps
checkpoint | Pump 1 Startup KPA
checkpoint | Pump 1 kick out pressure KPA
checkpoint | Pump 2 Startup KPA
checkpoint | Pump 2 kick out pressure KPA
checkpoint | Pressure vessel pressure
section | General
checkpoint | Mains water change over
checkpoint | Flow test pump
checkpoint | Pressure tests pipework
checkpoint | Visual check (for leaks from valves, tees, saddles, etc)
checkpoint | Non return valves fitted
checkpoint | Installers name & date works completed
textbox | Installers name
textbox | Date:
checkpoint | Tested by & date
textbox | Tested by:
textbox | Date tested:
checkpoint | Council inspector sign off and date
checklist | Blockwork Checklist
section | Blockwork Set Out/Pre Start QA
checkpoint | Grids available for reference and base of wall marked accurately
checkpoint | RL reference/TOW confirmed
checkpoint | Starter bars correct (location, length and strength)
checkpoint | Concrete/footing clean, tidy and level (ready for first course)
checkpoint | Blockwork reinforcement steel delivered correct and accessible (Attach photos of respective reinforcement docket)
checkpoint | Any additional pre start observations
checkpoint | Correct blocks delivered, checked & accessible
checkpoint | Latest drawings available, checked and referenced
textbox | Relevant drawings & revisions for reference:
checkpoint | Approval given to start laying blockwork
section | Blockwall Pre Pour
checkpoint | Base of wall in correct location
checkpoint | Horizontal reinforcement installed correctly (centres/ size / splicing etc)
checkpoint | Ties / Control joints installed as required
checkpoint | Vertical reinforcement installed as required with appropriate splice laps & secure
checkpoint | Openings checked and correct - location, height and width
checkpoint | Washouts correct/openings covered correctly and wall braced adequately (if required)
checkpoint | Any additional observations/ inspections attached
checkpoint | Wall built within tolerance - straight, level and to the correct height (Approval to pour)
section | Blockwall Pour
checkpoint | Any remedial work completed/observations closed out and approval given to pour
checkpoint | Concrete specifications checked and correct - delivery docket(s) photographed
checkpoint | General photos and any additional observations
checkpoint | All blocks filled to correct height
checkpoint | Starter bars in centre of block if applicable
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Any concrete spillage/splatter cleaned up
checkpoint | Blockwork wall(s) complete to required specification
checklist | Wall Preline
section | Interior Framing
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All framing set out correctly & surveyed in respective area
tickbox | Spot checks on frames for square
tickbox | Spot checks on frame level
tickbox | Fixings are correct including seismic requirements
tickbox | Service Nogs installed
checkpoint | Any additional photos, comments and observations
section | Plumbing Walls First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Plumbing install First fix complete - checks done based on elevations of current drawings
checkpoint | Any additional photos, comments and observations
checkpoint | Council inspection and testing complete and signed off
section | Fire Protection Walls (Alarms) First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with Subcontractor (alarms)
checkpoint | All required 1st fix testing complete
checkpoint | Any additional photos, comments and observations
section | Mechanical Services Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with subcontractor
checkpoint | Any additional photos, comments and observations
section | Electrical Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with Subcontractor
checkpoint | All required first fix testing complete
checkpoint | Any additional photos, comments and observations
section | Data Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | Security Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | AV Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | Insulation/Acoustic
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Spot checks on correct product
checkpoint | Spot checks on correct R value
checkpoint | Fitting Snug
checkpoint | Any additional photos, comments and observations
section | Council Sign Off
checkpoint | Council preline inspection passed
checklist-flat | Council Inspection - ISU Substrate Inspection
checkpoint | Inspection Details: To check the deck, roof or gutter substrate before the membrane is applied
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checklist | Curtain Walls
section | Pre-construction
checkpoint | Inspected and accepted the work area and surfaces ready to commence work
checkpoint | Confirmed site storage requirements, packaging and preservation
section | Opening Handover
checkpoint | Visual check of opening is completed
checkpoint | Steel flat plates or sill have been installed correctly
checkpoint | Trade inspected and opening handed over
section | Installation
checkpoint | Stud welds completed in the area
checkpoint | Brackets installed and welded off
checkpoint | Curtain wall panel installed correctly
checkpoint | 150mm depth rockwool fire insulation installed with 33% compression with 50mm LG zed clips at 600mm centers
checkpoint | Hilti CFS-SP Sil silicone based joint sealant spray min 15mm overlap with 2mm min film thickness
checkpoint | 1.2mm THK continuous galvanised pressing on top of HILTI spray
checkpoint | Aluminum flashing installed and sealed with silicone
section | Airtightness
checkpoint | Top and bottom of all mullions capped and sealed
checkpoint | Smoke seals are sealed with a light coloured caulk
checkpoint | Beware of smoke seals near columns where the installers are restricted in applying caulk
section | Completion
checkpoint | Removal of temporary fixings, spacers & packers
checkpoint | Panel cleaned to remove installation marks
checkpoint | Panel surface are defects free
section | Final Inspection
checkpoint | All defects complete and “signed off”
checkpoint | Issued Façade Maintenance Manuals, service agreements & all warranties and guarantees
section | Subcontractor Sign Off
checkpoint | Subcontractor Sign Off
checklist | Piling
section | Pile Construction
checkpoint | Depth as per Design
textbox | If not, note new depth and approval from Engineer
section | Reinforcing
checkpoint | Reinforcement checked prior to installation
checkpoint | Cover to reinforcing achieved
checkpoint | Alignment of cage correct
checkpoint | RL to top of cage correct
section | Inspections Completed
checkpoint | Approved to pour
checkpoint | Concrete checked on arrival and correct – slump, MPa etc.
section | Post Pour Checks:
checkpoint | RL & location checked and correct
checklist-flat | Council Inspection - IFG Wall/ Roof Framing
checkpoint | Inspection Details: To check hold down straps, bolts, wall and roof framing members; bracing; tie downs; wall framing; beams and lintels; plywood substrates for membranes including falls and outlets
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | Timber treatment and truss layout certificates required
checklist-flat | Council Inspection - IDT Drainage
checkpoint | Inspection Details: To check that all stormwater and sewer drains have been laid to the correct fall and are under test prior to backfilling trenches
textbox | Date of Inspection & Name of inspector
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | Note: An as-built plan is required at time of inspection
checklist | BCO10343425 - Demolition of EBH (baggage handling facility), single-story standalone building. OOG2 Baggage Fitout of 200m2 of existing truck dock undercroft, to be used as an extension to the West Bag Hall (adjacent) internal work - SP1
section | Energy Works Certificates
checkpoint | Energy Works Certificate - Electrical
checkpoint | Energy Works Certificate - Gas (if not, select N/A)
section | Structural Elements
checkpoint | PS4 Construction Review
checkpoint | Engineer Site Observation Report
section | PS3 - Fire Protection – Interior Surface Finishes, floor coverings and suspended flexible fabrics.
checkpoint | Attach PS3
section | PS3 - Passive fire protection systems (if none, select N/A)
checkpoint | Attach PS3
section | PS3 - Overall work from Contractor
checkpoint | Attach PS3
section | SS1.1 Sprinkler Systems – Certification
checkpoint | PS3 - automatic sprinkler system from a fire protection contractor confirming compliance with NZS4541:2013
checkpoint | Accredited Inspection Company’s certification for automatic sprinkler system confirming compliance with NZS4541:2013 (altered, extended or new system).
checkpoint | Sprinkler System Certifiers (AON) Certificate of Compliance for the automatic sprinkler system confirming compliance with NZS4541:2013 (new or extended system)
checkpoint | As built plans
checkpoint | Clear copy of sprinkler block plan
checkpoint | Equipment manufacture register – if make of system not shown on plans
checkpoint | Electrical work certificate for any prescribed electrical work
section | SS2.1 Manual and automatic fire alarms – Certification
checkpoint | PS3 - Manual / automatic fire alarm from a fire alarm installer confirming compliance with NZS4512:2010
checkpoint | Accredited Inspection Bodies Certificate of Completion for manual / automatic fire alarm fire alarm confirming compliance with NZS4512:2010 (new system)
checkpoint | Accredited Inspection Bodies (BFS or Aon Inspections) certification for the alerted manual / automatic fire alarm fire alarm confirming compliance with NZS4512:2010 (altered systems)
checkpoint | As built plans
checkpoint | Zone index plan
checkpoint | Operation and Maintenance manual
checkpoint | Electrical work certificate for any prescribed electrical work
section | SS4 Emergency lighting systems – Certification
checkpoint | PS3 - Emergency Lighting from the electrical contractor confirming compliance with NZBC F6
checkpoint | Duration test results for each emergency light fitting from the electrical contractor or IQP
checkpoint | Lux test results for the emergency lighting system (if required by design)
checkpoint | As Built plan including model of systems installed
checkpoint | Electrical work certificate for any prescribed electrical work
section | SS13.1 Mechanical smoke control systems – Certification
checkpoint | PS3 - Mechanical smoke control system
checkpoint | PS4 - Mechanical smoke control system (Mechanical Engineer)
checkpoint | Copies of test/commissioning results verifying measured airflow rates meets design (including interface test with fire alarm system)
checkpoint | As built plans
checkpoint | Equipment schedules noting make of systems installed
checkpoint | Operation and Maintenance manual
checklist-flat | Item Handover documents
checkpoint | Handover
textbox | Closeout document type: (e.g. CoC for Security Systems or Commissioning results or PS3 for Security, O&M manual, Quality Assurance document etc.)
textbox | Mail reference (if submitted on Aconex):
checkpoint | Additional information (if applicable)
signoff | REQUEST REVIEW
checklist-flat | Retaining Wall Checklist
checkpoint | Retaining wall(s) Set Out/heights confirmed
checkpoint | Area prepared - Excavation depths and location of wall checked and correct
checkpoint | General install photos and observations attached
checkpoint | Correct materials used and installed using appropriate methodology
checkpoint | All relevant services / waterproofing elements completed, checked and approved prior to backfill
checkpoint | Backfill completed - correct materials and compaction methodology used - specified compaction achieved
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Additional observations/ inspections attached and all remedial items closed out
checkpoint | Retaining wall completed to required specifications
checklist-flat | Timber Framing
checkpoint | Dimensions / locations checked and accurate
checkpoint | All frames are square
checkpoint | Frames are straight and level
checkpoint | Fixings are correct including seismic requirements
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All framing completed correctly within tolerance in respective area
checkpoint | Signed Off
checklist-flat | Council Inspection - IPP Plumbing P/L - Preline plumbing
checkpoint | Inspection Details: To check pipe work is under test (water supply and soil wastes)
textbox | Date of Inspection & Name of inspector
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | Note: This inspection may be included with the preline building inspection
checklist-flat | Council Inspection - IPL Postline (Bracing) Inspection
checkpoint | Inspection Details: To check the nailing of all bracing elements nailed prior to installation of architraves, skirtings and cornices prior to any stopping
textbox | Date of Inspection & Name of inspector
checkpoint | Inspection Outcome
checkpoint | Council inspection report (attach)
checkpoint | Any observations/ Failures requiring closeout? (select N/A if none)
checkpoint | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed)
checkpoint | Council inspection completed, attached and any relevant observations closed out Note: PASS once all information is attached including Observations/Failed comments with evidence of closeout
checkpoint | Note: includes nailing of diaphragm ceilings and floors

## Civil Checklists
checklist-flat | Gas Checklist
checkpoint | Location details and relevant mark ups attached
text | Location
checkpoint | Separation to other services
checkpoint | Consultant inspection completed as required
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Gas Installation completed
checklist-flat | Lightning Protection Checklist
checkpoint | Location details and relevant mark ups attached
text | Location
checkpoint | Separation to other services
checkpoint | Consultant inspection
checkpoint | Received QA from Subcontractor?
checkpoint | Continuity test
checkpoint | As Built drawings received
checkpoint | Installation record photos
checkpoint | Lightning Installation completed
checklist-flat | Civil - Sanitary Sewer
checkpoint | Location details and relevant mark ups attached
checkpoint | Consultant inspection completed as required
checkpoint | Council Inspection completed as required
checkpoint | Watercare Inspection completed as required
checkpoint | Invert levels recorded
checkpoint | Invert levels as per design
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | CCTV Survey
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Foul Installation completed
checkpoint | Any onsite changes documented (Attach marked up drawings, etc)
checklist-flat | Flushing Water Checklist
checkpoint | Location details and relevant mark ups attached
text | Location
checkpoint | Consultant inspection completed as required
checkpoint | Council Inspection completed as required
checkpoint | Watercare Inspection completed as required
checkpoint | Invert levels recorded
checkpoint | Invert levels as per design
text | Invert Levels
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | CCTV Survey
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Flushing Water Installation completed
checklist-flat | HV Ducts Checklist
checkpoint | Location details and relevant mark ups attached
text | Location
checkpoint | Separation to other services
checkpoint | Vector / North Power Review
checkpoint | Consultant inspection
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | Installation record photos
checkpoint | HV Ducts Installation completed
checklist-flat | 22kV Ducts Checklist
checkpoint | Location details and relevant mark ups attached
text | Location
checkpoint | Separation to other services
checkpoint | Consultant inspection
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | Installation record photos
checkpoint | 22kV Ducts Installation completed
checklist-flat | Earthing Protection Checklist
checkpoint | Location details and relevant mark ups attached
text | Location
checkpoint | Separation to other services
checkpoint | Consultant inspection
checkpoint | Received QA from Subcontractor?
checkpoint | Continuity test
checkpoint | As Built drawings received
checkpoint | Installation record photos
checkpoint | Earthing Protection Installation completed
checklist-flat | Potable Water Checklist
checkpoint | Location details and relevant mark ups attached
text | Location
checkpoint | Consultant inspection
checkpoint | Council Inspection
checkpoint | Watercare Inspection
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Potable Water Installation completed
checklist-flat | Comms Checklist
checkpoint | Location details and relevant mark ups attached
text | Location
checkpoint | Consultant inspection
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Comms Installation completed
checklist-flat | Storm Checklist
checkpoint | Location details and relevant mark ups attached
text | Location
checkpoint | Consultant inspection completed as required
checkpoint | Council Inspection completed as required
checkpoint | Watercare Inspection completed as required
checkpoint | Invert levels recorded
checkpoint | Invert levels as per design
text | Invert Levels
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | CCTV Survey
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Storm Installation completed
checklist-flat | Sub Soil Checklist
checkpoint | Location details and relevant mark ups attached
text | Location
checkpoint | Consultant inspection completed as required
checkpoint | Correct pipe used?
checkpoint | Correct backfill used?
checkpoint | Installation record photos
checkpoint | Sub Soil Installation completed
checklist-flat | Foul Checklist
checkpoint | Location details and relevant mark ups attached
text | Location
checkpoint | Consultant inspection completed as required
checkpoint | Council Inspection completed as required
checkpoint | Watercare Inspection completed as required
checkpoint | Invert levels recorded
checkpoint | Invert levels as per design
text | Invert Levels
checkpoint | Received QA from Subcontractor?
checkpoint | As Built drawings received
checkpoint | CCTV Survey
checkpoint | Certificates provided
checkpoint | Installation record photos
checkpoint | Foul Installation completed

## Foundations Checklists
checklist-flat | Site Establishment Checklist
checkpoint | Any relevant dilapidation requirements captured
checkpoint | Attach relevant site establishment photos/ documents
checkpoint | Appropriate isolation of site (hoardings / fencing)
checkpoint | Sufficient & Appropriate site/H&S signage erected
checkpoint | Site establishment completed
checklist-flat | Service Location / Isolation Checklist
checkpoint | Power located/Isolated
checkpoint | Hydraulic services located/isolated
checkpoint | Gas located/isolated
checkpoint | Telecommunication/Fibre located/isolated
checkpoint | Any other relevant services located/ isolated
checkpoint | All Services located/ isolated (Pass once all services are located/isolated)
checklist-flat | Asbestos Removal Checklist
checkpoint | Initial Environment/Planning Asbestos report attached
checkpoint | Asbestos Removal approved to commence (all pre-commencement considerations allowed for)
checkpoint | Attach relevant asbestos removal photos (Label all photos with relevant location)
checkpoint | Independent asbestos report completed and attached
checkpoint | Trade contractor QA received, attached, reviewed and approved
checkpoint | Any remedial requirements actioned and completed / closed out
checkpoint | All asbestos removed and approval given to progress with work
checklist | Demolition Checklist
section | Pre Demolition QA
checkpoint | Traffic management in place (attach TMP)
checkpoint | NVMP completed and attached
checkpoint | Attach any other relevant pre start documentation
checkpoint | All relevant services isolated
bool | Power isolated
bool | Waste/storm water isolated
bool | Gas isolated
bool | Telecommunication/Fibre isolated
bool | Any other relevant services isolated
text | Specify which other services were isolated
checkpoint | General Photos of controls (attach and label)
checkpoint | All pre demolition QA completed and approval given to commence demolition
section | Demolition QA
checkpoint | Prior to demolition, all pre start checks have been completed
checkpoint | General photos and observations of demo (attached and labelled)
section | Demolition Complete
checkpoint | All rubbish/debris removed and area left clean and tidy
checkpoint | Trade Contractor QA received, attached, reviewed and approved
checkpoint | All demolition works completed, checked and approved
checklist-flat | Setout / Surveying Checklist
checkpoint | Any RL's setout are correct, labelled and photographed
checkpoint | Any grid setout are correct, labelled and photographed
checkpoint | Any other relevant setout/ survey documentation attached
checkpoint | Survey work completed, checked and accurate
checklist-flat | Bulk Excavation Checklist
checkpoint | Excavation depth determined using appropriate RL's
checkpoint | Confirm location and isolation of relevant services
checkpoint | General excavation documentation and photos attached
checkpoint | Any batters formed correctly
checkpoint | Any trenches/ pits / hazardous areas appropriately isolated
checkpoint | Any soft spots identified and appropriate remedial completed
checkpoint | Any hardfill/ blinding installed correctly to required specification
checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-flat | Detailed Excavation Checklist
checkpoint | Location accurate
checkpoint | Depth correct (allow for site concrete if required)
checkpoint | Width correct (allow for boxing if required)
checkpoint | Any relevant excavation for services is completed and accurate
checkpoint | Excess Material Cleaned up and removed as required
checkpoint | Detailed excavation completed, reviewed and approved
checklist | Concrete Pour Checklist (Self Perform)
section | Pour Details
checkpoint | Pour Details
text | Area to be poured:
text | Date of pour:
checkpoint | Latest drawings available, checked and referenced
section | Formwork and Embedded Items
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
section | Reinforcing
checkpoint | Trades QA received, attached, reviewed and approved
holdpoint | Raise Remedial / Request trades QA / Signoff
checkpoint | Size and type correct to specification
checkpoint | Reinforcing spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint | Welding certificates sited and attached
checkpoint | Mill certificate reviewed, attached and approved
checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
section | Pre-Pour Completion (Approval to pour)
checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint | Any relevant service requirements completed (locations checked and accurate)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | All relevant inspections completed and attached
checkpoint | Main contractor inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
checkpoint | Concrete Supplier Specifics
text | Supplier Name:
text | Specified concrete strength:
text | Concrete strength ordered:
text | Concrete quantity ordered:
checkpoint | Test blocks booked
checkpoint | All concrete dockets photographed/ attached
checkpoint | Concrete strength test reports attached and required concrete strength achieved
section | Concrete Distribution
checkpoint | General distribution photos, documents and observations attached
checkpoint | All concrete distributed correctly (area left clean and tidy)
section | Placement Method
checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification | Yes, No
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint | Area left clean and tidy
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat | Tanking / Waterproofing Checklist (Audit)
checkpoint | Preparation / Substrate acceptable
checkpoint | Correct product delivered and checked - approval given to install
checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint | Trades QA received & attached as applicable
checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
checklist-flat | Grouting Precast Panels
checkpoint | Dry pack completed?
checkpoint | Pumped used?
checkpoint | Grout Used: Mapei SP (If different add in comments)
text | Number of bags of grout used
checkpoint | Is the grout mixed properly? (3.0 to 3.4 Litres of Water per bag)
text | Number of grout tubes in panel
text | Duration of pumping the whole panel
checkpoint | Did grout came out of top of dross tube?
checkpoint | No blow outs
checklist-flat | Timber Framing (Audit)
checkpoint | Approval given to install timber framing
checkpoint | Dimensions / locations checked and accurate
checkpoint | All frames are square
checkpoint | Frames are straight and level
checkpoint | Fixings are correct
checkpoint | Any bracing requirements installed
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received, attached, reviewed and approved
hold point | Raise Remedial / Request trades QA / Signoff
checkpoint | All framing completed correctly within tolerance in respective area
checklist-flat | Underslab Services Checklist (Audit)
checkpoint | Electrical services/ conduits installed, fixed in correct location, backfilled and correct as per design
hold point | Raise Remedial / Request trades QA / Signoff
checkpoint | Hydraulic services installed, fixed in correct location, backfilled and correct as per design
bool | Storm Water
bool | Sewer
bool | Water Supply
hold point | Raise Remedial / Request trades QA / Signoff
checkpoint | Gas installed, fixed in correct location, backfilled and correct as per design
hold point | Raise Remedial / Request trades QA / Signoff
checkpoint | Telecommunication/Fibre installed, fixed in correct location, backfilled and correct as per design
hold point | Raise Remedial / Request trades QA / Signoff
checkpoint | Any other relevant services installed, fixed in correct location, backfilled and correct as per design
hold point | Raise Remedial / Request trades QA / Signoff
checkpoint | Any additional observations / attachments
checkpoint | Any relevant inspections carried out and attached - observations documented and closed out
checkpoint | All subfloor services correctly installed to respective area
checklist-flat | Retaining Wall Checklist
checkpoint | Retaining wall(s) setout/heights confirmed
checkpoint | Area prepared - Excavation depths and location of wall checked and correct
checkpoint | General install photos and observations attached
checkpoint | Correct materials used and installed using appropriate methodology
checkpoint | All relevant services / waterproofing elements completed, checked and approved prior to backfill
checkpoint | Backfill completed - correct materials and compaction methodology used - specified compaction achieved
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Additional observations/ inspections attached and all remedial items closed out
checkpoint | Retaining wall completed to required specifications
checklist-flat | Waterproofing Checklist
checkpoint | Preparation / Substrate acceptable
checkpoint | Correct product delivered and checked - approval given to install
checkpoint | General photos/comments during install
checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
checklist-flat | Site Concrete Checklist
checkpoint | Excavation depth and location checked and correct
checkpoint | Ground conditions acceptable
checkpoint | Concrete specifications checked, correct and delivery docket photographed
checkpoint | Site concrete placed
text | Placed by:
checkpoint | Concrete placed to the correct height
checkpoint | Site concrete pour completed and finish acceptable
checklist | Blockwork Checklist
Section | Blockwork Setout/Pre Start QA
checkpoint | Grids available for reference and base of wall marked accurately
checkpoint | RL reference/TOW confirmed
checkpoint | Starter bars correct (location, length and strength)
checkpoint | Concrete/footing clean, tidy and level (ready for first course)
checkpoint | Blockwork reinforcing steel delivered correct and accessible (Attach photos of respective reinforcing docket)
checkpoint | Any additional pre start observations
checkpoint | Correct blocks delivered, checked & accessible
checkpoint | Latest drawings available, checked and referenced
text | Relevant drawings & revisions for reference:
checkpoint | Approval given to start laying blockwork
Section | Blockwall Prepour
checkpoint | Base of wall in correct location
checkpoint | Horizontal reinforcing installed correctly (centres/ size / splicing etc)
checkpoint | Ties / Control joints installed as required
checkpoint | Vertical reinforcing installed as required with appropriate splice laps & secure
checkpoint | Openings checked and correct - location, height and width
checkpoint | Washouts correct/openings covered correctly and wall braced adequately (if required)
checkpoint | Any additional observations/ inspections attached
checkpoint | Wall built within tolerance - straight, level and to the correct height (Approval to pour)
Section | Blockwall Pour
checkpoint | Any remedial work completed/observations closed out and approval given to pour
checkpoint | Concrete specifications checked and correct - delivery docket(s) photographed
checkpoint | General photos and any additional observations
checkpoint | All blocks filled to correct height
checkpoint | Starter bars in centre of block if applicable
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Any concrete spillage/splatter cleaned up
checkpoint | Blockwork wall(s) complete to required specification
checklist-flat | Backfill Checklist
checkpoint | Backfill methodology and material confirmed
checkpoint | Any formwork/ debris removed from area
checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint | General photos and observations during backfill
checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | Intumescent Painting Checklist
checkpoint | Steel Erection completed and approval given to apply Intumescent Paint
checkpoint | Paint specifications and product checked
checkpoint | Paint applied using correct methodology
checkpoint | General photos, comments and observations during paint application
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Paint application complete - area inspected, checked and correct to required specification
checklist-flat | Precast Panel Installation Checklist
checkpoint | Inspected on arrival and damage free
checkpoint | Installed in correct location
checkpoint | Adequately braced
checkpoint | Grout sleeves correctly grouted
checkpoint | Panel install complete (checked location & level)
checklist-flat | Piling Pre-Start Checklist
checkpoint | Piles setout, surveyed and clearly marked
checkpoint | Accurate RL confirmed for piling reference
checkpoint | Acceptable site conditions and access for piling rig
checkpoint | Additional photos/ observations / reports attached
checkpoint | Approval given to commence piling
bool | approval given to dig
bool | relevant services identified and isolated / clearly marked
bool | relevant information communicated to piling trade
bool | any environmental requirements considered and enacted
checklist-flat | Piling Checklist (Audit)
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Relevant inspections completed and attached - any observations recorded and closed out
checkpoint | Piling spoil removed and work area left clean and tidy
checkpoint | Any additional completion/handover documents completed and attached
checkpoint | All piles completed (locations and heights checked and correct within tolerance)
checklist | Insitu Stitch Joints
section | Pour Details
text | Area to be poured:
text | Date of pour:
section | Formwork
checkpoint | Formwork braced & fixed correctly
checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
section | Reinforcing
checkpoint | Size and type correct to specification
section | Pre-Pour Completion (Approval to pour)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | All relevant inspections completed and attached
checkpoint | Main contractor inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
text | Supplier Name:
text | Specified concrete strength:
text | Concrete strength ordered:
text | Concrete quantity ordered:
checkpoint | Test blocks booked
checkpoint | All concrete dockets photographed/ attached
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached

## Foundations Services Checklists
checklist-flat | Underground Services Checklist (Audit)
checkpoint | Electrical services/ conduits installed, fixed in correct location, backfilled and correct as per design
checkpoint | Hydraulic services installed, fixed in correct location, backfilled and correct as per design
checkpoint | Gas installed, fixed in correct location, backfilled and correct as per design
checkpoint | Telecommunication/Fibre installed, fixed in correct location, backfilled and correct as per design
checkpoint | Any other relevant services installed, fixed in correct location, backfilled and correct as per design
checkpoint | Any additional observations / attachments
checkpoint | Any relevant inspections carried out and attached - observations documented and closed out
checkpoint | All subfloor services correctly installed to respective area
checklist-flat | Manhole Install Checklist
checkpoint | Latest construction drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Ground Conditions Checked and Acceptable
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct manhole size installed to specified Invert Level
checkpoint | Manhole risers & steps installed and joints sealed as specified (photo required)
checkpoint | Manhole benching completed and acceptable (photo required)
checkpoint | Concrete manhole cover installed and sitting correctly with hole covered if required (photo required)
checkpoint | Cast Iron Lid installed and fixed at correct height (photo required)
checkpoint | CCTV test complete
checkpoint | Manhole Installation reviewed and approved (photo required)
checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
checklist-flat | Stormwater (Main Line) - Pipeline Installation Checklist
checkpoint | Latest construction drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Ground conditions checked & acceptable
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
text | Invert Level (upstream manhole)
text | Invert Level (downstream manhole)
text | Design length of pipe (m)
text | Length of pipe installed (m)
text | Grade of Pipe-Line %
checkpoint | Connections to manholes complete and approved (photo required)
checkpoint | Backfill completed & compacted as specified (Photos during backfill required)
checkpoint | Relevant tests, photos & as-built information provided
checklist-flat | Waste Water (Main Line) - Pipeline Installation Checklist
checkpoint | Latest construction drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Ground Conditions Checked & Acceptable
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
text | Invert Level (upstream manhole)
text | Invert Level (downstream manhole)
text | Design length of pipe (m)
text | Length of pipe installed (m)
text | Grade of Pipe-Line %
checkpoint | Connections to manholes complete and approved (photo required)
checkpoint | Air/water test completed (photo of pressure gauge taken at START & FINISH)
checkpoint | Backfill completed & compacted as specified
checkpoint | Relevant tests, photos & as-built information attached
checklist-flat | Watermain - Pipeline Installation Checklist
checkpoint | Latest construction drawings referenced and followed
text | Drawing & Revision Number
checkpoint | Setout & Excavation completed checked and accurate
checkpoint | Ground Conditions Checked & Acceptable
checkpoint | Bedding depth and material correct (photo required)
checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
text | Design length of pipe (m)
text | Length of pipe installed (m)
checkpoint | Connections complete and approved (photo required)
checkpoint | Relevant test completed (photos required)
checkpoint | Backfill completed & compacted as specified
checkpoint | Relevant tests, photos & as-built information attached
checklist-flat | Connection from Private - Public Checklist
checkpoint | Approval to connect given by relevant Authority
text | EPA number
text | Corridor Access Request
checkpoint | Advice notice conditions from relevant Authority received
checkpoint | Work done in accordance with requirements (photos required)
checklist | Core Water Checklist
section | Cold water main
checkpoint | Connections brazed correctly
checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint | Valves fitted correctly
section | Hot water main
checkpoint | Connections welded correctly
checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint | Expansion allowed for
checkpoint | Lagging installed and neat
checkpoint | Valves fitted correctly
section | General
checkpoint | Open ends of riser capped for testing
checkpoint | Checked for crossovers
checkpoint | Tidy work areas
checkpoint | Allowance for expansion
checkpoint | Pressure test to 1500kpa for 30mins
checkpoint | Visual check (for leeks from valves, tees, saddles, etc)
checkpoint | Seismic bracing for pipework longitude and latitude
checkpoint | Lateral labelling of pipework backflow devices fitted
checkpoint | Pre Line Inspection Passed
checkpoint | Installers name & date works completed
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date
checklist | In Ground Water & Gas Mains Checklist
section | Water mains
checkpoint | All fittings scrapped correctly
checkpoint | Iso used on fittings
checkpoint | Valves fitted correctly
checkpoint | Fittings welded & weld indicator has popped out
checkpoint | Trace wire and ID tape installed
section | Gas main
checkpoint | All fittings scrapped correctly
checkpoint | Iso used on fittings
checkpoint | Valves fitted correctly
checkpoint | Fittings welded & weld indicator has popped out
checkpoint | Trace wire and ID tape installed
section | General
checkpoint | All open ends capped
checkpoint | Pipework bedded correctly
checkpoint | Tidy work areas
checkpoint | Pressure test pipework
checkpoint | Visual check (for leeks from valves, tees, saddles, etc)
checkpoint | Backfill around pipework with fines
checkpoint | as-built completed and photo
checkpoint | Installers name & date works completed
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date
checklist | Water Pump Commissioning
section | Pumpset manifold
checkpoint | Connections welded correctly
checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint | Valves fitted correctly
checkpoint | Line strainer fitted between pump & tank
section | Pumps
checkpoint | Pump 1 Startup KPA
checkpoint | Pump 1 kick out pressure KPA
checkpoint | Pump 2 Startup KPA
checkpoint | Pump 2 kick out pressure KPA
checkpoint | Pressure vessel pressure
section | General
checkpoint | Mains water change over
checkpoint | Flow test pump
checkpoint | Pressure tests pipework
checkpoint | Visual check (for leaks from valves, tees, saddles, etc)
checkpoint | Non return valves fitted
checkpoint | Installers name & date works completed
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date
checklist-flat | Slab Penetration(s) Checklist
checkpoint | Area clear and ready for work (accessible & acceptable)
bool | Grid lines marked out available
label | Any issues "Fail" and send report to Kalmar
checkpoint | Slab Penetration(s) Completed
label | Select "PASS" once all slab penetrations are installed, double checked & mark up/photos attached
text | Drawing number used for set out
text | Penetration sizes
text | Total number of penetrations installed
bool | Measurements double checked
bool | Marked up drawing attached
checklist | Sewer - Pipeline Installation Checklist
section | Pipe Laying
checkpoint | Latest consented drawings
text | Drawing Ref No.
checkpoint | Setout completed checked and accurate
checkpoint | Excavation Accurate - Location & Depth
checkpoint | Ground Conditions Checked & Acceptable
checkpoint | Bedding depth and material correct
checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | Start Invert
text | Finish Invert
text | Grade of Pre-Line %
text | Product Type
checkpoint | Install Tests completed, reviewed & approved
text | Local Authority Inspection Passed
text | Name of inspector
text | Date
checkpoint | Pipe Laying Completed
bool | Bedding Sound
bool | Soil Removed
bool | Trench Compacted
bool | Hard Filled
checkpoint | Connections to manholes complete and approved
checkpoint | Air Test Complete
section | Backfill
checkpoint | Backfill methodology and material confirmed
checkpoint | Any formwork/ debris removed from area
checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint | General photos and observations during backfill
checkpoint | Backfill completed correctly and heights checked/ correct

## Structure Checklists
checklist-flat | Backfill
checkpoint | Backfill methodology and material confirmed
checkpoint | Any formwork/ debris removed from area
checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint | General photos and observations during backfill
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Backfill completed correctly and heights checked/ correct - desired compaction achieved
checklist-flat | Waterproofing Checklist
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Preparation / Substrate acceptable
checkpoint | Correct product delivered and checked - approval given to install
checkpoint | General photos/comments during install
checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
checklist | Concrete Pour
section | Formwork and Embedded Items
checkpoint | Latest drawings available, checked and referenced
text | Grid Line
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Grids and RLs clearly marked for reference
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Formwork sufficiently fixed and braced (incl any propping)
checkpoint | Shear studs installed as-per shop drawings & check ring test
checkpoint | Any rebates/ nibs / cast in items are correctly positioned, sized and appropriately fixed in place
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g joints to exisiting concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint | Any additional formwork photos and observations
checkpoint | All formwork elements completed and ready for concrete pour ( excess debris removed )
section | Reinforcing
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Size and type correct to specification
checkpoint | Reinforcing spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
section | Pre-Pour Completion (Approval to pour)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Council inspection completed and attached
checkpoint | All relevant inspections completed and attached
checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification | YES, NO, N/A
checkpoint | General photos and observations of concrete placement attached
section | Pour / Post-Pour Checks/Sign Off
checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete surface to specifications
checkpoint | Area left clean and tidy
checkpoint | Any remedial work completed
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist | Structure - Concrete Pour - Modified (NB: Only to be used upon Approval by PM)
section | Formwork and Embedded Items
checkpoint | Latest drawings available, checked and referenced
checkpoint | Any additional formwork photos and observations
checkpoint | All formwork elements completed and ready for concrete pour ( excess debris removed )
section | Reinforcing
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Verified Size and type correct to specification
checkpoint | Any additional photos and observations
section | Pre-Pour Completion (Approval to pour)
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification | YES, NO, N/A
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint | General photos and observations of concrete placement attached
section | Pour / Post-Pour Checks/Sign Off
checkpoint | Concrete checked on arrival & correct (slump, MPa, approved mix, etc)
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint | Concrete surface to specifications
checkpoint | Concrete results 7D & 28D Passed
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Any remedial work completed
checklist-flat | Drypacking and Grouting
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Preparation / Substrate acceptable
checkpoint | Installed as per installation requirements
checkpoint | General photos/comments during install
checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint | All drypacking and grouting completed , reviewed and approved to meet required specifications
checklist-flat | CFRP Strengthening
checkpoint | Has the concrete been prepared
checkpoint | Has the product been installed as per manufacturers requirement
checkpoint | Trades QA received, attached, reviewed and approved
button | Is this an architectural area requiring attention | YES, NO, N/A
checklist-flat | Intumescent Painting Checklist
checkpoint | Steel Erection completed and approval given to apply Intumescent Paint
checkpoint | Paint specifications and product checked
checkpoint | Paint applied using correct methodology
checkpoint | Positector readings uploaded
checkpoint | General photos, comments and observations during paint application
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Paint application complete - area inspected, checked and correct to required specification
checklist | Blockwork
section | Pre-Pour Checks
checkpoint | Location Recorded
text | Zone / Level / Grid(s) recorded
checkpoint | Starter bars: correct size, length, position, clean
checkpoint | Control joints/construction joints/expansion joints are located and provided
checkpoint | Penetrations/embedded items - Overall Pass
button | Penetrations located and formed/allowed for (i.e openings, services penetrations) | YES, NO, N/A
button | Embedded items (i.e anchor bolts etc) are correct and at the correct location | YES, NO, N/A
checkpoint | Blockwork specification and quality - Overall Pass
button | Mortar condition, specification, finish | YES, NO, N/A
button |  | YES, NO, N/A
button | Course type, square cuts, aligned | YES, NO, N/A
button | Cleanout ports provided | YES, NO, N/A
button | Debris and droppings removed | YES, NO, N/A
checkpoint | Reinforcement - Overall Pass
button | Bars: Correct location, quantity, diameter, grade, spacing, | YES, NO, N/A
button | Reinforcement is clean and securely tied Laps and bends correct | YES, NO, N/A
button | Lintel and trimmer reinforcing above and around openings and penetrations etc | YES, NO, N/A
button | Control joint reinforcing, dowel bars, tape provided | YES, NO, N/A
button | Bond beam reinforcing provided at the top of wall | YES, NO, N/A
button | Earthing bars present where required, including cable connections | YES, NO, N/A
button | Grout compressive strength, condition and admixtures (20MPa min., 5mm - 12mm agg.) | YES, NO, N/A
checkpoint | Engineer informed of pour (see consultant folder and ensure observations are closed out)
holdpoint | All inspectors comments addressed
section | Pour /Post Pour
checkpoint | General photos/comments/observations during placement
checkpoint | Trades QA received & complete
button | Grout dockets & test cylinder results recorded | YES, NO, N/A
checklist-flat | Structural Steel Checklist
checkpoint | Steel inspected on arrival, checked and correct and no significant damage
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Correct location and orientation
checkpoint | All drypacking and grouting completed , reviewed and approved to meet required specifications
checkpoint | General photos / comments / observations during install

## Facade Checklists
checklist-flat | Service Penetrations to Rigid Air Barriers
checkpoint | All pipes should be sealed with caulk, a gap between the pipe and air barrier should be between 3-8mm
checkpoint | Ducts are sealed with caulking and backing rods for gaps under 35mm. Gaps over 35mm is sealed with rubber gaskets or flashing with caulking. All seals on duct penetrations require photographic evident particularly the top seal and be signed off.
checkpoint | Cables penetrations are sealed with caulking.
button | Caulking material should be applied between cables before packing the bundle, a minimum of 2 cable ties should be tightly applied between 5 and 10mm apart to minimise movement where the caulking material is applied. | YES, NO, N/A
button | Bundling of cables should be limited to 8 cables. | YES, NO, N/A
button | Spacer (backing rods) with a minimum size of 5mm should be placed between cable bundles. | YES, NO, N/A
checkpoint | Cable trays are expected to be treated similar to fire/smoke penetration which the red highlighting the caulking material.
checklist-flat | Envelope - Warm Roof Checklist
checkpoint | Substrate clear of debris (no sharp edges/ air pockets)
checkpoint | Vapour barrier installed (up parapet)
checkpoint | PIR insulation (brick pattern, tight joint)
checkpoint | Cement board (Perma base Dek correct fixing)
checkpoint | Soprema Sopradere quick primer
checkpoint | Membrane installed (80mm min lap)
checkpoint | Duo Capsheet installed
checkpoint | Internal gutters (ply installed, lap of membrane and capsheet into drain)
checkpoint | Seal around drain
checklist-flat | Envelope - Internal Gutter Checklist
checkpoint | 17mm C-D structural plywood
checkpoint | minimum fall of 1:100 (0.57°)
checkpoint | 5 mm fillets
checkpoint | Locations for outlets and sumps
checkpoint | Correct width and level/depth
checkpoint | General photos, comments and observations during paint application
checkpoint | Trades QA received, attached, reviewed and approved
checklist-flat | Timber Framing Checklist
checkpoint | Dimensions / locations checked and accurate
checkpoint | All frames are square
checkpoint | Frames are straight and level
checkpoint | Fixings are correct including seizmac requirements
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All framing completed correctly within tolerance in respective area
checkpoint | Signed Off
checklist-flat | Envelope - Parapet
checkpoint | Structural stee level and in correct location
checkpoint | Dry packing complete
checkpoint | Timber/DPC adequately fixed to framing
checkpoint | Timber framing @ 400 c/c
checkpoint | Ply correctly fixed (21mm H3.2)
checkpoint | Insulation correctly installed
checkpoint | Curtain wall bracket checked
checkpoint | Curtain wall checked
checkpoint | Photograph curtain wall junctions
checkpoint | Steel top plate (parapet build up)
checkpoint | Parapet ply installed (21mm H3.2)
checkpoint | EDPM installed to parapet
checkpoint | Integrity of the EPDM airseals. All corner junctions must be photographed and signed off
checkpoint | The connection between the EPDM airseal and the EQUUS SOPREMA DUOTHERM warm roof cap sheet requires sign off.
checkpoint | Membrane installed to EPDM (check laps and junctions 150mm to roofing)
checkpoint | Integrity of the membrane to the EPDM. All corner junctions must be photographed and signed off
checkpoint | Cap flashing installed
checklist-flat | Envelope - Anchors
checkpoint | Installed as per drwg
checkpoint | sealed/waterproofed
checkpoint | General photos, comments and observations during paint application
checkpoint | Trades QA received, attached, reviewed and approved
checklist-flat | Profile Metal Checklist
checkpoint | Product checked and correct as per specification
checkpoint | All prestart checks completed and approval given to install
checkpoint | General photos, comments and observations during install
checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint | All cladding elements completed, checked and approved as per specifications
holdpoint | Request Signoff
checklist | Envelope - Sills
section | Sills
checkpoint | No sharp edges
checkpoint | Substrate applied (membrane applied)
checkpoint | Sill try to be sealed (check for backing rod and sealant)
checkpoint | Sill tray fixed at correct centres
checkpoint | Check workmanship of junctions and seals
checkpoint | Check lap of membrane
section | Airtightness
checkpoint | All unexposed caulking should use light colour caulk (eg, Light gray, or white)
checkpoint | Check corner junctions for quality. (Typically, the lab test only covers typical panels.) Particularly without factory made corners.
checkpoint | Mounting brackets sealed to the slab with caulking, tolerance slots should also be sealed
checklist | Aluminium Joinery / Glazing
section | Joinery Install
checkpoint | Opening approved (ready for install)
checkpoint | Joinery in correct location
checkpoint | Appropriate fixings installed
checkpoint | Any air/ weather seals completed
checkpoint | Appropriate external flashings installed and sealed
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Inspection completed and joinery install completed as per specification
section | Final Inspection/Sign Off
checkpoint | Install completed, reviewed and approved
checkpoint | Item checked, functioning and damage free
checklist | Curtain Wall Checklist
section | Pre-construction
checkpoint | Inspected and accepted the work area and surfaces ready to commence work
checkpoint | Confirmed site storage requirements, packaging and preservation
section | Opening Handover
checkpoint | Visual check of opening is completed
checkpoint | Steel flat plates or sill have been installed correctly
checkpoint | Trade inspected and opening handed over
section | Installation
checkpoint | Stud welds completed in the area
checkpoint | Brackets installed and welded off
checkpoint | Curtain wall panel installed correctly
checkpoint | 150mm depth rockwool fire insulation installed with 33% compression with 50mm LG zed clips at 600mm centers
checkpoint | Hilti CFS-SP Sil silicone based joint sealant spray min 15mm overlap with 2mm min film thickness
checkpoint | 1.2mm THK continuous galvanised pressing on top of HILTI spray
checkpoint | Aluminum flashing installed and sealed with silicone
section | Airtightness
checkpoint | Top and bottom of all mullions capped and sealed
checkpoint | Smoke seals are sealed with a light coloured caulk
checkpoint | Beware of smoke seals near columns where the installers are restricted in applying caulk
section | Completion
checkpoint | Removal of temporary fixings, spacers & packers
checkpoint | Panel cleaned to remove installation marks
checkpoint | Panel surface are defects free
section | Final Inspection
checkpoint | All defects complete and “signed off”
checkpoint | Issued Façade Maintenance Manuals, service agreements & all warrantees and guarantees
section | Subcontractor Sign Off
checkpoint | Subcontractor Sign Off

## Fitout Checklists
checklist | Ceiling Preline incl High Level Services Checklist
section | QA - Plumbing First Fix
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Consultants Inspection sign off
checkpoint | Any additional photos, comments and observations
checkpoint | Council inspection and testing complete and signed off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of pipework by Hawkins
section | Fire Protection (Sprinklers & Alarms) First Fix
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Consultant inspection sign off
checkpoint | Any additional photos, comments and observations
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of pipework by Hawkins
section | Mechanical Services First Fix
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
checkpoint | All required testing complete
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Consultant sign off
checkpoint | All ends covered/protected to reduce debris
checkpoint | Witness testing of compliance check by Hawkins
section | Electrical First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required testing complete
checkpoint | Any additional photos, comments and observations
checkpoint | Consultant sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of compliance check by Hawkins
section | Data First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required testing complete
checkpoint | Any additional photos, comments and observations
checkpoint | Consultant sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of compliance check by Hawkins
section | Security First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required testing complete
checkpoint | Any additional photos, comments and observations
checkpoint | Consultant sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of compliance check by Hawkins
section | Rondo Ceiling Grid Installation
checkpoint | Service penetrations mark out completed, checked and acceptable (clashes considered)
checkpoint | Ceiling Grid ( pass when all below ticked)
tickbox | Ceiling height correct
tickbox | Appropriate fixings used and installed as per required specification
tickbox | Appropriate spacings for respective grid elements
tickbox | Perimeter channel/angle installed correctly
tickbox | All strong backs installed where required to meet specification
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
section | Insulation Prior to Lining
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Insulation pre lining works completed, checked & approved
tickbox | Correct product & R value as per specification
tickbox | Fitting Snug
checkpoint | Any additional photos, comments and observations
section | Council Sign Off
checkpoint | Council preline inspection passed
checklist-flat | Final Sign Off Checklist
checkpoint | Doors Installed including drop down seals if applicable
checkpoint | Hardware as per approved schedule
checkpoint | Architraves and skirtings installed
checkpoint | Electrical Power/Lighting second fix installed
checkpoint | Sprinkler/Alarm second fix installed
checkpoint | Security second fix installed
checkpoint | Data second fix installed
checkpoint | HVAC second fix installed
checkpoint | Floor finishes installed as per architectural plan
checkpoint | Paint correct colour
checkpoint | Door signage installed
checkpoint | Manifestations on glazing
checkpoint | Joinery installed correctly
checklist-flat | Walls Postline Checklist
checkpoint | Correct linings installed as per linings plan
checkpoint | Bracing fixings installed correctly as per requirements
checkpoint | Linings cut out for flush boxes neat and tidy
checkpoint | All screws installed flush
checkpoint | Wall approved for stopping
checkpoint | Stopping light check complete ready for paint
checklist-flat | Flooring Checklist
checkpoint | Floor substrate clean, dry, ready for finishes
checkpoint | Finishes as per architectural plans
checkpoint | Trim thresholds junction as per detail
checkpoint | Any additional photos, comments and observations
checklist | Walls Preline Checklist
section | Interior Framing
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All framing setout correctly & surveyed in respective area
tickbox | Spot checks on frames for square
tickbox | Spot checks on frame level
tickbox | Fixings are correct including seismic requirements
tickbox | Service Nogs installed
checkpoint | Any additional photos, comments and observations
section | Plumbing Walls First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Plumbing install First fix complete - checks done based on elevations of current drawings
checkpoint | Any additional photos, comments and observations
checkpoint | Council inspection and testing complete and signed off
section | Fire Protection Walls (Alarms) First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with Subcontractor (alarms)
checkpoint | All required 1st fix testing complete
checkpoint | Any additional photos, comments and observations
section | Mechanical Services Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with subcontractor
checkpoint | Any additional photos, comments and observations
section | Electrical Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with Subcontractor
checkpoint | All required first fix testing complete
checkpoint | Any additional photos, comments and observations
section | Data Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | Security Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | AV Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | Insulation/Acoustic
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Spot checks on correct product
checkpoint | Spot checks on correct R value
checkpoint | Fitting Snug
checkpoint | Any additional photos, comments and observations
section | Council Sign Off
checkpoint | Council preline inspection passed
checklist-flat | Ceiling Postline Checklist
checkpoint | Correct linings installed as per linings plan
checkpoint | Fixings as per specification including if glue required
checkpoint | Service penetrations cut out as per architecture RCP
checkpoint | Any ceiling hatches installed & fixed correctly
checkpoint | Ceiling approved for stopping
checkpoint | Stopping light check complete ready for paint