## Checklist Templates
Warnings | Id | Type | Name | Values | Prompting Name | Resource Id
|  | checklist | Cst - S - Completion Documents |  | Cst - S - Completion Documents | 44c11e7b-4c4a-4831-bbfa-e9ba04cbc9ed
|  | checkpoint | All relevant Compliance Documentation completed and attached above
| e8bbb8c9-787d-570e-b97f-a58f4aced4b3 | button | LBP Memorandum/ Record of works filled out, signed and attached | Yes, No
| 31666c12-7a27-5da5-b851-24b6e58619fa | button | Any Additional Compliance Documentation - Completed and Attached | Yes, No
| 09a00379-7fe7-5779-b183-4466df51fa0d | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
|  | signoff | Request Signoff
|  | checklist | Cst - S - Completion Documents |  | Cst - S - Completion Documents | 58c28b58-7c20-4459-af18-878f47899bfb
|  | checkpoint | All relevant Compliance Documentation completed and attached above
DataPoint is missing 'button' values | 57f99dc3-e084-5ac8-a2f8-386e35bb10dc | button | LBP Memorandum/ Record of works filled out, signed and attached
DataPoint is missing 'button' values | 346306d2-1bb8-56f1-b4f7-1dd59e8b85ca | button | Any Additional Compliance Documentation - Completed and Attached
| b8ffe595-6011-50b7-bf62-b77e2980eb5a | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
|  | signoff | Request Signoff
|  | checklist | ST - S - Concrete Pour |  | ST - S - Concrete Pour | be61ffa9-cfa9-49e4-8b28-b6cb0469486f
|  | section | Pour Details
|  | checkpoint | Pour details entered
| 9a9325fa-2274-529a-ab8e-f94ee22ee9f9 | textbox | Area to be poured:
| 56ed79b4-5a63-5605-beb7-5ef2caa1a8e0 | textbox | Date of pour:
|  | checkpoint | Latest drawings available, checked and referenced
|  | section | Formwork and Embedded Items
|  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
|  | checkpoint | Service penetrations formed correctly and locations checked/correct
|  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
|  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
|  | section | Reinforcing
|  | checkpoint | Size and type correct to specification
|  | checkpoint | Reinforcing spacing and location correct
|  | checkpoint | Specified covers checked/correct
|  | checkpoint | Splice laps checked/correct
|  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
| 34bb84e4-10b4-5507-b628-772e4575a3e0 | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
| 891cfc02-39b2-5f28-a05b-ae610f07dad0 | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
|  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
|  | checkpoint | All starter bars are installed correctly (location, size and spacing )
|  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
|  | checkpoint | Welding certificates sited and attached
|  | checkpoint | Mill certificate reviewed, attached and approved
|  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
|  | section | Pre-Pour Completion (Approval to pour)
|  | checkpoint | Waterproofing elements have been correctly installed and checked
|  | checkpoint | Relevant service requirements completed (locations checked and accurate)
|  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
|  | checkpoint | Ryman inspection completed - Approval given to pour concrete
|  | section | Concrete Supplier Specifics
|  | checkpoint | Concrete Supplier details entered
| d2388cb1-564d-5695-98e2-fde19be8314a | textbox | Supplier Name:
| a27d744c-a869-5ba2-a9da-6528e8047052 | textbox | Specified concrete strength: | mPA
| e5c71b25-c337-5535-bb91-06107a008acf | textbox | Concrete strength ordered: | mPA
| 871da1c4-a6c9-5a75-aeb3-45c29959710c | textbox | Concrete quantity ordered: | m3
| 388991e7-056c-5b32-ae73-12a274ca12d2 | button | Test blocks booked | Yes, No
|  | checkpoint | All concrete dockets photographed/ attached
|  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
|  | section | Placement Method
|  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
|  | checkpoint | Heights and falls checked/confirmed before placement
| d61fd526-e8d8-5e4b-ad33-fc06b0dee556 | button | Is the cover correct to specification | Yes, No
|  | checkpoint | Heights and falls checked/ confirmed after placement
|  | checkpoint | Any curing compound applied correctly
|  | checkpoint | Concrete placement completed - specified level of finish achieved
|  | section | Post Pour Checks/Sign Off
|  | checkpoint | Any remedial work completed
|  | signoff | Raise remedial/ Request Signoff
|  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
|  | checkpoint | Inspections completed and issued to Foreman
|  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
|  | checklist | ST - S - Concrete Pour (2) |  | ST - S - Concrete Pour | 02ec139b-7391-4d55-8c2e-9b5895441e2b
|  | section | Pour Details
|  | checkpoint | Pour details entered
| 112a07df-c3f2-55fb-81d1-a31aa182aefe | textbox | Area to be poured:
| 86e83e67-b402-5285-b33f-97987244d42e | textbox | Date of pour:
|  | checkpoint | Latest drawings available, checked and referenced
|  | section | Formwork and Embedded Items
|  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
|  | checkpoint | Service penetrations formed correctly and locations checked/correct
|  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
|  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
|  | section | Reinforcing
|  | checkpoint | Size and type correct to specification
|  | checkpoint | Reinforcing spacing and location correct
|  | checkpoint | Specified covers checked/correct
|  | checkpoint | Splice laps checked/correct
|  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
| 653754c7-8741-56eb-9990-0fc17450442f | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
| 1157f30f-6907-5392-a4da-4dcabd260076 | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
|  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
|  | checkpoint | All starter bars are installed correctly (location, size and spacing )
|  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
|  | checkpoint | Welding certificates sited and attached
|  | checkpoint | Mill certificate reviewed, attached and approved
|  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
|  | section | Pre-Pour Completion (Approval to pour)
|  | checkpoint | Waterproofing elements have been correctly installed and checked
|  | checkpoint | Relevant service requirements completed (locations checked and accurate)
|  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
|  | checkpoint | Ryman inspection completed - Approval given to pour concrete
|  | section | Concrete Supplier Specifics
|  | checkpoint | Concrete Supplier details entered
| 3dc188ec-d2dd-564f-8b3d-a4362a2e26e2 | textbox | Supplier Name:
| 3622c47a-ed79-59c7-9dcb-05f0c207f87f | textbox | Specified concrete strength: | mPA
| 0739c6d5-4cfc-5585-8cbc-dde22e1dcc03 | textbox | Concrete strength ordered: | mPA
| d6ccc68d-272d-5355-b48b-3610619d9582 | textbox | Concrete quantity ordered: | m3
DataPoint is missing 'button' values | f58b6e7c-b1c3-5fdc-9a91-f598b8af82a9 | button | Test blocks booked
|  | checkpoint | All concrete dockets photographed/ attached
|  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
|  | section | Placement Method
|  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
|  | checkpoint | Heights and falls checked/confirmed before placement
DataPoint is missing 'button' values | e519905f-0f22-5e72-801e-353c573079f4 | button | Is the cover correct to specification
|  | checkpoint | Heights and falls checked/ confirmed after placement
|  | checkpoint | Any curing compound applied correctly
|  | checkpoint | Concrete placement completed - specified level of finish achieved
|  | section | Post Pour Checks/Sign Off
|  | checkpoint | Any remedial work completed
|  | signoff | Raise remedial/ Request Signoff
|  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached