## Sheet1
DESCRIPTION OF CHECK
PRE-START HRV
Area clear, access good, enough space for install
Duct Route clear, Penetrations complete
Nogs/Supports in place
FIRST FIX HRV
HRV installed straight and level and correct orientation.
Cowl sealed to Upstand
Correct HRV installed. (Insert Photo)
Filter installed and easily accessable
HRV seismically braced and vibration isolated
Heater Bank installed to Manufacturers instructions
Fire dampers installed to manufacturers instructions. Drop tested where applicable
Breakaway joins either side of fire dampers
Access Panels in duct for fire dampers, filters, cleaning etc
Ductwork straight/level and well supported incl any seismic restraints
Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
Balancing Dampers locked open and accessible
Flexible ducts taped then cable tied
Second fix grille and access panel locations recorded
All open ducts sealed off with plastic film or similar
Control Cables installed
Power Cables installed
Plans marked up for As Builts and 2nd fix grille locations
SECOND FIX HRV
Grilles installed square and level
Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
Area left clean and tidy, finger prints removed
Controllers fitted off
Power fitted off
Plant and controllers labelled
COMMISSION HRV
Commissioned and Paperwork submitted
COC issued