## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | HRV Checklist | [5 empty] | HRV Checklist
section | PRE-START HRV
checkpoint | Area clear, access good, enough space for install
checkpoint | Duct Route clear, Penetrations complete
checkpoint | Nogs/Supports in place
section | FIRST FIX HRV
checkpoint | HRV installed straight and level and correct orientation.
checkpoint | Cowl sealed to Upstand
checkpoint | Correct HRV installed. (Insert Photo)
checkpoint | Filter installed and easily accessable
checkpoint | HRV seismically braced and vibration isolated
checkpoint | Heater Bank installed to Manufacturers instructions
checkpoint | Fire dampers installed to manufacturers instructions. Drop tested where applicable
checkpoint | Breakaway joins either side of fire dampers
checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
checkpoint | Ductwork straight/level and well supported incl any seismic restraints
checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
checkpoint | Balancing Dampers locked open and accessible
checkpoint | Flexible ducts taped then cable tied
checkpoint | Second fix grille and access panel locations recorded
checkpoint | All open ducts sealed off with plastic film or similar
checkpoint | Control Cables installed
checkpoint | Power Cables installed
checkpoint | Plans marked up for As Builts and 2nd fix grille locations
section | SECOND FIX HRV
checkpoint | Grilles installed square and level
checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
checkpoint | Area left clean and tidy, finger prints removed
checkpoint | Controllers fitted off
checkpoint | Power fitted off
checkpoint | Plant and controllers labelled
section | COMMISSION HRV
checkpoint | Commissioned and Paperwork submitted
checkpoint | COC issued