## ITP Summary
Job | 2025-14 - Iron Arena - OD & H
checklist-sectioned | Precast Components ITP
section | Job Approval Documents/Construction Documents
checkpoint | Received Construction drawing from Client | Pass/Fail/NA | attachments/photos
checkpoint | Shop drawings Prepared, reviewed and updated. Issued "As For Construction" | Pass/Fail/NA | attachments/photos
All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint | FormWork |  | attachments/photos/Sign
checkpoint | Reinforcement (Reo) |  | attachments/photos/Sign
checkpoint | Embedded Items and their placement |  | attachments/photos/Sign
checkpoint | Concreting (mix design) |  | attachments/photos/Sign
section | Test on Concrete (requests and approvals)
checkpoint | Request From Client |  | attachments/photos/Sign
checkpoint | Test schedule and Test Results |  | attachments/photos/Sign
section | Transport
Sub section 01 | Transport 01
| Any Lifting, Loading, Transport Instructions from Client | Pass/Fail/NA | attachments/photos/Sign
| Transport Vehicle Approvals | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. | Pass/Fail/NA | attachments/photos/Sign
section | Other Documentations
checkpoint | Special Instructions |  | attachments/photos/Sign
checkpoint | Other |  | attachments/photos/Sign
section | Final Inspection | Pass/Fail/NA | attachments/photos/Sign
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected. | Pass/Fail/NA | attachments/photos/Sign
This is a general section
& no repeating items pls

## Flight 1
Job | 2025-14 - Iron Arena - OD & H
checklist | Checkers Checklist - Flight 1
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos
checkpoint | Overall Measurements of Construction Element (1.915m x .3m x .07m)
Tick Box | T1-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-07 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-08 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-09 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-10 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing
Tick Box | T1-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-07 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-08 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-09 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-10 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm)
Tick Box | T1-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-07 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-08 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-09 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T1-10 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation -Foot Anchors Galvanised1.3T-35mm (Nexus P52155) 02 Nos
checkpoint | Formwork - Timber | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments
checklist | Installers Checklist
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
section | Pre-Pour Check Approvals
Tic Box | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Overall Measurements of Construction Element (1.915m x .3m x .07m) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm) | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete- N40Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged - Broom | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
Repeating items
no repeating items pls

## Flight 2
Job | 2025-14 - Iron Arena - OD & H
checklist | Checkers Checklist - Flight 2
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos
checkpoint | Overall Measurements of Construction Element (1.925m x .282m x .07m)
Tick Box | T2-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-07 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-08 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-09 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing
Tick Box | T2-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-07 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-08 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-09 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm)
Tick Box | T2-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-07 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-08 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T2-09 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation -Foot Anchors Galvanised1.3T-35mm (Nexus P52155) 02 Nos
checkpoint | Formwork - Timber | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments
checklist | Installers Checklist
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
section | Pre-Pour Check Approvals
Tic Box | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Overall Measurements of Construction Element (1.925m x .282m x .07m) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm) | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete- N40Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged - Broom | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
Repeating items
no repeating items pls

## Flight 3
Job | 2025-14 - Iron Arena - OD & H
checklist | Checkers Checklist - Flight 3
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos
checkpoint | Overall Measurements of Construction Element (1.925m x .272m x .07m)
Tick Box | T3-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-07 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing
Tick Box | T3-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-07 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm)
Tick Box | T3-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-07 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation -Foot Anchors Galvanised1.3T-35mm (Nexus P52155) 02 Nos
checkpoint | Formwork - Timber | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments
checklist | Installers Checklist
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
section | Pre-Pour Check Approvals
Tic Box | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Overall Measurements of Construction Element (1.925m x .272m x .07m) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm) | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete- N40Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged - Broom | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
Repeating items
no repeating items pls

## Flight 4
Job | 2025-14 - Iron Arena - OD & H
checklist | Checkers Checklist - Flight 4
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos
checkpoint | Overall Measurements of Construction Element (1.925m x .265m x .07m)
Tick Box | T4-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T3-06 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing
Tick Box | T4-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T4-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T4-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T4-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T4-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T4-06 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm)
Tick Box | T4-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T4-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T4-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T4-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T4-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T4-06 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation -Foot Anchors Galvanised1.3T-35mm (Nexus P52155) 02 Nos
checkpoint | Formwork - Timber | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments
checklist | Installers Checklist
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
section | Pre-Pour Check Approvals
Tic Box | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Overall Measurements of Construction Element ((1.925m x .265m x .07m) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm) | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete- N40Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged - Broom | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
Repeating items
no repeating items pls

## Flight 5
Job | 2025-14 - Iron Arena - OD & H
checklist | Checkers Checklist - Flight 5
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos
checkpoint | Overall Measurements of Construction Element (1.915m x .315m x .07m)
Tick Box | T5-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-05 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing
Tick Box | T5-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-05 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm)
Tick Box | T5-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T5-05 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation -Foot Anchors Galvanised1.3T-35mm (Nexus P52155) 02 Nos
checkpoint | Formwork - Timber | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments
checklist | Installers Checklist
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
section | Pre-Pour Check Approvals
Tic Box | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Overall Measurements of Construction Element (1.915m x .315m x .07m) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm) | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete- N40Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged - Broom | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
Repeating items
no repeating items pls

## Flight 6
Job | 2025-14 - Iron Arena - OD & H
checklist | Checkers Checklist - Flight 6
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos
checkpoint | Overall Measurements of Construction Element (1.915m x .315m x .07m)
Tick Box | T6-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-07 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-08 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-09 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing
Tick Box | T6-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-07 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-08 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-09 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm)
Tick Box | T6-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-07 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-08 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T6-09 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation -Foot Anchors Galvanised1.3T-35mm (Nexus P52155) 02 Nos
checkpoint | Formwork - Timber | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments
checklist | Installers Checklist
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
section | Pre-Pour Check Approvals
Tic Box | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Overall Measurements of Construction Element (1.915m x .315m x .07m) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm) | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete- N40Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged - Broom | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
Repeating items
no repeating items pls

## Flight 7
Job | 2025-14 - Iron Arena - OD & H
checklist | Checkers Checklist - Flight 7
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos
checkpoint | Overall Measurements of Construction Element (1.875m x .315m x .07m)
Tick Box | T7-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-07 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing
Tick Box | T7-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-07 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm)
Tick Box | T7-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T7-07 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation -Foot Anchors Galvanised1.3T-35mm (Nexus P52155) 02 Nos
checkpoint | Formwork - Timber | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments
checklist | Installers Checklist
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
section | Pre-Pour Check Approvals
Tic Box | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Overall Measurements of Construction Element (1.875m x .315m x .07m) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules -4 x M12-50mm - Position, Size, Orientation - As per the drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm) | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete- N40Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged - Broom | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
Repeating items
no repeating items pls

## Flight 8
Job | 2025-14 - Iron Arena - OD & H
checklist | Checkers Checklist - Flight 8
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos
checkpoint | Overall Measurements of Construction Element (1.915m x .315m x .07m)
Tick Box | T8-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-07 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules - 4 x M12-50mm - Position, Size, Orientation - As per the drawing
Tick Box | T8-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-07 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm)
Tick Box | T8-01 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-02 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-03 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-04 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-05 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-06 | Pass/Fail/NA | attachments/photos/Comments
Tick Box | T8-07 | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation - Foot Anchors Galvanised 1.3T-35mm (Nexus P52155) 02 Nos
checkpoint | Formwork - Timber | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments
checklist | Installers Checklist
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
section | Pre-Pour Check Approvals
Tic Box | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments
Tic Box | Overall Measurements of Construction Element (1.915m x .315m x .07m) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules - 4 x M12-50mm - Position, Size, Orientation - As per the drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check (min 30mm) | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete- N40Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged - Broom | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
Repeating items
no repeating items pls

## Instaler CheckList PL Panels (hidden)
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Overall Measurements of construction Eliment |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Void - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules - - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Fillet / Chamfer instasllation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel Thickness check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 150mm
dropdown |  | 200mm
checkpoint | Panel length check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 15m
dropdown |  | 16m
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Panel is clean |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment (Reo) arrangmnet |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photoes/Coments
Kempsey Sale Yard
checklist | Installers Checklist
section | Job Aproval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Eye Anchor - Pinhead Lifter Galvanised 5Ton x 180mm (LA05180) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Void - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes
dropdown |  | 0
dropdown |  | 4
dropdown |  | 6
dropdown |  | 7
dropdown |  | 8
dropdown |  | 9
dropdown |  | other
checkpoint | Embeded Item - Ferrules -M16x96 - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes
dropdown |  | 2
dropdown |  | 6
dropdown |  | 8
dropdown |  | 9
dropdown |  | 10
dropdown |  | 12
dropdown |  | other
checkpoint | ID Plate |  |  | attachments/photoes/Coments
text box
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Use Required Mould,Supports,Ties - Bridge Plank Mould |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & alligned -Check |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover Check - (top min cov30mm, Bottom Min Cov 25mm) |  | Pass/Fail/NA | attachments/photoes/Coments
section | Quality Assuarance
checkpoint | QA - Final Check of ALL measurerments & Diaganals |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | APPROVAL FROM ENGINEER
section | Other Arangments
checkpoint | Concrete surface Finish Requirment arranged (Fine Finish) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
[5 empty] | Repeating items | SP1
SP2
SP3
SP4
SP5
SP6
SP7
SP8
SP9
SP10
SP11
SP12
SP13
SP14

## Instaler CheckList ST(steps) (hidden)
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Overall Measurements of construction Eliment |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Void - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules - - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Fillet / Chamfer instasllation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel Thickness check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 150mm
dropdown |  | 200mm
checkpoint | Panel length check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 15m
dropdown |  | 16m
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Panel is clean |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment (Reo) arrangmnet |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photoes/Coments
Kempsey Sale Yard
checklist | Installers Checklist
section | Job Aproval Documents/Constrction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item -Lifters -XXXXXX - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules -M12x50 - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes
checkpoint | ID Plate |  |  | attachments/photoes/Coments
text box
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Use Required Mould,Supports,Ties - Bridge Plank Mould |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & alligned -Check |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover Check - (min cov XXmm) |  | Pass/Fail/NA | attachments/photoes/Coments
section | Quality Assuarance
checkpoint | QA - Final Check of ALL measurerments & Diaganals |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | APPROVAL FROM ENGINEER
section | Other Arangments
checkpoint | Concrete surface Finish Requirment arranged (BROOM\SPONGE Finish) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
[5 empty] | Repeating items | STD1-1
STD1-2
STD1-3
STD1-4
STD1-5
STD1-6
STD1-7
STD1-8
STD1-9
STD1-10
STD1-11

## Sheet1 (hidden)
Repeating items | SP1 | STD1-1
| SP2 | STD1-2
| SP3 | STD1-3
| SP4 | STD1-4
| SP5 | STD1-5
| SP6 | STD1-6
| SP7 | STD1-7
| SP8 | STD1-8
| SP9 | STD1-9
| SP10 | STD1-10
| SP11 | STD1-11
SP12
SP13
SP14

## Sheet2 (hidden)
Repeating items |  | Ferrule (M16x96) | Holes | Thk | Length (Max) | Width (Max) | Weight | Volume | Con .Grade | Min:Cover (Top) | Min:Cover (Bot) | Test Freeq: | Con Grade
| SP1 | 2 | 8 | 200 | 1580 | 5695 | 4.26 | 1.72 | S32 | 30 | 25 | 1 test- 3 cylinders- 7days & 28days | 40
| SP2 | 10 | 8 | 200 | 1100 | 5979 | 3.96 | 1.6 | S32 | 30 | 25
| SP3 | 10 | 9 | 200 | 1100 | 6263 | 4.16 | 1.68 | S32 | 30 | 25
| SP4 | 12 | 0 | 200 | 890 | 6480 | 2.8 | 1.13 | S32 | 30 | 25
| SP5 | 2 | 4 | 200 | 1100 | 2909 | 1.88 | 0.76 | S32 | 30 | 25
| SP6 | 6 | 7 | 200 | 1580 | 5226 | 3.53 | 1.42 | S32 | 30 | 25
| SP7 | 9 | 8 | 200 | 1100 | 5793 | 3.74 | 1.51 | S32 | 30 | 25
| SP8 | 10 | 9 | 200 | 1100 | 6361 | 4.13 | 1.66 | S32 | 30 | 25
| SP9 | 12 | 0 | 200 | 890 | 6796 | 2.89 | 1.16 | S32 | 30 | 25
| SP10 | 2 | 6 | 200 | 1100 | 4311 | 2.83 | 1.14 | S32 | 30 | 25
| SP11 | 8 | 6 | 200 | 1100 | 4595 | 3.02 | 1.22 | S32 | 30 | 25
| SP12 | 9 | 7 | 200 | 1100 | 4878 | 3.21 | 1.3 | S32 | 30 | 25
| SP13 | 9 | 7 | 200 | 1100 | 5162 | 3.41 | 1.38 | S32 | 30 | 25
| SP14 | 10 | 0 | 200 | 890 | 5380 | 2.31 | 0.93 | S32 | 30 | 25
| STD1-1 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-2 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-3 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-4 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-5 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-6 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-7 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-8 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-9 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-10 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-11 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
xx
xx
SLUMP AT TIME OF POURING TO BE WITHIN THE PERMISSIBLE TOLERANCE IN AS1379-2007 FOR NOMINAL
SLUMP SPECIFIED.
- AT LEAST 1 SAMPLE FOR EVERY 50m³ SHALL BE TAKEN AT THE SITE, BUT NOT LESS THAN 3 SAMPLES
SHALL BE TAKEN PER POUR. FIRST AND LAST BATCH PER DAY TO BE SAMPLED, THE OTHER TAKEN
PROGRESSIVELY DURING THE POUR, RECORDING LOCATION IN POUR WHERE SAMPLE WAS TAKEN.
- IT IS PERMISSIBLE TO REDUCE THE NUMBER OF SAMPLES TO 2 FOR POURS OF LESS THAN 30m³, AND 1
FOR POURS OF LESS THAN 10m³, SAMPLE CONSISTS OF AT LEAST 3 CYLINDERS. ONE CYLINDER SHALL BE
TESTED AT 7 DAYS. TWO CYLINDERS SHALL BE TESTED AT 28 DAYS. 7 & 28 DAY TEST RESULTS TO BE
SENT IMMEDIATELY TO NORTHROP CONSULTING ENGINEERS.
PC12. COLOUR AND FINISH SAMPLES OF PRECAST ELEMENTS SHALL BE SUBMITTED TO THE ARCHITECT FOR
APPROVAL BEFORE ELEMENTS ARE CAST.
Pinhead Lifters
Plastic Solutions Australia
https://www.psa.com.au › psa-products › pinhead-lifters
LA05180. Description: *Capacity x length (L) 5 Series Pinhead Lifter Galvanised x 180mm. Box30. CodeLA05240. Description: *Capacity x length (L) 5 Series ..
Pinhead Lifter Galvanised 5Ton x 180mm (LA05180)

## old doc (hidden)
BP-01 | Bridge Plank | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Testing
section | Transport
Checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Final Inspection |  |  | 6.3 | 0.6 | 0.1 | 0.378 | 0.9072
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected. |  |  | 6.3 | 0.6 | 0.1 | 0.378 | 0.9072
|  |  |  | 0.8 | 0.6 | 0.1 | 0.048 | 0.1152
checklist | Checkers Checklist
checkpoint | Overall Measurements | [5 empty] | 0.804 | 1.9296
checkpoint | Void Correct Position
checkpoint | Ferrules - Measurements & Size - NS / FS
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 30mm
checkpoint | Panel Thickness confirmed
dropdown |  | 150mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Eye Anchor - 2.5T | 4
textbox | Ferrules - M20 x 96mm | 10
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Bridge Plank Mould
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 30mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - Broom
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?