## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
b9970d66-4dfd-451e-91ae-e2268d7d47f1 |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 14 | 1401 | Waterproofing | Balcony Areas
4df8e8a7-ced7-4fb8-aeff-806d2dbcee75 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 14 | 1402 | Waterproofing | Balcony Areas
51aef3b2-1651-49e6-bf2c-103517311454 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 14 | 1403 | Waterproofing | Balcony Areas
aaec0da3-de40-4f5f-882a-ba66fa08d254 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 14 | 1405 | Waterproofing | Balcony Areas
048f38ac-fc99-4533-bde2-9cdea559b179 |  | fail | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 14 | Landscaping | Waterproofing - Lv14 NW Planters
b8e37835-ec3c-49c2-bf2e-54b79c081e9f |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 15 | 1501 | Waterproofing | Balcony Areas
8343739e-2a9a-46a0-8b0d-d3d32f6ba2aa |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 15 | 1502 | Waterproofing | Balcony Areas
ba0ea8fb-d136-41ef-bcf2-0dc6c3ca7dfe |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 15 | 1503 | Waterproofing | Balcony Areas
41c93b47-66ed-47e5-b166-78d7bfac77b6 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 15 | 1505 | Waterproofing | Balcony Areas
75c759b7-cf46-47af-bfa4-18f2ae18af82 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 15 | 1506 | Waterproofing | Balcony Areas
15398984-417d-40c3-a07b-eece217d6cce |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 16 | 1601 | Waterproofing | Balcony Areas
b36d533a-6f65-4220-bb6f-9bbc657719c0 |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 16 | 1602 | Waterproofing | Balcony Areas
a577d56b-0239-4821-9263-a7fb44eb3b54 |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 16 | 1603 | Waterproofing | Balcony Areas
7486f4a2-da54-4c43-8b03-72231282169c |  | fail | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 16 | 1605 | Waterproofing | Balcony Areas
7b041f44-0069-42c1-a54f-3c00ab2642a0 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 16 | 1606 | Waterproofing | Balcony Areas
4e3f371d-2342-45be-9e06-cdbb62d8f858 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 16 | 1607 | Waterproofing | Balcony Areas
74c9054a-b254-443b-9288-84c9812f1b40 |  | fail | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 17 | 1701 | Waterproofing | Balcony Areas
e737f02b-0a78-473b-b20f-8e10d01bd868 |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 17 | 1702 | Waterproofing | Balcony Areas
69e6ad88-1531-48a5-9215-9d9383b0e1f5 |  | fail | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 17 | 1703 | Waterproofing | Balcony Areas
159e7af2-bfca-4a6a-9795-14e5b5d9ebe3 |  | fail | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 17 | 1705 | Waterproofing | Balcony Areas
fa5a878b-0611-4717-a703-fa1d939d20cc |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 17 | 1706 | Waterproofing | Balcony Areas
539e504c-cb0b-491d-8c42-5ced995e7f7c |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 17 | 1707 | Waterproofing | Balcony Areas
b9e34ea9-6d7c-4a22-a962-18087412abff |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 18 | 1801 | Waterproofing | Balcony Areas
abcd731c-0dd0-47fb-8d17-eb7c640d46d2 |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 18 | 1802 | Waterproofing | Balcony Areas
83cb61d6-8283-429e-a2be-3fc41b9d0f32 |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 18 | 1803 | Waterproofing | Balcony Areas
1a802d38-28e5-4738-9946-355bdbd8a510 |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 18 | 1805 | Waterproofing | Balcony Areas
9847b31a-3082-400c-812c-1f00d38108f7 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 18 | 1806 | Waterproofing | Balcony Areas
3d68f269-a9fd-4eb5-b5a1-f51ab08780dc |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 18 | 1807 | Waterproofing | Balcony Areas
ee91bf6f-4feb-4db5-82a6-9df763c15542 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 19 | 1901 | Waterproofing | Balcony Areas
29c621e0-f5c4-4a8c-af7e-7400bd91f12b |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 19 | 1902 | Waterproofing | Balcony Areas
76fbe378-6efb-427e-bc75-fafbd9ef30b4 |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 19 | 1903 | Waterproofing | Balcony Areas
e9afbec5-1b0d-421b-97d5-e8f55d1ba5e6 |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 19 | 1905 | Waterproofing | Balcony Areas
02784b74-c4cf-48bc-8774-87e4b482b83a |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 19 | 1906 | Waterproofing | Balcony Areas
4eee1f03-25b6-4d63-9ddb-d99a4624001e |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 19 | 1907 | Waterproofing | Balcony Areas
154b432e-54ca-44d8-bff5-59915670ec0a |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 20 | 2001 | Waterproofing | Balcony Areas
575f2986-8da4-43f8-8cdf-15c02c6cc875 |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 20 | 2002 | Waterproofing | Balcony Areas
594e41f9-f43d-4d57-bc78-903ab72a41e0 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 20 | 2003 | Waterproofing | Balcony Areas
aa442e91-755b-4112-86b6-552bf23d92e0 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 20 | 2005 | Waterproofing | Balcony Areas
dc4e4f2e-e99f-4d83-89cb-888ae4608f8e |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 20 | 2006 | Waterproofing | Balcony Areas
f4e46fe8-ecf1-4c18-8f8e-eb193198cbe9 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 20 | 2007 | Waterproofing | Balcony Areas
047a386f-3935-48d8-94a2-6b4bb2396ef9 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 21 | 2101 | Waterproofing | Balcony Areas
3833cda5-79ed-4274-9dbe-d639cb3bc0d5 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 21 | 2102 | Waterproofing | Balcony Areas
1b3e0232-10a4-4833-8076-e636649f0945 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 21 | 2103 | Waterproofing | Balcony Areas
3b81e0c6-3ce1-471d-9a86-531953e31e6f |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 21 | 2105 | Waterproofing | Balcony Areas
93e02cb3-131b-4656-9ad8-3e481f335b0a |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 21 | 2106 | Waterproofing | Balcony Areas
3ba10fde-31b9-44f4-9a49-c462fb47aef8 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 21 | 2107 | Waterproofing | Balcony Areas
11da0c1c-4600-4ecf-9187-c50b81a7393b |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 22 | 2201 | Waterproofing | Balcony Areas
522b9534-9c0f-4afb-9b6d-2998d46678b7 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 22 | 2202 | Waterproofing | Balcony Areas
31a81eea-449f-46cd-8294-2392b54ee129 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 22 | 2205 | Waterproofing | Balcony Areas
41b3b2c1-d937-443b-a86d-c26b090bdd89 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 22 | 2206 | Waterproofing | Balcony Areas
a67c40eb-7b82-42b5-a5df-4e31086c9267 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 22 | 2207 | Waterproofing | Balcony Areas
e47ec6f6-77e9-419a-af2f-5542dbc69475 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 23 | 2301 | Waterproofing | Balcony Areas
ebe90bbd-2711-48a9-8622-a9a98aa8437c |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 23 | 2302 | Waterproofing | Balcony Areas
2ec2acb2-910c-416e-9073-05c0132d9b43 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 23 | 2305 | Waterproofing | Balcony Areas
4a64c0fd-a948-41e7-9692-c95d7c31de7a |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 23 | 2306 | Waterproofing | Balcony Areas
c5cdb263-c446-4266-bb1f-824d10081878 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 23 | 2307 | Waterproofing | Balcony Areas
e8b98bfe-0035-4364-9ecc-3500759f3d8f |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 24 | 2401 | Waterproofing | Balcony Areas
299ad427-32c8-4b18-9dd8-45f7c6d87af7 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 24 | 2402 | Waterproofing | Balcony Areas
ac2a8c2f-9c47-42e2-8790-23a614a9f707 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 24 | 2405 | Waterproofing | Balcony Areas
2ca12435-fb48-467d-b542-f20e6bb86647 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 24 | 2406 | Waterproofing | Balcony Areas
921a6963-79ea-4848-ab81-9b302895827d |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 24 | 2407 | Waterproofing | Balcony Areas
3bc3e123-25af-4f2e-ad58-5a453b034a98 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 25 | 2501 | Waterproofing | Balcony Areas
6708f08d-b118-48bf-a9f3-56ee11999049 |  | fail | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 25 | 2502 | Waterproofing | Balcony Areas
67ec46d4-281d-47c5-a141-78207a30ccd4 |  | fail | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 25 | 2503 | Waterproofing | Balcony Areas
2a1f7561-2baa-4489-b8d1-5d24dccee004 |  | fail | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 25 | 2505 | Waterproofing | Balcony Areas
2e9008f6-987e-44c5-a4d0-879960d5fa1d |  | fail | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 25 | 2506 | Waterproofing | Balcony Areas
367b00f0-7dfb-4b84-9903-fdfe65b7f162 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 25 | 2507 | Waterproofing | Balcony Areas
59841ee0-2421-40e4-a94b-3fe9046eb15c |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 26 | 2601 | Waterproofing | Balcony Areas
4b801c0f-8b21-42f1-87e6-805769f9af0f |  | fail | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 26 | 2602 | Waterproofing | Balcony Areas
a4b2c543-b480-4f92-a837-710621a44494 |  | fail | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 26 | 2603 | Waterproofing | Balcony Areas
87a0cd0d-0cd8-4042-afbe-c7162d5a8489 |  | work-in-progress | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 26 | 2605 | Waterproofing | Balcony Areas
ed9d3aac-ccc8-411c-860a-2e9aaaed29c9 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 26 | 2606 | Waterproofing | Balcony Areas
569b69b0-61fd-4a13-861a-c52393e50217 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 27 | 2701 | Waterproofing | Balcony Areas
241f0a7b-ad0e-4ee3-9aab-ca64ff22f0b0 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 27 | 2702 | Waterproofing | Balcony Areas
44694bca-c438-41e6-9a7c-c194ec1b7352 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 27 | 2703 | Waterproofing | Balcony Areas
109f4d10-d6f4-4f63-b234-5d80a7cfe3a3 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 27 | 2705 | Waterproofing | Balcony Areas
8343d81b-9e98-4d9a-b84d-282bcd19e1ac |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 27 | 2706 | Waterproofing | Balcony Areas
7345e69d-f379-41ce-88af-08b5b6f049e3 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 28 | 2801 | Waterproofing | Balcony Areas
8b044d38-aecd-474d-bd56-23cad109fda9 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 28 | 2802 | Waterproofing | Balcony Areas
cc0af45b-8dfc-4748-b102-bfb192ce05d5 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 28 | 2803 | Waterproofing | Balcony Areas
28839d91-307c-49c9-850e-29a6afbab38d |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 28 | 2805 | Waterproofing | Balcony Areas
eb361e9e-8062-402e-9179-3880d18e510a |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 28 | 2806 | Waterproofing | Balcony Areas
6d075b94-c83b-4b3b-8493-b5b26a59421a |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 29 | 2901 | Waterproofing | Balcony Areas
cbfe5e1a-a037-4892-a691-bcc7122e1adc |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 29 | 2902 | Waterproofing | Balcony Areas
5e82fa7d-103d-4e61-bf1c-fd04f8061ed1 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 29 | 2903 | Waterproofing | Balcony Areas
85996d32-c236-409c-93e8-c5bb94c49055 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 29 | 2905 | Waterproofing | Balcony Areas
bf7b27c0-3386-42ec-bf48-f1cdcc862b86 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 29 | 2906 | Waterproofing | Balcony Areas
c92681fe-673e-4f66-adbb-b49ca2912089 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 30 | 3001 | Waterproofing | Balcony Areas
5ca66f52-96ed-4d20-82cb-c92e3f6f5c0b |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 30 | 3002 | Waterproofing | Balcony Areas
609a10ed-1aef-494e-94da-04ec947caf1c |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 30 | 3003 | Waterproofing | Balcony Areas
1970bb70-d847-438f-b1a3-c49c80d050a8 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 30 | 3005 | Waterproofing | Balcony Areas
0c338494-cf97-44ae-8868-92a2c65370cc |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 31 | 3101 | Waterproofing | Balcony Areas
a1ecefa6-381a-48f1-afbf-7e9f491bdc2b |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 31 | 3102 | Waterproofing | Balcony Areas
a279f27f-00c2-482c-ae2e-12177465e2d0 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 31 | 3103 | Waterproofing | Balcony Areas
9e365624-afbe-44ce-828a-68574a6e96dd |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 31 | 3105 | Waterproofing | Balcony Areas
6816fa81-d2b9-46b8-a149-3f1217056394 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 32 | 3201 | Waterproofing | Balcony Areas
6c9441a7-818b-4631-88d6-e37a37b050c7 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 32 | 3202 | Waterproofing | Balcony Areas
66f60d8c-d4e4-4b02-b62b-45403d961c61 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 32 | 3203 | Waterproofing | Balcony Areas
c1146aeb-d1ba-4191-9e88-27346a61141e |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 32 | 3205 | Waterproofing | Balcony Areas
cba799d3-f8b4-4b71-8cf8-7da49f862cb5 |  | not-started | Waterproofing - Balcony Areas | checklist | FALSE | FALSE | Site QA | Fit Out & Façade | Level 34 | 3401 | Waterproofing | Balcony Areas