## Project Structure
Folder Structure |  |  | Checklists
Site QA
| Prelim Activities | To Contain Preliminary Checklist | Preliminary Activities and Materials Approval
| Byford U-beams | To Contain Viaduct Checklist | Ability to Add Stage-1 casting Checklist
Ability to Add Stage-2 casting Checklist

## Preliminary activities and Mate
type | name | values
checklist-sectioned | Preliminary Activities and Materials Approval Checklist
section | Preliminary Activities (Approved by Client)
checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint | Permacast Project Quality Management Plan
checkpoint | Inspection & Test Plan
checkpoint | MDR Index
checkpoint | Work Method Statement (WMS) - Prestress
checkpoint | Work Method Statement (WMS) - Curing
checkpoint | Concrete Repair Methodology
checkpoint | Shop Drawings
checkpoint | Test Panel Prepared and Inspected by Client
checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
section | Concrete
checkpoint | S65 Concrete Mix Design Approved by Client
section | Steel Reinforcement
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
section | Prestressing Tendons
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Ensure that all Coil Numbers are recorded
checkpoint | Stressing Calculations Submitted and Approved by Client for Works
checkpoint | Stressing Jack Calibration Certificates
section | Lifting Anchors
checkpoint | Lifting Design Approved by Client
checkpoint | Lifting Devices Approved by Client
checkpoint | Inspection of Delivery for Completeness and Quality
section | Cast-in Items and Ferrules
checkpoint | All Cast in Materials Approved
checkpoint | Inspection of Delivery for Completeness and Quality

## Stage-1 Casting Checklist
checklist-sectioned | Byford U-Beam Stage-1 Casting Checklist
section | Pre-Pour Checklist
text | Cast Number | 1
text | Beam Number and Orientation | 3
text | Strand Arrangement Type | 4
text | End Diaphragm
checkpoint | Shop Drawings approved for Works
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Mould Surface Checked
label | Cleaned
label | Sealed
label | Rubbers in Place
label | Oiled
label | Chamfers in Place
checkpoint | Reinforcement in Accordance with Drawings
label | Reinforcement size
label | Lap Length
label | Splicing
label | Bar Chairs
text | Reinforcement bars with couplers
text | Reinforcement around lifting loops
checkpoint | Detailed inspection of Mould and cage
checkpoint | Cover maintained and within tolerance
checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
text | Ferrules KSN16M (Web)
text | Ferrules M20x96 (Bottom Flange)
text | Ferrules M16x45 (Ladder)
text | Ferrules M16x70 (Web, Laingorourke Formwork)
text | Ferrules (Other type, specify)
checkpoint | All Stainless Items are installed in accordance with Drawings
text | Other type, specify
checkpoint | All Blockout Conduits are installed in accordance with Drawings
text | 20NB PVC Pipe
checkpoint | All Lifting Inserts are installed in accordance with Drawings
text | Lifting Hoops
checkpoint | All Bartek Couplers are installed in accordance with Drawings
text | BPB28
text | BPB36
text | BPB20
checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered aith KSN16M in web
text | LENTON EL20A12
checkpoint | All Bearing plates in Diaphragms are installed as per drawings
text | Specify Bearing plate Size/Type
checkpoint | Earthing and Bonding is installed in accordance with Drawings
text | Earthing Terminals (FDB-16)
text | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
text | <20 mOhm across cage Length
text | Checklist Completed (North & South) (attach results)
checkpoint | Prestressing Strands
text | Coil Number Used for this Cast
text | Dia and No. of strands
text | Strands arrangementr verified
label | Sag Load all Strands
label | Mutli-Stress as per Pre-stressing Procedures
label | Verify debonding strands if any
checkpoint | Stressing Records subject to Client Review (HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint | All Temperature Loggers are installed as per Approved WMS
text | Ensure All temperature Loggers are Working (Check Maturix)
checkpoint | All Cooling tubes installed as per drawings
checkpoint | Installation of tubs
label | Tubs are tightened and positioned correctly
label | All Sliding arms are locked in position
label | All accrow props are locked in position
label | Dimensions of Tub and Webb are correct
label | All feet for tubs resting on mould & bolted down
label | Tubs have release agent
checkpoint | QA Engineer Check Completed by
checkpoint | Client Inspector (if present)
section | Supervisor Release
checkpoint | Supervisor Release to Engineering Team
section | Casting Checklist
checkpoint | Casting Information
text | Cast Date | 2
checkpoint | Concrete Delivery Dockets
text | Concrete Delivery Dockets (list all)
checkpoint | Total Concrete Volume
text | Volume (m3) | 6
checkpoint | Mix Design Verified
text | Specify mix used | 5
checkpoint | Ambient Temperature within Limits
label | max 38°C
checkpoint | Concrete Temperature
label | max 32°C
checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
text | Slump (list all) | 7
checkpoint | Trucks Tested for strength
text | Test Report Reference Number (list all)
checkpoint | Time Lag Between Trucks not exceeded 20 minutes
checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
checkpoint | Required Finish Applied as per Drawings
checkpoint | Retarders applied on Green Cut areas as shown in drawings
checkpoint | Concrete Covered Overnight
checkpoint | Cylinders Stored next to Bed
section | Stripping Checklist
checkpoint | Date Stripped
text | Enter Date
checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
label | Conversion KN to MPa = Reading / 7.851
label | Stripping strength 45.5MPa
text | Stripping Strength (Stage-1 Casting) | 8
checkpoint | Verify Destressing/Transfer of stress required strength
label | Destress at 45.5MPa
text | Specify Strength at time of destressing
checkpoint | Lifting Strength Achieved
label | Lifting strength required for stage 1 casting - 40MPa
text | Specify strength at time of lifting
checkpoint | Curing strength (Stage-1 Casting)
label | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
label | Mould and Steam Cured until the curing strength achieved
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint | Secondary Curing as per Approved Methodology if required
label | Temperature 5 degrees less than its peak value
label | Max temperature doesnot exceed 70°C
label | Differential between Core and Ambient within 30°C
label | Differential between Core and Cover within 25°C
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Specified Finish Achieved
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
text | Ferrules
text | Couplers
text | Stainless Items
text | Lifters
text | Blockouts
checkpoint | Post-Pour Works Completed (As Required)
text | Strands are Cut Flush and Epoxied except debonding strands
text | Couplers are Cleaned and Capped
text | Roughened Surfaces are Greencut
text | Water Removed out of Cooling Pipes
text | All Miscellaneous Items are Completed
text | Bottom surface clear from tie wire (Attach Pictures)
checkpoint | Survey Hog of Beams (Dumpy)
text | First Reading (Within 2 days of Stripping)
text | Second Reading (After casting stage 2 top slab and atleast 7days after stage 1 casting)
text | Third Reading (At 28 days after stage 1 casting)
text | Final Reading (7 days prior to scheduled delivery)
checkpoint | Temperature Logging Completed and Conforming. Attach Results
section | Any Defect Identified
checkpoint | Punchlist Completed
checkpoint | Repairs Required (if applicable)
checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint | Crack Map Completed
checkpoint | Any NCR Required (if applicable)
checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
section | As-Built Drawings
checkpoint | As-Built Drawings Completed, Stamped and Attached
section | Concrete Strength Test Report
checkpoint | Concrete Strength Test Report Received
text | Concrete Test Report | 9
text | 7 Day Strength (List all) | 10
text | 28 Day Strength (List all) | 11
section | Transportation Requirements
checkpoint | Certificate of Conformance
checkpoint | Inspection Release Certificate
checkpoint | Punchlist signed copy
checkpoint | Delivery Notes
checkpoint | Delivery Docket
section | Final Acceptance
checkpoint | Completed by
checkpoint | Reviewed by
checkpoint | Client Representative (if applicable)

## Stage-2 Casting Checklist
checklist-sectioned | Byford U-Beam Stage-2 Casting Checklist
section | Pre-Pour Checklist
text | Cast Number | 1
text | Beam Number and Orientation | 3
text | End Diaphragm
checkpoint | Shop Drawings approved for Works
checkpoint | Mould and Sacrificial formwork Dimensions are within Shop Drawings Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Condek Surface Checked
label | Cleaned
label | Sealed
label | Oiled
checkpoint | Reinforcement in Accordance with Drawings
label | Reinforcement size
label | Lap Length
label | Splicing
label | Bar Chairs
text | Stitch pour Reinforcement lapping bars spacing maintained and template plate installed
text | Blockout recess around lifting Hoops
checkpoint | Detailed inspection of Mould and cage
checkpoint | Condek (Top Slab) - Verify all brackets fixed at slab thickening
checkpoint | Cover maintained and within tolerance
checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
text | Ferrules M16x70 (Handrails)
text | Ferrules M10x45 (Expansion Joint Cover)
text | Ferrules M16x45 (Ladder) | Size not confirmed
text | Ferrules (Other type, specify)
checkpoint | All Stainless Items are installed in accordance with Drawings
text | Other type, specify
checkpoint | Earthing and Bonding is installed in accordance with Drawings
text | Earthing Terminals (FDB-16)
text | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
text | <20 mOhm across cage Length
text | Checklist Completed (North & South) (attach results)
checkpoint | QA Engineer Check Completed by
checkpoint | Client Inspector (if present)
section | Supervisor Release
checkpoint | Supervisor Release to Engineering Team
section | Casting Checklist
checkpoint | Casting Information
text | Cast Date | 2
checkpoint | Concrete Delivery Dockets
text | Concrete Delivery Dockets (list all)
checkpoint | Total Concrete Volume
text | Volume (m3) | 6
checkpoint | Mix Design Verified
text | Specify mix used | 5
checkpoint | Ambient Temperature within Limits
label | max 38°C
checkpoint | Concrete Temperature
label | max 32°C
checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
text | Slump (list all) | 7
checkpoint | Trucks Tested for strength
text | Test Report Reference Number (list all)
checkpoint | Time Lag Between Trucks not exceeded 20 minutes
checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
checkpoint | Required Finish Applied as per Drawings
checkpoint | Retarders applied on Green Cut areas as shown in drawings
checkpoint | Concrete Covered Overnight
checkpoint | Cylinders Stored next to Bed
section | Stripping Checklist
checkpoint | Date Stripped
text | Enter Date
checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
label | Conversion KN to MPa = Reading / 7.851
label | Stripping strength 20MPa
text | Stripping Strength (Stage-2 Casting) | 8
Checkpoint | Lifting Strength Achieved
label | Lifting strength required for stage 2 casting - 45MPa
text | Specify strength at time of lifting
Checkpoint | Curing Strength (Stage-2 Casting)
label | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
label | Tarped until the curing strength achieved
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint | Secondary Curing as per Approved Methodology
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Specified Finish Achieved
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
text | Ferrules
text | Stainless Items
text | Lifters
text | Blockouts
checkpoint | Post-Pour Works Completed (As Required)
text | Ferrules are Cleaned and Capped
text | Roughened Surfaces are Greencut
text | All Miscellaneous Items are Completed
section | Any Defect Identified
checkpoint | Punchlist Completed
checkpoint | Repairs Required (if applicable)
checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint | Crack Map Completed
checkpoint | Any NCR Required (if applicable)
checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
section | As-Built Drawings
checkpoint | As-Built Drawings Completed, Stamped and Attached
section | Concrete Strength Test Report
checkpoint | Concrete Strength Test Report Received
text | Concrete Test Report | 9
text | 7 Day Strength (List all) | 10
text | 28 Day Strength (List all) | 11