## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Access control door |  | Access control door | 2e3f0261-5896-429d-a911-29277a750f27
| checkpoint | Details
6a3b2dee-c054-5283-bc28-cada25516a7d | textbox | Door Architectural Space Number
f00b9812-87a2-51d6-bf4d-5adbcc01341b | textbox | Door Name
| checkpoint | Lock type
793d4234-430f-5b52-9f7f-06a1ab163d1c | dropdown | type | Double Mag lock, Single Mag lock, V-Lock, Automatic Door, Electric Mortise Lock, Electric Strike Lock
| checkpoint | Entry RDR:
393eed2e-dc78-5499-a058-49c68be39f26 | dropdown | type | Card Reader, Card + Pin Reader
| checkpoint | Exit Device
1d4b69bc-944b-5db4-9556-5a168f94f002 | dropdown | type | Card Reader, Card + Pin Reader, Rex Button, Free Handle Egress
| checkpoint | EDR
| checkpoint | Functionality test
b6a59160-298e-56ad-b50f-f96858a84efb | button | Door locks/unlocks when Overridden | Pass, N/A
8be282bc-4fd3-50bb-98f9-ffd4d927d325 | button | Door unlocks when Card present to Entry Reader | Pass, N/A
66e66b25-4d34-54c4-83d5-3085de241a05 | button | Door unlock when Rex Button pushed | Pass, N/A
b3297210-8eb4-5454-9165-6e675d0643eb | button | Door unlock when Card presented to exit reader | Pass, N/A
4deb1073-90c1-5735-aec3-22364ac0392f | button | Generates ‘open to long’ alarm | Pass, N/A
dd479540-bcf9-56cd-948d-2045682e2d86 | button | Generates door ‘not locked’ alarm when not locked | Pass, N/A
339f0b9f-f277-5f5c-a674-61d651163deb | button | EDR cuts power to lock and gives alarm | Pass, N/A
eeb9f94c-d918-5db5-9f11-b0f1728f7b97 | button | Generates ‘door forced&#39; alarm when door open w/o valid exit | Pass, N/A
100c2c85-4cbc-5aaa-8a67-d8ecbea53d30 | button | Door Unlocks when Fire Interface relay in Security panel is de-energised | Pass, N/A
3d9f669a-d0b5-5c30-a7ab-70c650c753ff | button | Hold backs release on door locked | Pass, N/A
c92a2af5-4d91-5192-8e9d-4b540f445caf | button | Remote release unlocks door | Pass, N/A
efdd1dfd-fd5b-59be-a29b-253247c46467 | button | REX/REN activates door opener to ‘open’ door | Pass, N/A
e71cf8db-e2d1-5b07-a00d-de85d9dd1807 | button | ‘Door’ icon available on site plan – (Gallagher) | Pass, N/A
ed497734-4ee6-59cf-8ef9-1464637ff742 | button | Door ID Label Installed | Pass, N/A
7aab0a41-140f-5cb2-826b-7386d515cfc0 | button | Door clearance after installing mag lock is greater than Building Code | Pass, N/A
| checkpoint | Any other comments
| signoff | Signed by Technician
| checklist | Camera Maintenance and Commissioning |  | Camera Maintenance and Comissioning | f565cd60-d9fb-46d1-9656-33e6295745af
| checkpoint | Camera Number:
8f60841b-6931-5540-8d20-a93a1d1176a2 | textbox | Camera Number:
| checkpoint | Camera specifications
b94169c0-af76-5700-8d3b-360b9405003d | dropdown | Make/Model | 2MP H5A Indoor, 2MP H5A Outdoor, 8MP H5A Internal, 8MP H5A External, H5A Multhead, 8MP H5A Bullet, Other
a673b663-394e-5f06-b297-7c63bd7c6c56 | dropdown | Connected to | Local NVR, Other (please specify in comments)
| checkpoint | Image details
58c925c8-b3ed-5a41-a5de-3cfd8d572a29 | dropdown | Image | MPEG, H264, H265
d509079e-57f6-50ba-b06d-8ead04474cb2 | dropdown | Recording | Motion, Alarm, Continuous
ab523d02-7bf8-5779-8a59-efd967a0ed34 | dropdown | Resolution | 1920 x 1080, 3840 x 2160, 2048 x 1536, other (please specify in comments)
fe2dedaa-660f-5822-9305-a368541adbec | textbox | FPS
4d60f21f-0630-5bb3-9b9d-6579e45e7c27 | dropdown | Bit Rate Control | Clean, Variable, Bad
| checkpoint | Insert Day Image
| checkpoint | Insert Night Image
| checkpoint | Camera Performance
| checkpoint | Coverage - Desired coverage has been achieved
| checkpoint | Image is in Focus
| checkpoint | Depth of field - Image is sharp before/behind object in focus
| checkpoint | Day/Night Mode - Switches to black/white on low light
| checkpoint | Auto iris operation - compensates for varying lighting levels
| checkpoint | Backlight compensation - compensates for excessive background light
| checkpoint | White Balance - colour reproduction correct
| checkpoint | PTZ Controls - pan, tilt, zoom and focus controls functioning correctly
| checkpoint | Hardware checklist
e958507d-723a-539f-8510-1d2960db9a48 | dropdown | Mechanical Protection | Excellent, Very good, Good, Average, Poor - Repairs required, N/A
be22f4b4-e813-5093-a9c7-80c9e3e5248a | dropdown | Enviromental Protection | Excellent, Very good, Good, Average, Poor - Repairs required, N/A
c53036ed-84dc-5bf5-88b4-3155e68cbd23 | dropdown | Anti-Tamper Devices | Excellent, Very good, Good, Average, Poor - Repairs required, N/A
f0fa93ab-c70c-5de9-b5be-759b6b35eab1 | dropdown | Mounting | Excellent, Very good, Good, Average, Poor - Repairs required, N/A
f3558095-1ac4-5caa-b747-a1085d17917f | dropdown | Cable Entries | Excellent, Very good, Good, Average, Poor - Repairs required, N/A
3bfacf76-acea-5c7b-9b5b-92380205c218 | dropdown | Terminations | Excellent, Very good, Good, Average, Poor - Repairs required, N/A
87618917-8843-500b-8f4a-aa18f5fceead | dropdown | Supply Voltage | Excellent, Very good, Good, Average, Poor - Repairs required, N/A
60ceba13-473d-5ccb-b271-f8f5d7be96f7 | dropdown | Ventilation | Excellent, Very good, Good, Average, Poor - Repairs required, N/A
e339be72-9a46-54fb-8c6e-7ee95b8dcdd4 | dropdown | Ambient Light Levels | Excellent, Very good, Good, Average, Poor - Repairs required, N/A
| signoff | Signed by technician if required
| checklist | Controller Test Sheet |  | Controller Test Sheet | ca772b4e-09c5-41b0-a31d-3adb70c0ff06
| checkpoint | Details
e5e6a8c4-2390-5dc8-b1f3-17979fb6e75e | dropdown | Controller type | C3000 8R, C3000 4R, C6000 8R, C6000 8H, C6000 4R, C6000 4H, C5000 GL
35f6e6d6-5a3b-59b4-b429-3d65363111ff | textbox | Controller label:
4b98e013-66f3-532c-9ade-cebe5d205d68 | textbox | Serial Number:
2887cad5-18f1-5030-96c1-242839efe730 | textbox | Mac Address:
a98ef8d1-8f24-5302-91b5-7a8674feb69b | textbox | Software Version:
85dec56d-8047-57ed-99a5-64c5a286791b | textbox | IP Address:
9fd02e17-0351-597f-8f55-b1bcc5b0fe14 | textbox | Subnet Mask:
95c96bfc-6728-5542-91db-725492cdf7e7 | textbox | Gateway:
91db4f9c-6b91-5b73-a6ea-726d37d5341c | button | Onboard Tamper | Enabled, Disabled
740f57ea-c292-53e8-8998-5de914c00512 | textbox | EOL Resistance Values
| checkpoint | Connected GBus/HBus Devices
5b916707-24f5-5ca1-b3a1-34a5bb4d2b83 | textbox | Type
995c3fc5-7316-53bc-887f-58a04e3005e4 | textbox | Label
5e6379fb-25ab-538c-b93b-e79c43997d44 | textbox | Address
| checkpoint | Functionality Test
5a1913b0-b34f-5861-99e6-f2d50a8eea86 | button | Dipswitch #1 ON | Pass, N/A
038d3f0f-c021-5217-9c9c-47bf8352a843 | button | All other Dipswitches OFF | Pass, N/A
3a097738-c85f-53d1-bfd2-c4552a703b44 | button | Connected and Online to Server | Pass, N/A
8967a124-b664-5153-b153-7c36985ae952 | button | Alarm Zones associated correctly | Pass, N/A
d8611145-3b84-5b93-9601-091300bbae46 | button | All G-Bus Devices communicating | Pass, N/A
| checkpoint | Any other comments
| signoff | Signoff by technician
| checklist | First Fix Doors |  | First Fix Doors | 48075c84-52d2-40bc-bdec-0f17ccde0593
| checkpoint | First Fix Doors
be8dfe1b-f838-50eb-93f0-636cff7d72bd | textbox | Cable Label Name
b753ce65-140e-5922-bd5d-399535b1188d | dropdown | Cable Supports | Catenary Wire, Cable Tray, Surface Containment
6608a3b0-653d-5a6b-94f5-a2eaf64b541b | button | Cables | Installed, Not Installed
| checkpoint | Termination Location - Insert Photo
| checklist | Intercom System Report |  | Intercom System Report | d6699749-0e2a-4a25-a34f-867ef5035d3d
| checkpoint | Details
14cc3a38-fa01-56d9-a97f-6a9366322369 | textbox | Type
8bb055df-deff-5f50-94a6-965feebccc1f | textbox | Location
f2e8ef07-cbb4-5496-a146-7654d633130f | button | Is this unit functioning correctly | Yes, No
5afafab0-5309-53a5-9263-c60258737e40 | button | Is the volume/clarity acceptable? | Yes, No
c816474d-9a1f-5a8f-906a-4a002f3c43e6 | button | Is the unit in good condition | Yes, No
| checklist | NVR |  | NVR | 137266e8-93b4-4b01-99e1-b25e1e409bd0
| checkpoint-no-value | Details
074783cc-e9f7-5e10-b79e-7ac31211cc09 | date | Installed Date
6bfcd230-d433-5860-9c94-91c4cabf8769 | textbox | Make
23f23524-5139-52d4-8dc6-36887ac593a6 | textbox | Model
9499ab7f-495c-5bfb-91b1-98db1bb8508d | textbox | Serial No.
d5aa22ba-6f54-50c9-ad18-a989e3b40eb5 | textbox | Firmware
7413abb3-dd59-5d59-90a6-ff34038952c3 | textbox | Mac Address
2c3130f0-a050-5cd4-a19d-eb8f9f5e738e | textbox | Configured client User name and code
97a60de7-f537-5efd-837f-90f57e26ae14 | textbox | Client Network IP address
| checkpoint | Has Internet Connection?
f4f39284-f308-52cd-be58-bbbb2ce6610f | textbox | Username
901969b2-b8a6-5a06-a10f-aefce3e93bf7 | textbox | Password
4733e151-b3d0-5903-8840-d008fc2b8856 | textbox | Camera count
0e87f902-a5e2-5b8e-9b3d-ab7b272c6e62 | textbox | Open NVR and label Hard Drives with date:
849345da-21d8-5e71-90c5-13422e9ea008 | button | Backup NVR and IPC configuaration to USB pendrive (give copy to office) | Yes, No
| checkpoint | Camera Recodering setting
| checklist | Power Supply/Cabinet Checks |  | Power Supply/Cabinet Checks | a9d72c0e-b973-483f-a5d8-4b13f8c96209
| checkpoint | Details
22e55540-ea3d-5143-bbf0-d00d21811227 | textbox | Manufacturer
55fc9db0-8ede-5104-96d3-53ba221455ea | textbox | Model
6b1e7fa3-f8a5-5a5d-9752-41b31b25e3c3 | textbox | Serial Number
a15c8fc6-aa9d-50f2-8223-26356eab802b | textbox | Cabinet Label
b674a38c-dbcd-56ed-97ab-f6f4b4c08c71 | textbox | Architectural Space Number
| checkpoint | Power Supply
5a06be2f-db66-5562-8367-bb155a5fa46d | textbox | Output Voltage
dc756435-e00a-5fbe-b1cd-13c801d113be | button | Is Fan Noisy? | Yes, No
a9bd695f-5985-5d26-a71e-05f3ed7e95f1 | button | Is transformer hum excessive? | Yes, No
9ed85dc4-882b-5e53-a9f1-9dd0688683cd | textbox | Record current load on system (photo)
9e382daa-95db-5082-98d6-2e19fa834a3d | button | Has 'main fail' alarm activated? | Yes, No
| checkpoint | Cabinet
27234baa-71b5-5da5-91c5-80b7b36c7a75 | button | Is Cabling Tidy within Cabinet? | Yes, No
b4f65fa5-ddc9-5770-9c27-5413871927f6 | button | Are all Trunking lids on? | Yes, No
31415bb0-7dc2-5b14-b5a9-d4302a1e6c42 | button | Is Cabinet Clean and Debris Free? | Yes, No
88db8190-0e3a-5c1e-a13e-572d1e5c4b3e | button | Is Wiring Report/Plans in Holder on Door? | Yes, No
| checkpoint | Battery A/the set
007e88ca-136f-5116-b7ab-adb2c2ba2993 | button | Battery Available? | Yes, No
f34d35b8-f43a-5906-b583-bad3ab16dd32 | textbox | Battery Rated Capacity (ah):
d6b8f2c6-f208-5739-80f7-94cc8a2aef8a | button | Are Battery Terminals Secure and Clean? | Yes, No
ad440479-781f-53f9-91c2-781ac4b5c5b5 | textbox | Keep Mains ON -Battery Voltage xx.x (vdc):
ae127959-2505-568a-bed4-ef21d9d8a6bd | button | Remove Battery terminals and load test Individually. Pass or Fail? | Pass, Fail
b5bc1d17-fd46-5736-8d48-e4098ae73610 | textbox | Have you replaced the Batteries? (see above, add date!)
52203459-a537-5c13-824f-025ee98d7bdc | textbox | Record Battery Date (dd-mm-yy):
5ad24c62-85e9-59dc-8e75-0edbec0898b5 | button | Have you Reconnect Battery Terminals: | Yes, No
| checkpoint | Battery B
eda4968a-78b7-5275-963c-740183558574 | button | Battery Available? | Yes, No
1b3b6e57-9eb5-57f2-8ed0-27a25bedfdc3 | textbox | Battery Rated Capacity (ah):
90abcf67-aaf5-5982-b9b0-e580621bb4f3 | button | Are Battery Terminals Secure and Clean? | Yes, No
c11f1dd2-6414-5c93-bd86-86cd7d857653 | textbox | Keep Mains ON -Battery Voltage xx.x (vdc):
3da99400-c6d2-524a-9295-0084d2e87d38 | button | Remove Battery terminals and load test Individually. Pass or Fail? | Pass, Fail
00e77508-4d4a-57d9-88bf-4f6aad1869f4 | textbox | Have you replaced the Batteries? (see above, add date!)
f73cd22c-10df-5747-9898-f7147ad99670 | textbox | Record Battery Date (dd-mm-yy):
357a114f-de0d-5c9e-bbd1-6a1e525886f5 | button | Have you Reconnect Battery Terminals: | Yes, No
| checkpoint | Battery C
0d11c9e5-0a35-5307-97a3-584091bfea6c | button | Battery Available? | Yes, No
c35f33df-86a2-5a01-82b5-42c0775cb3bd | textbox | Battery Rated Capacity (ah):
4689631b-3918-5e0c-aabd-6b0400617e3e | button | Are Battery Terminals Secure and Clean? | Yes, No
1b1ce80e-50fe-5b9b-9536-c3d731dedaef | textbox | Keep Mains ON -Battery Voltage xx.x (vdc):
b6c1c131-fae5-5a18-87c4-647cb9310472 | button | Remove Battery terminals and load test Individually. Pass or Fail? | Pass, Fail
5602dfa6-4b44-5369-8e0e-7e28e9ccfe12 | textbox | Have you replaced the Batteries? (see above, add date!)
04c2d0ee-eb89-5e40-954a-513478781176 | textbox | Record Battery Date (dd-mm-yy):
eb8257f7-fc59-5629-815f-c3c3cf478ab6 | button | Have you Reconnect Battery Terminals: | Yes, No
| checkpoint | Battery D
02b1907f-4155-598d-89d5-221a091d4166 | button | Battery Available? | Yes, No
192944f6-2d2a-553c-a8d2-7a2a920fd1cd | textbox | Battery Rated Capacity (ah):
5df9a1a4-a07d-5ad2-9c5c-8be2eb3c3a99 | button | Are Battery Terminals Secure and Clean? | Yes, No
6664a77d-d66b-584f-aa8c-85c55e2a6fef | textbox | Keep Mains ON -Battery Voltage xx.x (vdc):
7cf02840-c76a-5da2-8c5a-8b23e1eeeb1d | button | Remove Battery terminals and load test Individually. Pass or Fail? | Pass, Fail
a003f3a2-80d8-5c33-9033-286f5f2bba9c | textbox | Have you replaced the Batteries? (see above, add date!)
da91d75d-6794-5eb2-b062-c0a9a9cf9b1f | textbox | Record Battery Date (dd-mm-yy):
4523a496-fca2-5e95-bd33-2342631ca51c | button | Have you Reconnect Battery Terminals: | Yes, No
| signoff | Turn Mains back ON -Wait 2mins the record Recovery Voltage xx.x (vdc):
| checklist | Security Panel |  | Security Panel | c92ab885-f0df-4116-9d74-bec600757561
| checkpoint | Security Panel
be8dfe1b-f838-50eb-93f0-636cff7d72bd | textbox | Cable Label Name
b753ce65-140e-5922-bd5d-399535b1188d | dropdown | Cable Supports | Catenary Wire, Cable Tray, Surface Containment
6608a3b0-653d-5a6b-94f5-a2eaf64b541b | button | Cables | Installed, Not Installed
| checkpoint | Termination Location - Insert Photo
| checklist | Seismic Bracketing |  | Seismic Bracketing | d6cad21e-c812-4619-bad0-d6b88fe6138e
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Location of Bracket checked on shop drawings
| checkpoint | Correct bracket type selected
| checkpoint | Correct Anchor selected and checked
| checkpoint | Anchor Hole Size and Depth checked
| checkpoint | Correct torque set for anchor
| checkpoint | Final Photo of bracket