## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
9630dacc-0e8f-4a76-b011-0f44d92b1f3e | checklist | ITP-005 - Rock Beaching/Structures Rev1 | itp | ITP-005 - Rock Beaching/Structures
23972fcd-7bf0-485a-ac31-5e448b46c69e | section | 1 - Preliminaries and Submissions
6479579f-6c2c-4b1e-a89e-77467c929dcc | checkpoint | 1.1 - Check for correct documentation
86972dc9-717c-56de-9723-2e365ed02dc4 | note | FREQUENCY: Before commencement of activity
109b2576-b80e-5fb3-bebf-2c1693479564 | note | ACCEPTANCE CRITERIA: Check correct documentation is being utilized
8ee83079-bc63-5a6a-b9e2-14515864c5f6 | note | REFERENCE DOCUMENTS: Drawings
43969167-b458-5a42-bc9f-5fa37505b8f7 | note | INSPECTION/TEST METHOD: Current revision of drawing
6b3cfc62-99e7-5838-bcc4-e55c7d32116c | note | CONFORMANCE RECORD: Current revision of drawing
e90ae509-7592-5d95-b1e7-fc4629e1913d | note | *HP
0afa7d27-b874-550b-858f-383c5cb4620f | note | RESPONSIBILITY: Fulton Hogan
739d4066-ea62-53c2-b927-84782f96cccc | date | Date Completed:
f7087bf2-a719-4215-8b9b-64a32731d43e | checkpoint | 1.2 - Ensure Safety, Traffic, Quality & Environmental management measures are in place
56b1dc22-a8a3-5bc0-9454-1655aef897dc | note | FREQUENCY: Prior to commencement of activity.
739479ae-0df5-5ce0-a052-c0e4269ffb15 | note | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
c88e006f-7ea6-52b6-b8d6-0d1d178b5f75 | note | REFERENCE DOCUMENTS: PSP, TMP, EMP
e43ac2c1-dd6d-5a76-8859-7c982d6e7324 | note | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
0dd9d6fe-9326-5539-b792-5e8ea3daaac1 | note | CONFORMANCE RECORD: Inspection
98eaedf5-c182-5b95-95b9-35edf8401c39 | note | HP
bf183dae-b682-564f-a294-db42f6653d2e | note | RESPONSIBILITY: Fulton Hogan/Client
9cf2ae88-731c-513f-93c0-0bd3dd2cc2c1 | date | Date Completed:
6153a31b-3628-4ea8-acbe-52b20e832026 | signoff | AUTHORITY HOLDPOINT
7bded62c-94a5-4f58-917e-16f4ad4de12f | checkpoint | 1.3 - Stockpiling
a888b771-997e-56da-95bf-013fade7b6d3 | note | FREQUENCY: Prior to removing material
72efd116-d161-513e-8480-67e7c6a6ba0b | note | ACCEPTANCE CRITERIA: Confirmation of stockpile location approved by superintendent.
e710054c-50ed-5222-8db3-b02b87b0f5fa | note | REFERENCE DOCUMENTS: FH Scope document, EMP
204db9ae-7c61-5ec7-8001-73ae20f97b81 | note | INSPECTION/TEST METHOD: Approval
996c17aa-fc6b-50df-815e-54f117387a92 | note | CONFORMANCE RECORD: ITP
50aa88b4-c34f-5f1d-b3cc-3aeae46d1f87 | note | WP
5a48a156-417d-50f0-8df3-172f4eb03ee1 | note | RESPONSIBILITY: Client/ Fulton Hogan
4ee9ca70-f562-5433-8da5-14827ed49665 | date | Date Completed:
37fad9cf-7b8a-418e-a609-314dd79b53bd | signoff | AUTHORITY HOLDPOINT
881d22ca-c6c1-4e0c-9dc2-942a83ae2733 | checkpoint | 1.4 - Identification of services
cc576fe2-5137-5715-a721-5b448147a045 | note | FREQUENCY: Prior to commencement
1b7ba89b-4d3e-5134-9b89-cd339783b595 | note | ACCEPTANCE CRITERIA: Any existence of underground services to be located and proven
e17436f1-948b-5b9f-a0cb-03aac9ff2b5f | note | REFERENCE DOCUMENTS: BYDA Section 100.8
86f05acf-7ad4-5afd-8e91-343f6d5ad87d | note | INSPECTION/TEST METHOD: Inspection
ddffdcea-2296-5148-b7e7-756d7066ab94 | note | CONFORMANCE RECORD: ITP
e06f025f-8db0-5fa0-aa6e-4d825a040535 | note | HP
24ad337c-370f-5833-b559-e6e6f438e6ad | note | RESPONSIBILITY: Fulton Hogan
c174aa04-a398-516e-b345-a7069605e5c8 | date | Date Completed:
05fb7890-3d22-4f3a-9347-56b5ec45d875 | signoff | AUTHORITY HOLDPOINT
92b393f8-cbc4-41f2-ac65-aa245ca66e47 | checkpoint | 1.5 - Project management Plan Completed
3344529d-d7ed-50a5-82c4-2b4c2df23bdb | note | FREQUENCY: Prior to commencement
0a5381db-e7bc-5327-9348-7cf52155ec21 | note | ACCEPTANCE CRITERIA: PMP Completed
bc100208-2b50-5af7-aaa2-70f86951a440 | note | REFERENCE DOCUMENTS: PMP checklist completed
7b6ec8b1-845e-535a-8c16-fe5dfaf5aed4 | note | INSPECTION/TEST METHOD: Inspection
195219c8-2320-58f5-b3c3-68838a2f11c2 | note | CONFORMANCE RECORD: ITP
6e5688d3-469c-55c7-b7a8-2446e580af67 | note | HP
5ddbe819-f32b-51d8-81d9-e75e676ab531 | note | RESPONSIBILITY: Fulton Hogan/Client
aca27d08-9b73-56b6-8db7-7dfc6614f57b | date | Date Completed:
44866846-2432-4872-b1f0-e41abaac75e2 | signoff | AUTHORITY HOLDPOINT
c2706d86-fc79-4be2-93ba-c77fc2edf2b5 | checkpoint | 1.6 - Site set out
3e52002d-1d45-585b-8934-24927a16803e | note | FREQUENCY: Prior to commencement
9f0552e9-7658-5d47-ba6d-73f2ac5999af | note | ACCEPTANCE CRITERIA: Site inspection
e2abe5b0-bdad-5ca5-83fb-b57285a313e9 | note | REFERENCE DOCUMENTS: Scope document Drawing 796684
1eb9242d-26ec-589c-b4ad-043561037f71 | note | INSPECTION/TEST METHOD: Site inspection
7df0f874-d0e5-57ef-9734-863a94c63dc2 | note | CONFORMANCE RECORD: ITP
6cdb30fe-988e-5f58-9790-0f24195053ac | note | HP
6cedc16b-78a0-5915-b72a-eb814c75f066 | note | RESPONSIBILITY: Client/ Fulton Hogan
081b0637-0b09-5f08-96ef-2a4841f95b93 | date | Date Completed:
fe2e276b-390e-47cc-9965-9f5dd1a4019a | signoff | AUTHORITY HOLDPOINT
7d3ef194-a5a5-4f36-9047-c25c45ee5003 | checkpoint | 1.7 - Ground breaking
cceb0762-fe35-5cb0-ac15-ea0e86823c02 | note | FREQUENCY: Prior to excavation
d64201e4-131c-5044-82b5-dc9e6f9b9a37 | note | ACCEPTANCE CRITERIA: Works to be reviewed and agreed by Superintendent
01eeb70c-27f6-5cef-a70c-9a33f8a459b2 | note | REFERENCE DOCUMENTS: Hold Point release for Commencement of Works Letter
d995078b-381f-5de4-8d8a-bdf9f295f329 | note | INSPECTION/TEST METHOD: Inspection
ee1f0828-1fd7-5083-8c18-4641f2b83890 | note | CONFORMANCE RECORD: ITP
acdec092-a7d7-529b-a808-a8a35fad8f8e | note | HP
1bd41eb8-8037-5fae-a1aa-11e0e4499ae6 | note | RESPONSIBILITY: Client
f9a4aee8-2bb0-5de0-a564-f3ac4b7b4560 | date | Date Completed:
c1b59637-7ad9-4494-a9ac-6a1b3ed7c6ff | signoff | AUTHORITY HOLDPOINT
f5685ce4-5701-4a74-9325-ed18a04580cf | checkpoint | 1.8 - Landowner Agreement with property owner
76dc988a-17d6-58b5-b5d9-1f73ddce1cc2 | note | FREQUENCY: Prior to breaking ground
3c571266-c38a-54be-97e6-8d1986e3861d | note | ACCEPTANCE CRITERIA: Letter to be signed
3a8d3b66-c4d0-50ec-923f-46ee72d98b88 | note | REFERENCE DOCUMENTS: Signed landowner agreement
312ade4e-2e58-5685-a81e-963d3a9c6572 | note | INSPECTION/TEST METHOD: Hold point
1fe4069b-edf7-5310-ae1a-b37c40ea94e1 | note | CONFORMANCE RECORD: ITP
2312b8a9-c5fe-559b-a472-e19b664f12fc | note | HP*
fb3f5b9c-1a45-5c3f-a593-d1b3b179a5c8 | note | RESPONSIBILITY: Fulton Hogan
ae0d9a35-f358-55a3-9bd2-d04136181bc4 | date | Date Completed:
4b4fda3d-0361-41c6-9aff-bcb25296e5f6 | checkpoint | 1.9 - Environmental controls
3408cb5f-cd00-5357-a975-b9296691913a | note | FREQUENCY: Prior to commencement
bfe2f238-ece3-5ddf-a060-6296ee64c74f | note | ACCEPTANCE CRITERIA: Environmental controls installed and maintained as per EMP/ GBCMA Working on Waterway Permit received
b0738b62-991f-56ba-a4be-3c6e8208e727 | note | REFERENCE DOCUMENTS: EMP
23acd49c-2366-5b78-8e6e-fb200707dd22 | note | INSPECTION/TEST METHOD: Inspection
4fe9b664-a444-50cc-9f3a-45cdf803c30a | note | CONFORMANCE RECORD: ITP
ed1ad6ee-e713-5cf4-88e6-113c6b4bdbcc | note | HP*
57e1cbbe-d3ae-5978-9ae4-aa2a6a57889d | note | RESPONSIBILITY: Fulton Hogan
3e59d740-9279-5c2a-ab6a-d3b167723df3 | date | Date Completed:
4717b1c5-4614-415d-bb71-6c9ca8d600e3 | checkpoint | Approval of steelwork and Formwork of footing prior to concrete pour
0b3cce6f-f11d-4998-9557-57dc0f44fe2e | signoff | CLIENT SIGNOFF
4c934cdb-4a5e-492e-a1bf-5e48abc70b3a | checkpoint | Approval of steelwork and Formwork of wall prior to concrete pour
616e76af-783f-4e51-983e-092397b78c02 | signoff | CLIENT SIGNOFF
dc8d5d43-31cd-439e-8dc8-adbc4e8dee81 | section | 2 - Site Access / Rock Fill / Wingwall Repairs
3fe307de-47f0-4cc0-85d1-f6f605300dc7 | checkpoint | 2.1 - Control of water through site
22a732b6-8004-5728-8850-829d6473d3de | note | FREQUENCY: Prior to excavation of toe
cc5ceccc-7d94-54bb-8c5b-18aafc1e84d5 | note | ACCEPTANCE CRITERIA: Dewatering and earth bund to be confirmed on site
371bc85b-511b-5536-8f7a-ed14559f9c3a | note | REFERENCE DOCUMENTS: Environmental Management plan
2f58e12c-16b6-5721-89d0-06d46c3ab29a | note | INSPECTION/TEST METHOD: Site inspection
d6939bff-57a3-5109-b683-a5bb23bcc60f | note | CONFORMANCE RECORD: ITP
8c7d01bd-34e2-5ec7-aced-e756583cf82e | note | IP
c2023ac1-3eee-5f9b-8470-429d4940025b | note | RESPONSIBILITY: Client and Fulton Hogan
187a8938-b4d9-58e5-952f-7f10e4994e53 | date | Date Completed:
152df5a6-b787-44be-99e2-7ad5f44ae11a | signoff | AUTHORITY HOLDPOINT
dc8a564e-6985-4f0d-bc04-4b91f4e37746 | checkpoint | 2.2 - Tree removal
b220dd35-f225-578f-8539-e2a66c3a2bd7 | note | FREQUENCY: Prior to commencement
4f005b0d-86a3-55bc-b462-83ab2e09416d | note | ACCEPTANCE CRITERIA: Trees for removal marked out and approved for removal
10eeb016-697b-5e8d-b15f-350651ba3e7e | note | REFERENCE DOCUMENTS: Environmental Management plan, DEECA permit
fa2cceab-eb7d-5d18-bb96-7fc71a86978f | note | INSPECTION/TEST METHOD: Site Inspection Permit
4756e140-5109-5fb5-aaaa-a277a6b3e06f | note | CONFORMANCE RECORD: ITP Permit
0c93464c-2a60-583c-b12d-b194c826ba38 | note | HP
522088ec-4e0c-5770-a33c-f882b66a5574 | note | RESPONSIBILITY: Client and Fulton Hogan
cf426b20-4f34-5154-84dd-2bf6db161ace | date | Date Completed:
0f86e23d-12dd-4164-8056-597f0bfdc33e | signoff | AUTHORITY HOLDPOINT
66db1a0f-4300-49f2-a8a2-d225af9a15ee | checkpoint | 2.3 - Site Benching/ access track
ca4f56d4-6736-5303-a908-0c320991f490 | note | FREQUENCY: Prior to commencement
a8f17b97-5129-5439-baa3-34a3a11f579d | note | ACCEPTANCE CRITERIA: Adequate benching and site access track constructed
7497f064-fe61-5a47-81c7-a3622b6c8f3e | note | REFERENCE DOCUMENTS: Scope document
52b7d868-db04-52b2-8da9-c9c5f376cd70 | note | INSPECTION/TEST METHOD: Inspection
5d620460-201c-5bad-9c7d-22b4ca08ade5 | note | CONFORMANCE RECORD: ITP
e51f381e-898d-5db0-be7a-58d1ac3bb153 | note | IP
4e86d240-2d7b-5d4f-8c86-6b96bc4933bd | note | RESPONSIBILITY: Fulton Hogan
3c4be706-9eba-5c74-9280-00f6c095c7a4 | date | Date Completed:
1786c8c2-9b3e-4d00-8c2d-d775c2238457 | checkpoint | 2.4 - Fill Material
09e9f7b4-a01b-51b1-a44b-6bf905de7b5a | note | FREQUENCY: Prior to placement
4d709c2a-3454-5cee-846e-653c68c19c64 | note | ACCEPTANCE CRITERIA: Suitable Type A Fill material used for placement behind upstream wingwall/ Vic Roads accreditation letter and relevant test results received for Type A Fill material
ddd07a7f-fda6-5d43-b857-cfd2f83df254 | note | REFERENCE DOCUMENTS: Scope document Drawing
72661d1a-ee5d-5d2a-8853-16760cb49504 | note | INSPECTION/TEST METHOD: Inspection
3fabbae5-825d-5f85-8f4a-9bfb14e5ab02 | note | CONFORMANCE RECORD: ITP
ea2bfde5-768b-5d88-a7cd-72756312743d | note | WP
59c90a93-627b-5857-8f0f-19b35c5fabc5 | note | RESPONSIBILITY: Fulton Hogan/Client
75397d65-b63a-5cc5-b93d-34571d3f4547 | date | Date Completed:
f367a006-44bd-4e66-9eae-2c871528a24f | signoff | AUTHORITY HOLDPOINT
4c34d7a5-51e0-4a84-9a2b-3fad41a1957a | checkpoint | 2.5 - Geofabric
e5a9f997-cdc8-5c79-ace9-231bdfe41200 | note | FREQUENCY: Prior to wingwall form and rock placement
a31e81d2-d192-5817-96b3-05463f78784f | note | ACCEPTANCE CRITERIA: Geotextile layer placed under rock beaching and behind wingwall
6a11e3e1-8628-5670-8828-debd2cc2b611 | note | REFERENCE DOCUMENTS: Drawing
6003b5dd-a924-53aa-bc61-568eaa7d3171 | note | INSPECTION/TEST METHOD: Inspection
536571fb-d06c-5b63-b12d-1934fcb1f77f | note | CONFORMANCE RECORD: ITP
139bfdcd-11f2-5a19-af3f-54b6efd84ecf | note | IP
79d8a9b3-7356-5c4b-8326-b86d285e4ff9 | note | RESPONSIBILITY: Fulton Hogan
3b87ded8-d0ca-550c-9c07-21e3124f65dd | date | Date Completed:
123c5750-9021-4ef9-aeb2-3217bc3378c9 | checkpoint | 2.6 - Toe Rock Placement (downstream)
ef80ed61-5dad-5756-a57c-1234db8d9a53 | note | FREQUENCY: During the placement of the toe rock
65e31746-f0d1-520a-bfd1-263ea26b2f7d | note | ACCEPTANCE CRITERIA: Solid base, Maximum particle sizes 750-1000mm
34f7119e-b208-57e7-8a07-f313472dff12 | note | REFERENCE DOCUMENTS: N/A
a7e7802d-c09d-5dbb-b8b7-21f05cd46aa6 | note | INSPECTION/TEST METHOD: Inspection
b738b76d-018d-5930-8674-2b04795fe788 | note | CONFORMANCE RECORD: ITP
9d0e1727-3427-5940-a396-61dc7f70bf92 | note | IP
98b9da54-ee7b-54a3-b218-f01a77f88317 | note | RESPONSIBILITY: Client/ Fulton Hogan
7b616f31-d2d5-52d4-9503-a010b370acbd | date | Date Completed:
60a1b02a-143f-4e30-a524-f29f1808ec37 | signoff | AUTHORITY HOLDPOINT
9649a14b-f864-46ad-9716-496530e0c81e | checkpoint | 2.7 - Flowable grout
e1deaa71-a772-5b2c-8b4c-b1de6fb010a5 | note | FREQUENCY: During construction
ea2168d9-3149-5437-9cc9-31f4971178b7 | note | ACCEPTANCE CRITERIA: Flowable grout adequately placed to fill void under downstream wingwall
5815cd49-a60f-5495-9b20-e9c2cc9f4d22 | note | REFERENCE DOCUMENTS: Drawing
76ee8585-27a5-5153-936a-9e86855122e6 | note | INSPECTION/TEST METHOD: Inspection
c247c4c3-5fc3-5a17-9a8e-687efb767177 | note | CONFORMANCE RECORD: ITP
d7fbff92-6ef2-50a7-bdd8-207b79225325 | note | HP
261e77dd-4725-55a0-a5d9-dad16b6b0a63 | note | RESPONSIBILITY: Client
b0300632-24d8-50c4-ae1b-07d80f7b65a7 | date | Date Completed:
e204b073-f4c9-4474-a594-fa66fce1fc59 | signoff | AUTHORITY HOLDPOINT
7705e782-e023-4af5-b8e3-8da2a0bcb44d | checkpoint | 2.7 - Rock beaching upstream
5b37d819-bccd-52f3-842e-bd9f88dc36f7 | note | FREQUENCY: During placement
cbe1caeb-c4dd-5b62-8bb0-36a6b984078d | note | ACCEPTANCE CRITERIA: Acceptance of placement
008ad678-8253-53b9-ad63-a9ff1adc11a0 | note | REFERENCE DOCUMENTS: Plans Sec 713
08cac132-28ee-5cdd-9939-fe5d2e4a6d14 | note | INSPECTION/TEST METHOD: Inspection
1b814c40-fabd-511d-9118-ae0de5d16ea5 | note | CONFORMANCE RECORD: ITP
56b337d3-c25c-5403-8937-0ff0763efc26 | note | HP
a4b05a04-a261-5575-a136-1c98582bb428 | note | RESPONSIBILITY: Fulton Hogan
65872976-34f6-5c6e-9219-4a73b94a9040 | date | Date Completed:
6a750525-e2c8-4322-a050-0df77c89dc89 | signoff | AUTHORITY HOLDPOINT
8969ef7b-0847-4126-9b3e-02a267e07936 | section | 3 - Wingwall
4d3fb996-8850-4c19-84d4-ed4f98d44ebe | checkpoint | 3.1 - Approval of excavation
b867f10f-5aa7-577e-9148-8d99e1db6f60 | note | FREQUENCY: Prior to steelwork
f8e6b5ab-adba-5a82-af0c-dce9ce23a4c9 | note | ACCEPTANCE CRITERIA: Approval of design excavation toe and acceptable base of excavation
cbcf034e-aeba-565c-a52a-ff61d3020b73 | note | REFERENCE DOCUMENTS: Plans
addc5848-798a-552a-bfe3-993b0ed89e8d | note | INSPECTION/TEST METHOD: Inspection
705bb325-f39c-528f-bba7-6fbe172e1253 | note | CONFORMANCE RECORD: ITP
455317fa-d1e5-5ac7-b375-7bb0983d4768 | note | HP
748dd619-0a17-5fe7-86eb-509a8beb6017 | note | RESPONSIBILITY: Client/ Fulton Hogan
c72b037d-1dfd-5cee-af2e-e6188bdf3f34 | date | Date Completed:
e99f03da-eda9-4e33-9216-d63ccb210ec6 | checkpoint | 3.2 - Approval of steel work
686f6c1c-6833-56c0-90d8-b05d44ba6718 | note | FREQUENCY: Prior to concrete pour
0b5d7eef-3a99-529c-aa09-d9351dc629dc | note | ACCEPTANCE CRITERIA: Approval of steelwork for wingwall footing
f9316114-524e-52ee-a1db-59f7b8d4790d | note | REFERENCE DOCUMENTS: Plans
5f159a29-74f7-5e43-a941-d76c69a8fbbc | note | INSPECTION/TEST METHOD: Inspection
fea37287-d7e0-58f6-87a1-cce07e79f096 | note | CONFORMANCE RECORD: ITP
ef0c3b4b-be2e-5309-9d41-476dc642711b | note | HP
5613ac1e-de30-52a7-b576-a532de3ce395 | note | RESPONSIBILITY: Client/ Fulton Hogan
2fffcd18-cd6c-5e77-b3b4-bca2eec5046e | date | Date Completed:
65002387-04ea-4fed-b9fe-f9beeb21a125 | checkpoint | 3.3 - Approval of excavation
837f36ba-8e0b-521c-9de5-1c58f134844c | note | FREQUENCY: Prior to steelwork
3563b4f5-a5a6-5971-853a-034b3fa1e50a | note | ACCEPTANCE CRITERIA: Approval of design excavation toe
831518e0-fd3b-5e98-9e4a-f4c2b083bd00 | note | REFERENCE DOCUMENTS: Plans
1423272f-b8ff-5bb2-b92b-b7e288095738 | note | INSPECTION/TEST METHOD: Hold point
33438aa4-af42-5eb8-8d62-836c17a063ba | note | CONFORMANCE RECORD: ITP
52d04e2b-45ab-5b6e-a02d-02c3a0ada23c | note | HP
de474510-62fe-5665-a70c-eebbe4033da3 | note | RESPONSIBILITY: Client/ Fulton Hogan
b557bb3c-6ded-5d7b-bb96-344a979e4fb1 | date | Date Completed:
ab8d6e1d-aba8-42ce-8852-d2e4946c870e | checkpoint | 3.4 - Approval of steel work
5ab0bf76-cf0d-5c9f-8cf9-f66edafce670 | note | FREQUENCY: Prior to concrete pour
c2315dc4-3cc5-58e4-881f-0a5c5669e6ab | note | ACCEPTANCE CRITERIA: Approval of steelwork for wingwall including placement of bitumen fibreboard
83556359-f81b-5a6b-b6d4-36b4243a1ff1 | note | REFERENCE DOCUMENTS: Plans
a07dacfb-5cf5-5d99-ab70-b08aac0c4166 | note | INSPECTION/TEST METHOD: Hold point
2f7902e8-4dce-5de2-a735-e3f461a4ba02 | note | CONFORMANCE RECORD: ITP
ab65ad07-bca6-591f-bff9-e116aab8a718 | note | HP
35110c7a-4563-5979-8c03-2558b00a62de | note | RESPONSIBILITY: Client/ Fulton Hogan
cd362684-a429-5902-b440-631868e69ea7 | date | Date Completed:
e433f4cd-941b-4f07-bbcc-79245900f84e | checkpoint | 3.5 - Concrete curing
8cafef37-5b0e-53f5-bf65-eaacad31d8d4 | note | FREQUENCY: Prior to stripping forms and placing fill
584bf750-c114-5e4e-9e93-c0fe0106045f | note | ACCEPTANCE CRITERIA: Concrete has undergone adequate curing time and achieved adequate strength
e7246e09-8e54-5b3e-87d2-79905161c4c0 | note | REFERENCE DOCUMENTS: Sec 204, Sec 610
259fa4b4-3f31-5d30-9de6-3f6caa6da9d6 | note | INSPECTION/TEST METHOD: Inspection
44d13583-124e-51db-a7d0-62c9a905ed33 | note | CONFORMANCE RECORD: ITP
9b2ca48c-c292-5db2-9f80-d378187464c8 | note | HP*
32710ea4-945a-519c-a5ca-b07e69448cf5 | note | RESPONSIBILITY: Fulton Hogan
3e4b4ce1-8e6d-5e6c-8ec6-520f3d019cf7 | date | Date Completed:
d0b6b495-2791-4dec-bc59-4af1c15b1fb7 | checkpoint | 3.6 - Concrete strength
73bdca3a-38e2-506a-b3f1-c1db75ba1cd4 | note | FREQUENCY: 7 Days after casting
d1824a87-fb0d-5ac3-aa48-7b10005f5307 | note | ACCEPTANCE CRITERIA: Concrete exceeds minimum 7 day strength of 26MPa
6d29716f-7590-5795-8d10-647c541040b6 | note | REFERENCE DOCUMENTS: Sec 610
27ed3dff-6e27-56c0-a117-d836fe73bf82 | note | INSPECTION/TEST METHOD: Witness
20bd8017-deda-5acf-b43e-f6602216735b | note | CONFORMANCE RECORD: Test result
730ed0c3-0562-5a84-bf0b-ef333ab3c334 | note | HP
8f423ce4-54f8-5982-959f-8f681b77dab5 | note | RESPONSIBILITY: Client/ Fulton Hogan
05fdf57e-3d2b-54a7-a966-2e28ff796e84 | date | Date Completed:
b8aba9e9-0116-4d42-8104-d4bad2202c48 | checkpoint | 3.7 - Concrete strength
167df910-5dc5-5cca-a8dc-e8983ee55b7e | note | FREQUENCY: 28 Days after casting
ace23502-878f-582e-84fb-5e93c8ad2bba | note | ACCEPTANCE CRITERIA: Concrete exceeds minimum 28 day strength of 40MPa
9bcbba18-99d0-5349-80e1-2f2a74bd9a2b | note | REFERENCE DOCUMENTS: Sec 610
7c5da2fb-fc4c-53d4-82c9-75cb2c82099a | note | INSPECTION/TEST METHOD: Witness
d274f5a8-216f-530a-9806-1b9e50749581 | note | CONFORMANCE RECORD: Test result
d283f16d-285b-5426-8d8a-686cb9125be0 | note | HP
65f24aee-b81d-5bd0-a762-f2240e62c66b | note | RESPONSIBILITY: Client/ Fulton Hogan
e69fe4b5-5c2b-5aec-bee6-04bf6e164072 | date | Date Completed:
871d7f18-f57a-41a8-8933-6e4b46665cde | section | 4 - Backfill and Pavement
6830b4d3-4019-45b5-bd3e-8b56db9b993a | checkpoint | 4.1 - Compaction of Type A Fill
aa2804d1-0616-5bdc-ae02-ac85a2e385e4 | note | FREQUENCY: During construction
eeac283e-0e87-5b3b-8983-0a20e63609a7 | note | ACCEPTANCE CRITERIA: Type A fill achieves minimum 98% density ratio
652b2b18-e974-5490-8d75-9b8de495e543 | note | REFERENCE DOCUMENTS: Sec 204
b36e6c3a-8283-5117-a386-56791a2be0ce | note | INSPECTION/TEST METHOD: Witness
49dbce9a-b124-5fe8-bbcb-242b368368ac | note | CONFORMANCE RECORD: Test Results
01e3c80b-8774-57c7-b329-850f2af747e2 | note | HP
5ad1353b-ea09-5267-81ed-65815fdcf4fb | note | RESPONSIBILITY: Client/ Fulton Hogan
3a18d8f2-a865-5e50-ac68-d16ccc5ec913 | date | Date Completed:
147ba57c-fd16-4474-9a45-3a2974848732 | checkpoint | 4.2 - Road base inspection
25c9d3f5-0ab0-5683-a2be-ee0e7eb5fdf4 | note | FREQUENCY: Prior to asphalt
332644b4-ac8a-5fb2-b80d-b554ffadf76d | note | ACCEPTANCE CRITERIA: Road base approved prior to installation of asphalt. Patch marked out in accordance with approved design
4a7d6ed7-0520-5779-a47b-27bc87c57d44 | note | REFERENCE DOCUMENTS: Inspection
630cc7e8-c27b-56a2-8c25-bbfb438ffdec | note | INSPECTION/TEST METHOD: ITP
4871b2d6-0f28-5be4-b5b3-e2a0a610b609 | note | CONFORMANCE RECORD: HP*
f7775ad0-a925-5b9c-be7a-81d6ee7ff597 | note | HP*
cf16680a-64d1-5278-a171-c8952557b070 | note | RESPONSIBILITY: Fulton Hogan
70912397-5fa4-574d-b861-ae77f2f8b2db | date | Date Completed:
4076a18e-ebe7-446d-bba7-51c18cc237f4 | checkpoint | 4.3 - Asphalt patch
6e92353e-0753-50f1-af79-f5e428f94b2e | note | FREQUENCY: After laying
cf6b8c31-c139-58b7-81fc-73465aeeb630 | note | ACCEPTANCE CRITERIA: Asphalt patch completed within tolerance of specification and approved design
2d7f8008-ce44-5010-af5a-ce578604bf60 | note | REFERENCE DOCUMENTS: Sec 407
aef03757-78db-5ab8-b58c-644b636b7270 | note | INSPECTION/TEST METHOD: Inspection
a537e8cb-da69-5f08-81a5-da5aee1e46a3 | note | CONFORMANCE RECORD: ITP
9dbd70b4-0dea-5103-95eb-87dc17cec737 | note | HP
e6695dd8-f856-5fa9-b4a8-1a7d20f78ddc | note | RESPONSIBILITY: Fulton Hogan / Client
5e7e01df-f5fb-5440-bc7e-d881a31424db | date | Date Completed:
5eb2395c-3d59-43ef-bad5-b4d2cb1d5834 | checkpoint | 4.4 - Linemarking
37cf7db8-d664-5cf2-94fc-b71092f85497 | note | FREQUENCY: After installation
249573a7-190f-5722-b869-9c7fec1c4855 | note | ACCEPTANCE CRITERIA: Linemarking and RRPMs reinstated accordingly
b0ce2188-d351-5c56-9d9e-0098b068082b | note | REFERENCE DOCUMENTS: Sec 721
c39a01ff-5818-56d8-ab6e-843e5ad219bf | note | INSPECTION/TEST METHOD: Inspection
915e16ef-2509-5c40-96b7-c9e9f02cbbcd | note | CONFORMANCE RECORD: ITP
a4fae26c-f7df-5a45-b30e-3b74111c6217 | note | HP
96f75e41-90a2-5e02-9e08-b6916c038f67 | note | RESPONSIBILITY: Fulton Hogan / Client
39d53abd-ac9b-5bc2-a0c6-f36a99eaed09 | date | Date Completed:
86e2cc55-3cd0-414c-a6b5-44a5a5d0f9a1 | checkpoint | 4.5 - Guardrail setout
013d8cd3-a7e4-5ce2-b648-2260fc8a9cb2 | note | FREQUENCY: Prior to installation
49a4725e-3d8a-5907-8cb9-b012eb910dfc | note | ACCEPTANCE CRITERIA: Setout of guardrail confirmed.
4e82409f-e095-56fa-bb18-e11588bbea52 | note | REFERENCE DOCUMENTS: Sec 708
7844bce4-9780-52d7-b6d2-79d978a8eb59 | note | INSPECTION/TEST METHOD: Inspection
b0672605-f0eb-5c76-87f7-e93a3e2dc4ee | note | CONFORMANCE RECORD: ITP
354c3d19-1e89-5c33-b53d-d9873e51fe34 | note | HP
f31ad29a-af51-5df4-8eaf-075cf70a6bf4 | note | RESPONSIBILITY: Fulton Hogan / Client
6618b46e-ea94-5241-97b6-b5ffd2fe01ad | date | Date Completed:
a8bdf7e8-d692-4ca0-8c43-e1a8fbe0641b | checkpoint | 4.6 - Guardrail installation
7f0adad9-8cf7-5e4c-8202-4c8f5c8bbcc4 | note | FREQUENCY: After completion
e53c0a0e-1767-5d0c-8291-472274dc4a2e | note | ACCEPTANCE CRITERIA: Guardrail installed within specification
dd2b89c0-3cc0-5b46-b181-5e3c2e25c407 | note | ○ Certificate of Compliance received
5f0b919f-a81a-5f05-9fa3-b1a0c4f61a8a | note | REFERENCE DOCUMENTS: Sec 708
3fd2609c-3fd3-5c88-914b-a1e54d7577d0 | note | INSPECTION/TEST METHOD: Inspection
090a2871-420e-51fd-88b1-670f849f9d83 | note | CONFORMANCE RECORD: ITP
3367d2cb-1d8a-5f9a-b64a-383ea4676668 | note | HP
09695252-cc2c-525a-ac6f-06872305d2a2 | note | RESPONSIBILITY: Fulton Hogan / Client
3fae2e37-aa07-5dd9-aa84-ea4aa927a6f7 | date | Date Completed:
3e8186c8-e503-4e50-9c34-9b5bd1b5ca22 | checkpoint | 4.7 - Demobilisation
31ca16d2-abe1-58ff-93e7-963ab53d53e5 | note | FREQUENCY: At the completion of works
ccdf9231-4030-5f45-a2e8-8ec6f791b257 | note | ACCEPTANCE CRITERIA: Worksite left clean and tidy.
f263b8f8-0189-5650-95ef-ea4e870c8284 | note | ○ All outstanding defects rectified
09c9d659-7312-5346-a3d8-0f9ef27613b3 | note | REFERENCE DOCUMENTS: NA
6c2a902a-955f-5f7e-ba48-794f04bc129d | note | INSPECTION/TEST METHOD: Inspection
ce2cee31-45a0-5fe5-860b-a92bcdfa4963 | note | CONFORMANCE RECORD: ITP
1ba09c54-53fc-515d-8ea1-75abcef6b8d9 | note | HP
16500acf-6bf4-591d-9619-3de49b6b959d | note | RESPONSIBILITY: Fulton Hogan / Client
1274209d-8441-57bf-b51d-f27d3de4d89c | date | Date Completed:
fa2ddeac-5a4e-4963-b46d-f5971794cde9 | signoff | AUTHORITY HOLDPOINT
2e38cba5-3b11-4e26-b65f-71267becce09 | checkpoint | Final Inspection
7cb09cc9-5b1c-5482-88b7-39c5eaaa1b58 | note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
4311ad4e-2c61-5654-bc8c-59f942490957 | textbox | Print Name:
4e1f2671-43dc-5586-9796-9d3069c606e4 | textbox | Position:
c66ee8ff-cbc2-57dc-b9cd-75dd1bf30e0d | date | Date: