## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Overall Progress
Scope
Rows
|  | Site QA | grouping | Site QA
|  | Floor outside WC |  | Floor outside WC
|  | Floor & Walls WC |  | Floor & Walls WC
Columns
|  | Is the area clean, & cleared, ready for necessary preparation |  | Is the area clean, and cleared, ready for necessary preparation
|  | Grinding, if req., completed before works & after works |  | Grinding, if required, completed before works (photo required) after works (photo required)
|  | Floor levelling completed & applied as per reqs. |  | Floor levelling completed and applied as per requirements. (m2 rate)
|  | Floor levelling completed - hours & bags used recorded |  | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
|  | Tiles set out according to latest drawing |  | Tiles set out according to latest drawing - always check revisions on site
|  | Specified product used with notched trowel or req. product |  | Specified product used with notched trowel or required product
|  | Correct spacer size used for spacing as per specs & tile lipping within BRANZ tolerances |  | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
|  | Floor/Wall substrate straight, signed off by MC, & ready for installation |  | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
|  | Install tiles to floors as per drawings |  | Install tiles to floors as per drawings
|  | Grout nominated is the correct colour & applied evenly & correctly |  | Grout nominated is the correct colour and applied evenly and correctly
|  | Grout is consistent throughout & no missing grout |  | Grout is consistent throughout and no missing grout.
|  | Tiling completed, checked & Supervisor signoff |  | Tiling completed, checked and Supervisor sign off
|  | Silicone is completed to all tile junctions where req. |  | Silicone is completed to all tile junctions where required
|  | Area left clean & tidy |  | Area left clean & tidy
|  | Builders clean completed |  | Builders clean completed
|  | Variations or extra works added into folder |  | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
|  | change of details & or instructions |  | change of details and or instructions
|  | Site specific details to be added |  | Site specific details to be added
|  | Material Details - Notes to be added of materials used on site |  | Material Details - Notes to be added of materials used on site
|  | No items are left on fail |  | No items are left on fail. If so, provide reasons why before invoiced out.