## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Prestart Inspections
section | Details
checkpoint | Site has been cleaned in advance of our arrival on site
checkpoint | Walls are plumb and level
label | IMPORTANT
checkpoint | Tiling works running to programme - prior trades completed
checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
checkpoint | Data sheets, of products, are supplied on site with TA's
checkpoint | Inductions completed & Site Inspection checklist has been completed
checkpoint | All tools tagged and tested - (photo's required)
checkpoint | Tiler has current site safe - Input number and expiry
checkpoint | Tiler has correct PPE relevant to project.
checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
checklist | Wall/Floor Preparation | [5 empty] | QA - Wall/Floor Preparation
section | Details
checkpoint | Is the area clean, and cleared, ready for necessary preparation
checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
checklist | Tiling Installation Floors | [5 empty] | QA - Tiling Installation Floors
section | Tiling to floors
checkpoint | Tiles set out according to latest drawing - always check revisions on site
checkpoint | Specified product used with notched trowel or required product
checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Install tiles to floors as per drawings
checkpoint | Grout nominated is the correct colour and applied evenly and correctly
checkpoint | Grout is consistent throughout and no missing grout.
checkpoint | Tiling completed, checked and Supervisor sign off
checkpoint | Silicone is completed to all tile junctions where required
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
checklist | Tiling Installation Floors/Walls | [5 empty] | QA - Tiling Installation Floors/Walls
section | Tiling to floors and walls
checkpoint | Tiles set out according to latest drawing - always check revisions on site
checkpoint | Specified product used with notched trowel or required product
checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Install tiles to floors as per drawings
checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
checkpoint | Install tiles to walls as per drawings
checkpoint | Grout nominated is the correct colour and applied evenly and correctly
checkpoint | Grout is consistent throughout and no missing grout.
checkpoint | Tiling completed, checked and Supervisor sign off
checkpoint | Silicone is completed to all tile junctions where required
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
checklist | Other Information | [5 empty] | QA - Other Information
section | Details
checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
checkpoint | change of details and or instructions
checkpoint | Site specific details to be added
checkpoint | Material Details - Notes to be added of materials used on site
checklist | Final Sign Off for Invoicing | [5 empty] | QA - Final Sign Off for Invoicing
section | Details
checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.