## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-004b - Cement Treated Crush Rock Sub Base | itp |  |  |  |  | ITP-004b - Cement Treated Crush Rock Sub Base
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and complete design drawing.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.3 Confirm CTCR is appropriate mix
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Cement treated crushed rock proposed for use shall be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
label | ○ CTCR shall be tested in accordance with 815.141 by supplier
label | REFERENCE DOCUMENTS: Design mix specifications
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
section | Construction Works
checkpoint | 2.1 Sub base
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
label | ○ ITP-001 HP for subgrade inspection signed off.
label | REFERENCE DOCUMENTS: VicRoads 173.03
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.2 Moisture content
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Moisture content shall be within 0.5 to 1% percentage of mass during time of spreading and compaction
label | REFERENCE DOCUMENTS: VicRoads 306.05
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: Record of conformity
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.3 Jointing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Material shall be spread to minimise number of joins.
label | ○ Transverse joints in adjoining paver runs shall be offsset by >2m
label | ○ Longitudinal joints shall be offset from each layer >150mm
label | ○ Longitudinal Joins shall be within 300mm from traffic lane lines or centre of traffic lane
label | REFERENCE DOCUMENTS: VicRoads 306.08
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.4 Conformity with drawings
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavement sub base shall be finished to smooth and uniform surface
label | ○ Surface of sub grade shall not lie more than 12mm below a 3m straightedge
label | ○ Subgrade height shall lie within +15 to -25mm
label | ○ Sub base height shall lie within +10 to -25mm
label | REFERENCE DOCUMENTS: VicRoads 306.03, 306.11
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.5 Curing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
label | ○ As per VicRoads, 4000m2 shall be maximum lot size
label | ○ No trafficking before 24hrs unless approved by superintendent
label | REFERENCE DOCUMENTS: VicRoads 306.11
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.6 Compaction testing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: CT material shall be placed, trimmed to level and compacted within allowable working time (306.091)
label | ○ At completion of compaction, any segregation shall be rectified
label | ○ >500m2 96% modified compaction 6 tests
label | ○ <500m2 98% modified compaction 3 tests
label | REFERENCE DOCUMENTS: VicRoads 306.09, 306.11
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: