## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-008 - Hot Mix Asphalt Rev3 | itp |  |  |  |  | ITP-008 - Hot Mix Asphalt Rev3
section | Construction Works
checkpoint | 1.1 Submission of Mix Design
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
label | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 Site Inspection and Base Condition
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | Date Completed:
checkpoint | 1.3 Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | REFERENCE DOCUMENTS: 407.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Thermometer
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | Date Completed:
checkpoint | 1.4 Planning of Joints
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints Offset from layer to layer by at least
label | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
label | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Paving Plan
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
text | Date Completed:
checkpoint | 1.5 Longitudinal Joints with existing Pavement
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each indiviual layer.
label | REFERENCE DOCUMENTS: 407.16 (c) Project Specs. Section 3040.06 (d)(vii)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
text | Date Completed:
section | Asphalt Placement works
checkpoint | 2.1 Tack Coat
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen) or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases.
label | ○ Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
label | REFERENCE DOCUMENTS: Vicroads Spec 407.19 AS2150 11
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | Date Completed:
checkpoint | 2.2 Commencement of Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | REFERENCE DOCUMENTS: 407.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Mix design confirmation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt mixes shall be in accordance with Yarra Trams Track Structure standard drawing.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06 STD_T9010 - Typical Track Structures
label | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
label | RECORD OF CONFORMITY: Delivery docket, Completed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | Date Completed:
checkpoint | 2.4 Delivery of mix
label | FREQUENCY: Each load
label | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | REFERENCE DOCUMENTS: 407.16 Table 407.081
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Delivery Docket
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | Date Completed:
checkpoint | 2.5 Traceability
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Daily Lot Record
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | Date Completed:
checkpoint | 2.6 Layer thickness and level control
label | FREQUENCY: Regularly during paving
label | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | Date Completed:
checkpoint | 2.7 Surface finish of wearing course
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | REFERENCE DOCUMENTS: 407.23 (a)(i)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | Date Completed:
checkpoint | 2.8 Alignment of layers not placed against concrete edge
label | FREQUENCY: During paving and at completion of work
label | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | Date Completed:
section | Testing
checkpoint | 3.1 Compaction
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: For wearing course layers <50mm, if characteristic density ratio is:
label | ○ 94.0% or greater Accept lot
label | ○ 91.0% to 93.9% Lot may be accepted at reduced rate.
label | ○ Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
label | REFERENCE DOCUMENTS: Table 407.221
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer/ FH Lab Technician
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: