## ITP
INSPECTION & TEST PLAN
Project No 7014 |  | Contract Name: |  |  |  |  | Rev: | Originator | Date | Approved | Date
|  | CON 21086 Bridges Upgrades at Hayward Road, Thompson Road, McAlister Road |  |  | Hold Point (H) | Review(R) | 0 | JW | 2023-09-15
[5 empty] | Submit (S) | Surveillance (SU) | 1 | GW | 2023-09-27 | GW | 2023-09-27
Approve(A)
Verify (V)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | WSP | DATE | COMMENTS
General
Preliminary
Pre-Works Documentation | Particular Specification, section 2.1, page 75 | Insurance, Programme of Works, Traffic Management Plans, Site Safety Plan, Quality Plan, Environemental Management Plan, Temporary Works Designs, Notification Letter, Existing Conditions Report | Engineer | Prior to works commencing | Approved by Engineer | S | H
Hayward Road Bridge No. 131
Steel Components
Structural Steel and Bolts | Particular Specification, section 1.1.17, page 97 | Material properties, Manufacturer's mill certificates | UCCL | On supply of materials | Bolts meet AS/NZS 2465. Steelwork meets AS/NZS 5131. | S
Structural Steel Coating | Particular Specification, section 1.1.17, page 97 | Ultrasonic coating thickness, Manufacturer's statement | UCCL/Subcontractor | On completion of steel coating | Approved by Engineer. Bolts meet AS/NZS 1214. Steelwork meets AS/NZS 4680 and AS/NZS 2312.2. | W | H
Structural Steel Welds | Particular Specification, section 1.1.17, page 97 | Visual Inspection, Welding certificates | Engineer | At completion of steel fabrication | Approved by Engineer | H | H
Timber Deck and Handrail Components | Particular Specification, section 1.1.17, page 97 | Timber properties | Engineer | On supply of materials | Meets Particular Specification and NZTPA specifications | W | W
Granular Aggregates | Particular Specification, section 1.1.17, page 97 | Grading, Soaked CBR, Crushing Resistance, Clay Index | Engineer | One test per 750m³ stockpiled. Compliance certificate not more than 3 months old. | Approved by Engineer. Compliance certificates not more than 3 months old. | S | A
Granular Fill Compaction | Particular Specification, section 1.1.17, page 98 | Clegg Impact Value | UCCL/Engineer | Three tests per compacted layer (150mm) at each abutment. | As per WDC EES | W | W
Pavement Compaction | Particular Specification, section 1.1.17, page 98 | Clegg Impact Value | UCCL/Engineer | Six tests per compacted layer (150mm) at each abutment. | As per WDC EES | W | W
Sealing Chip | Particular Specification, section 1.1.17, page 98 | Size, Shape, Grading, Cleanness, Crushing Resistance, Weathering Resistance | Engineer | Compliance certificate not more than 3 months old. | Approved by Engineer. Compliance certificates not more than 3 months old. | W | W
Thompson Road Bridge No. 129
Steel Components
Structural Steel and Bolts | Particular Specification, section 1.1.17, page 97 | Material properties, Manufacturer's mill certificates | UCCL | On supply of materials | Bolts meet AS/NZS 2465. Steelwork meets AS/NZS 5131. | S
Structural Steel Coating | Particular Specification, section 1.1.17, page 97 | Ultrasonic coating thickness, Manufacturer's statement | UCCL/Subcontractor | On completion of steel coating | Approved by Engineer. Bolts meet AS/NZS 1214. Steelwork meets AS/NZS 4680 and AS/NZS 2312.2. | W | H
Structural Steel Welds | Particular Specification, section 1.1.17, page 97 | Visual Inspection, Welding certificates | Engineer | At completion of steel fabrication | Approved by Engineer | H | H
Timber Deck and Handrail Components | Particular Specification, section 1.1.17, page 97 | Timber properties | Engineer | On supply of materials | Meets Particular Specification and NZTPA specifications | W | W
Granular Aggregates | Particular Specification, section 1.1.17, page 97 | Grading, Soaked CBR, Crushing Resistance, Clay Index | Engineer | One test per 750m³ stockpiled. Compliance certificate not more than 3 months old. | Approved by Engineer. Compliance certificates not more than 3 months old. | S | A
Granular Fill Compaction | Particular Specification, section 1.1.17, page 98 | Clegg Impact Value | UCCL/Engineer | Three tests per compacted layer (150mm) at each abutment. | As per WDC EES | W | W
Pavement Compaction | Particular Specification, section 1.1.17, page 98 | Clegg Impact Value | UCCL/Engineer | Six tests per compacted layer (150mm) at each abutment. | As per WDC EES | W | W
Sealing Chip | Particular Specification, section 1.1.17, page 98 | Size, Shape, Grading, Cleanness, Crushing Resistance, Weathering Resistance | Engineer | Compliance certificate not more than 3 months old. | Approved by Engineer. Compliance certificates not more than 3 months old. | W | W
McAlister Road Bridge No. A117A
Steel Components
Structural Steel and Bolts | Particular Specification, section 1.1.17, page 97 | Material properties, Manufacturer's mill certificates | UCCL | On supply of materials | Bolts meet AS/NZS 2465. Steelwork meets AS/NZS 5131. | S
Structural Steel Coating | Particular Specification, section 1.1.17, page 97 | Ultrasonic coating thickness, Manufacturer's statement | Engineer | On completion of steel coating | Approved by Engineer. Bolts meet AS/NZS 1214. Steelwork meets AS/NZS 4680 and AS/NZS 2312.2. | H | H
Structural Steel Welds | Particular Specification, section 1.1.17, page 97 | Visual Inspection, Welding certificates | Engineer | Throughout steel fabrication | Approved by Engineer | H | H
Superstrucutral Removal | Particular Specification, section 13.3.1, page 88 | Visual Inspection | Engineer | Engineer's observation of superstructural removal | Approved by Engineer | W | W
Capping Beam and Columns | Particular Specification, section2.1.1.3, page99 | Supplier Docket | UCCL | Prior to delivery to site | Timber is Greenheart hardwood, 250mm x 250mm | H | V