## ITP Cover Page
[16 empty] | Pavement & Surfacing Inspection and Test Plan | [7 empty] | Subordinate Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 1 | [5 empty] | Subordinate ITP Cover page UPDATE
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Pavement & Surfacing ITP - Subbase |  |  |  |  | Revision: | 1000 |  | A
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity | [6 empty] | Subordinate Inspection and Test Plan Details
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key |  |  |  | Construction Pack Number: |  |  | CP##
A | Draft for Approval | 2023-04-04 |  | Gabriel |  | First Revieion for Review and Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep |  |  | Work Area / Chainage / Lot: | [5 empty] | SUB ITP NO. S-
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval | 2023-04-18 |  | Emil |  | Review A reviewed by the BBO engineer, some changes were made and resent for approval. DN1205-BBO-GCO-0051 (14/04/2023) |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager |  |  | Master ITP Details:
C | Draft for Approval | 2023-05-01 |  | Emil |  | Review B reviewed by the BBO engineer, some changes were made and resent for approval. DN1205-BBO-GCO-0055 (26/04/2023) |  |  |  | E | Examine |  | OP | Operations Manager |  |  | Review / Update History
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep |  |  | Rev: | Status: | Date: |  | Reviewed By: | Revision Details:
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep |  |  | A |  |  |  |  | Subordinate ITP Creation for
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor |  |  | SUB ITP Instructions: 0. Master ITP to be Approved and Accepted 1. Extract Cover page (this page) and Body page to new Workbook 2. Drag and drop the two white cell blocs above into the cover page 3. Assign an ITP Number in Mater ITP Register tab 4. Populate Title Page Details 5. Remove all Inspection points in the Body which do not relate to works 6. Review for approval, submitting to Client / Engineer once internally approved
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Sub-base
Pavement & Surfacing Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence | Downer | Construction Pack | Prior to Works start | H | PE
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works start | H | SV
3.01.03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.04 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable. | Downer | Internal Permits | Prior to activity being undertaken | H | SE
3.01.05 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable. | Downer | External Permits | Prior to commencment of activity | H | PE
3.01.06 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
3.01.07 | Stabilising Methodology | Written approval of the Engineer with the approval of the methodology | PS - 7.3.3 | Correspondence | Prior to stabilisation start | HP | ENG
3.01.08 | Acceptance of the SIL layer | Written approval of the Engineer - All compliant test results for subgrade, SIL, all road crossings, storm water, wastewater, watermain, subsoil/pavement drains and any other activity that has been completed in the pavement area. | PS - 4.8.3, Table 4.3 | Hold point relesed / Testing reports | All sections before proceeding to the next layer | HP | ENG
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
5.01 | General Materials
5.01.01 | Sampling and testing | For all aggregates, test information confirming compliance shall be supplied to the Engineer not less than five working days prior to delivery of the material to site. | PS - 7.2.4 | IANZ Lab Reports | five working days prior to delivery of the material to site. | HP | ENG
5.01.02 | Sampling and testing | Water to be used in stabilisation - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening, strength or durability of the bound aggregate layer. Water from sources other than public supply may have its suitability established to the satisfaction of the Engineer by repeating the final approved laboratory based mix design tests with the water now being considered for use. The results of these subsequent mix verification tests shall be greater than 90% of the final results from the previously verified mix design. In addition, work shall be stopped if any discolouration or residue is observed when adding or sprinkling water into or onto the material.” Verifying documents to be dockets from fill up station, or proof of using public water supply. Or Lab reports for alternative supply. | NZTA B/6 item 5 | Lab reports | Prior to Works start, per source | HP | ENG
5.02 | Sub-base aggregate
5.02.01 | Sub-base MDD and OMC | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 1 test per material type | H | PE
5.02.02 | Cement for sub-base stabilisation | Cement for stabilisation shall meet the requirements of NZTA B6. | PS - 7.3.2 PS - 7.2.6 | Datasheets | Prior to Use | H | PE
5.02.05 | Crushing Resistance | The crushing resistance shall not be less than 130kN when the aggregate is tested | NZS 4407: 1991 Test 3.10. | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works | HP | ENG
5.02.06 | Weathering Resistance | The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested | NZS 4407: 1991 Test 3.11 | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works | HP | ENG
5.02.07 | Particle size distribution | The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1. | NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving | IANZ Lab Reports | 0 to 400m³ - 2 tests 400 to 1,500m³ - 3 tests 1,500 to 4,000m³ - 4 tests >4,000m³ - 1 test for each additional 1,000m³ | HP | ENG
5.02.08 | Sand Equivalent | The sand equivalent shall not be less than 25 when the aggregate is tested | NZS 4407: 1991 Test 3.6 (Wet Method) | IANZ Lab Reports |  | HP | ENG
5.02.09 | Liquid Limit | Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested - The LL may also be inferred (where appropriate) from the Cone Penetrometer Limit (CPL). | NZS 4402 Test 2.2 NZS4407:2015 Test 3.2. | IANZ Lab Reports |  | HP | ENG
5.02.10 | Plasticity Index | Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested | NZS 4407 Test 3.4 | IANZ Lab Reports |  | HP | ENG
5.02.11 | Clay Index | Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested | NZS 4407 Test 3.5 | IANZ Lab Reports |  | HP | ENG
5.02.12 | Proportion of Broken Rock | In each of the aggregate fractions between the 63.0mm and 4.75mm sieves not less than 50% by weight shall have two or more broken faces | PS - 7.2.2 | IANZ Lab Reports | 1 Test per source of the coarse aggregate. Additional samples if source is changed | HP | ENG
5.02.13 | Organic Matter | It shall be free of organic matter | PS - 7.2.2 | Photos | Continuous | I | SE/PE
5.02.14 | Accelerated Weathering Testing | If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis The levels of smectite clay minerals are not classified as “abundant” | In accordance with NZTA Standard Specification T20 Draft Specification | Lab Reports | 2 tests per source 4 weeks before use in the works. | HP | ENG
5.02.15 | Repeat Load Triaxial Test | In accordance with NZTA T15 | NZTA T15 | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works. | HP | ENG
5.02.16 | Unconfined Compressive Strength (UCS) | Unconfined Compressive Strength (UCS) testing of source aggregate for modified layers to test sensitivity to additives. | PS - Table No. 7.2 | IANZ Lab Reports | 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed. | HP | ENG
5.02.17 | Indirect Tensile Strength (ITS) | In accordance with draft NZTA T/19 at the rate specified in Table A7.4 using 4.0%, 4.5% and 5.0% cement (with 7 days curing) and results forwarded to the Engineer not less than 7 Working Days prior to construction for confirmation or adjustment of the additive contents. | NZTA T/19 - Table A7.4 | IANZ Lab Reports | 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed. | HP | ENG
SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
6.02 | Sub-base - Non stabilised AP65
6.02.01 | Sub-base MDD and OMC | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | No less than 1 test every 5,000m³ (in place) | R | PE
6.02.02 | Plasticity Index | Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested | Table 7.2 | IANZ Lab Reports | 2 tests per 1000m3 (in place) - Test on Mat Samples | R | PE
6.02.03 | Clay Index | Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested | Table 7.2 | IANZ Lab Reports | 2 tests per 1000m3 (in place) - Test on Mat Samples | R | PE
6.02.04 | Sand Equivalent | Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested | Table 7.2 | IANZ Lab Reports | 2 tests per 1000m3 (in place) - Test on Mat Samples | R | PE
6.02.05 | Particle size distribution | The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1 | Table 7.1 | IANZ Lab Reports | 2 tests per 1000m3 (in place) - Test on Mat Samples | R | PE
6.02.06 | Average Uncompacted Layer Thickness | The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer. | TNZ B/02: 2005 - 7.3 | Survey / Level Checks | 1 test per 20m | I | SV / PE
6.02.07 | Plateau Density Test | The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing. | PS - Table 7.2 - 2.3 | Plateau Density Report | 5 tests per 10,000m2 | I | PE
6.02.08 | Sub-basecourse Pavement Layer Compaction | Mean Value ≥ 95 Minimum Value ≥ 92 | TNZ B/02: 2005 | NDM Report | Min 5 Tests per lot 1000m2 max lot size | I | PE
6.02.09 | Surface shape control | Width: -20mm +100mm (Unconstrained) Vertical: - 25mm +5mm Cross fall: 0.5% on 2m straight edge | TNZ B/2 | Total station Topo showing levels compared to design | Continuous | I | SV / PE
6.03 | Sub-base Stabilisation trial
6.03.01 | Stabilization Production Plan | Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3. | NZTA B/6 7.2.3 | Correspondence | 48H hours prior sabilising commencing | HP | ENG
6.03.02 | Longitudinal Joints | To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater. | NZTA B/6 7.5.2 | Stabilisation Prodution Plan | 48H hours prior sabilising commencing | H | PE
6.03.03 | Stabilisation trial | A trial shall be conducted on a minimum stabilised area of 2,000m2 to verify the performance of the stabilising operation and finished product prior to full scale production. | PS - 7.3.3 | Triall Report | prior to full scale production | HP | ENG
6.03.04 | Stabilising Equipment | The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling. The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation. | PS - 7.3.2 | Plant Approval | Prior to works | H | PE
6.03.05 | Stabilising Supervisor | During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m. | PS - 7.3.2 | Supervisor Approval | Prior to works | H | PE
6.03.06 | Before Stabilisation Surface shape control, layer thickness | Width: -20mm +100mm (Unconstrained) Vertical: - 25mm +5mm Cross fall: 0.5% on 2m straight edge | TNZ B/2 | Total station Topo showing levels compared to design | 1 test per 20m | I | SV / PE
6.03.07 | Average Uncompacted Layer Thickness | The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer. | TNZ B/02: 2005 - 7.3 | Survey / Level Checks | 1 test per 20m | I | SV / PE
6.03.08 | Pre Stabilisation Compaction | The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01 | PS - 7.3.2 | IANZ NDMS | Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation) | I | PE
6.03.09 | Pre Stabilisation Crossfall | Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design. | PS - 7.3.2 | Total station Topo showing levels compared to design | 1 test per 20m Prior to stabilisation | I | SV / PE
6.03.10 | Stabilising Visual appearance | The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing. | PS - 7.3.2 | Site Notes | every 100m | I | PE
6.03.11 | Cement Mat Test / Spread Rate | The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate | Table 7.2 | Stab. Sheet | One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats. Upon successful demonstration of this, the 1 per 500m2 minimum can apply | I | PE
6.03.12 | Cement Average usage test | Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate | TNZ B6 | Stab. Sheet / Delivery Doc. | Upon emptying the spreader and bulk tanker | R | SE
6.03.13 | Control of cut depth | Maximum variation from the specified depth of cut is –5 mm and +15 mm. Without picking up sand from SIL | TNZ B6 | Stab. Sheet | First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer | R | SE
6.03.14 | Plateau Density Test | The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing. | PS - Table 7.2 - 2.4 | Plateau Density Report | 5 tests per 10,000m2 | I | PE
6.03.15 | Particle size distribution behind stabilizer (Wet Sieve) | The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1. A Wet sieve analysis will be completed within 4 hours after stabilizing | NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving | IANZ Lab Reports | 3 samples bag per stabilise day post hoe | I | PE
6.03.16 | Mixed material testing (ITS) | During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day. These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19 | TNZ B6 7.5 | Test Results | 2 tests per stabilise day | R | PE
6.03.17 | NDM Water correction | Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density. Will get the Moisture correction factor from the Plateau report itself. That is the difference between the Moisture reading on the NDM vs the actual moisture when dried in the oven. | NZS 4407 | Corrected NDM Results | Per Stabilise day | R | PE
6.03.18 | Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing | The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct Transmission | PS - 7.3.2 | IANZ Lab Reports | Min 5 Tests per lot 1000m2, minimum 7 days after stab. | I | PE
6.03.19 | Post Stabilisation Surface shape control, layer thickness | Width: -20mm +100mm (Unconstrained) Vertical: - 5mm +10mm Cross fall: 0.5% on 2m straight edge | TNZ B/2 | Total station Topo showing levels compared to design | 1 test per 20m | I | SV / PE
6.03.20 | Protection, Curing and Maintenance before Overlaying | The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied. Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation | TNZ B6 - 7.8 | Site Notes | For 7 days after stabilisation / Photos | R | PE
6.03.21 | Benkelman Beam | Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer. Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY | PS - 7.3.2 | Benkelman Beam Report | Every 10m of each lane – staggered between left and right wheel path. | R | SE
6.03.22 | MDD / OMC / SD | Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing. | NZS 4402:1986, Test 4.1.3 | Lab Report | 1 test per 2000m² or a days work whichever gives the greater number of testing. | I | PE
6.03.23 | Sub-base stabilisation trial | After the sub-base stabilisation trial, prior to proceeding with further stabilisation. | PS - 2.2.16 | Hold Point Release | Min 48h Notice | HP | ENG
6.04 | Stabilised sub-base
6.04.01 | Stabilization Production Plan | Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3. | NZTA B/6 7.2.3 | Correspondence | 48H hours prior sabilising commencing | HP | ENG
6.04.02 | Longitudinal Joints | To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater. | NZTA B/6 7.5.2 | Stabilisation Prodution Plan | 48H hours prior sabilising commencing | H | PE
6.04.03 | Stabilising Equipment | The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling. The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation. | PS - 7.3.2 | Plant Approval | Prior to works | H | PE
6.04.04 | Stabilising Supervisor | During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m. | PS - 7.3.2 | Supervisor Approval | Prior to works | H | PE
6.04.05 | Before Stabilisation Surface shape control, layer thickness | Width: -20mm +100mm (Unconstrained) Vertical: - 25mm +5mm Cross fall: 0.5% on 2m straight edge | TNZ B/2 | String sheet | 1 test per 20m | I | SV / PE
6.04.06 | Average Uncompacted Layer Thickness | The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer. | TNZ B/02: 2005 - 7.3 | Survey / Level Checks | 1 test per 20m | I | SV / PE
6.04.07 | Pre Stabilisation Compaction | The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01 | TNZ B/02: 2005 | IANZ NDMS | Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation) | I | PE
6.04.08 | Pre Stabilisation Crossfall | Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design. | PS - 7.3.2 | Total station Topo showing levels compared to design | 1 test per 20m Prior to stabilisation | I | SV / PE
6.04.09 | Stabilising Visual appearance | The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing. | PS - 7.3.2 | Site Notes | every 100m | I | PE
6.04.10 | Cement Mat Test | The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate | TNZ B6 | Site Notes | One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats. Upon successful demonstration of this, the 1 per 500m2 minimum can apply | R | SE
6.04.11 | Cement Average usage test | Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate | TNZ B6 | Site Notes | Upon emptying the spreader and bulk tanker | R | SE
6.04.12 | Maintain OMC during stabilising | The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content by NDM | TNZ B6 | Site Notes | Continuous | R | SE
6.04.13 | Control of cut depth | Maximum variation from the specified depth of cut is –5 mm and +15 mm. | TNZ B6 | Site Notes | First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer | R | SE
6.04.14 | Mixed material testing (ITS) | During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day. These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19 | TNZ B6 7.5 | Test Results | 2 pairs of representative samples per day | R | PE
6.04.15 | Particle size distribution behind stabilizer (Wet Sieve) | A Wet sieve analysis will be completed within 4 hours after stabilizing, and consist of a minimum of 3 sample bags per lot. | TNZ B6 7.5 | Test Results | 3 sample bags per lot. | R | PE
6.04.16 | Plateau Density Test | The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing. | PS - Table 7.2 - 2.3 | Plateau Density Report | 5 tests per 10,000m2 | I | PE
6.04.17 | Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing | The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct transmission | PS - 7.3.2 | IANZ NDMS | Min 5 Tests per lot 1000m2 max lot size | I | PE
6.04.18 | NDM Water correction | Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density | NZS 4407 | Corrected NDM Results | Per Stabilise day | R | PE
6.04.19 | Post Stabilisation Surface shape control, layer thickness | Width: -20mm +100mm (Unconstrained) Vertical: - 5mm +10mm Cross fall: 0.5% on 2m straight edge | TNZ B6 8.2 | Total station Topo showing levels compared to design | Continuous | R | SV / PE
6.04.20 | Protection, Curing and Maintenance before Overlaying | The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied. Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation | TNZ B6 - 7.8 | Site Notes with photos | For 7 days after stabilisation | R | PE
6.04.21 | Benkelman Beam | Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer. Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY | PS - 7.3.2 | Benkelman Beam Report | Every 10m of each lane – staggered between left and right wheel path. | HP | ENG
6.04.22 | MDD / OMC / SD | Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing. | NZS 4402:1986, Test 4.1.3 | Lab Report | 1 test per 2000m² or a days work whichever gives the greater number of testing. | I | PE
SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7.02 | Site Post Construction Activities
7.02.01 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen mark up showing lot numbers and areas stabilised in different days including clear delineation of all joins. | Downer | Redlines | Post construction | H | PE