## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Pavement & Surfacing - Subbase - Rev E | itp |  |  |  |  | ITP - Pavement & Surfacing - Subbase - Rev E
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
checkpoint | 3.01.01 - Construction Pack
note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
note | Standard / Specification - Downer
note | Verifying Document - Construction Pack
note | Frequency - Prior to Works start
note | Activity - H
note | By - PE
checkpoint | 3.01.02 - Survey Setout
note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
note | Standard / Specification - Downer
note | Verifying Document - Survey Records
note | Frequency - Prior to Works start
note | Activity - H
note | By - SV
checkpoint | 3.01.03 - Service Location
note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
note | Standard / Specification - Downer
note | Verifying Document - Excavation Permit
note | Frequency - Prior to Excavation
note | Activity - H
note | By - SE
checkpoint | 3.01.04 - Internal Permits
note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
note | Standard / Specification - Downer
note | Verifying Document - Internal Permits
note | Frequency - Prior to activity being undertaken
note | Activity - H
note | By - SE
checkpoint | 3.01.05 - External Permits
note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
note | Standard / Specification - Downer
note | Verifying Document - External Permits
note | Frequency - Prior to commencment of activity
note | Activity - H
note | By - PE
checkpoint | 3.01.06 - Approved Construction Drawings
note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
note | Standard / Specification - Downer
note | Verifying Document - IFC Drawings
note | Frequency - Prior to works start
note | Activity - H
note | By - PE
checkpoint | 3.01.07 - Stabilising Methodology
note | Acceptance / Conformance Criteria - Written approval of the Engineer with the approval of the methodology
note | Standard / Specification - PS - 7.3.3
note | Verifying Document - Correspondence
note | Frequency - Prior to stabilisation start
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.08 - Acceptance of the SIL layer
note | Acceptance / Conformance Criteria - Written approval of the Engineer - All compliant test results for subgrade, SIL, all road crossings, storm water, wastewater, watermain, subsoil/pavement drains and any other activity that has been completed in the pavement area.
note | Standard / Specification - PS - 4.8.3, Table 4.3
note | Verifying Document - Hold point relesed / Testing reports
note | Frequency - All sections before proceeding to the next layer
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials
checkpoint | 5.01.01 - Sampling and testing
note | Acceptance / Conformance Criteria - For all aggregates, test information confirming compliance shall be supplied to the Engineer not less than five working days prior to delivery of the material to site.
note | Standard / Specification - PS - 7.2.4
note | Verifying Document - IANZ Lab Reports
note | Frequency - five working days prior to delivery of the material to site.
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.02 - Sampling and testing
note | Acceptance / Conformance Criteria - Water to be used in stabilisation - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening, strength or durability of the bound aggregate layer.
note | • Water from sources other than public supply may have its suitability established to the satisfaction of the Engineer by repeating the final approved laboratory based mix design tests with the water now being considered for use.
note | • The results of these subsequent mix verification tests shall be greater than 90% of the final results from the previously verified mix design. In addition, work shall be stopped if any discolouration or residue is observed when adding or sprinkling water into or onto the material.”
note | • Verifying documents to be dockets from fill up station, or proof of using public water supply. Or Lab reports for alternative supply.
note | Standard / Specification - NZTA B/6 item 5
note | Verifying Document - Lab reports
note | Frequency - Prior to Works start, per source
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate
checkpoint | 5.02.01 - Sub-base MDD and OMC
note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
note | Verifying Document - IANZ Lab Reports
note | Frequency - 1 test per material type
note | Activity - H
note | By - PE
checkpoint | 5.02.02 - Cement for sub-base stabilisation
note | Acceptance / Conformance Criteria - Cement for stabilisation shall meet the requirements of NZTA B6.
note | Standard / Specification - PS - 7.3.2, PS - 7.2.6
note | Verifying Document - Datasheets
note | Frequency - Prior to Use
note | Activity - H
note | By - PE
checkpoint | 5.02.05 - Crushing Resistance
note | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
note | Standard / Specification - NZS 4407: 1991 Test 3.10.
note | Verifying Document - IANZ Lab Reports
note | Frequency - 2 tests per source 4 weeks before use in the works
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.06 - Weathering Resistance
note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
note | Standard / Specification - NZS 4407: 1991 Test 3.11
note | Verifying Document - IANZ Lab Reports
note | Frequency - 2 tests per source 4 weeks before use in the works
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.07 - Particle size distribution
note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1.
note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
note | Verifying Document - IANZ Lab Reports
note | Frequency - 0 to 400m³ - 2 tests
note | • 400 to 1,500m³ - 3 tests
note | • 1,500 to 4,000m³ - 4 tests
note | • >4,000m³ - 1 test for each additional 1,000m³
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.08 - Sand Equivalent
note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 25 when the aggregate is tested
note | Standard / Specification - NZS 4407: 1991 Test 3.6 (Wet Method)
note | Verifying Document - IANZ Lab Reports
note | Frequency - 0 to 400m³ - 2 tests
note | • 400 to 1,500m³ - 3 tests
note | • 1,500 to 4,000m³ - 4 tests
note | • >4,000m³ - 1 test for each additional 1,000m³
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.09 - Liquid Limit
note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested - The LL may also be inferred (where appropriate) from the Cone Penetrometer Limit (CPL).
note | Standard / Specification - NZS 4402 Test 2.2, NZS4407:2015 Test 3.2.
note | Verifying Document - IANZ Lab Reports
note | Frequency - 0 to 400m³ - 2 tests
note | • 400 to 1,500m³ - 3 tests
note | • 1,500 to 4,000m³ - 4 tests
note | • >4,000m³ - 1 test for each additional 1,000m³
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.10 - Plasticity Index
note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
note | Standard / Specification - NZS 4407 Test 3.4
note | Verifying Document - IANZ Lab Reports
note | Frequency - 0 to 400m³ - 2 tests
note | • 400 to 1,500m³ - 3 tests
note | • 1,500 to 4,000m³ - 4 tests
note | • >4,000m³ - 1 test for each additional 1,000m³
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.11 - Clay Index
note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
note | Standard / Specification - NZS 4407 Test 3.5
note | Verifying Document - IANZ Lab Reports
note | Frequency - 0 to 400m³ - 2 tests
note | • 400 to 1,500m³ - 3 tests
note | • 1,500 to 4,000m³ - 4 tests
note | • >4,000m³ - 1 test for each additional 1,000m³
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.12 - Proportion of Broken Rock
note | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves not less than 50% by weight shall have two or more broken faces
note | Standard / Specification - PS - 7.2.2
note | Verifying Document - IANZ Lab Reports
note | Frequency - 1 Test per source of the coarse aggregate. Additional samples if source is changed
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.13 - Organic Matter
note | Acceptance / Conformance Criteria - It shall be free of organic matter
note | Standard / Specification - PS - 7.2.2
note | Verifying Document - Photos
note | Frequency - Continuous
note | Activity - I
note | By - SE/PE
checkpoint | 5.02.14 - Accelerated Weathering Testing
note | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
note | • The levels of smectite clay minerals are not classified as “abundant”
note | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
note | Verifying Document - Lab Reports
note | Frequency - 2 tests per source 4 weeks before use in the works.
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.15 - Repeat Load Triaxial Test
note | Acceptance / Conformance Criteria - In accordance with NZTA T15
note | Standard / Specification - NZTA T15
note | Verifying Document - IANZ Lab Reports
note | Frequency - 2 tests per source 4 weeks before use in the works.
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.16 - Unconfined Compressive Strength (UCS)
note | Acceptance / Conformance Criteria - Unconfined Compressive Strength (UCS) testing of source aggregate for modified layers to test sensitivity to additives.
note | Standard / Specification - PS - Table No. 7.2
note | Verifying Document - IANZ Lab Reports
note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.17 - Indirect Tensile Strength (ITS)
note | Acceptance / Conformance Criteria - In accordance with draft NZTA T/19 at the rate specified in Table A7.4 using 4.0%, 4.5% and 5.0% cement (with 7 days curing) and results forwarded to the Engineer not less than 7 Working Days prior to construction for confirmation or adjustment of the additive contents.
note | Standard / Specification - NZTA T/19 - Table A7.4
note | Verifying Document - IANZ Lab Reports
note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
checkpoint | 6.02.01 - Sub-base MDD and OMC
note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
note | Verifying Document - IANZ Lab Reports
note | Frequency - No less than 1 test every 5,000m³ (in place)
note | Activity - R
note | By - PE
checkpoint | 6.02.02 - Plasticity Index
note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested
note | Standard / Specification - Table 7.2
note | Verifying Document - IANZ Lab Reports
note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
note | Activity - R
note | By - PE
checkpoint | 6.02.03 - Clay Index
note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
note | Standard / Specification - Table 7.2
note | Verifying Document - IANZ Lab Reports
note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
note | Activity - R
note | By - PE
checkpoint | 6.02.04 - Sand Equivalent
note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
note | Standard / Specification - Table 7.2
note | Verifying Document - IANZ Lab Reports
note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
note | Activity - R
note | By - PE
checkpoint | 6.02.05 - Particle size distribution
note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1
note | Standard / Specification - Table 7.1
note | Verifying Document - IANZ Lab Reports
note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
note | Activity - R
note | By - PE
checkpoint | 6.02.06 - Average Uncompacted Layer Thickness
note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
note | Standard / Specification - TNZ B/02: 2005 - 7.3
note | Verifying Document - Survey / Level Checks
note | Frequency - 1 test per 20m
note | Activity - I
note | By - SV / PE
checkpoint | 6.02.07 - Plateau Density Test
note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
note | • Testing shall be at OWC.
note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
note | Standard / Specification - PS - Table 7.2 - 2.3
note | Verifying Document - Plateau Density Report
note | Frequency - 5 tests per 10,000m2
note | Activity - I
note | By - PE
checkpoint | 6.02.08 - Sub-basecourse Pavement Layer Compaction
note | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
note | Standard / Specification - TNZ B/02: 2005
note | Verifying Document - NDM Report
note | Frequency - Min 5 Tests per lot 1000m2 max lot size
note | Activity - I
note | By - PE
checkpoint | 6.02.09 - Surface shape control
note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
note | • Vertical: - 25mm +5mm
note | • Cross fall: 0.5% on 2m straight edge
note | Standard / Specification - TNZ B/2
note | Verifying Document - Total station Topo showing levels compared to design
note | Frequency - Continuous
note | Activity - I
note | By - SV / PE
section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
checkpoint | 6.03.01 - Stabilization Production Plan
note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
note | Standard / Specification - NZTA B/6 7.2.3
note | Verifying Document - Correspondence
note | Frequency - 48H hours prior sabilising commencing
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.03.02 - Longitudinal Joints
note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
note | Standard / Specification - NZTA B/6 7.5.2
note | Verifying Document - Stabilisation Prodution Plan
note | Frequency - 48H hours prior sabilising commencing
note | Activity - H
note | By - PE
checkpoint | 6.03.03 - Stabilisation trial
note | Acceptance / Conformance Criteria - A trial shall be conducted on a minimum stabilised area of 2,000m2 to verify the performance of the stabilising operation and finished product prior to full scale production.
note | Standard / Specification - PS - 7.3.3
note | Verifying Document - Triall Report
note | Frequency - prior to full scale production
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.03.04 - Stabilising Equipment
note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - Plant Approval
note | Frequency - Prior to works
note | Activity - H
note | By - PE
checkpoint | 6.03.05 - Stabilising Supervisor
note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - Supervisor Approval
note | Frequency - Prior to works
note | Activity - H
note | By - PE
checkpoint | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
note | • Vertical: - 25mm +5mm
note | • Cross fall: 0.5% on 2m straight edge
note | Standard / Specification - TNZ B/2
note | Verifying Document - Total station Topo showing levels compared to design
note | Frequency - 1 test per 20m
note | Activity - I
note | By - SV / PE
checkpoint | 6.03.07 - Average Uncompacted Layer Thickness
note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
note | Standard / Specification - TNZ B/02: 2005 - 7.3
note | Verifying Document - Survey / Level Checks
note | Frequency - 1 test per 20m
note | Activity - I
note | By - SV / PE
checkpoint | 6.03.08 - Pre Stabilisation Compaction
note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - IANZ NDMS
note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
note | Activity - I
note | By - PE
checkpoint | 6.03.09 - Pre Stabilisation Crossfall
note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - Total station Topo showing levels compared to design
note | Frequency - 1 test per 20m Prior to stabilisation
note | Activity - I
note | By - SV / PE
checkpoint | 6.03.10 - Stabilising Visual appearance
note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - Site Notes
note | Frequency - every 100m
note | Activity - I
note | By - PE
checkpoint | 6.03.11 - Cement Mat Test / Spread Rate
note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
note | Standard / Specification - Table 7.2
note | Verifying Document - Stab. Sheet
note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
note | • Upon successful demonstration of this, the 1 per 500m2 minimum can applya
note | Activity - I
note | By - PE
checkpoint | 6.03.12 - Cement Average usage test
note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
note | Standard / Specification - TNZ B6
note | Verifying Document - Stab. Sheet / Delivery Doc.
note | Frequency - Upon emptying the spreader and bulk tanker
note | Activity - R
note | By - SE
checkpoint | 6.03.13 - Control of cut depth
note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm. Without picking up sand from SIL
note | Standard / Specification - TNZ B6
note | Verifying Document - Stab. Sheet
note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
note | Activity - R
note | By - SE
checkpoint | 6.03.14 - Plateau Density Test
note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
note | • Testing shall be at OWC.
note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
note | Standard / Specification - PS - Table 7.2 - 2.4
note | Verifying Document - Plateau Density Report
note | Frequency - 5 tests per 10,000m2
note | Activity - I
note | By - PE
checkpoint | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1. A Wet sieve analysis will be completed within 4 hours after stabilizing
note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
note | Verifying Document - IANZ Lab Reports
note | Frequency - 3 samples bag per stabilise day post hoe
note | Activity - I
note | By - PE
checkpoint | 6.03.16 - Mixed material testing (ITS)
note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
note | Standard / Specification - TNZ B6 7.5
note | Verifying Document - Test Results
note | Frequency - 2 tests per stabilise day
note | Activity - R
note | By - PE
checkpoint | 6.03.17 - NDM Water correction
note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density.
note | • Will get the Moisture correction factor from the Plateau report itself. That is the difference between the Moisture reading on the NDM vs the actual moisture when dried in the oven.
note | Standard / Specification - NZS 4407
note | Verifying Document - Corrected NDM Results
note | Frequency - Per Stabilise day
note | Activity - R
note | By - PE
checkpoint | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct Transmission
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - IANZ Lab Reports
note | Frequency - Min 5 Tests per lot 1000m2, minimum 7 days after stab.
note | Activity - I
note | By - PE
checkpoint | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
note | • Vertical: - 5mm +10mm
note | • Cross fall: 0.5% on 2m straight edge
note | Standard / Specification - TNZ B/2
note | Verifying Document - Total station Topo showing levels compared to design
note | Frequency - 1 test per 20m
note | Activity - I
note | By - SV / PE
checkpoint | 6.03.20 - Protection, Curing and Maintenance before Overlaying
note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied. Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
note | Standard / Specification - TNZ B6 - 7.8
note | Verifying Document - Site Notes
note | Frequency - For 7 days after stabilisation / Photos
note | Activity - R
note | By - PE
checkpoint | 6.03.21 - Benkelman Beam
note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - Benkelman Beam Report
note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
note | Activity - R
note | By - SE
checkpoint | 6.03.22 - MDD / OMC / SD
note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
note | Standard / Specification - NZS 4402:1986, Test 4.1.3
note | Verifying Document - Lab Report
note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
note | Activity - I
note | By - PE
checkpoint | 6.03.23 - Sub-base stabilisation trial
note | Acceptance / Conformance Criteria - After the sub-base stabilisation trial, prior to proceeding with further stabilisation.
note | Standard / Specification - PS - 2.2.16
note | Verifying Document - Hold Point Release
note | Frequency - Min 48h Notice
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
checkpoint | 6.04.01 - Stabilization Production Plan
note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
note | Standard / Specification - NZTA B/6 7.2.3
note | Verifying Document - Correspondence
note | Frequency - 48H hours prior sabilising commencing
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.04.02 - Longitudinal Joints
note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
note | Standard / Specification - NZTA B/6 7.5.2
note | Verifying Document - Stabilisation Prodution Plan
note | Frequency - 48H hours prior sabilising commencing
note | Activity - H
note | By - PE
checkpoint | 6.04.03 - Stabilising Equipment
note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - Plant Approval
note | Frequency - Prior to works
note | Activity - H
note | By - PE
checkpoint | 6.04.04 - Stabilising Supervisor
note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - Supervisor Approval
note | Frequency - Prior to works
note | Activity - H
note | By - PE
checkpoint | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
note | • Vertical: - 25mm +5mm
note | • Cross fall: 0.5% on 2m straight edge
note | Standard / Specification - TNZ B/2
note | Verifying Document - String sheet
note | Frequency - 1 test per 20m
note | Activity - I
note | By - SV / PE
checkpoint | 6.04.06 - Average Uncompacted Layer Thickness
note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
note | Standard / Specification - TNZ B/02: 2005 - 7.3
note | Verifying Document - Survey / Level Checks
note | Frequency - 1 test per 20m
note | Activity - I
note | By - SV / PE
checkpoint | 6.04.07 - Pre Stabilisation Compaction
note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
note | Standard / Specification - TNZ B/02: 2005
note | Verifying Document - IANZ NDMS
note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
note | Activity - I
note | By - PE
checkpoint | 6.04.08 - Pre Stabilisation Crossfall
note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - Total station Topo showing levels compared to design
note | Frequency - 1 test per 20m Prior to stabilisation
note | Activity - I
note | By - SV / PE
checkpoint | 6.04.09 - Stabilising Visual appearance
note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - Site Notes
note | Frequency - every 100m
note | Activity - I
note | By - PE
checkpoint | 6.04.10 - Cement Mat Test
note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
note | Standard / Specification - TNZ B6
note | Verifying Document - Site Notes
note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
note | • Upon successful demonstration of this, the 1 per 500m2 minimum can apply
note | Activity - R
note | By - SE
checkpoint | 6.04.11 - Cement Average usage test
note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
note | Standard / Specification - TNZ B6
note | Verifying Document - Site Notes
note | Frequency - Upon emptying the spreader and bulk tanker
note | Activity - R
note | By - SE
checkpoint | 6.04.12 - Maintain OMC during stabilising
note | Acceptance / Conformance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content by NDM
note | Standard / Specification - TNZ B6
note | Verifying Document - Site Notes
note | Frequency - Continuous
note | Activity - R
note | By - SE
checkpoint | 6.04.13 - Control of cut depth
note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm.
note | Standard / Specification - TNZ B6
note | Verifying Document - Site Notes
note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
note | Activity - R
note | By - SE
checkpoint | 6.04.14 - Mixed material testing (ITS)
note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
note | Standard / Specification - TNZ B6 7.5
note | Verifying Document - Test Results
note | Frequency - 2 pairs of representative samples per day
note | Activity - R
note | By - PE
checkpoint | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
note | Acceptance / Conformance Criteria - A Wet sieve analysis will be completed within 4 hours after stabilizing, and consist of a minimum of 3 sample bags per lot.
note | Standard / Specification - TNZ B6 7.5
note | Verifying Document - Test Results
note | Frequency - 3 sample bags per lot.
note | Activity - R
note | By - PE
checkpoint | 6.04.16 - Plateau Density Test
note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
note | • Testing shall be at OWC.
note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
note | Standard / Specification - PS - Table 7.2 - 2.3
note | Verifying Document - Plateau Density Report
note | Frequency - 5 tests per 10,000m2
note | Activity - I
note | By - PE
checkpoint | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct transmission
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - IANZ NDMS
note | Frequency - Min 5 Tests per lot 1000m2 max lot size
note | Activity - I
note | By - PE
checkpoint | 6.04.18 - NDM Water correction
note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density
note | Standard / Specification - NZS 4407
note | Verifying Document - Corrected NDM Results
note | Frequency - Per Stabilise day
note | Activity - R
note | By - PE
checkpoint | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
note | • Vertical: - 5mm +10mm
note | • Cross fall: 0.5% on 2m straight edge
note | Standard / Specification - TNZ B6 8.2
note | Verifying Document - Total station Topo showing levels compared to design
note | Frequency - Continuous
note | Activity - R
note | By - SV / PE
checkpoint | 6.04.20 - Protection, Curing and Maintenance before Overlaying
note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied.
note | • Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
note | Standard / Specification - TNZ B6 - 7.8
note | Verifying Document - Site Notes with photos
note | Frequency - For 7 days after stabilisation
note | Activity - R
note | By - PE
checkpoint | 6.04.21 - Benkelman Beam
note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
note | Standard / Specification - PS - 7.3.2
note | Verifying Document - Benkelman Beam Report
note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.04.22 - MDD / OMC / SD
note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
note | Standard / Specification - NZS 4402:1986, Test 4.1.3
note | Verifying Document - Lab Report
note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
note | Activity - I
note | By - PE
section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
checkpoint | 7.02.01 - Redline Drawings
note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen mark up showing lot numbers and areas stabilised in different days including clear delineation of all joins.
note | Standard / Specification - Downer
note | Verifying Document - Redlines
note | Frequency - Post construction
note | Activity - H
note | By - PE