## Road pavement surfacing
|  |  |  | Process Control Plan |  | Asphalt Surfacing | Approved |  | Signature
|  |  |  | Contract Name: | Ponsonby_Pompallier Pedetrian Improvement |  | FH Engineer
|  |  |  | Procedure: | Asphalt Surfacing |  | FH Project Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding SWMS: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Traffic Management | W | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS | Prior to commencement | Document Review | TMP is approved by AT for the site and works are only completed within the approved dates | TMP on MyWorksites/On Site | Site Engineer
2 | Pre-construction sign offs | W | Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site | Prior to commencement | Document Review | Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated | Subcontract and Supplier Agreements, A & Updated Induction Register | Site Engineer
3 | Base course sign off | H | Ensure that base course checklist and QA records are signed by AT representative/Engineer | Prior to commencement | Document Review | Completion approved as per Pavement ITP | Pavement Base course checklist signed | Site Engineer | Engineer's Rep / MSQA
4 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | IFC Label on drawings | Check Drawing Register | Site Engineer | Engineer's Rep / MSQA
5 | Material testing and control - AC | H | Asphalt mix design approval | Prior to commencement | Submission and review | Accepted by AT representative/Engineer | Approval evidence | Site Engineer | Engineer's Rep / MSQA
6 | Construction | M | Check weather forecast and record weather | Prior and during application | Monitor | No foggy or raining or wet surface, base temperature > 7° | NA | Site Engineer
|  | M | Joints | Per joint of the road | Visual inspection | Edges and joints to existing surfaces must be tapered to provide a smooth transition from the slurry to the adjacent surfaces | Visual inspection | Site Engineer
|  | H | Milling/surface preparation | Prior to emulsion application | Visual inspection, survey | If the surface is being milled and filled, surface levels and condition are to be inspected by the Engineer and confirmed acceptable before proceeding. Not applicable if pavement has been constructed under the Pavement ITP process. | Visual inspection, survey | Site Engineer | Engineer's Rep / MSQA
|  | M | Surface finish | Per section of road | Visual inpsection | Uniform texture , no roller marks no bleeding, cracking, no crushing of aggregate | Visual inspection | Site Engineer
|  | M | Level | As required | Visual inpsection | Asphalt against kerb and channel, the surface of the edge shall be flush or no more than 5mm above the lip of channel Any irregularities which vary more than 5mm under straight edge, longitudinally or transversely shall be corrected | Visual inspection | Site Engineer
|  | H | Compaction | As required | Testing | Nuclear Densometer tests meet specified density | Nuclear Densometer test results | Site Engineer | Engineer's Rep / MSQA
7 | Post construction | H | Inspection/ joint inpsection | As required | Visual inspection | Asphalt joint sealing as per AT standard Accepted by AT representative/Engineer | Visual inspection | Site Engineer | Engineer's Rep / MSQA
8 | Linemarking | W | Ensure that linemarking is set out and applied in the correct location and to the level of quality expected | Before & after linemarking | Visual inspection, survey | Linemarking adheres to design alignments and is of a good quality | Visual inspection, survey | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices etc.):
| QA Compiled By: |  |  |  | Signature: |  |  | Date:
| QA checked By Project Manager: |  |  |  | Signature: |  |  | Date:
| Accepted By Design Engineer: |  |  |  | Signature: |  |  | Date: