## Network Drainage
|  |  |  | Process Control Plan |  |  | Approved |  | Signature
|  |  |  | Contract Name: | Ponsonby_Pompallier Pedetrian Improvement |  | FH Engineer
|  |  |  | Procedure: | Stormwater Drainage |  | FH Project Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding SWMS: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | W | Obtain Permits | As required | Document Review | Control Checklist - Digging / Excavating (incl. marking out & potholing existing services). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
2 | Traffic Management | W | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS | Prior to commencement | Document Review | TMP is approved by AT for the site and works are completed within the approved dates | TMP on MyWorksites/ On Site | Site Engineer
3 | Pre-construction sign offs | W | Ensure that Sub-Contract and Supplier Agreements are signed and that personnel have gone through the NWBI induction. | Prior to commencement | Document Review | Signed subcontract & Supplier agreements. Issued induction stickers and number | Signed Agreements, Updated Induction Register | Site Engineer
4 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | IFC label on drawings | Check Drawing Register | Site Engineer | Engineer's Rep / MSQA
5 | Survey Setout | M | Set out pegs installed every 10m of the footpath showing the FL. | Prior to commencement | Survey |  | Visual Inspection | Site Engineer
6 | Material Compliance | H | Bedding, Haunching and Backfill Material | Prior to commencement | AS/NZS 3725 AS/NZS 3500.3 | Crushing Resistance not less than 100kN. Maximum percentage of weight passing 0.075mm sieve shall not exceed 10% | Test report | Site Engineer | Engineer's Rep / MSQA
7 | Pipes and Precast Units | M | Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition. | Delivery to site | Visual Inspection | Pipe - Diameter & Class, Manholes, Catchpits as per SW CoP and AS/NZS 3725 | Delivery Dockets | Site Engineer
8 | Trenching and Excavation | M | Inspect trench profile and ensure it is correct to lines and levels to design | Daily | Visual/Inspection | Line and level is correct | Checksheet | Site Engineer
|  | M | Ensure trench width is sufficient as per AS/NZS 3725 namely 3x Diameter of Pipe | Daily | Visual Inspection | As per AS/NZS 3725 | Checksheet | Site Engineer
9 | Foundation Compliance | H | As per specification, Shear Vane <50 KPa 2%<CBR<3% Undercut 150mm, CBR<2% Seek Design Engineer's advice | 1 Test every 20m | Testing | Shear Vane >50 Kpa CBR > 3% | QA Sheets | Site Engineer | Engineer's Rep / MSQA
10 | Undercut Backfill Material Compliance Testing | H | Undercut If subgrade fails testing requirements and replace with copmpacted GAP40 for depth of undercut | 1 Test every 20m | Testing | CIV> 15 | QA Sheets | Site Engineer | Engineer's Rep / MSQA
11 | Pipe and Structure Bedding | H | Specified Bedding Construction Material Pipe Diameter<300mm bedding, side and haunch zones to be 100mm Pipe Diameter >300mm bedding, side and Haunch zones to be 150mm Stucture Bedding to comprise of a 75-100mm levelling course GAP20 | 1 Test every 20m | Testing | As per AS/NZS 3725 Minimum Bedding, Side and Haunch Zone CIV > 15 | Checksheet | Site Engineer | Engineer's Rep / MSQA
12 | Structure and Pipe Backfill | H | Backfill zone compacted in GAP40 layers no greater than 200mm . | Test Per Structure | Document Review | Compliance with requirements from Specifications and SW CoP. Under Carraigeway CIV >=32 Under Footpath and Berm CIV >=25 | Checksheet | Site Engineer | Engineer's Rep / MSQA
13 | Pipe Laying | M | Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place and sealed. Ensure Pipes do not exceed ±25 mm from design levels for any five metres of pipe | Prior to backfilling | Visual/Inspection | No defects/ gaps / pipes are aligned correctly. Compliance with the Stormwater Contract specification | Photos, Checksheet | Site Engineer
|  | M | As-built survey of pipes installed | Once line is completed between 2 structures | Survey | Survey Receipts | Checksheet | Site Engineer
14 | Trench Overlay Zone | M | Ensure correct thickness of compacted overlay zone - 150mm overlay above top of pipe for Pipe Diameter between 300 and 1500mm | During Backflling | Visual Inspection | Compliance with the drawings . 150mm overlay above top of pipe. Refer to AS/NZS 3725 | Checksheet | Site Engineer | Engineer's Rep / MSQA
15 | Pipe Backfill Compliance | M | Backfill zone compacted in GAP40 layers no greater than 200mm . Requirements based on pipe location. Minimum cover 1200mm from top of pipe in carraigeway and 800mm in berm. If Cover cannot be achieveded seek advice from design engineer | 1 Test every 20m | Document Review & Testing | Compliance with requirements from Specifications and SW CoP. Under Carraigeway >=95% Compaction and CIV >=32 Under Footpath and Berm >=85% Compaction and CIV >=25 | Checksheet, Lab Report, QA Sheets | Site Engineer | Engineer's Rep / MSQA
16 | Structure installation (Manhole, Catchpit) | W | Galvanised Step irons required in chambers over 1500mm deep | As required | Visual/Inspection | Maximum 600mm from manhole frame to first rung. Maximum 300mm between rungs. As Per ATCoP | Photos | Site Engineer
|  | W | Structures to be installed to the design survey location and level | During structure construction | Visual/Inspection | Survey markouts for centre of structure and insatllment to be from centre of structure | Checksheet | Site Engineer
|  | W | All joints are to be sealed including rungs and lids | During structure construction | Visual/Inspection | 25 MPa concrete to be used for throat haunching and cradle around inlets an outlets | Photos | Site Engineer
|  | W | Adjustment rings to ensure correct level and fall to cover | During structure construction | Visual/Inspection | Maximum throat depth on manholes to be 450mm. Miminimum riser usage is required and minimum riser height to be 300mm. All Joints between risers must be epoxied | Photos | Site Engineer
|  | W | Concrete benching | During structure construction | Visual/Inspection | Benching at base of Manhole shall be formed with 25 Mpa concrete. | Delivery Dockets | Site Engineer
|  | W | Manhole covers & frames set to correct level | During structure construction | Visual/Inspection/ Check | Heavy Duty Class E manhole covers required in trafficable areas as per AS 3996 400 KN rating | Checksheet, Delivery Dockets, SW CoP | Site Engineer
|  | W | Catchpit sump depth | During structure construction | Measurement | Minimum sump depth to 450mm as per AT CoP | ATCOP | Site Engineer
|  | W | Catchpit grate levels are set to correct level | During structure construction | Visual/Inspection/ Check | Measure on site and must be Cycle friendly Class D lids as per AS/ 3996 rating 210 KN | Checksheet, Delivery Dockets, SW CoP | Site Engineer
17 | CCTV | H | CCTV record at completion of trench backfill and prior to final surfacing | At completion of the works | Visual Inspection/ CCTV inspection | No Defects | Inspection Report CCTV | Site Engineer | Engineer's Rep / MSQA
18 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer | Engineer's Rep / MSQA
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices etc.):
| QA Compiled By: |  |  |  | Signature: |  |  | Date:
| QA checked By Project Manager: |  |  |  | Signature: |  |  | Date:
| Accepted By Design Engineer: |  |  |  | Signature: |  |  | Date: