## 001
|  |  |  | Process Control Plan |  |  | Approved |  | Signature
|  |  |  | Project: | Ponsonby_Pompallier Pedetrian Improvement |  | FH Engineer
|  |  |  | Procedure: | Earthworks and Retaining Wall |  | FH Project Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding SWMS: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | W | Obtain Permits | As required | Document Review | Control Checklist - Digging / Excavating (incl. marking out & potholing existing services). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
2 | Traffic Management | W | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS | Prior to commencement | Document Review | TMP is approved by AT for the site and works are only completed within the approved dates | TMP on MyWorksites/On Site | Site Engineer
3 | Pre-construction sign offs | W | Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site | Prior to commencement | Document Review | Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated | Subcontract and Supplier Agreements, A & Updated Induction Register | Site Engineer
4 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | IFC Label on drawings | Check Drawing Register | Site Engineer | Engineer's Rep / MSQA
5 | Material Compliance | H | Granular Fill Material requirements | Prior to commencement | As per TNZ F/1:1997 | Maximum percenetage of weight passing 35% 0.0075m sieve shall not exceed 35% and has a sand equivalent greater than 20. | Test Report | Site Engineer | Engineer's Rep / MSQA
6 | Survey Setout | W | Setout cut/fill areas as required by to construct to design. Topographical surveys to be completed prior to starting, monthly and upon completion | Prior to commencement, monthly and at completion | Survey |  | Check Drawing Register | Site Engineer
7 | Installation of Erosion and Sediment Controls where required | H | Setout Environmental Controls and confirm location with Environmental Manager | Prior to commencement | Review | Correct volume for area and setup to TP90: 1999 | Survey receipt | Environmental/ Project Manager | Engineer's Rep / MSQA
|  | H | Design Engineer Rep/ Client Rep to inspect controls after implementation | Prior to commencement | Submission | Correct volume for area and setup to TP90: 1999 | As-built | Environmental/Project Manager | Engineer's Rep / MSQA
|  | M | Monitor sediments tracked out onto any roads and the generation of any Foreign objects and debris as well as dust generated | Continuous monitoring | Visual Inspection | Roads free of debris using watercart where required to minimise dust generation | This ITP | Site Engineer
|  | M | Monitor effectiveness of the ESCP Controls throughout the work | Continuous monitoring | Measure | In accordance with Auckland Council TP90:1999 | Audits | Site Engineer
8 | Site Clearing | W | Removal of pavement layers, vegetation, services and other objects | During Physical Works | Visual Inspection |  | Photographic / Videography | Site Engineer
9 | Stripping | W | Determine if topsoil suitable for respread after earthworks are complete | As required | Visual Inspection | Stripping in accordance with TNZ F/1:1997 | Photographic / Videography/ Checksheets | Site Engineer
|  | H | Joint inspection with Engineers Rep and carry out topo survey | On completion of stripping | Visual Inspection | Ensure topsoil stripping is complete and area is clear of organic material | Photographic / Videography/ Checksheets | Site Engineer | Engineer's Rep / MSQA
10 | Stockpiling | M | Ensure stockpiles are separately stockpiled, exposed surfaces to be compacted sufficiently and away from runway, inlets and coastline | As required | Visual Inspection | Stockpiling in accordance with TNZ F/1:1997. Stockpiles to be minimum 50m away from watercourses. | Photographic / Videography | Site Engineer
11 | Retaining Wall Foundations | H | Shear vane Strength | 1 tests per 4m2 | Testing | Shear vane to exceed 80 Kpa or otherwise subgrade to be undercut and repalced by specfieid granular material at Deign Engineer's discretion | Lab Test reports | Site Engineer | Engineer's Rep / MSQA
12 | Cut Subgrade testing | M | Subgrade Surface - Straight Edge | During Construction | Survey | As per TNZ F/1 clause 11.2.2 - All points within 30mm of true from a 3m straight edge laid parallel to centreline of road. The subgrade surface shall not pond water, where the design slope of the subgrade is 2% or steeper. | Survey receipt | Site Engineer
|  | H | Scala Penetrometer Testing | 20m intervals to a depth of 1m at alternating wheel tracks | Lab Testing | Scala Penetrometer to a minimum depth of 1m and shall have no reading less than specified CBR of 3.5%, where Subgrade is gravel, Clegg hammer shall have no reading less than CIV 7. | QA Sheets | Site Engineer | Engineer's Rep / MSQA
13 | Bulk Fill Material Testing | H | Compaction shall be to TNZ F/1 with maximum layer thickness to not exceed 200mm | Every 200mm lift at/ 1 test per 4m2 | Lab Testing | CIV >= 25 | QA Sheets | Site Engineer | Engineer's Rep / MSQA
14 | Final Inspection | H | Subgrade inspection by Engineer | Once per area | Visual Inspection | Final sign off of subgrade by Engineer. | Photographic / Videography | Site Engineer | Engineer's Rep / MSQA
15 | Retaining Wall Construction | H | Material Compliance | During Construction | Document review | High Density H6 treated Radiata poles to be used for construction unless specified other wise by Design Engineer H5 treated timber to be used as railings unless specified otherwise by Design Engineer | Delivery Dockets/ Design Engineer Correspondence | Site Engineer | Engineer's Rep / MSQA
|  | M | Concrete Encasement | During Construction | Visual Inspection | Concrete mix to be a minimum 17.5 Mpa, high slump mix, 10mm chip. Minimum of 100mm cover below timber poles | Photgraphic / Videography / Delivery Dockets | Site Engineer
|  | H | Subsoil drainage | During Construction | Visual Inspection | Subsoils to be 110mm preforated pipe with filter sleeve sock. Bidim A29 or approved geofabric to be placed between drainage material and surroundign ground. Drainage 40/20 freeflowing aggregate to be used as bedding and cover. | Photgraphic / Videography / Delivery Dockets | Site Engineer | Engineer's Rep / MSQA
16 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer | Engineer's Rep / MSQA
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices etc.):
| QA Compiled By: |  |  |  | Signature: |  |  | Date:
| QA checked By Project Manager: |  |  |  | Signature: |  |  | Date:
| Accepted By Design Engineer: |  |  |  | Signature: |  |  | Date: