## Footpath Construction
|  |  |  | Process Control Plan |  |  | Approved |  | Signature
|  |  |  | Contract Name: | Ponsonby_Pompallier Pedetrian Improvement |  | FH Engineer
|  |  |  | Procedure: | Footpath, Vehicle Crossings |  | FH Project Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding SWMS: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | W | Obtain Permits | As required | Document Review | Control Checklist - Digging / Excavating (incl. marking out & potholing existing services). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
2 | Traffic Management | W | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS | Prior to commencement | Document Review | TMP is approved by AT for the site and works are completed within the approved dates | TMP on MyWorksites | Site Engineer
3 | Pre-construction sign offs | W | Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site | Prior to commencement | Document Review | Signed Subcontract and Supplier Agreements and Induction Register updated | Subcontract and Supplier Agreements, & Updated Induction Register | Site Engineer
4 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | IFC Label on drawings | Check Drawing Reegister | Site Engineer | Engineer's Rep / MSQA
5 | Survey Setout | W | Set out pegs installed every 10m of the footpath showing the FL & giving indication of line, extra pegs required on curves or special features | Prior to commencement | Survey |  | Visual Inspection | Site Engineer
6 | Material Compliance | H | GAP40 - Basecourse | Prior to commencement | Lab Testing | Grading test only | Lab Test Report | Site Engineer | Engineer's Rep / MSQA
|  | H | Concrete Mix Design at 20 Mpa in accordance with ATCoP | Prior to commencement | Document Review | Mix Design is approved prior to any concrete being delivered to site by Design Engineer | Mix Design Report | Site Engineer | Engineer's Rep / MSQA
7 | Subgrade Compliance | H | If Existing Subgrade CBR<3% or CIV<7 (if granular), Base layer thickness can be increased by 100mm at Design Engineer's discretion | One test per 10 linear metres | Design Engineer Inspection and Correspondence | CBR> 3% or CIV>=7 | QA Sheets | Site Engineer | Engineer's Rep / MSQA
8 | Basecourse - GAP40 | H | Compaction of GAP 40 with minimun 100mm thickness | Upon Completion | Clegg Test | ClV >= 12 | QA Sheets | Site Engineer | Engineer's Rep / MSQA
9 | Concreting | H | Before any concrete is poured a prepour inspection to be carried out | Pre-Pour | Visual inspection | Concrete pre-pour checksheet | Checksheets | Site Engineer | Engineer's Rep / MSQA
|  | W | Ensure concrete type and finish is as per specifications & drawings. Concrete panels should be no longer than 3m. | Pre-Pour | Visual inspection | U5 Broom Finish | Concrete docket/ Photos | Site Engineer
|  | H | Vehicle crossing basecourse to be of a minimum 100mm thickness of compacted GAP40 | Pre-Pour | Clegg Test | CIV >= 25 as per ATCoP drawings | QA Sheets | Site Engineer | Engineer's Rep / MSQA
|  | H | Bus Shelter Foundation Prep Concrete thickness to be 2oomm 100mm GAP40 Basecourse. 2 layers of 665 mesh | Pre-Pour | Clegg Test | CIV >= 25 as per ATCoP drawings | QA Sheets/ Photos | Site Engineer | Engineer's Rep / MSQA
|  | H | Tactile pavers are installed per drawings & specifications | Pre-Pour | Visual inspection | As per drawing | Photos | Site Engineer | Engineer's Rep / MSQA
10 | Signage | W | Signage sockets and signs are installed as per drawings and specification | Upon Completion | Visual inspection | As per drawings | Photos | Site Engineer
11 | As-builts | H | Red pen mark up drawings and RAMM to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer | Engineer's Rep / MSQA
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices etc.):
| QA Compiled By: |  |  |  | Signature: |  |  | Date:
| QA checked By Project Manager: |  |  |  | Signature: |  |  | Date:
| Accepted By Design Engineer: |  |  |  | Signature: |  |  | Date: