## Kerb & Channel
|  |  |  | Process Control Plan |  | Kerb and Channel | Approved |  | Signature
|  |  |  | Contract Name: | Ponsonby_Pompallier Pedetrian Improvement |  | FH Engineer
|  |  |  | Procedure: | Kerbs & Channel |  | FH Project Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding SWMS: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | W | Obtain Permits | As required | Document Review | Control Checklist - Digging / Excavating (incl. marking out & potholing existing services). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit number noted | Site Engineer
2 | Traffic Management | W | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS | Prior to commencement | Document Review | TMP is approved by AT for the site and works are only completed within the approved dates | TMP on MyWorksites/On Site | Site Engineer
3 | Pre-construction sign offs | W | Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site | Prior to commencement | Document Review | Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated | Subcontract and Supplier Agreements, A & Updated Induction Register | Site Engineer
4 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | IFC Label on drawings | Check Drawing Register | Site Engineer | Engineer's Rep / MSQA
5 | Survey Setout | W | Check constructed Sub base is within level tolerance. | Prior to commencement | Survey |  | Survey receipt | Site Engineer
|  | W | Set out Vehicle Crossing transition points and Pedestrian Drop Downs. | Prior to commencement | Survey, Measurement and Visual inspection | Kerbing Specification and Geometrics Drawing |  | Site Engineer
6 | Material Compliance | W | Mortar consist of two parts fine, sharp sand to one part of cement. | Prior to commencement | Delivery Docket | Must be discarded if not used within 30mins of mixing | Delivery Dockets | Site Engineer
|  | H | Precast work shall be 20MPa concrete Concrete haunching to also be 20MPa in accordance with ATCoP | Prior to commencement | Delivery Docket | Check product & dockets upon arrival onsite Mix Design is approved prior to any concrete being delivered to site by Design Engineer | Delivery Dockets Mix Design report | Site Engineer | Engineer's Rep / MSQA
|  | H | GAP40 and GAP65 - Basecourse | Prior to commencement | Lab Testing | Grading test only | Lab Test Report | Site Engineer | Engineer's Rep / MSQA
7 | Subsoils | W | Preforated filter sleeve Drain Pipe to be placed minimium 375mm below subgrade bedded and covered with F/2 sand | 10m | Site Check | As per TDM Technical standards RD0100 | QA Sheets | Site Engineer
8 | Precast kerb and channel | M | All chamfer to be 20mm, kerb joints to be 10mm min cement mortared | Prior installation | Visual inspection and Measurement | To ensure the correct kerb types are installed at the correct locations | ATCOP, Photos | Site Engineer
9 | Kerb and channel foundation | H | If Existing Subgrade <3% or CIV<7 (if granular), undercut required and bakcfilled with appropriate material and at depth for Design Engineer to specify. | 10m | Testing | Subgrade material >3%or CIV =>7 | QA Sheets | Site Engineer | Engineer's Rep / MSQA
|  | H | Kerbing must be laid on 300mm min GAP 65 subbase in Road and 100mm GAP 40 on Footpaths. The subbase for the K&C must be Clegg Tested with no CIV<30 Concrete haunching must be done as per drawings. | 10m | Testing | Pavement depth and type under the kerb varies depending on location . CIV for foundations >=30 | QA Sheets | Site Engineer | Engineer's Rep / MSQA
10 | Kassel Kerbs Foundation | H | If the existing Subgrade material <3% CBR or CIV<7 if granular, Undercut 300mm and backfill with Granular GAP 40. Design Engineer to Specify Depth. | 10m | Testing | Subgrade material =>3%or CIV =>7 | QA Sheets | Site Engineer | Engineer's Rep / MSQA
|  | H | The Kassel Kerbs must be laid on minimum 15 MPa Concrete at correct 200mm thickness on GAP65 subbase CIV >15 | 10m | Test/Site Check | As per Drawing: 2019-AT-017_G502 | QA Sheets | Site Engineer | Engineer's Rep / MSQA
11 | Island Infill | H | If the existing Subgrade material <CBR 3% or CIV <7 (if granular), Increase base thickness by upto 100mm at the discretion of Design Engineer | 10m | Lab/test | Subgrade material >3% or CIV>= 7 | QA Sheets, Design Engineer Correspondence | Site Engineer | Engineer's Rep / MSQA
|  | H | The sub-base must be GAP40 and must be clegg tested at every 10m intervals | 10m | Lab/test | CIV >=30 | QA Sheets | Site Engineer | Engineer's Rep / MSQA
|  | W | Concrete must be minimum of 20 Mpa and must be of correct 150mm thickness | During Pour | Visual Inspection | Exposed finish compliant with NZS3104 and constructed accordance with NZS3109 | Visual inspection | Site Engineer
12 | Stringing for All Kerb Type | H | Kerbs laid out accurately to lines, gradients & levels shown in drawings. | Prior to commencement | Visual inspection and Measurement | Prior to laying, string lines or levels to be inspected by Engineers Rep. When a 3 m straight edge is laid parallel to any surface of a pre-cast or bluestone kerb and channel there shall be no more than 5 mm variation from the straight edge, except at change of grades or curves | ATCOP | Site Engineer | Engineer's Rep / MSQA
13 | Dish Channels | M | Contraction joints at a maximum of 3m intervals. | During Slip forming | Visual inspection and Measurement | Kerbing Specification | ATCOP | Site Engineer
|  | M | Top surface to channels to be finished smooth and even with a trowel. | Prior to commencement | Visual inspection | Shall not pond any water. | ATCOP | Site Engineer
14 | Tie-in with pre-cast components | M | Ensure Kerb & channel to be cut and tied-in with pre-cast components by forming concrete aprons | During works | Visual inspection | Consistency with Work Instruction | ATCOP | Site Engineer
|  | M | Channel joint material set flush with surfaces (ensure levels are within the tolerances). | During works | Visual inspection | Consistency with Channel Specifications | ATCOP | Site Engineer
|  | M | Catchpit frame, grating and back entry kerb installed at correct level | During Works | Document review visual inspection | Consistency with Kerbing detail | ATCOP | Site Engineer
15 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer | Engineer's Rep / MSQA
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices etc.):
| QA Compiled By: |  |  |  | Signature: |  |  | Date:
| QA checked By Project Manager: |  |  |  | Signature: |  |  | Date:
| Accepted By Design Engineer: |  |  |  | Signature: |  |  | Date: