## Road pavement
|  |  |  | Process Control Plan |  | Road Pavement - Specified Areas | Approved |  | Signature
|  |  |  | Contract Name: | Ponsonby_Pompallier Pedetrian Improvement |  | FH Engineer
|  |  |  | Procedure: | Road Pavement |  | FH Project Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding SWMS: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | W | Obtain Permits | As required | Document Review | Control Checklist - Digging / Excavating (incl. marking out & potholing existing services). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit number noted | Site Engineer
2 | Traffic Management | W | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS | Prior to commencement | Document Review | TMP is approved by AT for the site and works are only completed within the approved dates | TMP on MyWorksites/On Site | Site Engineer
3 | Pre-construction sign offs | W | Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site | Prior to commencement | Document Review | Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated | Subcontract and Supplier Agreements, A & Updated Induction Register | Site Engineer
4 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | IFC Label on drawings | Check Drawing Register | Site Engineer | Engineer's Rep / MSQA
5 | Subgrade | H | Subgrade Scala Penetrometer Testing (CBR) at 10m intervals in each traffic lane-staggered and /or stitch section - unless directed otherwise by engineer | 10m | Testing | Accepted by or subgrade improvement instruction received from AT representative/Engineer | Testing records/ QA sheets if applicable | Site Engineer | Engineer's Rep / MSQA
|  | W | Subgrade undercutting/improvement inpsection | Prior to commencement | Visual inspection | Accepted by or subgrade improvement instruction received from AT representative/Engineer | Testing records/ QA sheets if applicable | Site Engineer | Engineer's Rep / MSQA
|  | M | Subgrade surfacing stringing | 1 in 10m | Measurement | Straight edge: ±30mm/3m | QA sheets | Site Engineer
6 | Subbase-GAP65 | M | Material source testing approved | Prior to commencement | Submission and review | Meets specified criteria and lab test report is recent within 6 months | Lab Test Report | Site Engineer
|  | M | Material delivery | Prior to commencement | Visual inspection | Check for quality of material | Visual inspection | Site Engineer
|  | H | Surface shape-stringing line check | 1 in 10m | Measurement | Within tolerances, ±20mm Crossfall no depart from exisitng crossfall or instruction from AT represenative/engineer | QA sheets | Site Engineer | Engineer's Rep / MSQA
|  | H | Compaction-NDM tests | 1 test per 30m of road per lane, staggered at 15m | Review | Mean >=95% of MDD Minimum>=92% of MDD | Testing records/ | Site Engineer | Engineer's Rep / MSQA
|  | H | Benkelman Beam Deflection Test | at 10m intervals in each traffic lane-staggered | Review | <=1mm (or specified by AT representative/engineer) Not applicable to stitch section | Testing records/ | Site Engineer | Engineer's Rep / MSQA
7 | Basecourse-NZTA M/4 AP40 | M | All chamfer to be 20mm, kerb joints to be 10mm min cement mortared | Prior installation | Visual inspection and Measurement | To ensure the correct kerb types are installed at the correct locations | ATCOP, Photos | Site Engineer
|  | M | Material source testing approved | Prior to commencement | Submission and review | 1/ source and at least 1/6 months | Lab Test Report | Site Engineer
|  | M | Material delivery | Prior to commencement | Visual inspection | Check for quality of material | Visual inspection | Site Engineer
|  | H | Surface shape-stringing line check | 1 in 10m | Measurement | Within tolerances, ±5mm Crossfall no depart from exisitng crossfall | QA sheets | Site Engineer | Engineer's Rep / MSQA
|  | H | Compaction-NDM tests | 1 test per 30m of road per lane, staggered at 15m | Review | Mean >=98% of MDD Minimum>=95% of MDD | Testing records/ | Site Engineer | Engineer's Rep / MSQA
|  | H | Benkelman Beam Deflection Test | at 10m intervals in each traffic lane-staggered | Review | <=1mm (or specified by AT representative/engineer) Not applicable to stitch section | Testing records/ | Site Engineer | Engineer's Rep / MSQA
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices etc.):
| QA Compiled By: |  |  |  | Signature: |  |  | Date:
| QA checked By Project Manager: |  |  |  | Signature: |  |  | Date:
| Accepted By Design Engineer: |  |  |  | Signature: |  |  | Date: