## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Roundabout | [5 empty] | Halsey/Maich RAB - ITP - Roundabout
section | Construction
checkpoint | 1 - Survey Setout
note | VERIFICATION ACTIVITY - Survey
note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
note | FREQUENCY - Prior to commencement.
note | ACCEPTANCE CRITERIA - Survey
note | Hold Point - As per Drawings
note | Records - Survey Receipt.
note | Onsite Responsibility - Site Engineer
checkpoint | 2 - Concrete Roundabout - Central Island
note | VERIFICATION ACTIVITY - QA FORM/ Drawings
note | METHODS OR REFERENCE - Construction Drawings
note | FREQUENCY - Each Site
note | ACCEPTANCE CRITERIA - Standard precast kerb to be hand-laid with 120mm reveal. Diameter to varies across with 2% cross fall.Kerbs to be sitted on 300mm Min AP40 Sub Basecourse, with CBR>5
note | • Central island to have 150mm GAP 65 Granular base course on removed pavement surface.
note | Hold Point - Inprocess Inspection
note | Records - Photos
note | Onsite Responsibility - Site Engineer
checkpoint | 3 - Concrete Infill - Central Island
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - Construction Drawings
note | FREQUENCY - Each Site
note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa Unreinforced Concrete with 3kg/m3 red oxide and Broom Finish
note | Hold Point - Inprocess Inspection
note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
note | Onsite Responsibility - Site Engineer
checkpoint | 4 - Apron
note | VERIFICATION ACTIVITY - QA FORM/ Drawings, Concrete Dockets
note | METHODS OR REFERENCE - Construction Drawings, TDM Technical Standards - IS0007
note | FREQUENCY - Each Site
note | ACCEPTANCE CRITERIA - Slip formed 25Mpa fibre reinforced concrete for roundabout edging
note | • Kerbs to be sitted on 300mm Min AP40 Sub Basecourse, with CBR>5
note | • Apron to have 2% min fall towards the road and 2 m wide throughout.
note | • Apron to have 50mm thick AC14 HF with 0.25mm Polythene layer on top below concrete
note | • 195mm depth of 40 Mpa concrete with 4kg/m3 Black oxide and Broom Finish
note | Hold Point - Inprocess Inspection
note | Records - Photos of smart level/ Asbuilts, FH concrete QA sheet. Concrete delivery Dockets kept as record
note | Onsite Responsibility - Site Engineer
section | Asbuilts
checkpoint | 7 - As built information
note | VERIFICATION ACTIVITY - Drawings
note | FREQUENCY - Every Site
note | ACCEPTANCE CRITERIA - As built drawings
note | Hold Point - In Process Inspection
note | Records - Asbuilt records
note | Onsite Responsibility - Supervisor and Engineer
checkpoint | 7 - RAMM DATA
note | VERIFICATION ACTIVITY - RAMM DATA SHEET
note | FREQUENCY - Every Site
note | ACCEPTANCE CRITERIA - RAMM SHEET
note | Hold Point - In Process Inspection
note | Records - Asbuilt records
note | Onsite Responsibility - Supervisor and Engineer
section | ITP APPROVAL
checkpoint-no-status | ITP Approval
note | Prepared by: Cimyona (4/02/2022)
note | Approving Delegate: Daniel Tat (4/02/2022)
checklist | Enabling Works - Footpath, Kerb and channel | [5 empty] | Halsey/Maich RAB - ITP - Enabling Works - Footpath, Kerb and channel
section | Site Set Out
checkpoint | 1 - Site Set out
note | VERIFICATION ACTIVITY - Surveyor
note | METHODS OR REFERENCE - Surveyor
note | FREQUENCY - Everysite
note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
note | Hold Point - Mandatory HOLD POINT -
note | Records - Onsite records/photos
note | Onsite Responsibility - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Kerb & Channel
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
note | FREQUENCY - Everysite
note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40
note | Hold Point - Inprocess Inspection
note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
note | Onsite Responsibility - Site Engineer
checkpoint | 3 - Channel Level
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
note | FREQUENCY - Everysite
note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
note | Hold Point - Inprocess Inspection
note | Records - FH concrete QA sheet, Photos
note | Onsite Responsibility - Site Engineer
section | CIVIL WORKS
checkpoint | 4 - Concrete Footpaths
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
note | FREQUENCY - 10m Intervals
note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40
note | • Clegg CIV > 12
note | • Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
note | Hold Point - Inprocess Inspection
note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
note | Onsite Responsibility - Site Engineer
checkpoint | 5 - Tactiles
note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
note | FREQUENCY - Each PX
note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 150mm concrete slab underneath
note | Hold Point - Inprocess Inspection, Measurement
note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
note | Onsite Responsibility - Site Engineer
checkpoint | 5.1 -
note | VERIFICATION ACTIVITY - Visual
note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impared pedestrians
note | • AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
note | FREQUENCY - Everysite
note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
note | Hold Point - Inprocess Inspection
note | Records - Photos
note | Onsite Responsibility - Site Engineer
checkpoint | 5.2 -
note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
note | FREQUENCY - Everysite
note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane.
note | Hold Point - Inprocess Inspection
note | Records - Photos
note | Onsite Responsibility - Site Engineer
checkpoint | 5.3 -
note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
note | FREQUENCY - Everysite
note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
note | Hold Point - Inprocess Inspection
note | Records - Materials Dockets
note | Onsite Responsibility - Site Engineer
checkpoint | 6 - Grass Berms
note | VERIFICATION ACTIVITY - Visual
note | METHODS OR REFERENCE - ATCOP Section 12 Footpaths and Pedestrian Facilities
note | FREQUENCY - 10m Intervals
note | ACCEPTANCE CRITERIA - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
note | Hold Point - Inprocess Inspection
note | Records - Photos
note | Onsite Responsibility - Site Engineer
section | 6
checkpoint | 7 - As built information
note | VERIFICATION ACTIVITY - RAMM DATA SHEET
note | FREQUENCY - Every Site
note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
note | Hold Point - In Process Inspection
note | Records - Asbuilt records
note | Onsite Responsibility - Supervisor and Engineer
section | ITP APPROVAL
checkpoint-no-status | ITP Approval
note | Prepared by: Yeswanth Vemula (1/05/2023)
note | Approving Delegate: Daniel Tat (27/01/2023)
checklist-flat | Stormwater Drainage | [5 empty] | Halsey/Maich RAB - ITP - Stormwater Drainage
checkpoint | 1 - Permits & Services
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
note | Frequency - Prior to any construction commencing
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
note | Records - Permit attached or permit number noted.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1 - Permits & Services (2)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Locate and mark out all existing services
note | Frequency - Prior to any construction commencing
note | Conformance Criteria - B4u dig procedure - follow utility protocols
note | Records - B4u dig plans & GPR report attached
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-Construction Sign Offs
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Sub-Contract and Supplier Agreements
note | Frequency - Prior to commencement.
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
note | Records - Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Design is approved and Drawings are of the latest revision.
note | Frequency - Prior to commencement.
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision.
note | • Drawings to be 'ISSUED FOR CONSTRUCTION' status.
note | • HOLD POINT of not issued to IFC.
note | Records - Drawing Register.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Survey Set out
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
note | Frequency - Prior to commencement.
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
note | Conformance Criteria - As per BlueBarn Engineering Drawings: 02237.17-T-400 & Set out files
note | Records - Survey Receipt.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pipe and Manhole Material Compliance
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
note | Frequency - Prior to commencement.
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review, Visual Inspection
note | Conformance Criteria - Pipe shall be
note | • Check for freshly formed pipes and return if required
note | 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058
note | 2). All Concrete RCRRJ pipes to be fitted with Rubber rings
note | 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
note | Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
note | Records - Manufacturers Data Sheets, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
note | Frequency - Prior to commencement.
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing / Survey
note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
note | Records - As-built Drawings. Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Excavation methodology
note | Frequency - Daily
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Prestart review
note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
note | Records - Prestart RCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (2)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Trench Profile - Width
note | Frequency - Daily / as trenching takes place. Different depth methodology
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Excavation methodology
note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
note | Records - Construction Photos
checkpoint | 7 - Trenching & Excavation (3)
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Trench Profile - Depth
note | Frequency - Daily / as trenching takes place.
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Measurement
note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
note | Records - FH Drainage Line Record / Construction Photos
checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Placing and compaction of Bedding Material.
note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
note | Records - FH Drainage Line Record / Construction Photos
checkpoint | 9 - Pipe Position Tolerance
note | ACTION (Hold, Monitor, Witness) - M
note | Frequency - At any point of pipe
note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
note | Records - FH Drainage Line Record, Survey Data.
checkpoint | 10 - Trench Backfill - Placing & Compacting
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Placing and compacting of Trench Backfill Material
note | Frequency - Throughout Trench Backfilling operation.
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
note | Records - Construction Photos
checkpoint | 11 - As-Built Drawings
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Red pen marked-up As-Built of every 'Issued for Construction' AT drawings
note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings / Visual Inspection
note | Conformance Criteria - As Built and GIS Data
note | Records - Redline As-Built Drawings, scanned as .pdf files.
checklist-flat | Concrete Speedtable | [5 empty] | Halsey/Maich RAB - ITP - Concrete Speedtable
checkpoint | 1 - Permits
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Obtain Permits
note | Frequency - As required
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
note | Records - Permit attached or permit number noted
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
note | Records - Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
note | Records - TMP on MyWorksites/On Site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
note | Frequency - On site daily
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Induction
note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
note | Records - Hazard ID and Pre-starts to safety team
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - IFC drawings have been received by Contractor
note | Records - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of Erosion and Sediment Controls
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that Erosion & Sediment Control in place
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
note | Records - Environmental Controls Audit
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Survey Setout
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey + Smart Level
note | Conformance Criteria - Consistency with Construction Drawing
note | Records - Site Photos post surveying
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing
note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Material Compliance
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Photos + Delivery Docket added to QA folder
note | Records - Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.1 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Document Review
note | Conformance Criteria - Photos + Delivery Docket added to QA folder
note | Records - Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - CIV >15
note | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.4 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Concrete Delivery Dockets
note | Conformance Criteria - Delivery Docket added to QA folder
note | Records - Concrete Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Temporary Works (Formwork)
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Formwork to be set to correct line and level
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Concrete Inspection Record
note | Records - Concrete Formwork Checklist
checkpoint | 8.1 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15)
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
note | Conformance Criteria - Designer to inspect formation level
note | Records - Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
note | Conformance Criteria - Designer to inspect formation level
note | Records - Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.3 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
note | Conformance Criteria - Designer to inspect formation level
note | Records - Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.4 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:15 relative to the road
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
note | Conformance Criteria - Designer to inspect gradient level
note | Records - Site photos / Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.5 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
note | Frequency - Prior to concrete pour
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Concrete Inspection Record
note | Records - Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Reinforcing
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
note | Conformance Criteria - Concrete Inspection Record
note | Records - Site photos/Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Concreting
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
note | Frequency - Prior to concrete pour
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
note | Records - Email / SMS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1 -
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Vibrator to be used throughout concrete pour
note | Frequency - When pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Concrete Inspection Record
note | Records - Concrete Formwork Checklist
checkpoint | 10.2 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
note | Frequency - At completion of pour
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Concrete Inspection Record
note | Records - Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Curing
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
note | Frequency - Post Pour
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Monitoring the time allowed for curing
note | Conformance Criteria - 48 hours minimum have passed
note | Records - Concrete Formwork Checklist
checkpoint | 12 - Remove formwork
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Remove formwork after 48 hours
note | Frequency - Post Curing
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Concrete Inspection Record
note | Records - Concrete Formwork Checklist
checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
note | Records - Site photos,delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.1 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
note | Records - Site photos,delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.2 -
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Tack Coat between AC and Concrete slab
note | Frequency - Post Curing
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Photos + Delivery Docket added to QA folder
note | Records - Site photos
checkpoint | 13.3 -
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - 50mm thick DG10 / Mix 7
note | Frequency - Post Curing
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
note | Conformance Criteria - Photos + Delivery Docket added to QA folder
note | Records - Site photos, delivery dockets
checkpoint | 14 - Lot Number QA File
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
note | Frequency - At completion of Lot
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - All QA files compiled and sumbitted to client
note | Records - QA records
checkpoint | 14.1 -
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Delivery Dockets to be included in QA file
note | Frequency - At completion of Lot
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Delivery Dockets to be included in QA file
note | Records - QA records
checkpoint | 15 - As-builts
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Red pen mark up drawings to be included in QA file
note | Frequency - At the completion of the Lot of work
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
note | Records - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist | Traffic Islands | [5 empty] | Halsey/Maich RAB - ITP - Traffic Islands
section | Materials
checkpoint | 1 - Mountable Kerb
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
note | FREQUENCY - Everysite
note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
note | Hold Point - Inprocess Inspection
note | Records - FH concrete QA sheet, photos.
note | Onsite Responsibility - Site Engineer
section | Construction
checkpoint | 2 - Survey Setout
note | VERIFICATION ACTIVITY - Survey
note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
note | FREQUENCY - Prior to commencement.
note | ACCEPTANCE CRITERIA - Survey
note | Hold Point - As per Construction Drawings
note | Records - Survey Receipt.
note | Onsite Responsibility - Site Engineer
checkpoint | 3 - Concrete Island
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
note | • TDM Technical Standards - IS0001 & IS0003
note | FREQUENCY - Each Site
note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
note | • Basecourse to be 150mm min thickness of GAP65
note | Hold Point - Inprocess Inspection
note | Records - Photos
note | Onsite Responsibility - Site Engineer
checkpoint | 4 - Concrete Infil
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
note | FREQUENCY - Each Site
note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 3 kg/m3 Red oxide
note | • Cross Fall of 2% or max rise in centre of 180mm
note | Hold Point - Inprocess Inspection
note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
note | Onsite Responsibility - Site Engineer
section | Asbuilts
checkpoint | 5 - As built information
note | VERIFICATION ACTIVITY - Drawings
note | FREQUENCY - Every Site
note | ACCEPTANCE CRITERIA - As built drawings
note | Hold Point - In Process Inspection
note | Records - Asbuilt records
note | Onsite Responsibility - Supervisor and Engineer
checkpoint | 6 - RAMM DATA
note | VERIFICATION ACTIVITY - RAMM DATA SHEET
note | FREQUENCY - Every Site
note | ACCEPTANCE CRITERIA - RAMM SHEET
note | Hold Point - In Process Inspection
note | Records - Asbuilt records
note | Onsite Responsibility - Supervisor and Engineer
section | ITP APPROVAL
checkpoint-no-status | ITP Approval
note | Prepared by: Yeswanth Vemula (1/05/2023)
note | Approving Delegate: Daniel Tat
checklist | Pavement Construction | [5 empty] | Halsey/Maich RAB - ITP - Pavement Construction
section | Precom
checkpoint | 1 - Permits & Services
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
note | Frequency - Prior to any construction commencing
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
note | Records - Permit attached or permit number noted.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1 - Permits & Services (2)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Locate and mark out all existing services
note | Frequency - Prior to any construction commencing
note | Conformance Criteria - B4u dig procedure - follow utility protocols
note | Records - B4u dig plans
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1 - Permits & Services (3)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Approved TMP
note | Frequency - Prior to any construction commencing
note | Conformance Criteria - Approved TMP and WAP onsite befor establishing traffic management
note | Records - TMP Plans
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-Construction Sign Offs
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Sub-Contract and Supplier Agreements
note | Frequency - Prior to commencement.
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
note | Records - Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Design is approved and Drawings are of the latest revision.
note | Frequency - Prior to commencement.
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision.
note | • Drawings to be 'ISSUED FOR CONSTRUCTION' status.
note | • HOLD POINT of not issued to IFC.
note | Records - Drawing Register.
holdpoint | AUTHORITY HOLDPOINT
section | SAC Pavement & Surfacing
checkpoint | 4 - Bitumen
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - NZTA M/1
note | Frequency - Passing all tests listed in Table 1 of NZTA M/1
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
note | Conformance Criteria - Passing all tests listed in Table 1 of NZTA M/1
note | Records - IANZ Lab results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Asphalt Mix Design
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - JMF approved
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
note | Conformance Criteria - AUSTROADS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Production Tests
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - NAS 2004 & TNZ sup to NAS 2006, TNZ P/9P (M/10 Table 5.1)/
note | Frequency - 1 set every 300t
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
note | Conformance Criteria - NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P or NZTA M/10 - Grading, Binder content, Max Density, Temprature
note | Records - IANZ Lab results
checkpoint | 7 - Check Weather Reports
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - No fog, rain or wet surface. Base temp greater or equal to 7 deg celcius
note | Frequency - Weather call the day before
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
note | Conformance Criteria - Forecast and thermometer
note | Records - Radar and Asphalt QA
checkpoint | 8 - Pre-Seal Inspection
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Surface finish
note | Frequency - Continuous
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
note | Conformance Criteria - The surface must be clear of deleterious material and not chocked with fines. The basecourse surface must present a stone mosaic surface with larger aggregates protruding and not appear damp
note | Records - Sealing QA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Tack Coat
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Minimum residual binder application of 0.3l/m2
note | Frequency - Each Run
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing & Visual
note | Conformance Criteria - Each spray of bitumen
note | Records - Asphalt QA
checkpoint | 10 - Construct 50MM PMB AC14
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - NZTA M/10, NDM and Stringline
note | Frequency - Each Run
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing & Visual
note | Conformance Criteria - Construct 50mm PMB AC14 . - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
note | Records - Asphalt QA
checkpoint | 11 - Construct 50MM HF AC14
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - NZTA M/10, NDM and Stringline
note | Frequency - Each Run
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
note | Conformance Criteria - Construct 50mm PMB AC14 in 1layer
note | Records - Asphalt QA
checkpoint | 16 - Construct 80MM AC 20
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - NZTA M/10, NDM and Stringline
note | Frequency - Each Run
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing & Visual
note | Conformance Criteria - Construct 80 MM AC20. - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
note | Records - Asphalt QA
checkpoint | 17 - Surface Finish
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - TNZ P/9P
note | Frequency - Each Lot
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
note | Conformance Criteria - Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
note | Records - Photos
checkpoint | 18 - Reinstatement of Linemarking and RRPM's
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - NZTA M7 approved (Class B or C as required for anticipated traffic level)
note | Frequency - Every site
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
note | Conformance Criteria - Carried out within 12 hours of each shift completed and as per the existing markings
note | • Suitable Traffic Control to remain in place until pavement markings have been reinstated
note | Records - Photos