## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Asphalt Surfacing | [5 empty] | Ponsonby - ITP - Asphalt Surfacing
checkpoint | 1 - Traffic Management
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
note | Records - TMP on MyWorksites/On Site
checkpoint | 2 - Pre-construction sign offs
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
checkpoint | 3 - Base course sign off
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that base course checklist and QA records are signed by AT representative/Engineer
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Completion approved as per Pavement ITP
note | Records - Pavement Base course checklist signed
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Design
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that Design is approved and Drawings are of the latest revision
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - IFC Label on drawings
note | Records - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material testing and control - AC
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Asphalt mix design approval
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission and review
note | Conformance Criteria - Accepted by AT representative/Engineer
note | Records - Approval evidence
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Construction
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Check weather forecast and record weather
note | Frequency - Prior and during application
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Monitor
note | Conformance Criteria - No foggy or raining or wet surface, base temperature > 7°
note | Records - NA
checkpoint | 6 - Construction (2)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Joints
note | Frequency - Per joint of the road
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Edges and joints to existing surfaces must be tapered to provide a smooth transition from the slurry to the adjacent surfaces
note | Records - Visual inspection
checkpoint | 6 - Construction (3)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Milling/surface preparation
note | Frequency - Prior to emulsion application
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection, survey
note | Conformance Criteria - If the surface is being milled and filled, surface levels and condition are to be inspected by the Engineer and confirmed acceptable before proceeding.
note | • Not applicable if pavement has been constructed under the Pavement ITP process.
note | Records - Visual inspection, survey
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Construction (4)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Surface finish
note | Frequency - Per section of road
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inpsection
note | Conformance Criteria - Uniform texture, no roller marks no bleeding, cracking, no crushing of aggregate
note | Records - Visual inspection
checkpoint | 6 - Construction (5)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Level
note | Frequency - As required
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inpsection
note | Conformance Criteria - Asphalt against kerb and channel, the surface of the edge shall be flush or no more than 5mm above the lip of channel
note | • Any irregularities which vary more than 5mm under straight edge, longitudinally or transversely shall be corrected
note | Records - Visual inspection
checkpoint | 6 - Construction (6)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Compaction
note | Frequency - As required
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
note | Conformance Criteria - Nuclear Densometer tests meet specified density
note | Records - Nuclear Densometer test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Post construction
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Inspection/ joint inpsection
note | Frequency - As required
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Asphalt joint sealing as per AT standard
note | • Accepted by AT representative/Engineer
note | Records - Visual inspection
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Linemarking
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure that linemarking is set out and applied in the correct location and to the level of quality expected
note | Frequency - Before & after linemarking
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection, survey
note | Conformance Criteria - Linemarking adheres to design alignments and is of a good quality
note | Records - Visual inspection, survey