## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Earthworks and Retaining Wall | [5 empty] | Ponsonby - ITP - Earthworks and Retaining Wall
checkpoint | 1 - Permits
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Obtain Permits
note | Frequency - As required
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services).
note | • Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
note | Records - Permit attached or permit number noted
checkpoint | 2 - Traffic Management
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
note | Records - TMP on MyWorksites/OnSite
checkpoint | 3 - Pre-construction sign offs
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
checkpoint | 4 - Design
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that Design is approved and Drawings are of the latest revision
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - IFC Label on drawings
note | Records - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Granular Fill Material requirements
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - As per TNZ F/1:1997
note | Conformance Criteria - Maximum percenetage of weight passing 35% 0.0075m sieve shall not exceed 35% and has a sand equivalent greater than 20.
note | Records - Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Survey Setout
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Setout cut/fill areas as required by to construct to design. Topographical surveys to be completed prior to starting, monthly and upon completion
note | Frequency - Prior to commencement, monthly and at completion
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
note | Records - Check Drawing Register
checkpoint | 7 - Installation of Erosion and Sediment Controls where required
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Setout Environmental Controls and confirm location with Environmental Manager
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
note | Conformance Criteria - Correct volume for area and setup to TP90: 1999
note | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Installation of Erosion and Sediment Controls where required (2)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Design Engineer Rep/ Client Rep to inspect controls after implementation
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission
note | Conformance Criteria - Correct volume for area and setup to TP90: 1999
note | Records - As-built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Installation of Erosion and Sediment Controls where required (3)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Monitor sediments tracked out onto any roads and the generation of any Foreign objects and debris as well as dust generated
note | Frequency - Continuous monitoring
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Roads free of debris using watercart where required to minimise dust generation
note | Records - This ITP
checkpoint | 7 - Installation of Erosion and Sediment Controls where required (4)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Monitor effectiveness of the ESCP Controls throughout the work
note | Frequency - Continuous monitoring
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measure
note | Conformance Criteria - In accordance with Auckland Council TP90:1999
note | Records - Audits
checkpoint | 8 - Site Clearing
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Removal of pavement layers, vegetation, services and other objects
note | Frequency - During Physical Works
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Records - Photographic / Videography
checkpoint | 9 - Stripping
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Determine if topsoil suitable for respread after earthworks are complete
note | Frequency - As required
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Stripping in accordance with TNZ F/1:1997
note | Records - Photographic / Videography/ Checksheets
checkpoint | 9 - Stripping (2)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Joint inspection with Engineers Rep and carry out topo survey
note | Frequency - On completion of stripping
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Ensure topsoil stripping is complete and area is clear of organic material
note | Records - Photographic / Videography/ Checksheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Stockpiling
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Ensure stockpiles are separately stockpiled, exposed surfaces to be compacted sufficiently and away from runway, inlets and coastline
note | Frequency - As required
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Stockpiling in accordance with TNZ F/1:1997. Stockpiles to be minimum 50m away from watercourses.
note | Records - Photographic / Videography
checkpoint | 11 - Retaining Wall Foundations
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Shear vane Strength
note | Frequency - 1 tests per 4m2
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
note | Conformance Criteria - Shear vane to exceed 80 Kpa or otherwise subgrade to be undercut and repalced by specfieid granular material at Deign Engineer's discretion
note | Records - Lab Test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Cut Subgrade testing
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Subgrade Surface - Straight Edge
note | Frequency - During Construction
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
note | Conformance Criteria - As per TNZ F/1 clause 11.2.2 - All points within 30mm of true from a 3m straight edge laid parallel to centreline of road.
note | • The subgrade surface shall not pond water, where the design slope of the subgrade is 2% or steeper.
note | Records - Survey receipt
checkpoint | 12 - Cut Subgrade testing (2)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Scala Penetrometer Testing
note | Frequency - 20m intervals to a depth of 1m at alternating wheel tracks
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
note | Conformance Criteria - Scala Penetrometer to a minimum depth of 1m and shall have no reading less than specified CBR of 3.5%, where Subgrade is gravel, Clegg hammer shall have no reading less than CIV 7.
note | Records - QA Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Bulk Fill Material Testing
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Compaction shall be to TNZ F/1 with maximum layer thickness to not exceed 200mm
note | Frequency - Every 200mm lift at/ 1 test per 4m2
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
note | Conformance Criteria - CIV >= 25
note | Records - QA Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Final Inspection
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Subgrade inspection by Engineer
note | Frequency - Once per area
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Final sign off of subgrade by Engineer.
note | Records - Photographic / Videography
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Retaining Wall Construction
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Material Compliance
note | Frequency - During Construction
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document review
note | Conformance Criteria - High Density H6 treated Radiata poles to be used for construction unless specified other wise by Design Engineer H5 treated timber to be used as railings unless specified otherwise by Design Engineer
note | Records - Delivery Dockets/ Design Engineer Correspondence
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Retaining Wall Construction (2)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Concrete Encasement
note | Frequency - During Construction
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Concrete mix to be a minimum 17.5 Mpa, high slump mix, 10mm chip.
note | • Minimum of 100mm cover below timber poles
note | Records - Photgraphic / Videography / Delivery Dockets
checkpoint | 15 - Retaining Wall Construction (3)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Subsoil drainage
note | Frequency - During Construction
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Subsoils to be 110mm preforated pipe with filter sleeve sock.
note | • Bidim A29 or approved geofabric to be placed between drainage material and surrounding ground.
note | • Drainage 40/20 freeflowing aggregate to be used as bedding and cover.
note | Records - Photgraphic / Videography / Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - As-builts
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Red pen mark up drawings to be included in QA file
note | Frequency - At the completion of the Lot of work
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
note | Records - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT