## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Footpath Construction | [5 empty] | Ponsonby - ITP - Footpath Construction
checkpoint | 1 - Permits
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Obtain Permits
note | Frequency - As required
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
note | Records - Permit attached or permit number noted
checkpoint | 2 - Traffic Management
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - TMP is approved by AT for the site and works are completed within the approved dates
note | Records - TMP on MyWorksites
checkpoint | 3 - Pre-construction sign offs
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Signed Subcontract and Supplier Agreements and Induction Register updated
note | Records - Subcontract and Supplier Agreements, & Updated Induction Register
checkpoint | 4 - Design
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that Design is approved and Drawings are of the latest revision
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - IFC Label on drawings
note | Records - Check Drawing Reegister
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Survey Setout
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Set out pegs installed every 10m of the footpath showing the FL & giving indication of line, extra pegs required on curves or special features
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
note | Records - Visual Inspection
checkpoint | 6 - Material Compliance
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - GAP40 - Basecourse
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
note | Conformance Criteria - Grading test only
note | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Material Compliance (2)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Concrete Mix Design at 20 Mpa in accordance with ATCoP
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Mix Design is approved prior to any concrete being delivered to site by Design Engineer
note | Records - Mix Design Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Subgrade Compliance
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - If Existing Subgrade CBR<3% or CIV<7 (if granular), Base layer thickness can be increased by 100mm at Design Engineer's discretion
note | Frequency - One test per 10 linear metres
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Design Engineer Inspection and Correspondence
note | Conformance Criteria - CBR> 3% or CIV>=7
note | Records - QA Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Basecourse - GAP40
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Compaction of GAP 40 with minimun 100mm thickness
note | Frequency - Upon Completion
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Clegg Test
note | Conformance Criteria - ClV >= 12
note | Records - QA Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Concreting
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Before any concrete is poured a prepour inspection to be carried out
note | Frequency - Pre-Pour
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Concrete pre-pour checksheet
note | Records - Checksheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Concreting (2)
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure concrete type and finish is as per specifications & drawings. Concrete panels should be no longer than 3m.
note | Frequency - Pre-Pour
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - U5 Broom Finish
note | Records - Concrete docket/ Photos
checkpoint | 9 - Concreting (3)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Vehicle crossing basecourse to be of a minimum 100mm thickness of compacted GAP40
note | Frequency - Pre-Pour
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Clegg Test
note | Conformance Criteria - CIV >= 25 as per ATCoP drawings
note | Records - QA Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Concreting (4)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Bus Shelter Foundation Prep
note | • Concrete thickness to be 2oomm
note | • 100mm GAP40 Basecourse.
note | • 2 layers of 665 mesh
note | Frequency - Pre-Pour
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Clegg Test
note | Conformance Criteria - CIV >= 25 as per ATCoP drawings
note | Records - QA Sheets/ Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Concreting (5)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Tactile pavers are installed per drawings & specifications
note | Frequency - Pre-Pour
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - As per drawing
note | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Signage
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Signage sockets and signs are installed as per drawings and specification
note | Frequency - Upon Completion
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - As per drawings
note | Records - Photos
checkpoint | 11 - As-builts
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Red pen mark up drawings and RAMM to be included in QA file
note | Frequency - At the completion of the Lot of work
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
note | Records - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT