## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Kerbs & Channel | [5 empty] | Ponsonby - ITP - Kerbs & Channel
checkpoint | 1 - Permits
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Obtain Permits
note | Frequency - As required
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services).
note | • Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
note | Records - Permit number noted
checkpoint | 2 - Traffic Management
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
note | Records - TMP on MyWorksites/OnSite
checkpoint | 3 - Pre-construction sign offs
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
checkpoint | 4 - Design
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that Design is approved and Drawings are of the latest revision
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - IFC Label on drawings
note | Records - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Survey Setout
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Check constructed Sub base is within level tolerance.
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
note | Records - Survey receipt
checkpoint | 5 - Survey Setout (2)
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Set out Vehicle Crossing transition points and Pedestrian Drop Downs.
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey, Measurement and Visual inspection
note | Conformance Criteria - Kerbing Specification and Geometrics Drawing
checkpoint | 6 - Material Compliance
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Mortar consist of two parts fine, sharp sand to one part of cement.
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Delivery Docket
note | Conformance Criteria - Must be discarded if not used within 30mins of mixing
note | Records - Delivery Dockets
checkpoint | 6 - Material Compliance (2)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Precast work shall be 20MPa concrete Concrete haunching to also be 20MPa in accordance with ATCoP
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Delivery Docket
note | Conformance Criteria - Check product & dockets upon arrival onsite
note | • Mix Design is approved prior to any concrete being delivered to site by Design Engineer
note | Records - Delivery Dockets, Mix Design report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Material Compliance (3)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - GAP40 and GAP65 - Basecourse
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
note | Conformance Criteria - Grading test only
note | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Subsoils
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Preforated filter sleeve Drain Pipe to be placed minimium 375mm below subgrade bedded and covered with F/2 sand
note | Frequency - 10m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Site Check
note | Conformance Criteria - As per TDM Technical standards RD0100
note | Records - QA Sheets
checkpoint | 8 - Precast kerb and channel
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - All chamfer to be 20mm, kerb joints to be 10mm min cement mortared
note | Frequency - Prior installation
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
note | Records - ATCOP, Photos
checkpoint | 9 - Kerb and channel foundation
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - If Existing Subgrade <3% or CIV<7 (if granular), undercut required and bakcfilled with appropriate material and at depth for Design Engineer to specify.
note | Frequency - 10m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
note | Conformance Criteria - Subgrade material >3%or CIV =>7
note | Records - QA Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Kerb and channel foundation (2)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Kerbing must be laid on 300mm min GAP 65 subbase in Road and 100mm GAP 40 on Footpaths.
note | • The subbase for the K&C must be Clegg Tested with no CIV<30
note | • Concrete haunching must be done as per drawings.
note | Frequency - 10m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
note | Conformance Criteria - Pavement depth and type under the kerb varies depending on location. CIV for foundations >=30
note | Records - QA Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Kassel Kerbs Foundation
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - If the existing Subgrade material <3% CBR or CIV<7 if granular, Undercut 300mm and backfill with Granular GAP 40. Design Engineer to Specify Depth.
note | Frequency - 10m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
note | Conformance Criteria - Subgrade material =>3%or CIV =>7
note | Records - QA Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Kassel Kerbs Foundation (2)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - The Kassel Kerbs must be laid on minimum 15 MPa Concrete at correct 200mm thickness on GAP65 subbase CIV >15
note | Frequency - 10m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Test/Site Check
note | Conformance Criteria - As per Drawing: 2019-AT-017_G502
note | Records - QA Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Island Infill
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - If the existing Subgrade material <CBR 3% or CIV <7 (if granular), Increase base thickness by upto 100mm at the discretion of Design Engineer
note | Frequency - 10m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab/test
note | Conformance Criteria - Subgrade material >3% or CIV>= 7
note | Records - QA Sheets, Design Engineer Correspondence
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Island Infill (2)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - The sub-base must be GAP40 and must be clegg tested at every 10m intervals
note | Frequency - 10m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab/test
note | Conformance Criteria - CIV >=30
note | Records - QA Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Island Infill (3)
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Concrete must be minimum of 20 Mpa and must be of correct 150mm thickness
note | Frequency - During Pour
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
note | Conformance Criteria - Exposed finish compliant with NZS3104 and constructed accordance with NZS3109
note | Records - Visual inspection
checkpoint | 12 - Stringing for All Kerb Type
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Kerbs laid out accurately to lines, gradients & levels shown in drawings.
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
note | Conformance Criteria - Prior to laying, string lines or levels to be inspected by Engineers Rep.
note | • When a 3 m straight edge is laid parallel to any surface of a pre-cast or bluestone kerb and channel there shall be no more than 5 mm variation from the straight edge, except at change of grades or curves
note | Records - ATCOP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Dish Channels
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Contraction joints at a maximum of 3m intervals.
note | Frequency - During Slip forming
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
note | Conformance Criteria - Kerbing Specification
note | Records - ATCOP
checkpoint | 13 - Dish Channels (2)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Top surface to channels to be finished smooth and even with a trowel.
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Shall not pond any water.
note | Records - ATCOP
checkpoint | 14 - Tie-in with pre-cast components
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Ensure Kerb & channel to be cut and tied-in with pre-cast components by forming concrete aprons
note | Frequency - During works
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Consistency with Work Instruction
note | Records - ATCOP
checkpoint | 14 - Tie-in with pre-cast components (2)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Channel joint material set flush with surfaces (ensure levels are within the tolerances).
note | Frequency - During works
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Consistency with Channel Specifications
note | Records - ATCOP
checkpoint | 14 - Tie-in with pre-cast components (3)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Catchpit frame, grating and back entry kerb installed at correct level
note | Frequency - During Works
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document review visual inspection
note | Conformance Criteria - Document review visual inspection
note | Records - ATCOP
checkpoint | 15 - As-builts
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Red pen mark up drawings to be included in QA file
note | Frequency - At the completion of the Lot of work
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
note | Records - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT