## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Road Pavement | [5 empty] | Ponsonby - ITP - Road Pavement
checkpoint | 1 - Permits
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Obtain Permits
note | Frequency - As required
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services).
note | • Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
note | Records - Permit number noted
checkpoint | 2 - Traffic Management
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
note | Records - TMP on MyWorksites/OnSite
checkpoint | 3 - Pre-construction sign offs
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
checkpoint | 4 - Design
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that Design is approved and Drawings are of the latest revision
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
note | Conformance Criteria - IFC Label on drawings
note | Records - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Subgrade
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Subgrade Scala Penetrometer Testing (CBR) at 10m intervals in each traffic lane-staggered and /or stitch section - unless directed otherwise by engineer
note | Frequency - 10m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
note | Conformance Criteria - Accepted by or subgrade improvement instruction received from AT representative/Engineer
note | Records - Testing records/ QA sheets if applicable
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Subgrade (2)
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Subgrade undercutting/improvement inpsection
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Accepted by or subgrade improvement instruction received from AT representative/Engineer
note | Records - Testing records/ QA sheets if applicable
checkpoint | 5 - Subgrade (3)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Subgrade surfacing stringing
note | Frequency - 1 in 10m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
note | Conformance Criteria - Straight edge: ±30mm/3m
note | Records - QA sheets
checkpoint | 6 - Subbase-GAP65
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Material source testing approved
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission and review
note | Conformance Criteria - Meets specified criteria and lab test report is recent within 6 months
note | Records - Lab Test Report
checkpoint | 6 - Subbase-GAP65 (2)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Material delivery
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Check for quality of material
note | Records - Visual inspection
checkpoint | 6 - Subbase-GAP65 (3)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Surface shape-stringing line check
note | Frequency - 1 in 10m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
note | Conformance Criteria - Within tolerances, ±20mm
note | • Crossfall no depart from exisitng crossfall or instruction from AT represenative/engineer
note | Records - QA sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Subbase-GAP65 (4)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Compaction-NDM tests
note | Frequency - 1 test per 30m of road per lane, staggered at 15m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
note | Conformance Criteria - Mean >=95% of MDD
note | • Minimum>=92% of MDD
note | Records - Testing records/
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Subbase-GAP65 (5)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Benkelman Beam Deflection Test
note | Frequency - at 10m intervals in each traffic lane-staggered
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
note | Conformance Criteria - <=1mm (or specified by AT representative/engineer)
note | • Not applicable to stitch section
note | Records - Testing records/
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Basecourse-NZTA M/4 AP40
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - All chamfer to be 20mm, kerb joints to be 10mm min cement mortared
note | Frequency - Prior installation
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
note | Records - ATCOP, Photos
checkpoint | 7 - Basecourse-NZTA M/4 AP40 (2)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Material source testing approved
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission and review
note | Conformance Criteria - 1/ source and at least 1/6 months
note | Records - Lab Test Report
checkpoint | 7 - Basecourse-NZTA M/4 AP40 (3)
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Material delivery
note | Frequency - Prior to commencement
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
note | Conformance Criteria - Check for quality of material
note | Records - Visual inspection
checkpoint | 7 - Basecourse-NZTA M/4 AP40 (4)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Surface shape-stringing line check
note | Frequency - 1 in 10m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
note | Conformance Criteria - Within tolerances, ±5mm
note | • Crossfall no depart from exisitng crossfall
note | Records - QA sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Basecourse-NZTA M/4 AP40 (5)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Compaction-NDM tests
note | Frequency - 1 test per 30m of road per lane, staggered at 15m
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
note | Conformance Criteria - Mean >=98% of MDD
note | • Minimum>=95% of MDD
note | Records - Testing records/
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Basecourse-NZTA M/4 AP40 (6)
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Benkelman Beam Deflection Test
note | Frequency - at 10m intervals in each traffic lane-staggered
note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
note | Conformance Criteria - <=1mm (or specified by AT representative/engineer)
note | • Not applicable to stitch section
note | Records - Testing records/
holdpoint | AUTHORITY HOLDPOINT