## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-037-RAIL-Brunt & Camms-OHLE Structure Installation | itp |  |  |  | Yes | ITP-037-RAIL-Brunt & Camms-OHLE Structure Installation
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-037-RAIL-OHLE Structure Installation
label | ITP Description: OHLE Structure Installation
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 1
label | Revision Date: 16/05/2023
label | ITP created by: Nikhil Siram
label | ITP approved for use by: MRPA Quality Team
checkpoint | 1.1 - Overhead Line Electrification
label | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | Reference - VRIOGS 001 AS 4100
checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
label | Reference - L1-CHE-STD-015(1) MEST 000002-06(1
checkpoint | 1.4 - Fabrication of Steelwork
label | Reference - VicRoads Section 630 January 2023
checkpoint | 1.5 - Structural Steel Work - Fabrication and Erection
label | Reference - AS 5131:2016
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Structural Steel Components and Fasteners
note | Reference - IFC Drawings
note | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
note | • Typically this consists of but not limited to:
note | i. Completed fabrication ITP
note | ii. Weld Procedure Specifications
note | iii. Weld Procedure Qualifications
note | iv. Welder Qualifications
note | v. Material Certificates
note | vi. Coating certificate(s)
note | vii. Non-destructive Testing (NDT) Reports (if any)
note | viii. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
note | • Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
note | • Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
note | • All bolts nuts and washers are hot-dipped galvanized.
note | Collate: Structural Steel Quality Assurance Documentation.
note | Attach: Collated QA documents in ConQA
note | Method - Document Review
note | Frequency - Where applicable/ Each element
note | Category - HP
note | Responsible person - PE
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Bolted Connections Using Direct Tension Indicators (DTIs)
note | Reference - AS4100 Clause 15.2.5.3 (a), AS5131 Clause 8.5.7 (a)
note | Acceptance Criteria - Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
note | i. technical data sheet or information on the product
note | Method - Document Review
note | Frequency - Where applicable, once
note | Category - HP
note | Responsible person - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Overhead Wiring Small Parts Steel and conductor wires
note | Reference - Relevant MTM Standard Drawings
note | Acceptance Criteria - Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
note | • Deliveries are to be inspected to match the purchase order
note | Attach: Purchase order/Delivery dockets/Certificate of conformity
note | Method - Visual inspection and measurement
note | Frequency - Upon delivery
note | Category - IP
note | Responsible person - PE
note | Verifying Documents - This ITP Signed Off
checkpoint | 2.4 - Grout
note | Reference - IFC Drawings
note | Acceptance Criteria - All grout under base plates shall be CONBEXTRA C or equivalent as approved. Approved grout to be Flowable shrinkage compensated with minimum 50 Mpa compressive strength.
textbox | Enter: Teambinder Material Approval number
note | Method - Document review
note | Frequency - Where applicable
note | Category - HP
note | Responsible person - PE
note | Verifying Documents - This ITP / Material Approval
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Installation Methodology & Works Method Statement
note | Reference - AS5131 Clause 11.2.3
note | Acceptance Criteria - Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
note | – Transported to site;
note | – Handled on site;
note | – Installation Procedure (subcontracor ITP's);
note | Submission of Work Package Plan and MRPA approval and acceptance.
textbox | Enter: WAP number
note | Method - Document Review
note | Frequency - Prior to Works Start
note | Category - HP
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - Approval of IFC drawings
note | Reference - Contractor Design Management procedure
note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
note | Method - Document/Drawings Review
note | Frequency - Prior to Works and at regular intervals.
note | Category - HP*
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 4.2 - Cantilever assembled.
note | Reference - Cantilever assembled as per IFC design.
note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
note | Attach: Signed off Cantilever fabrication Checkshit
note | Method - Visual, Document Review
note | Frequency - Each Task prior to works start.
note | Category - IP
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Mast istallation
note | Reference - IFC Drawings:
note | Acceptance Criteria - Mast installed as per IFC. Mast rake is as specified in the drawings
note | Method - Measure
note | Frequency - Where applicable
note | Category - IP
note | Responsible person - PE
note | Verifying Documents - This ITP
checkpoint | 5.2 - Cantilever installed.
note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
note | Acceptance Criteria - Work instructions in accordance to IFC design
note | Method - Measure, Visual
note | Frequency - Each OHLE Structure
note | Category - IP
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.3 - Bearing type Joints TB Friction type joints TF
note | Reference - IFC Drawings
note | Acceptance Criteria - BOLTS DESIGNATED TB & TF ARE TENSIONED AS PER AS 5131 and Table 8.5.6
note | – Bolt mark ups (in case of partial tensionening) should be visible for inspection
note | – DTI squirts are to be visible for inspection
note | Method - Visual
note | Frequency - Where applicable
note | Category - IP
note | Responsible person - PE
note | Verifying Documents - This ITP Signed Off/Visible marks
checkpoint | 5.4 - Install SPS to correct height / position relative to track
note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
note | Method - Measure, Visual
note | Frequency - Each OHLE Structure
note | Category - IP
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.5 - Cantilever checked once installed.
note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
note | Method - Measure, Visual
note | Frequency - Each OHLE Structure
note | Category - IP
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.6 - Base Plate Grout
note | Reference - IFC Drawings
note | Acceptance Criteria - Grout to be mixed as per manufacturer TDS.
note | • Grout to be poured under base plate as per IFC drawings. Grout over pour is to be 6mm and cover area with Nom 50mm offset around the base plate.
note | Method - Visual
note | Frequency - Where applicable
note | Category - IP
note | Responsible person - PE
note | Verifying Documents - This ITP
checkpoint | 5.7 - Installation of wire supports at the correct height and stagger.
note | Reference - Install as per design drawings.
note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
note | Method - Visual
note | Frequency - Each OHLE BWA structure
note | Category - IP
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.8 - Install to correct tension
note | Reference - Install as per design, use span/ambient temp. tension charts.
note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
note | Method - Measure, Visual
note | Frequency - Prior termination
note | Category - IP
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
section | 6. Post-construction Activities
checkpoint | 6.1 - Defects/Temporary Works
note | Reference - IFC wiring layouts, cross sections and design drawings.
note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
note | • Defect list to be provided at the end of Occo identifying planned work to rectify
note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
note | Method - Document Review, Visual
note | Frequency - Each OHLE Structure
note | Category - IP
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
note | Method - Document Review, Visual
note | Frequency - Each OHLE Structure
note | Category - IP
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
note | Reference - MTM Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP