## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP 006 - Duct Install | itp |  |  |  | Yes | ITP 006 - Duct Install | 5d8b1884-e64e-4664-915d-abccb38703b3
checkpoint-group |  |  | section | 1.0 Documentation
checkpoint-status |  |  | checkpoint | 1.1 Material approval
label | ee3ab39f-588d-5d12-b981-119acc8bd1c3 |  | note | Type of inspect / Test and Frequency - RFI cover the approval of the service ducts
label | c0cbc17e-ede4-58dc-bf35-682162931b12 |  | note | Acceptance Criteria - RFI response
label | 7ef188a8-21fe-517b-8ecf-235a69d578f8 |  | note | Inspection Responsibility: BCL - D
label | d5465aac-4861-5968-8fca-995796faab02 |  | note | Inspection Responsibility: Client - A
label | 272e031d-0090-5f8b-b104-13d620296fc3 |  | note | Verification Records of Inspection(s) / Test(s) - RFI
checkpoint-status |  |  | checkpoint | 1.2 Service duct Order
label | ebf01d38-5937-5b8c-8b8d-18d83da7c708 |  | note | Type of inspect / Test and Frequency - Humes Drawings – HN-HO-72
label | bc556fce-f9a4-5e0a-91dc-11c58d546cd2 |  | note | Acceptance Criteria - Drawings
label | b67db67a-3368-533a-a8dd-d15491fbacc0 |  | note | Inspection Responsibility: BCL - D
label | 025192ef-f24c-5c6c-a793-343b29b94f8b |  | note | Inspection Responsibility: Client - I
label | 07b607e8-d7f9-5d6b-ac4b-46b13e243fa2 |  | note | Verification Records of Inspection(s) / Test(s) - Humes Drawings
checkpoint-status |  |  | checkpoint | 1.3 Delivery docket
label | 14621f08-ac0f-521a-841c-c12296087308 |  | note | Type of inspect / Test and Frequency - Confirmation that ducts delivered match RFI016 material approval
label | aeccfb25-8a6f-5c3e-8963-249d6e4abcb2 |  | note | Acceptance Criteria - Delivery docket
label | 0baf211e-1d04-56c2-b5fe-275a514d15bf |  | note | Inspection Responsibility: BCL - D
label | 1dadae54-be75-5a6d-bfdf-90dfa1b827f7 |  | note | Inspection Responsibility: Client - I
label | e284fdf8-3561-5152-a0f0-e72eb1a96479 |  | note | Verification Records of Inspection(s) / Test(s) - Delivery Docket
checkpoint-group |  |  | section | 2.0 Install
checkpoint-status |  |  | checkpoint | 2.1 Subgrade
label | a4de0ad5-af4a-5725-8e8f-f89e4fdc4acd |  | note | Type of inspect / Test and Frequency - Confirm uniform subgrade under the duct
label | 1d74aba0-74ff-5dab-80ee-d0e67e0ff682 |  | note | Acceptance Criteria - Subgrade uniform, soft spots removed
label | 1b57cb57-e8b9-5f30-8aef-78e656613426 |  | note | Inspection Responsibility: BCL - V
label | 0d47a4db-4daf-542d-b42f-19892eb12ba4 |  | note | Inspection Responsibility: Client - I
label | b963132f-0f56-5ddc-8812-f190f5dcb16c |  | note | Verification Records of Inspection(s) / Test(s) - Photo of works
checkpoint-status |  |  | checkpoint | 2.2 Bedding
label | 5ee691b5-5c65-58f6-a2c4-53d268e0a2fb |  | note | Type of inspect / Test and Frequency - Prep and bedding, installed, levelled,
label | f4cf58b2-eee5-58e4-a151-cd15c1024d5b |  | note | Acceptance Criteria - Bedding levelled to avoid uneven loading on the ducts
label | a357e57b-415d-5bcc-a742-d40b73d21383 |  | note | Inspection Responsibility: BCL - V
label | 600396aa-dd31-5625-8d3a-f424cde6e7a6 |  | note | Inspection Responsibility: Client - I
label | ef5336ae-809c-5426-8dad-c63b3961d614 |  | note | Verification Records of Inspection(s) / Test(s) - Photo of works
checkpoint-status |  |  | checkpoint | 2.3 Duct Install
label | e3d63912-7e62-5ab7-9530-8a102db3cf16 |  | note | Type of inspect / Test and Frequency - Ducts installed and locked together, top level installed to string line to avoid any steps in top of channel
label | bbe4e5d4-581e-52b6-8ba0-5799eec21810 |  | note | Acceptance Criteria - No steps in top of channel
label | edec60de-f068-5e73-a764-c675fb011144 |  | note | Inspection Responsibility: BCL - V
label | 6603963e-5e5c-560f-a371-bc516b5e3ad6 |  | note | Inspection Responsibility: Client - I
label | e5a0f863-cf9f-5350-be45-af3b6569e90f |  | note | Verification Records of Inspection(s) / Test(s) - Photo of works
checkpoint-group |  |  | section | 3.0 As-builts
checkpoint-status |  |  | checkpoint | 3.1 Redline Drawings
label | 292b85fd-c003-5877-868a-fae388680632 |  | note | Type of inspect / Test and Frequency - Redline drawings of install
label | 4154a47e-0118-5e72-84e9-3302b287f8aa |  | note | Acceptance Criteria - N/A
label | 830966bf-1f79-596e-a375-4da2c10d332b |  | note | Inspection Responsibility: BCL - S
label | e56b8b52-3441-5445-a973-e66cffed3586 |  | note | Inspection Responsibility: Client - A
label | f144d053-2257-5ca3-9dc6-36fa866a122c |  | note | Verification Records of Inspection(s) / Test(s) - Redline Drawings Issued
checkpoint-status |  |  | checkpoint | 3.2 Survey
label | da604390-1211-5971-bd05-fbe3f390fc7d |  | note | Type of inspect / Test and Frequency - GPS coordinates of duct install
label | f90e9f29-e79c-52a2-96d0-f07dc1aac3f1 |  | note | Acceptance Criteria - N/A
label | f6feab7f-c142-5388-bd4f-7cc39e5e55c4 |  | note | Inspection Responsibility: BCL - S
label | 5dec842d-02a6-5123-b02b-cfa2c7307de0 |  | note | Inspection Responsibility: Client - A
label | 099fdb21-3cc1-5159-9888-28119d00a04e |  | note | Verification Records of Inspection(s) / Test(s) - GPS coordinates marked up on drawing