## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 006 - Duct Install | itp |  |  |  |  | ITP 006 - Duct Install | 5d8b1884-e64e-4664-915d-abccb38703b3
section | 1.0 Documentation
checkpoint | 1.1 Material approval
label | Type of inspect / Test and Frequency - RFI cover the approval of the service ducts
label | Acceptance Criteria - RFI response
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - A
label | Verification Records of Inspection(s) / Test(s) - RFI
checkpoint | 1.2 Service duct Order
label | Type of inspect / Test and Frequency - Humes Drawings – HN-HO-72
label | Acceptance Criteria - Drawings
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Humes Drawings
checkpoint | 1.3 Delivery docket
label | Type of inspect / Test and Frequency - Confirmation that ducts delivered match RFI016 material approval
label | Acceptance Criteria - Delivery docket
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Delivery Docket
section | 2.0 Install
checkpoint | 2.1 Subgrade
label | Type of inspect / Test and Frequency - Confirm uniform subgrade under the duct
label | Acceptance Criteria - Subgrade uniform, soft spots removed
label | Inspection Responsibility: BCL - V
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Photo of works
checkpoint | 2.2 Bedding
label | Type of inspect / Test and Frequency - Prep and bedding, installed, levelled,
label | Acceptance Criteria - Bedding levelled to avoid uneven loading on the ducts
label | Inspection Responsibility: BCL - V
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Photo of works
checkpoint | 2.3 Duct Install
label | Type of inspect / Test and Frequency - Ducts installed and locked together, top level installed to string line to avoid any steps in top of channel
label | Acceptance Criteria - No steps in top of channel
label | Inspection Responsibility: BCL - V
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Photo of works
section | 3.0 As-builts
checkpoint | 3.1 Redline Drawings
label | Type of inspect / Test and Frequency - Redline drawings of install
label | Acceptance Criteria - N/A
label | Inspection Responsibility: BCL - S
label | Inspection Responsibility: Client - A
label | Verification Records of Inspection(s) / Test(s) - Redline Drawings Issued
checkpoint | 3.2 Survey
label | Type of inspect / Test and Frequency - GPS coordinates of duct install
label | Acceptance Criteria - N/A
label | Inspection Responsibility: BCL - S
label | Inspection Responsibility: Client - A
label | Verification Records of Inspection(s) / Test(s) - GPS coordinates marked up on drawing