## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP 007 - Kerb and Bund Works | itp |  |  |  | Yes | ITP 007 - Kerb and Bund Works | 7bc2f48b-be5f-4479-8d72-c98016c5828e
checkpoint-group |  |  | section | 1.0 Documentation
checkpoint-status |  |  | checkpoint | 1.1 IFC drawings
label | dc767edf-0b29-5f9c-8051-5272965c84ca |  | note | Type of inspect / Test and Frequency - IFC drawings and RFIs for any changes
label | cc1681a0-a8ea-5dfe-995d-8292a712a9dd |  | note | Acceptance Criteria - Approved IFC/RFI responses
label | 7c54ec8d-76b2-5cdc-92e9-c736526aa1e7 |  | note | Inspection Responsibility: BCL - D
label | d161aef2-361b-54e4-b1ee-eef0d9184403 |  | note | Inspection Responsibility: Client - A
label | ea0f1cc0-cbe4-5366-8180-020a33cd0ebd |  | note | Verification Records of Inspection(s) / Test(s) - IFC Drawings and RFIs uploaded
checkpoint-status |  |  | checkpoint | 1.2 Material compliance
label | c3864a5b-1449-5523-8349-57281ad812e7 |  | note | Type of inspect / Test and Frequency - Material compliance prior to works – GAP40, GAP20
label | 7f8db901-1f7c-55de-83cb-2476faacdc0b |  | note | Acceptance Criteria - Quary test certificates
label | c7816fb6-0028-57f2-b948-a7afa5c91919 |  | note | Inspection Responsibility: BCL - D
label | 6baa541e-bd0e-535c-9c9f-e60ce003d7d2 |  | note | Inspection Responsibility: Client - A
label | e238dede-61c3-5c3e-9d0c-8005521da9b3 |  | note | Verification Records of Inspection(s) / Test(s) - Quary test certificates
checkpoint-status |  |  | checkpoint | 1.3 Reinforcing
label | 38ec6aee-cc45-5bae-bc19-de3befa0edf5 |  | note | Type of inspect / Test and Frequency - Documentation review
label | 53d39489-efa8-5250-8109-7728b614f8e4 |  | note | Acceptance Criteria - Mill Certs
label | a9809306-8638-56fb-9894-99f7f1c71c3e |  | note | Inspection Responsibility: BCL - D
label | 1abcd14c-b39f-5bdd-b8e0-740bc9525c67 |  | note | Inspection Responsibility: Client - A
label | c51b5aca-546d-53b0-923e-38b7a1b516fa |  | note | Verification Records of Inspection(s) / Test(s) - Mill certs
checkpoint-group |  |  | section | 2.0 Construction - Kerb
checkpoint-status |  |  | checkpoint | 2.1 Excavation
label | c1caf4bc-9301-5dec-ac9a-6aa46cca9b51 |  | note | Type of inspect / Test and Frequency - Subgrade checked and uniform
label | 3e6abb60-ee1f-55e4-a57f-091b855c9dc2 |  | note | Acceptance Criteria - Subgrade uniform
label | dc50862d-df82-54b3-b40d-e7573ebd4a23 |  | note | Inspection Responsibility: BCL - V
label | 1f0bc053-d97a-54a0-a4ba-11bcbcd43f08 |  | note | Inspection Responsibility: Client - I
label | a1f53241-50e0-5b29-aad2-de6b747d462f |  | note | Verification Records of Inspection(s) / Test(s) - Photos
checkpoint-status |  |  | checkpoint | 2.2 Bedding
label | 3d571bcf-c042-5b66-9632-6a63e13ad8b5 |  | note | Type of inspect / Test and Frequency - Prep and bedding, installed, levelled,
label | a8e989ba-55c2-5290-9210-3522e51c1ec1 |  | note | Acceptance Criteria - Level 100mm of bedding under kerb
label | 915a715b-faba-528b-b1cd-255c5ecafa98 |  | note | Inspection Responsibility: BCL - V
label | 8014e555-e93a-58ab-a4f7-64b03de89a3e |  | note | Inspection Responsibility: Client - I
label | ed825f88-fad6-5130-bd18-961e7d44aa12 |  | note | Verification Records of Inspection(s) / Test(s) - Photos
checkpoint-status |  |  | checkpoint | 2.3 Reinforcing
label | 2956f5b2-f36b-52bc-8ed2-e6221b8ea612 |  | note | Type of inspect / Test and Frequency - Bars installed at 400mm centres, top of hook checked for cover to top of concrete
label | 92e769ec-7401-5eb6-a0c5-adbc2dcdae86 |  | note | Acceptance Criteria - Visual inspection, String out the TOC
label | 1f5e9db5-215f-5a0a-81a2-9c027391748b |  | note | Inspection Responsibility: BCL - V
label | 438fef78-2e36-5826-8062-8d18c12ce2dc |  | note | Inspection Responsibility: Client - I
label | d8f83b56-1537-51dc-9cfb-1ac42ed6a130 |  | note | Verification Records of Inspection(s) / Test(s) - Photo
checkpoint-status |  |  | checkpoint | 2.4 Concrete
label | 7357f322-9869-5c1f-928a-6a53447fb98a |  | note | Type of inspect / Test and Frequency - Delivery docket checked, once per pour. Concrete strength verified.
label | 5bbc344b-84e1-551d-b1a3-f2ac893b8b1c |  | note | Acceptance Criteria - 20MPA concrete installed, level checked
label | 261cb615-ff25-5c34-846e-0567afd6d779 |  | note | Inspection Responsibility: BCL - D
label | 875228cd-ed42-5394-a160-5e76d116cc99 |  | note | Inspection Responsibility: Client - I
label | 31a26a7c-b8df-58e2-9e77-61aba32c102c |  | note | Verification Records of Inspection(s) / Test(s) - Delivery docket, Concrete crushing strength verified
checkpoint-group |  |  | section | 3.0 As-builts
checkpoint-status |  |  | checkpoint | 3.1 Excavation
label | 96bf89a7-619b-5387-868c-829ea6694689 |  | note | Type of inspect / Test and Frequency - Subgrade checked and uniform
label | 6ad59e59-b5be-5cad-b363-23425344e224 |  | note | Acceptance Criteria - Subgrade uniform
label | 682e3c3d-db24-5ddf-b5d6-b7513b9cd414 |  | note | Inspection Responsibility: BCL - V
label | 9530dac3-e5b1-581a-b6fb-9d9081628785 |  | note | Inspection Responsibility: Client - I
label | 46a2f89f-94a3-5552-ba9b-69dae4718ff7 |  | note | Verification Records of Inspection(s) / Test(s) - Photos
checkpoint-status |  |  | checkpoint | 3.2 Bedding
label | 619b6d42-851f-52be-9094-7463c0d0adb4 |  | note | Type of inspect / Test and Frequency - Prep and bedding, installed, levelled,
label | 947e8329-0708-5315-8c0b-983023fef3d5 |  | note | Acceptance Criteria - Level 100mm of bedding under kerb
label | 888cf871-9f44-5a3c-bb14-c89259e4152b |  | note | Inspection Responsibility: BCL - V
label | 5b22b2af-18d4-541c-a063-de57afcb6542 |  | note | Inspection Responsibility: Client - I
label | b9dd8e41-2aad-5656-b2ce-8f5de19d92ec |  | note | Verification Records of Inspection(s) / Test(s) - Photos
checkpoint-status |  |  | checkpoint | 3.3 Reinforcing
label | cdab7cd3-1544-5445-a574-5e586b3ad65b |  | note | Type of inspect / Test and Frequency - Bars installed at 400mm centres, top of hook checked for cover to top of concrete
label | 2a6f2f9e-9767-511a-97f6-98d0621f944e |  | note | Acceptance Criteria - Visual inspection, String out the TOC
label | cd2a51a3-f6ae-5efc-96c0-eaa7702b1322 |  | note | Inspection Responsibility: BCL - V
label | 2d4e13cc-ed7f-5392-bcf6-2bc10941ecc8 |  | note | Inspection Responsibility: Client - I
label | 90474fb7-83de-5e1b-b8ab-8922080a5bfb |  | note | Verification Records of Inspection(s) / Test(s) - Photo
checkpoint-status |  |  | checkpoint | 3.4 Concrete
label | e0f7cb3c-83ad-5b3f-9057-16e810caad24 |  | note | Type of inspect / Test and Frequency - Delivery docket checked, once per pour. Concrete strength verified.
label | 38b2ed43-66a9-5fd8-9e34-607dd1dacc24 |  | note | Acceptance Criteria - 20MPA concrete installed, level checked
label | 14f550ff-05f6-5cc6-aad4-59a30d33eb03 |  | note | Inspection Responsibility: BCL - D
label | f19fbc5c-7bd2-55dd-be1f-3bd315b549bc |  | note | Inspection Responsibility: Client - I
label | 06dc565f-3ca6-57f0-a036-c96843dbffe9 |  | note | Verification Records of Inspection(s) / Test(s) - Delivery docket, Concrete crushing strength verified
checkpoint-group |  |  | section | 4.0 Asbuilt
checkpoint-status |  |  | checkpoint | 4.1 Redline drawings
label | 008980a4-db0e-59eb-a707-1c47d4c54c0d |  | note | Type of inspect / Test and Frequency - Complete as built redline drawings of works once complete
label | cc6ed880-0706-5b9d-ab25-293206960b82 |  | note | Acceptance Criteria - Redline drawings capturing changes
label | a450b0be-1804-590b-a0d9-f155977f29f6 |  | note | Inspection Responsibility: BCL - D
label | c558546a-bf1b-58ac-9b41-b48c515461db |  | note | Inspection Responsibility: Client - A
label | 20206f0e-08c7-50f7-be78-e7d0d2c36181 |  | note | Verification Records of Inspection(s) / Test(s) - Redline drawings