## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 007 - Kerb and Bund Works | itp |  |  |  |  | ITP 007 - Kerb and Bund Works | 7bc2f48b-be5f-4479-8d72-c98016c5828e
section | 1.0 Documentation
checkpoint | 1.1 IFC drawings
label | Type of inspect / Test and Frequency - IFC drawings and RFIs for any changes
label | Acceptance Criteria - Approved IFC/RFI responses
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - A
label | Verification Records of Inspection(s) / Test(s) - IFC Drawings and RFIs uploaded
checkpoint | 1.2 Material compliance
label | Type of inspect / Test and Frequency - Material compliance prior to works – GAP40, GAP20
label | Acceptance Criteria - Quary test certificates
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - A
label | Verification Records of Inspection(s) / Test(s) - Quary test certificates
checkpoint | 1.3 Reinforcing
label | Type of inspect / Test and Frequency - Documentation review
label | Acceptance Criteria - Mill Certs
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - A
label | Verification Records of Inspection(s) / Test(s) - Mill certs
section | 2.0 Construction - Kerb
checkpoint | 2.1 Excavation
label | Type of inspect / Test and Frequency - Subgrade checked and uniform
label | Acceptance Criteria - Subgrade uniform
label | Inspection Responsibility: BCL - V
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Photos
checkpoint | 2.2 Bedding
label | Type of inspect / Test and Frequency - Prep and bedding, installed, levelled,
label | Acceptance Criteria - Level 100mm of bedding under kerb
label | Inspection Responsibility: BCL - V
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Photos
checkpoint | 2.3 Reinforcing
label | Type of inspect / Test and Frequency - Bars installed at 400mm centres, top of hook checked for cover to top of concrete
label | Acceptance Criteria - Visual inspection, String out the TOC
label | Inspection Responsibility: BCL - V
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Photo
checkpoint | 2.4 Concrete
label | Type of inspect / Test and Frequency - Delivery docket checked, once per pour. Concrete strength verified.
label | Acceptance Criteria - 20MPA concrete installed, level checked
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Delivery docket, Concrete crushing strength verified
section | 3.0 As-builts
checkpoint | 3.1 Excavation
label | Type of inspect / Test and Frequency - Subgrade checked and uniform
label | Acceptance Criteria - Subgrade uniform
label | Inspection Responsibility: BCL - V
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Photos
checkpoint | 3.2 Bedding
label | Type of inspect / Test and Frequency - Prep and bedding, installed, levelled,
label | Acceptance Criteria - Level 100mm of bedding under kerb
label | Inspection Responsibility: BCL - V
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Photos
checkpoint | 3.3 Reinforcing
label | Type of inspect / Test and Frequency - Bars installed at 400mm centres, top of hook checked for cover to top of concrete
label | Acceptance Criteria - Visual inspection, String out the TOC
label | Inspection Responsibility: BCL - V
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Photo
checkpoint | 3.4 Concrete
label | Type of inspect / Test and Frequency - Delivery docket checked, once per pour. Concrete strength verified.
label | Acceptance Criteria - 20MPA concrete installed, level checked
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Delivery docket, Concrete crushing strength verified
section | 4.0 Asbuilt
checkpoint | 4.1 Redline drawings
label | Type of inspect / Test and Frequency - Complete as built redline drawings of works once complete
label | Acceptance Criteria - Redline drawings capturing changes
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - A
label | Verification Records of Inspection(s) / Test(s) - Redline drawings