## ITP Cover Page
Pavement Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: - 104.3 - Rev 2
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | SH1/29 Intersection Upgrade |  |  |  |  | ITP Number: |  |  | 104.3
Project Number: | [7 empty] | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Pavement Inspection and Test Plan |  |  |  |  | Revision: | 1000 |  | 2
Contract Number: |  |  | 7991 |  |  |  |  | Drawing Sets:
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification:
Quality Specified: |  |  | Z8
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Approval | 2023-12-14 |  | Stuart McCarron |  | First Draft Pavement ITP |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Pavement Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: - 104.3 - Rev 2
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | PAVING ENGINEERS COMMENTS - Date: 22/2/24 | DOWNER RESPONSE - Date:
4.24 | AP65 Subgrade Improvement Layer (SIL) - B/2 Materials (Pavement Type A,B,C)
4.24.01 | Source Property Tests and Sampling | The SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio. | PS 20.4.1 | IANZ Lab Reports | 10,000m3 |  | HP | ENG |  |  | Frequency TBC
4.24.02 | Crushing Resistance | The crushing resistance shall be not less than 100kN when the aggregate is tested in accordance with NZS:4407: Test 3.10
4.24.03 | Weathering Quality Index | The aggregate shall have a weathering quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11.
4.24.04 | CBR | The material shall have a minimum CBR of 40 when compacted to New Zealand heavy compaction standard in accordance with NZS4402 Test 4.1.2 at water content between 4% and 6% by weight of aggregate. CBR testing shall be in accordance with NZS 4407 Test 3.15.
| Production Property Test Sampling | The SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter. | PS 20.4.1 | IANZ Lab Reports |  |  | HP | ENG |  |  | Frequency TBC
4.24.05 | Aggregate Fractions | In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 50% by weight shall have two or more broken faces. It shall be free of organic matter.
4.24.06 | Sand Equilavent | The sand equivalent shall not be less than 30 when the aggregate is tested according to NZS 4407: 1991: Test 3.6. The sand equivalent test may be neglected if the grading test shows less than 4% passing the 75-micron sieve.
4.24.07 | Plasticity Index | The Plasticity Index shall be no less than 8 when the aggregate is tested according to NZS 4407: Test 3.4.
4.24.08 | Clay Index | The Clay Index shall be no less than 5 when the aggregate is tested according to NZS 4407: Test 3.5
4.24.09 | Wet Sieving | When tested according to NZS: 4407: Test 3.8.1 Standard Method by Wet Sieving or Test 3.8.2 Subsidiary Method by Dry Sieving, the grading of the aggregate shall fall within their respective envelopes defined below or as directed by the Engineer.
4.24.10 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for SIL construction shall be the maximum laboratory dry density using Heavy compaction. | TNZ B/02: 2005 - 7.5 PS 20.4.1 | IANZ Lab Reports | 5,000m2 |  | R | PE
4.25 | WHAP65 Sub-Base - B/2 Materials (Pavement Type C)
4.25.01 | Source Property Tests and Sampling | The WHAP65 Sub-Base shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio. | PS 20.5.1.1 | IANZ Lab Reports | 10,000m3 |  | HP | ENG |  |  | Frequency TBC
4.25.02 | Crushing Resistance | The crushing resistance shall be not less than 130kN when the aggregate is tested in accordance with NZS:4407: Test 3.10
4.25.03 | Weathering Quality Index | The aggregate shall have a weathering quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11.
4.25.04 | CBR | The material shall have a minimum CBR of 40 when compacted to New Zealand heavy compaction standard in accordance with NZS4402 Test 4.1.2 at water content between 4% and 6% by weight of aggregate. CBR testing shall be in accordance with NZS 4407 Test 3.15.
| Production Property Test Sampling | The WHAP65 Sub-Base shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter. | PS 20.5.1.1 | IANZ Lab Reports |  |  | HP | ENG |  |  | Frequency TBC
4.25.05 | Aggregate Fractions | In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 50% by weight shall have two or more broken faces. It shall be free of organic matter.
4.25.06 | Sand Equilavent | The sand equivalent shall not be less than 25 when the aggregate is tested according to NZS 4407: 1991: Test 3.6. The sand equivalent test may be neglected if the grading test shows less than 4% passing the 75-micron sieve.
4.25.07 | Wet Sieving | When tested according to NZS: 4407: Test 3.8.1 Standard Method by Wet Sieving or Test 3.8.2 Subsidiary Method by Dry Sieving, the grading of the aggregate shall fall within their respective envelopes defined below or as directed by the Engineer.
4.25.08 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for WHAP65 Sub-Base construction shall be the maximum laboratory dry density using Heavy compaction. | TNZ B/02: 2005 - 7.5 PS 20.5.11 | IANZ Lab Reports | 5,000m2 |  | R | PE
4.26 | GAP65 Subgrade Improvement Layer - B/2 Materials
4.26.01 | Source Property Tests and Sampling | The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio. | PS 20.9.1 | IANZ Lab Reports | 10,000m3 |  | HP | ENG |  |  | Frequency TBC
4.26.02 | Production Property Test Sampling | The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter. | PS 20.9.1 | IANZ Lab Reports |  |  | HP | ENG |  |  | Frequency TBC
4.26.03 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for GAP65 SIL construction shall be the maximum laboratory dry density using Heavy compaction. | TNZ B/02: 2005 - 7.5 PS 20.9.1 | IANZ Lab Reports | 5,000m2 |  | R | PE
4.28 | TNZ M/4 - AP40 Material Approval (Pavement Type C,D)
| Source Property Tests and Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio. | PS 20.8.1 TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986 | IANZ Lab Reports | At least 1 sample every 10,000m3 |  | HP | ENG
4.28.01 | Crushing Resistance | When tested in accordance with NZS 4407 : 1991, Test 3.10, The Crushing Resistance Test, under a load of 130 kN less than 10% fines passing 2.36 mm sieve size shall be produced. | TNZ M/4 Spec Clause 3.3.1
4.28.02 | Weathering Quality Index | The aggregate shall have a quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11. | TNZ M/4 Spec Clause 3.3.2
4.28.03 | CBR | The sample shall be: (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand Vibrating Hammer Compaction Test at Optimum Water Content and; (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%. | TNZ M/4 Spec Clause 3.3.3
| Production Property Test Sampling | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per PS 20.8.1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control. | PS 20.8.1 TNZ M/4: 2006 - 4 NZS 4407 : 1991 | IANZ Lab Reports |  |  | HP | ENG
4.28.04 | Sand Equilavent | The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407: 1991: Test 3.6. | TNZ M/4 Spec Clause 4.2.1.1
4.28.05 | Clay Index | The clay index of the fraction of basecourse passing the 75μm sieve shall not be greater than 3 when the aggregate is tested according to NZS 4407 : 1991, Test 3.5 Clay Index Test. | TNZ M/4 Spec Clause 4.2.1.2
4.28.06 | Plasticity Index | The plasticity index of the fraction of basecourse passing the 425μm sieve shall not be greater than 5 when the aggregate is tested according to NZS 4407 : 1991, Test 3.4 Plasticity Index Test. | TNZ M/4 Spec Clause 4.2.1.3
4.28.07 | Broken Face Content | The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407 : 1991, Test 3.14 Broken Face Test. | TNZ M/4 Spec Clause 4.2.2
4.28.08 | Particle Size Distribution | The particle-size distribution of the aggregate shall conform with the envelope limits defined in both Tables 2 and 3 below, when the aggregate is tested according to NZS 4407 : 1991, Test 3.8.1 Wet Sieving Test. If testing has been performed to show that the dry sieving method is not significantly different to the wet sieving method at 95% confidence limit for the same aggregate then dry sieving method may be used. | TNZ M/4 Spec Clause 4.2.3
4.28.09 | Testing for Layer Compaction - MDD | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | PS 20.8.1 TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 5,000m2 |  | R | PE |  |  | 5000m3 is typically used where source is consistent
4.3 | NZTA M27 2020 - STONE MASTIC ASPHALT MATERIALS
4.30.01 | Coarse Aggregate - Property Tests and Sampling | The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, Bulk SG and Density, Absorption, and Particle Size Distribution | PS 21.3.1 NZTA M27:2020 - 2.1 | IANZ Lab Reports | Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne. |  | H | PE
4.30.02 | Fine Aggregate - Property Tests and Sampling | The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, Bulk SG and Density, Absorption, and Particle Size Distribution | PS 21.3.1 NZTA M27:2020 - 2.1 | IANZ Lab Reports | Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne. |  | H | PE
4.30.03 | Mineral Filler | Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt. | PS 21.3.1 NZTA M27:2020 - 2.2 ASTM D242 | IANZ Lab Reports | Prior to use |  | H | PE
4.30.04 | Bitumen | The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification. | PS 21.3.1 NZTA M27:2020 - 2.4.1 NZTA M01-A | IANZ Lab Reports | Prior to use |  | H | PE
4.30.05 | Mix Design Approval | The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use. | PS 21.3.1 NZTA M27:2020 - 3.1 , 3.6 | Approved Mix Design | Prior to Use |  | HP | ENG
4.31 | Tack Coating Materials
4.31.01 | Bitumen - Quality Testing | The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01. | NZTA M01: 2022 - 6 | IANZ Lab Reports | One test per grade supplied |  | R | SE
4.32 | Sealing Chip Supply
4.32.01 | Sealing Chip - Source Property Tests and Sampling | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV | PS 21.1.1 TNZ M/6: 2019 - 4 | IANZ Lab Reports | Before Supply and Every 10,000m3 Thereafter |  | R | SE
4.32.02 | Sealing Chip - Production Property Test Sampling | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6 | PS 21.1.1 TNZ M/6: 2019 - 5 | IANZ Lab Reports | Every 500m3 |  | R | SE
4.33 | Bitumen Supply
4.33.01 | Bitumen - Quality Testing | The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01. | PS 21.1.1 NZTA M01: 2022 - 6 | IANZ Lab Reports | One test per grade supplied |  | R | SE
4.33.02 | Bitumen - Supply Testing | The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05. | PS 21.1.1 NZTA Q05: 2022 - 6.2 | IANZ Lab Reports | Every 200 tonnes supplied. |  | R | SE
4.33.03 | Adhesion Agents | When used, Adhesion agents must be approved and blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents. | TNZ M13 | Binder Aggregate Adhesion Test | Each Adhesion Agent & Dosage Rate for a Particular Chip Source |  | R | SE
4.33.04 | Sprayer Certification | The binder shall be applied with a bitumen distributor, operated in accordance with BCA E/2, Specification for Performance of Bitumen Distributors administered by the New Zealand Bitumen Contractors' Association Inc. | TNZ P3 TNZ P4 | E2 Cert | Each Sprayer |  | R | SE
SECTION 13 – CONSTRUCTION ACTIVITY – PAVEMENT
13.02 | AP65 Subgrade Improvement Layer Pavement Type A,B,C
13.02.01 | Material Placement | The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout | PS 20.5.2.1 TNZ B/02: 2005 - 5.1 | Survey / Level Checks | Continuous monitoring. |  | I | SV / PE |  |  | Added item as its missing from Spec
13.02.02 | Plateau Density Tests | The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC. | PS 20.5.2.1 TNZ B/02: 2005 - 7.5 | MDD and Plateau Reports | 1 test per 5,000m2 |  | HP | ENG |  |  | Added item as its missing from Spec
13.02.03 | SIL Pavement Layer Compaction | Mean Value ≥ 95 Minimum Value ≥ 92 | PS 20.5.2.1 TNZ B/02: 2005 - 7.6 | NDM Report | Min 5 Tests per lot 1000m2 max lot size |  | HP | ENG |  |  | Added item as its missing from Spec
13.02.04 | SIL Layer thickness. | The SIL layer shall be monitored for Layer thickness. | PS 20.5.2.1 TNZ B/02: 2005 - 7.5 | Survey / Level Checks | 1 test per 20m |  | W | SV / PE |  |  | Added item as its missing from Spec
13.02.05 | Surface Shape | The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual. | PS 20.5.2.1 TNZ B/02: 2005 - 7.7 | Survey / Straight edge Report | Prior to sealing |  | I | SV / PE |  |  | Added item as its missing from Spec
13.02.06 | Holding Water | No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1% | PS 20.5.2.1 TNZ B/02: 2005 - 7.7 | Survey | Prior to sealing |  | I | SV / PE |  |  | Added item as its missing from Spec
13.02.07 | Proof Rolling | SIL layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass. | PS 20.5.2.2 | Site Records | Before proceeding with works |  | HP | ENG |  |  | Added item as its missing from Spec
13.02.08 | Benkelman Beam | be ˂ 1.5mm (95th%) and max ≤1.8mm | B10 Notes | Report | All Lanes |  | R | SE
13.03 | Construction Of Unbound WHAP65 Sub-Base Pavement Type C
13.03.01 | Material Placement | The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout | PS 20.5.2.1 TNZ B/02: 2005 - 5.1 | Survey / Level Checks | Continuous monitoring. |  | I | SV / PE
13.03.02 | Plateau Density Tests | The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC. | PS 20.5.2.1 TNZ B/02: 2005 - 7.5 | MDD and Plateau Reports | 1 test per 5,000m2 |  | HP | ENG
13.03.04 | WHAP65 Sub-Base Pavement Layer Compaction | Mean Value ≥ 95 Minimum Value ≥ 92 | PS 20.5.2.1 TNZ B/02: 2005 - 7.6 | NDM Report | Min 5 Tests per lot 1000m2 max lot size |  | HP | ENG
13.03.05 | WHAP65 Sub-Base Layer thickness. | The Sub-basecourse shall be monitored for Layer thickness. | PS 20.5.2.1 TNZ B/02: 2005 - 7.5 | Survey / Level Checks | 1 test per 20m |  | W | SV / PE
13.03.06 | Surface Shape | The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual. | PS 20.5.2.1 TNZ B/02: 2005 - 7.7 | Survey / Straight edge Report | Prior to sealing |  | I | SV / PE
13.03.07 | Holding Water | No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1% | PS 20.5.2.1 TNZ B/02: 2005 - 7.7 | Survey | Prior to sealing |  | I | SV / PE
13.03.08 | Proof Rolling | Sub-base layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass. | PS 20.5.2.2 | Site Records | Before proceeding with works |  | HP | ENG
13.07 | Construction Of Basecourse – NZTA M/4 AP40 Pavement Type C
13.07.01 | Material Placement | The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout | PS 20.8.1 TNZ B/02: 2005 - 5.1 | Survey / Level Checks | Continuous monitoring. |  | I | SV / PE
13.07.02 | Greenfield Sites Plateau Density Tests | The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. | PS 20.8.1 TNZ B/02: 2005 - 7.5 | MDD and Plateau Reports | 1 test per 5,000m2 |  | HP | ENG
13.07.03 | Overlay Sites Plateau Density Tests | The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC. | PS 20.8.1 TNZ B/02: 2005 - 7.5 | MDD and Plateau Reports | 1 test per 5,000m2 |  | HP | ENG
13.07.04 | Basecourse Pavement Layer Compaction | Mean Value ≥ 98 Minimum Value ≥ 95 | PS 20.8.1 TNZ B/02: 2005 - 7.6 | NDM Report | Min 5 Tests per lot 1000m2 max lot size |  | HP | ENG
13.07.05 | Basecourse Layer thickness. | The Basecourse shall be monitored for Layer thickness. | PS 20.8.1 TNZ B/02: 2005 - 7.5 | Survey / Level Checks | 1 test per 20m |  | W | SV / PE
13.07.06 | Surface Shape | The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.. | PS 20.8.1 TNZ B/02: 2005 - 7.7 | Survey / Straight edge Report | Prior to sealing |  | I | SV / PE
13.07.07 | Holding Water | No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1% | PS 20.8.1 TNZ B/02: 2005 - 7.7 | Survey | Prior to sealing |  | I | SV / PE
13.07.08 | Running Course | If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface. | PS 20.8.1 TNZ B/02: 2005 - 10.1 | Site Notes | Prior to sealing |  | S | SUP
13.07.09 | Surface Finish post sweeping | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept. | PS 20.8.1 TNZ B/02: 2005 - 7.8 | Photos | Prior to sealing |  | R | PE
13.07.10 | NAASRA roughness | The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. | PS 20.8.1 TNZ B/02: 2005 - 7.7 | Test Report | Prior to sealing |  | HP | ENG
13.07.11 | Presealing Requirements | The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 60%. | PS 20.8.1 TNZ B/02: 2005 - 12 | NDM Report | Min 5 Tests per lot 1000m2 max lot size |  | HP | ENG
SECTION 14 – CONSTRUCTION ACTIVITY – SURFACING
14.02 | Chipsealing
14.02.01 | Sealing Procedure | Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, P4, P17, and Q/1. | M/1, M/6, M/13, P/3, P4, P17, and Q/1. | Methodology / Construction Pack | Prior to Sealing |  | R | SE
14.02.02 | Seal Design / Binder application rate | The sealing design including binder application rate to suit the surface conditions shall be approved by the Design Engineer prior to sealing. | TNZ P3 TNZ P4 | Approved Seal Design | Prior to Sealing |  | HP | ENG
14.02.03 | Presealing Requirements | The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 60%. | TNZ B02 | NDM Report | Min 5 Tests Per Lot 1000m2 Max Lot Size |  | HP | ENG
14.02.04 | PreSeal inspection | The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site. | TNZ P3 TNZ B02 | Hold Point Release | A minimum of 24 hours’ notice of intention to seal. |  | HP | ENG
14.02.05 | Spray Temperature | The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC. | TNZ P3 | Site Notes | Prior to Seal |  | I | SE
14.02.06 | Binder Sampling | A minimum of two samples per bitumen distributor load shall be taken. The first of these samples shall be taken at the end of the initial spray run and the other immediately before the final spray run. Bitumen to be tested on Engineers instruction. | TNZ P3 | Site Notes | Each Worksite |  | I | SE
14.02.07 | Quantity of Binder Sprayed | The quantity of binder sprayed in any spray run, measured by dipstick reading, shall not vary from the amount directed by more than 50 litres plus 4% of the amount directed. | TNZ P3 | Site Notes | Every Spray Run |  | I | SE
14.02.08 | Chip Application | All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying. | TNZ P3 | Site Notes | Every Spray Run |  | I | SE
14.02.09 | Surplus Chip Removal | Surplus chips shall be removed from the sealed surface prior to the removal of the temporary speed restriction signs. | TNZ P3 | Site Notes | 24 hours of Completion of any Section of Seal. |  | R | SE
14.02.10 | Post Seal Inspections | The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed. | TNZ P3 | Engineers Acceptance | Prior to TM Removal and After Final Sweeping |  | HP | ENG
14.02.11 | Chipseal Repairs | The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used. | TNZ P3 | Approved Repair Methodology | Prior to Repairs |  | HP | ENG
14.03 | Construction Activity - NZTA M10 - Specification for dense-graded asphaltic concrete
14.03.01 | Construction Trail | Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. Asphalt manufactured in the production trial can also be used in the construction trial if it meets the requirements of the specification. | PS 21.3.1 NZTA M10:2020 - 7 | Test Results | As Required, two days before the site work is due to commence. |  | I | PE
14.03.02 | Paving Plan | The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement. | NZTA M10:2020 - 8, 9 | Construction Work Pack | 7 days prior to construction of the asphalt pavement. |  | HP | ENG
14.03.03 | Preparation of Area to be Paved | The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected. | NZTA M10:2020 - 9 | Site Notes | Pre Seal |  | I | PE
14.03.04 | Protection of Services | The Contractor shall prevent tack coat, binder, aggregate, asphalt or other material used on the work from entering, adhering or obstructing gratings, hydrants, valve boxes, inspection pit covers, kerbs and other road fixtures | NZTA M10:2020 | Environmental Inspections | Daily |  | R | SE
14.03.05 | Ambient Conditions for Placing | Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C, for SAC the minimum temperature is 5°C | NZTA M10:2020 | Site Notes | Pre Seal |  | H | SE |  |  |  | Add that for SAC the minimum temperature is 5°C
14.03.06 | Tack Coating | Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. | NZTA M10:2020 - 9 | Site Notes | Prior to Paving |  | I | PE
14.03.07 | Asphalt Production Conformance | Conforming Grading and Binder content by mass | NZTA M10:2020 -Table 3.1 & 5.1 | Test Results | 1 per 200T Min 3 tests per mix |  | I | PE |  |  |  | Add volumetric testing at frequency of 1/600t, refer clause 5.2 and table 5.2 for frequency and tolerances
14.03.08 | Core Thickness | The layer thickness determined from measurements on the cores LCV of no less than the specified thickness - refer clause 9.7 | NZTA M10:2020 | Lab Report | min 8 per lot (day) (1 for every 300 m²) |  | R | SE |  |  |  | This is incorrect, the -0 to +10mm is the M/10: 2014 requirement, the 2020 requirement is LCV of no less than the specified thickness - refere clause 9.7
14.03.09 | Mat Density | 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300m² with a minimum of eight cores representing each lot | ASTM D5361 NZTA M10:2020 - 9 | Cores | min 8 per lot (day) (1 for every 300 m²) |  | R | PE
14.03.10 | Joint Density | 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100m of joint with a minimum of three representing each lot | NZTA M10:2020 - 9 | Cores | min 3 per lot (day) (1 per 100 m of joint) |  | R | PE
14.03.11 | Density Testing | The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2 | NZTA M10:2020 - 9 | Lab Report | within 24 hours of them being cut from the pavement |  | I | PE
14.03.12 | NDM Density | NDMs are to be completed at the time of placing to ensure compliance when cores are taken | NZTA M10:2020 - 9 | IANZ Lab Report | min 8 per lot (day) |  | I | PE
14.03.13 | Transverse truth of the surface | The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge. | NZTA M10:2020 - 9 | Site Notes | Post Seal |  | I | SE
14.03.14 | Finished Pavement Level, Alignment, and Thickness | The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements. | NZTA M10:2020 - 10 | Survey | Continuous thought construction |  | I | SE
14.04 | Construction Activity - NZTA M27 - Specification for stone mastic asphalt.
14.04.01 | Construction Trail | Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. SMA manufactured in the production trial can also be used in the construction trial provided that it meets the requirements of the specification. | PS 21.2.1 NZTA M27:2020 - 7 | Test Results | As Required, two days before the site work is due to commence. |  | I | PE
14.04.02 | Paving Plan | The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement. | NZTA M27:2020 - 8, 9 | Construction Work Pack | 7 days prior to construction of the asphalt pavement. |  | HP | ENG
14.04.03 | Preparation of Area to be Paved | The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected. | NZTA M27:2020 - 9 | Site Notes | Pre Seal |  | I | PE
14.04.04 | Protection of Services | The Contractor shall prevent tack coat, binder, aggregate, asphalt or other material used on the work from entering, adhering or obstructing gratings, hydrants, valve boxes, inspection pit covers, kerbs and other road fixtures | NZTA M27:2020 - 9 | Environmental Inspections | Daily |  | R | SE
14.04.05 | Ambient Conditions for Placing | Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C, | NZTA M27:2020 - 9 | Site Notes | Pre Seal |  | H | SE
14.04.06 | Tack Coating | Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. Where SMA is to be spread over clean, freshly placed asphalt, the Engineer can direct the Contractor to omit the tack coat. | NZTA M27:2020 - 9 | Site Notes | Prior to Paving |  | I | PE
14.04.07 | Asphalt Production Conformance | Conforming Grading and Binder content by mass | NZTA M27:2020 - Table 3.1 & 5.1 | Test Results | 1 per 200T Min 3 tests per mix |  | I | PE |  |  |  | Add volumetric testing at frequency of 1/600t, refer clause 5.2 and table 5.2 for frequency and tolerances
14.04.08 | Core Thickness | The M/27:2020 requirement is LCV of no less than the specified thickness - refere clause 9.7 | NZTA M27:2020 - | Lab Report | min 8 per lot (day) (1 for every 300 m²) |  | R | SE |  |  |  | This is incorrect, theM/27:2020 requirement is LCV of no less than the specified thickness - refere clause 9.7
14.04.09 | Mat Density | 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot | ASTM D5361 NZTA M27:2020 - 9 | Cores | min 8 per lot (day) (1 for every 300 m²) |  | R | PE
14.04.10 | Joint Density | 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100 m of joint with a minimum of three representing each lot | NZTA M27:2020 - 9 | Cores | min 3 per lot (day) (1 per 100 m of joint) |  | R | PE
14.04.11 | Density Testing | The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2 | NZTA M27:2020 - 9 | Lab Report | within 24 hours of them being cut from the pavement |  | I | PE
14.04.12 | NDM Density | NDMs are to be completed at the time of pacing to ensure compile when cores are taken | NZTA M27:2020 - 9 | IANZ Lab Report | min 8 per lot (day) |  | I | PE
14.04.13 | Transverse truth of the surface | The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge. | NZTA M27:2020 - 9 | Site Notes | Post Seal |  | I | SE
14.04.14 | Finished Pavement Level, Alignment, and Thickness | The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements. | NZTA M27:2020 - 10 | Survey | Continuous thought construction |  | I | SE
14.05 | Roughness
14.05.01 | For a Chip Sealed Surface | Target is an average of 60 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 70 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km. | PS 21.4.1 | Test Report | Prior to sealing |  | HP | ENG
14.05.02 | For an Asphaltic Concrete Surface | Target is an average of 50 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 60 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km. | PS 21.4.1 | Test Report | Prior to sealing |  | HP | ENG
14.06 | Skid Resistance
14.06.01 | Skid Resistance | The surfacing shall meet the requirements specified in the Transport Agency’s T10:2010 Skid Resistance Deficiency Investigation and Treatment Selection, and any other subsequent amendments. | PS 21.5.1 | Prior to Project Completion | Prior to sealing |  | HP | ENG

## ITP Register
Inspection and Testing Plan Register
Project: SH1/29 Intersection Upgrade
Document Revision & Date: Rev: 01 - Date: 01/12/2021
Inspection and Testing Plan Register | [9 empty] | Rev: 01 | Date: 01/12/2021
ITP No. | Sub ITP No. | Master ITP Revision | Discipline | Description | Work Area / Chainage / Lot: | Work Commencement Date: | Work Completion Date | Work Status | Owner | Submission Status | Comments
1 |  | A |  | Master ITP
101 |  | A |  | Earthworks ITP
102 |  | A |  | Stormwater ITP
103 |  | A |  | Structures ITP
104.3 |  | A |  | Pavement ITP