## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Pavement - Type A - 104.1 - Rev 2 | itp |  |  |  |  | ITP - Pavement - Type A - 104.1 - Rev 2
section | 4.23 General Pavement Materials
checkpoint | 4.23.01 - TX180 Triaxial Geogrid
label | Acceptance / Conformance Criteria - The Contractor is to supply the product details to the Engineer for approval prior to installation on site.
label | Standard / Specification - PS 20.3.1
label | Verifying Document - Datasheet
label | Frequency - Each Item
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.24 AP65 Subgrade Improvement Layer (SIL) - B/2 Materials (Pavement Type A,B,C)
checkpoint | 4.24.01 - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
label | Standard / Specification - PS 20.4.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.24.02 - Crushing Resistance
label | Acceptance / Conformance Criteria - The crushing resistance shall be not less than 100kN when the aggregate is tested in accordance with NZS:4407: Test 3.10
label | Frequency - 10,000m3
checkpoint | 4.24.03 - Weathering Quality Index
label | Acceptance / Conformance Criteria - The aggregate shall have a weathering quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11.
label | Frequency - 10,000m3
checkpoint | 4.24.04 - CBR
label | Acceptance / Conformance Criteria - The material shall have a minimum CBR of 40 when compacted to New Zealand heavy compaction standard in accordance with NZS4402 Test 4.1.2 at water content between 4% and 6% by weight of aggregate. CBR testing shall be in accordance with NZS 4407 Test 3.15.
label | Frequency - 10,000m3
checkpoint | Production Property Test Sampling
label | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
label | Standard / Specification - PS 20.4.1
label | Verifying Document - IANZ Lab Reports
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.24.05 - Aggregate Fractions
label | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 50% by weight shall have two or more broken faces. It shall be free of organic matter.
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.24.06 - Sand Equilavent
label | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 30 when the aggregate is tested according to NZS 4407: 1991: Test 3.6. The sand equivalent test may be neglected if the grading test shows less than 4% passing the 75-micron sieve.
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.24.07 - Plasticity Index
label | Acceptance / Conformance Criteria - The Plasticity Index shall be no less than 8 when the aggregate is tested according to NZS 4407: Test 3.4.
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.24.08 - Clay Index
label | Acceptance / Conformance Criteria - The Clay Index shall be no less than 5 when the aggregate is tested according to NZS 4407: Test 3.5
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.24.09 - Wet Sieving
label | Acceptance / Conformance Criteria - When tested according to NZS: 4407: Test 3.8.1 Standard Method by Wet Sieving or Test 3.8.2 Subsidiary Method by Dry Sieving, the grading of the aggregate shall fall within their respective envelopes defined below or as directed by the Engineer.
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.24.10 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for SIL construction shall be the maximum laboratory dry density using Heavy compaction.
label | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.4.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 4.26 GAP65 Subgrade Improvement Layer - B/2 Materials
checkpoint | 4.26.01 - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
label | Standard / Specification - PS 20.9.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.26.02 - Production Property Test Sampling
label | Acceptance / Conformance Criteria - The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
label | Standard / Specification - PS 20.9.1
label | Verifying Document - IANZ Lab Reports
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.26.03 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for GAP65 SIL construction shall be the maximum laboratory dry density using Heavy compaction.
label | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.9.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 4.29 NZTA M10 2020 - DENSE GRADED ASPHALTIC CONCRETE MATERIALS
checkpoint | 4.29.01 - Coarse Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, and Particle Size Distribution
label | Standard / Specification - PS 21.2.1 NZTA M10:2020 - 2.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.29.02 - Fine Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, and Particle Size Distribution
label | Standard / Specification - PS 21.2.1 NZTA M10:2020 - 2.1.
label | Verifying Document - IANZ Lab Reports
label | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.29.03 - Mineral Filler
label | Acceptance / Conformance Criteria - Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt.
label | Standard / Specification - PS 21.2.1 NZTA M10:2020 - 2.2 ASTM D242
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.29.04 - Bitumen
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
label | Standard / Specification - PS 21.2.1 NZTA M10:2020 - 2.3.1, NZTA M01-A
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.29.05 - Mix Design Approval
label | Acceptance / Conformance Criteria - The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use.
label | Standard / Specification - PS 21.2.1, PS 20.7.5 NZTA M10:2020 - 3.1 , 3.6
label | Verifying Document - Approved Mix Design
label | Frequency - No less than 10 working days prior to the pre-paving planning meeting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.30 NZTA M27 2020 - STONE MASTIC ASPHALT MATERIALS
checkpoint | 4.30.01 - Coarse Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, Bulk SG and Density, Absorption, and Particle Size Distribution
label | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.30.02 - Fine Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, Bulk SG and Density, Absorption, and Particle Size Distribution
label | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.30.03 - Mineral Filler
label | Acceptance / Conformance Criteria - Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt.
label | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.2 ASTM D242
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.30.04 - Bitumen
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
label | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.4.1, NZTA M01-A
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.30.05 - Mix Design Approval
label | Acceptance / Conformance Criteria - The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use.
label | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 3.1 , 3.6
label | Verifying Document - Approved Mix Design
label | Frequency - Prior to Use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.31 Tack Coating Materials
checkpoint | 4.31.01 - Bitumen - Quality Testing
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
label | Standard / Specification - NZTA M01: 2022 - 6
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test per grade supplied
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.32 Sealing Chip Supply
checkpoint | 4.32.01 - Sealing Chip - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
label | Standard / Specification - PS 21.1.1 TNZ M/6: 2019 - 4
label | Verifying Document - IANZ Lab Reports
label | Frequency - Before Supply and Every 10,000m3 Thereafter
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.32.02 - Sealing Chip - Production Property Test Sampling
label | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
label | Standard / Specification - PS 21.1.1 TNZ M/6: 2019 - 5
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 500m3
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.33 Bitumen Supply
checkpoint | 4.33.01 - Bitumen - Quality Testing
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
label | Standard / Specification - PS 21.1.1 NZTA M01: 2022 - 6
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test per grade supplied
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.33.02 - Bitumen - Supply Testing
label | Acceptance / Conformance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
label | Standard / Specification - PS 21.1.1 NZTA Q05: 2022 - 6.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 200 tonnes supplied.
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.33.03 - Adhesion Agents
label | Acceptance / Conformance Criteria - When used, Adhesion agents must be approved & blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents.
label | Standard / Specification - TNZ M13
label | Verifying Document - Binder Aggregate Adhesion Test
label | Frequency - Each Adhesion Agent and Dosage Rate for a Particular Chip Source
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.33.04 - Sprayer Certification
label | Acceptance / Conformance Criteria - The binder shall be applied with a bitumen distributor, operated in accordance with BCA E/2, Specification for Performance of Bitumen Distributors administered by the New Zealand Bitumen Contractors' Association Inc.
label | Standard / Specification - TNZ P3 TNZ P4
label | Verifying Document - E2 Cert
label | Frequency - Each Sprayer
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.34 Hi-Lab 65 Material Pavement Type A,B
checkpoint | Hi-Lab 65 - Source Properties
label | Acceptance / Conformance Criteria - The Hi-Lab aggregate shall be crushed from quarried rock and consist of hard, sound material of uniform quality, free from soft or disintegrated stone or other deleterious material.
label | ○ Source property testing shall beOnly one set is needed if HI-LAB40 and 65 come for the same source
label | Standard / Specification - NZTA B10 - 2.2.1, 2.3.5
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test for every 10,000m³
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.34.01 - Crushing Resistance
label | Acceptance / Conformance Criteria - < 10% Fines @ 160kN
label | Standard / Specification - NZS 4407 Test 3.10
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test for every 10,000m³
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.34.02 - Weathering Quality Index
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - NZS 4407 Test 3.11
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test for every 10,000m³
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.34.03 - Ethylene Glycol Accelerated Weathering
label | Acceptance / Conformance Criteria - Proportional change < 30%
label | ○ Note: If the result for the source rock exceeds 30%, further testing to detect the presence of smectite clays shall be carried out using X-ray diffraction. If the aggregate is shown contain trace amounts only of smectite clays (i.e. XRD <100 counts) then the source rock may be considered compliant with this criterion
label | Standard / Specification - NZTA T20
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test for every 10,000m³
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.34.04 - Solid Density
label | Acceptance / Conformance Criteria - The solid density of the Hi-Lab shall be determined in accordance with NZS 4407 Test 3.7.1 Solid Density of Aggregate Particles.
label | Standard / Specification - NZS 4407 Test 3.7.1 Solid Density of Aggregate Particles
label | Verifying Document - IANZ Lab Reports
label | Frequency - Two tests per aggregate source then one test every 5,000m³
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Hi-Lab 65 - Production Properties
label | Acceptance / Conformance Criteria - The Hi-Lab 65 shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Broken Faces, Aggregate Flakiness Value, and Grading.
label | Standard / Specification - NZTA B10 - 1.2.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - Test for every 1,000 tonnes of material produced
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.34.05 - Two Broken Faces
label | Acceptance / Conformance Criteria - 100% of sample
label | ○ Note: Hi-Lab aggregate produced from a hard rock quarry source using angular and broken feedstock need not be tested for Broken Faces Content which may be assumed to be 100%.
label | Standard / Specification - NZS 4407 Test 3.14
label | Verifying Document - IANZ Lab Reports
label | Frequency - Test for every 1,000 tonnes of material produced
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.34.06 - Clay Index (<0.075mm)
label | Acceptance / Conformance Criteria - 5 maximum
label | Standard / Specification - NZS 4407 Test 3.5
label | Verifying Document - IANZ Lab Reports
label | Frequency - Test for every 1,000 tonnes of material produced
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.34.07 - Plasticity Index
label | Acceptance / Conformance Criteria - 8 maximum
label | Standard / Specification - NZS 4407 Test
label | Verifying Document - IANZ Lab Reports
label | Frequency - Test for every 1,000 tonnes of material produced
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.34.08 - Aggregate Particle Size Distribution
label | Acceptance / Conformance Criteria - The particle size distribution during production of the blended Hi-Lab products shall comply with the limits in Table 0.3.
label | ○ A minimum sample of 90kg of aggregate shall be used for each test.
label | Test results shall be evaluated as follows:
label | (a) The rolling average results of five consecutive test samples shall be within the upper and lower limits for each test sieve
label | (b) No individual test result shall be outside the envelope formed by the lower buffer zone and the upper limit.
label | ○ Note: Experience has shown that a blending plant with a minimum of three component feed bins is required to produce a consistently compliant Hi-Lab aggregate product.
label | – – – – – – – – – – – – – –
label | Table 0.3 Hi-Lab 65 Particle Size Distribution Limits
label | Sieve Size (mm) ¦¦ Lower Buffer / Lower Limit / Upper Limit
label | – – – – – – – – – – – – – –
label | 63.0 ¦¦ - / 95 / 100
label | 37.5 ¦¦ 35 / 40 / 50
label | 19 ¦¦ 15 / 20 / 30
label | 9.5 ¦¦ 10 / 12 / 16
label | 4.75 ¦¦ 9 / 10 / 14
label | 2.36 ¦¦ 6 / 7 / 12
label | 1.18 ¦¦ 4 / 5 / 10
label | 0.075 ¦¦ - / 0 / 6
label | – – – – – – – – – – – – – –
label | Standard / Specification - NZS 4407 Test 3.8.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Test samples shall be drawn and tested for every 1,000 tonnes produced. A minimum of 5 production test samples shall be drawn and tested for any one production lot.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.34.09 - Aggregate Flakiness Value
label | Acceptance / Conformance Criteria - The percentage of flaky particles for each of the aggregate test fractions coarser than 9.50mm specified by AS 1141.15 Table 1 shall be determined and reported, and the Flakiness Value for each size fraction comply with the minimum requirement of Table 0.5:
label | – – – – – – – – – – – – – –
label | Table 0.5 Aggregate Flakiness Value Requirement for Each Fraction
label | Aggregate Grade ¦¦ Test Method ¦¦ Requirement
label | – – – – – – – – – – – – – –
label | Hi Lab 65 ¦¦ AS 1141.15 ¦¦ < 30%
label | Hi-Lab 40 ¦¦ AS 1141.15 ¦¦ < 30%
label | – – – – – – – – – – – – – –
label | Standard / Specification - Method of AS 1141.15
label | Verifying Document - IANZ Lab Reports
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.35 Hi-Lab 40 Material Pavement Type A
checkpoint | Hi-Lab 40 - Source Properties
label | Acceptance / Conformance Criteria - The Hi-Lab aggregate shall be crushed from quarried rock and consist of hard, sound material of uniform quality, free from soft or disintegrated stone or other deleterious material.
label | ○ Source property testing shall beOnly one set is needed if HI-LAB40 and 65 come for the same source
label | Standard / Specification - NZTA B10 - 2.2.1, 2.3.5
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test for every 10,000m³
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.35.01 - Crushing Resistance
label | Acceptance / Conformance Criteria - < 10% Fines @ 160kN
label | Standard / Specification - NZS 4407 Test 3.10
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test for every 10,000m³
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.35.02 - Weathering Quality Index
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - NZS 4407 Test 3.11
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test for every 10,000m³
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.35.03 - Ethylene Glycol Accelerated Weathering
label | Acceptance / Conformance Criteria - Proportional change < 30%
label | ○ Note: If the result for the source rock exceeds 30%, further testing to detect the presence of smectite clays shall be carried out using X-ray diffraction. If the aggregate is shown contain trace amounts only of smectite clays (i.e. XRD <100 counts) then the source rock may be considered compliant with this criterion
label | Standard / Specification - NZTA T20
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test for every 10,000m³
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.35.04 - Hi-Lab 40 - Solid Density Testing
label | Acceptance / Conformance Criteria - The solid density of the Hi-Lab shall be determined in accordance with NZS 4407 Test 3.7.1 Solid Density of Aggregate Particles.
label | Standard / Specification - NZS 4407 Test 3.7.1 Solid Density of Aggregate Particles
label | Verifying Document - IANZ Lab Reports
label | Frequency - Two tests per aggregate source then one test every 5,000m³
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Hi-Lab 40 - Production Properties
label | Acceptance / Conformance Criteria - The Hi-Lab 40 shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Broken Faces, Aggregate Flakiness Value, and Grading.
label | Standard / Specification - NZTA B10 - 1.2.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Test for every 1,000 tonnes of material produced
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.35.05 - Two Broken Faces
label | Acceptance / Conformance Criteria - 100% of sample
label | ○ Note: Hi-Lab aggregate produced from a hard rock quarry source using angular and broken feedstock need not be tested for Broken Faces Content which may be assumed to be 100%.
label | Standard / Specification - NZS 4407 Test 3.14
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.35.06 - Clay Index (<0.075mm)
label | Acceptance / Conformance Criteria - 5 maximum
label | Standard / Specification - NZS 4407 Test 3.5
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.35.07 - Plasticity Index
label | Acceptance / Conformance Criteria - 8 maximum
label | Standard / Specification - NZS 4407 Test
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.35.08 - Aggregate Particle Size Distribution
label | Acceptance / Conformance Criteria - The particle size distribution during production of the blended Hi-Lab products shall comply with the limits in Table 0.4.
label | ○ A minimum sample of 90kg of aggregate shall be used for each test.
label | Test results shall be evaluated as follows:
label | (a) The rolling average results of five consecutive test samples shall be within the upper and lower limits for each test sieve
label | (b) No individual test result shall be outside the envelope formed by the lower buffer zone and the upper limit.
label | ○ Note: Experience has shown that a blending plant with a minimum of three component feed bins is required to produce a consistently compliant Hi-Lab aggregate product.
label | – – – – – – – – – – – – – –
label | Table 0.4 Hi-Lab 40 Particle Size Distribution Limits
label | Sieve Size (mm) ¦¦ Lower Buffer / Lower Limit / Upper Limit
label | – – – – – – – – – – – – – –
label | 37.5 ¦¦ - / 90 / 100
label | 19.0 ¦¦ 20 / 25 / 35
label | 9.5 ¦¦ 13 / 15 / 20
label | 4.75 ¦¦ 9 / 10 / 15
label | 2.36 ¦¦ 6 / 7 / 12
label | 1.18 ¦¦ 3 / 4 / 10
label | 0.075 ¦¦ - / 0 / 6
label | – – – – – – – – – – – – – –
label | Standard / Specification - NZS 4407 Test 3.8.2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.35.09 - Aggregate Flakiness Value
label | Acceptance / Conformance Criteria - The percentage of flaky particles for each of the aggregate test fractions coarser than 9.50mm specified by AS 1141.15 Table 1 shall be determined and reported, and the Flakiness Value for each size fraction comply with the minimum requirement of Table 0.5:
label | – – – – – – – – – – – – – –
label | Table 0.5 Aggregate Flakiness Value Requirement for Each Fraction
label | Aggregate Grade ¦¦ Test Method ¦¦ Requirement
label | – – – – – – – – – – – – – –
label | Hi Lab 65 ¦¦ AS 1141.15 ¦¦ < 30%
label | Hi-Lab 40 ¦¦ AS 1141.15 ¦¦ < 30%
label | – – – – – – – – – – – – – –
label | Standard / Specification - Method of AS 1141.15
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.36 Hi-Lab General Material (Pavement Type A,B)
checkpoint | 4.36.01 - Portland Cement Stabilising Agent
label | Acceptance / Conformance Criteria - Cement shall comply with NZS 3122 Specification for Portland and blended cements (general and special purpose) for GP, GB, LH
label | ○ General purpose Portland cement, type GP, shall be used unless otherwise specified in the Contract Documents. Note that high-early strength cement, type HE, shall not be used as a stabilising agent.
label | Standard / Specification - NZTA B10 - 2.4.1
label | Verifying Document - Datasheet
label | Frequency - Prior to Use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.36.02 - Water Supply
label | Acceptance / Conformance Criteria - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening or strength of the stabilised material. Water from sources other than public supply shall have its suitability established to the satisfaction of the Engineer.
label | Standard / Specification - NZTA B10 - 2.4.2
label | Verifying Document - Site Records
label | Frequency - Prior to Use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.36.03 - PAP 7 - Choking Aggregate
label | Acceptance / Conformance Criteria - PAP 7 crusher dust choking aggregate can be a by-product of the Hi-Lab crushing or sealing chip production with all passing the 9.5mm sieve. The aggregate source properties (crushing resistance and quality of fines) shall be equal to or better than the required source properties for Hi-Lab aggregate.
label | ○ The grading of the running course shall confirm with figure below when tested in the same manner as required for the parent basecourse
label | ○ The quality of fines (those materials passing 75µm) shall be not less than that required for the basecourse below the running course when tested in accordance with the requirements for the basecourse. This requirement shall be waived for running course where its percentage passing 7 µm sieve is less than 1.5% and the percentage passing the 150µm sieve is less than 2.0%.
label | – – – – – – – – – – – – – –
label | Test Sieve Aperture ¦¦ Percent Passing
label | – – – – – – – – – – – – – –
label | 19 mm ¦¦ 100%
label | 4.75 mm ¦¦ 60% maximum
label | 600 µm ¦¦ 23% maximum
label | 75 µm ¦¦ 8% maximum
label | – – – – – – – – – – – – – –
label | Standard / Specification - NZTA B10 - 2.3.6
label | Verifying Document - IANZ Lab Reports
label | Frequency - Test for every 1,000 tonnes of material produced
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 13.01 Triaxial Geogrid
checkpoint | 13.01.01 - Triaxial Geogrid storage and Inspection
label | Acceptance / Conformance Criteria - The geogrid is to be checked once delivered to site to confirm there is no damage that may effect its performance. The material shall be stored out of direct sunlight to ensure no degradation of the material occurs prior to installation.
label | Standard / Specification - PS 20.3.1
label | Verifying Document - Site Records
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 13.01.02 - Triaxial Geogrid Installation
label | Acceptance / Conformance Criteria - The triaxial grid is to be installed in accordance with the manufacturer’s specification. Where overlaps are required they shall confirm with the manufacturers installation specification.
label | Standard / Specification - PS 20.3.1
label | Verifying Document - Site Records
label | Frequency - During Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 13.02 AP65 Subgrade Improvement Layer Pavement Type A,B,C
checkpoint | 13.02.01 - Material Placement
label | Acceptance / Conformance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.02.02 - Plateau Density Tests
label | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC.
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
label | Verifying Document - MDD and Plateau Reports
label | Frequency - 1 test per 5,000m2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.02.03 - SIL Pavement Layer Compaction
label | Acceptance / Conformance Criteria - The compaction density for the lower layers must be at least 81% of aggregate Solid Density. The nuclear gauge in direct transmission is used for reporting in-situ density.
label | Standard / Specification - NZTA B10 Notes
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.02.04 - SIL Layer thickness.
label | Acceptance / Conformance Criteria - The SIL layer shall be monitored for Layer thickness.
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Verification Activity: Activity - W
label | Verification Activity: By - SV / PE
checkpoint | 13.02.05 - Surface Shape
label | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey / Straight edge Report
label | Frequency - Prior to sealing
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.02.06 - Holding Water
label | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey
label | Frequency - Prior to sealing
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.02.07 - Proof Rolling
label | Acceptance / Conformance Criteria - SIL layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass.
label | Standard / Specification - PS 20.5.2.2
label | Verifying Document - Site Records
label | Frequency - Before proceeding with works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.02.08 - Benkelman Beam
label | Acceptance / Conformance Criteria - be ˂ 1.5mm (95th%) and max ≤1.8mm
label | Standard / Specification - B10 Notes
label | Verifying Document - Report
label | Frequency - All Lanes
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 13.04 Hi-Lab Plant and Staff
checkpoint | 13.04.01 - Plant for Supply of Cement
label | Acceptance / Conformance Criteria - For areas greater than 500m², cement shall be delivered to the site in purpose built bulk tankers unless otherwise approved by the Engineer. Each bulk tanker shall be issued a Certificate of Loading that contains the following information which shall form part of the project quality plan.
label | Standard / Specification - NZTA B10 - 3.1
label | Verifying Document - Certificate of Loading
label | Frequency - Each Tanker For areas greater than 500m²
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.04.02 - Plant for Spreading Chemical Stabilising Agents
label | Acceptance / Conformance Criteria - The spreading equipment shall be capable of varying the spread width to cater for different road widths. The spread rate should be consistent along the spread width of the equipment.
label | Standard / Specification - NZTA B10 - 3.2
label | Verifying Document - Methodology
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.04.03 - Plant for Stabilisation Process
label | Acceptance / Conformance Criteria - The plant used for the mixing shall be a purpose-built recycling machine. It shall be from a reputable manufacturer having a demonstrable track record and manufacturing history for the equipment used.
label | Standard / Specification - NZTA B10 - 3.3
label | Verifying Document - Methodology
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.04.04 - Primary Compaction Equipment
label | Acceptance / Conformance Criteria - A steel drum roller (i.e. having a smooth drum) is required for the initial placement of aggregate. The roller shall have a gross weight of at least 12 tonnes. For primary compaction, the Contractor shall use GPS control to ensure all areas of the pavement receive the required number of passes with each type of roller.
label | Standard / Specification - NZTA B10 - 3.4
label | Verifying Document - Methodology
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.04.05 - Personnel Training and Experience
label | Acceptance / Conformance Criteria - The Contractor shall submit a list of such personnel to the Engineer for approval. Where approved personnel are not available the Contractor shall cease operations.
label | Standard / Specification - NZTA B10 - 4.2
label | Verifying Document - Methodology
label | Frequency - Prior to Works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 13.05 Hi-Lab Pavement Trial
checkpoint | 13.05.01 - Pavement Trial
label | Acceptance / Conformance Criteria - The Constructor shall construct a pavement test trial of Hi-Lab sub-base and basecourse pavement to verify design assumptions, material properties and construction methodology. The trial shall be undertaken in the presence of the Designer using the construction procedures, equipment and operating personnel proposed for the work in the placing, stabilising, compaction and finishing of the individual layers.
label | Standard / Specification - NZTA B10 - 5
label | Verifying Document - Conforming Trail and Test Results
label | Frequency - Prior to Hi-Lab Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 13.06 Hi-Lab Construction
checkpoint | 13.06.01 - Production Quality Plan
label | Acceptance / Conformance Criteria - The Contractor shall prepare a Production Plan for approval by the Engineer prior to commencement of delivery of Hi-Lab aggregate to site, detailing all aspects of its Hi-Lab production process, how it will achieve compliance with this specification, and procedures in the event of non-compliance or plant breakdown. The Production Plan shall include the Contractor’s detailed methodology.
label | Standard / Specification - NZTA B10 - 4.1
label | Verifying Document - Production Plan
label | Frequency - Prior to commencement
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.06.02 - Daily production sketches
label | Acceptance / Conformance Criteria - Daily production sketches shall also be produced for approval by the Engineer ahead of each forthcomingday’s work.
label | Standard / Specification - NZTA B10 - 4.1
label | Verifying Document - Production sketches
label | Frequency - Daily Prior to commencement of days work
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.06.03 - Initial placement of aggregate
label | Acceptance / Conformance Criteria - The Contractor is responsible for ensuring the surface level after spreading and compaction prior to stabilisation will result in final layer thickness and finished levels after stabilisation that are within the required tolerances.
label | Standard / Specification - NZTA B10 - 4.3.2
label | Verifying Document - Survey Records
label | Frequency - prior to stabilisation
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 13.06.04 - Cement Mat Test
label | Acceptance / Conformance Criteria - The cement spread rate shall be measued by a 1m² canvas Mat Test every 250m2 and be Within ±0.5kg/m² of the specified rate.
label | Standard / Specification - NZTA B10 - 4.4.1
label | Verifying Document - Test Results
label | Frequency - Every 250m²
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 13.06.05 - Cement Average usage test
label | Acceptance / Conformance Criteria - The Average usage of cement spread rate shall be measued by comparing tonnes used (from delivery docket) with measured area and be Within ±2.5% of the specified rate.
label | Standard / Specification - NZTA B10 - 4.4.1
label | Verifying Document - Test Results
label | Frequency - Upon emptying the spreader and bulk tanker
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 13.06.06 - Weather limitations
label | Acceptance / Conformance Criteria - Spreading of cement on the road ahead of stabilisation shall not continue when the cement becomes a dust problem due to dryness or when the wind speed exceeds 25km/hr. No spreading of cement shall commence if it is raining. If rain is likely to start before the cement can be mixed into the aggregate, then spreading shall not take place.
label | Standard / Specification - NZTA B10 - 4.4.2
label | Verifying Document - Site Records
label | Frequency - Duing stabilisation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.07 - Time limitations
label | Acceptance / Conformance Criteria - The maximum time period, from mixing of the materials to completion of primary compaction, shall be 2.0 hours. Unless specifically justified in the approved Production Plan, stabilisation shall commence no later than 10:00 am and the area to be stabilized shall not exceed 4,000m² per day, unless agreed otherwise by the Engineer, to ensure sufficient time to complete the full stabilisation process.
label | Standard / Specification - NZTA B10 - 4.4.3
label | Verifying Document - Site Records
label | Frequency - Duing stabilisation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.08 - Stabilisation/Addition of Water
label | Acceptance / Conformance Criteria - The Contractor shall continuously monitor the moisture content of the material behind the recycler and in consultation with the Engineer adjust the rate of water injection as necessary. The Contractor shall also monitor continuously for blocked nozzles or any other risk to the consistency of the mixture. The stabilisation area shall not exceed 4000m2 per day, with a maximum single stabilisation run length of 225m, unless agreed otherwise by the Engineer.
label | Standard / Specification - NZTA B10 - 4.5.1
label | Verifying Document - Site Records
label | Frequency - Duing stabilisation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.09 - Control of mixing depth
label | Acceptance / Conformance Criteria - The Contractor shall determine the mixing depth so that the final stabilised layer thickness after compaction meets the contract requirements. During stabilisation the depth of the cut shall be physically measured at both ends of the mixing drum at least once every 50m. The measured stabilisation depth shall confirm full mixture of the placed Hi-Lab layer at full depth with no untreated materials present at the bottom of the test hole.
label | ○ The maximum allowable variation from the specified depth of cut is –5mm and +15mm.
label | Standard / Specification - NZTA B10 - 4.5.2
label | Verifying Document - Survey Records
label | Frequency - Duing stabilisation
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 13.06.10 - Overlap on longitudinal joints
label | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 100mm or half the layer thickness, whichever is greater. Overlap width shall be increased if any dry material is noticed between runs. The locations of longitudinal joints shall be agreed between the Contractor and Engineer and recorded in the production plan.
label | Standard / Specification - NZTA B10 - 4.5.3
label | Verifying Document - Production Plan
label | Frequency - Duing stabilisation
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 13.06.11 - Continuity of stabilised layer
label | Acceptance / Conformance Criteria - The exact location of the end of the cut shall be carefully marked. This mark shall coincide with the position of the centre of the mixing drum at the point at which the supply of cement ceased. To ensure continuity of the stabilised layer, the next successive cut shall be started 3m behind this mark. This tie-in length shall be reduced to 1m for stabilised layers older than 7 days. Cement shall be spread on the overlap for the next run.
label | Standard / Specification - NZTA B10 - 4.5.4
label | Verifying Document - Daily Production Drawings.
label | Frequency - Duing stabilisation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.12 - Daily production sketches
label | Acceptance / Conformance Criteria - The Contractor shall sample the material behind the stabiliser for particle size distribution analysis using the specified method below and advise the Engineer of the result as soon as practicable. The sample frequency shall be a minimum of 5 samples per 4000m2. The samples shall be representative of the full stabilised area.
label | Standard / Specification - NZTA B10 - 4.5.5
label | Verifying Document - Test Results
label | Frequency - A minimum of 5 samples per 4000m2
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.13 - Primary Compaction
label | Acceptance / Conformance Criteria - Primary compaction shall be monitored for conformance to the methodology
label | Standard / Specification - NZTA B10 - 4.6.1
label | Verifying Document - Site Records
label | Frequency - Duing Compaction
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.14 - Secondary Compaction and Choking
label | Acceptance / Conformance Criteria - Secondary Compaction and Choking shall be monitored for conformance to the methodology
label | Standard / Specification - NZTA B10 - 4.6.2
label | Verifying Document - Site Records
label | Frequency - Duing stabilisation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.15 - Surface prior to placing next Hi-Lab layer and/or sealing
label | Acceptance / Conformance Criteria - Fines shall be removed and broomed to produce a mosaic surface prior to placing the next Hi-Lab layer or sealing. The surface shall not have any loose fines and/or “caked” laminations of fines, and shall be a mosaic stone surface free of fines.
label | Standard / Specification - NZTA B10 - 4.6.3
label | Verifying Document - Site Records
label | Frequency - Prior to placing next Hi-Lab layer and/or sealing
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.16 - Surface shape
label | Acceptance / Conformance Criteria - The surface shape of the completed pavement layer shall be such that, when all loose aggregate is removed, it conforms to the shape specified within the tolerances in Table 4.3.
label | Standard / Specification - NZTA B10 - 4.6.4
label | Verifying Document - Survey Records
label | Frequency - Each Layer (Subbase / Basecourse)
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 13.06.17 - Crossfall
label | Acceptance / Conformance Criteria - The crossfall between two points more than 2.0m apart, transverse to the centreline, shall not depart from the design crossfall by more than 0.5%.
label | Standard / Specification - NZTA B10 - 4.6.5
label | Verifying Document - Survey Records
label | Frequency - Each Layer (Subbase / Basecourse)
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 13.06.18 - Hi-Lab Protection
label | Acceptance / Conformance Criteria - No construction equipment shall be driven on any Hi-Lab aggregate layers until at least 48 hours have passed following completion of secondary compaction. At no time during the construction of the Hi-Lab pavement layers shall any haulage of earthworks and/or drainage construction activities e.g. excavators be allowed, only construction activities directly associated with the construction of the Hi-Lab layers, e.g. placement of aggregate.
label | Standard / Specification - NZTA B10 - 4.6.6
label | Verifying Document - Site Records
label | Frequency - at least 48 hours have passed following completion of secondary compaction
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.19 - Hi-Lab Maintenance
label | Acceptance / Conformance Criteria - For a minimum of 48 hours after stabilisation the Contractor shall
label | (a) provide additional PAP7 running course, if required (using clause 10 of NZTA B02 as a guide)
label | (b) keep the surface damp but not wet to prevent drying and ravelling
label | (c) drag-broom the whole surface, keeping a balanced distribution of PAP7.
label | Standard / Specification - NZTA B10 - 4.6.6
label | Verifying Document - Site Records
label | Frequency - at least 48 hours have passed following completion of secondary compaction
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.20 - Compaction Testing - Subbase and Basecourse - Moisture Corrected - Direct Transmission against Solid Density
label | Acceptance / Conformance Criteria - The degree of compaction for the Hi-Lab layer shall be determined by direct transmission, a hole shall be drilled to accommodate the probe to the full depth of the Hi-Lab layer and/or layers. The probe shall be set at increasing increments of 50mm and a measurement shall be recorded for each depth setting. This process shall be repeated twice with a 180 degree rotational off-set around the hole. Tests shall be Moisture corrected.
label | ○ Average Value 83 %
label | ○ Minimum Value 81 %
label | Standard / Specification - NZTA B10 - 4.6.7
label | Verifying Document - Test Results
label | Frequency - At least five (5) randomly selected areas per 4,000m² or part thereof. For lot sizes larger than 4,000m² additional testing shall be undertaken at a rate of 1 test per 1000m²
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 13.06.21 - Moisture Correction Cores
label | Acceptance / Conformance Criteria - A minimum of two core samples per 4,000m² or lot size whichever is the lesser, shall be taken within 0.5m of the probe hole to be used for moisture correction. After oven drying to calculate moisture correct, the same core sample shall be used for ITS.
label | Standard / Specification - NZTA B10 - 4.6.7
label | Verifying Document - Test Results
label | Frequency - A minimum of two core samples per 4,000m² or lot size, whichever is the lesser
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 13.06.22 - Coring
label | Acceptance / Conformance Criteria - After a minimum of 7 days post stabilisation the Contractor shall take 200mm diameter core samples from representative locations in the stabilised layers for Indirect Tensile Strength (ITS) testing. If the Hi-Lab basecourse is placed prior to 7 days after sub-base construction, both layers shall be cored together at least 7 days after basecourse construction.
label | Standard / Specification - NZTA B10 - 4.7.1
label | Verifying Document - Test Results
label | Frequency - One core is required per 2,000m² lot or part thereof for each stabilised layer.
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.23 - Hi-Lab Sub-Base Deflection Testing
label | Acceptance / Conformance Criteria - Benkelman beam testing shall be carried out on top of the Hi-Lab sub-base layers in accordance with TNZ T01 specification at 10m intervals in alternating wheel paths for all lanes, within 7 days after stabilisation. All measured deflection measurements from each construction lot shall meet 95 the percentile ≤ 0.4mm (max < 0.5mm)
label | Standard / Specification - NZTA B10 - 4.8
label | Verifying Document - Test Results
label | Frequency - Prior to Next Layer / Surfacing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.06.24 - Hi-Lab Basecourse Deflection Testing
label | Acceptance / Conformance Criteria - Benkelman beam testing shall be carried out on top of the Hi-Lab basecourse layers in accordance with TNZ T01 specification at 10m intervals in alternating wheel paths for all lanes, within 7 days after stabilisation. All measured deflection measurements from each construction lot shall meet 95 the percentile ≤ 0.3mm (max < 0.4mm)
label | Standard / Specification - NZTA B10 - 4.8
label | Verifying Document - Test Results
label | Frequency - Prior to Next Layer / Surfacing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.06.25 - Hi-Lab Pre Chipseal inspection
label | Acceptance / Conformance Criteria - Before sealing, the Contractor shall advise the Engineer that the pavement surface has been prepared in accordance with this specification although final sweeping may not have been performed. The Engineer shall be given the opportunity to inspect the swept pavement surface for approval.
label | Standard / Specification - NZTA B10 - 4.9
label | Verifying Document - Engineers Acceptance
label | Frequency - Before sealing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.06.26 - Hi-Lab Basecourse Surface - Pre Asphalt NAASRA
label | Acceptance / Conformance Criteria - For in-service chip seal surfacing - the 100m moving average lane roughness of Hi-Lab basecourse shall not exceed a NAASRA (100m rolling avg/km) < 75 counts/km.
label | Standard / Specification - NZTA B10 - 4.9
label | Verifying Document - Test Results
label | Frequency - Prior to Asphalting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.06.27 - Rut Measurements - After initial first coat sealing
label | Acceptance / Conformance Criteria - No part of the surface of the Hi-Lab pavement shall deviate by more than 10mm from a 3m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline. Rutting shall be checked by independent testing specialist.
label | Standard / Specification - NZTA B10 - 4.10
label | Verifying Document - Independent Test Results
label | Frequency - After initial first coat sealing
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.28 - Hi-Lab Pre Levelling
label | Acceptance / Conformance Criteria - The Constructor shall submit the asphalt pre-levelling methodology to the designer for review and approval prior to implementation.
label | Standard / Specification - NZTA B10 - 4.9
label | Verifying Document - Methodology
label | Frequency - Prior to Asphalting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.06.29 - Hi-Lab Pre Asphalt inspection
label | Acceptance / Conformance Criteria - Before sealing, the Contractor shall advise the Engineer that the pavement surface has been prepared in accordance with this specification although final sweeping may not have been performed. The Engineer shall be given the opportunity to inspect the swept pavement surface for approval.
label | Standard / Specification - NZTA B10 - 4.9
label | Verifying Document - Engineers Acceptance
label | Frequency - Before Asphalting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.06.30 - Hi-Lab Basecourse Surface - Final Asphalt Surface NAASRA
label | Acceptance / Conformance Criteria - For asphalt in-service surfacing - the roughness requirements on SMA or Epoxy modified OGPA final surfacing shall be NAASRA (100m rolling avg/km) < 50 and max NAASRA < 60.
label | Standard / Specification - NZTA B10 - 4.9
label | Verifying Document - Test Results
label | Frequency - After Asphalting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.06.31 - Rut Measurements - Prior to final EMOGPA or SMA surfacing
label | Acceptance / Conformance Criteria - No part of the surface of the Hi-Lab pavement shall deviate by more than 10mm from a 3m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline. Rutting shall be checked by independent testing specialist.
label | Standard / Specification - NZTA B10 - 4.10
label | Verifying Document - Independent Test Results
label | Frequency - Prior to final EMOGPA or SMA surfacing
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.32 - Rut Measurements - After 12 months of trafficking on final surface
label | Acceptance / Conformance Criteria - No part of the surface of the Hi-Lab pavement shall deviate by more than 10mm from a 3m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline. Rutting shall be checked by independent testing specialist.
label | Standard / Specification - NZTA B10 - 4.10
label | Verifying Document - Independent Test Results
label | Frequency - After 12 months of trafficking on final surface
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 13.06.33 - Rut Measurements - At the end of the Defects Notification Period.
label | Acceptance / Conformance Criteria - No part of the surface of the Hi-Lab pavement shall deviate by more than 10mm from a 3m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline. Rutting shall be checked by independent testing specialist.
label | Standard / Specification - NZTA B10 - 4.10
label | Verifying Document - Independent Test Results
label | Frequency - At the end of the Defects Notification Period.
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 14.02 Chipsealing
checkpoint | 14.02.01 - Sealing Procedure
label | Acceptance / Conformance Criteria - Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, P4, P17, and Q/1.
label | Standard / Specification - M/1, M/6, M/13, P/3, P4, P17, and Q/1.
label | Verifying Document - Methodology / Construction Pack
label | Frequency - Prior to Sealing
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.02.02 - Seal Design / Binder application rate
label | Acceptance / Conformance Criteria - The sealing design including binder application rate to suit the surface conditions shall be approved by the Design Engineer prior to sealing.
label | Standard / Specification - TNZ P3 TNZ P4
label | Verifying Document - Approved Seal Design
label | Frequency - Prior to Sealing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.02.03 - Presealing Requirements
label | Acceptance / Conformance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 60%.
label | Standard / Specification - TNZ B02
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests Per Lot 1000m2 Max Lot Size
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.02.04 - PreSeal inspection
label | Acceptance / Conformance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
label | Standard / Specification - TNZ P3 TNZ B02
label | Verifying Document - Hold Point Release
label | Frequency - A minimum of 24 hours’ notice of intention to seal.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.02.05 - Spray Temperature
label | Acceptance / Conformance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Prior to Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.02.06 - Binder Sampling
label | Acceptance / Conformance Criteria - A minimum of two samples per bitumen distributor load shall be taken. The first of these samples shall be taken at the end of the initial spray run and the other immediately before the final spray run. Bitumen to be tested on Engineers instruction.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Each Worksite
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.02.07 - Quantity of Binder Sprayed
label | Acceptance / Conformance Criteria - The quantity of binder sprayed in any spray run, measured by dipstick reading, shall not vary from the amount directed by more than 50 litres plus 4% of the amount directed.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Every Spray Run
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.02.08 - Chip Application
label | Acceptance / Conformance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Every Spray Run
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.02.09 - Surplus Chip Removal
label | Acceptance / Conformance Criteria - Surplus chips shall be removed from the sealed surface prior to the removal of the temporary speed restriction signs.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - 24 hours of Completion of any Section of Seal.
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.02.10 - Post Seal Inspections
label | Acceptance / Conformance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
label | Standard / Specification - TNZ P3
label | Verifying Document - Engineers Acceptance
label | Frequency - Prior to TM Removal and After Final Sweeping
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.02.11 - Chipseal Repairs
label | Acceptance / Conformance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
label | Standard / Specification - TNZ P3
label | Verifying Document - Approved Repair Methodology
label | Frequency - Prior to Repairs
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 14.03 Construction Activity - NZTA M10 - Specification for dense-graded asphaltic concrete
checkpoint | 14.03.01 - Construction Trail
label | Acceptance / Conformance Criteria - Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. Asphalt manufactured in the production trial can also be used in the construction trial if it meets the requirements of the specification.
label | Standard / Specification - PS 21.3.1 NZTA M10:2020 - 7
label | Verifying Document - Test Results
label | Frequency - As Required, two days before the site work is due to commence.
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.02 - Paving Plan
label | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
label | Standard / Specification - NZTA M10:2020 - 8, 9
label | Verifying Document - Construction Work Pack
label | Frequency - 7 days prior to construction of the asphalt pavement.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.03.03 - Preparation of Area to be Paved
label | Acceptance / Conformance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Pre Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.04 - Protection of Services
label | Acceptance / Conformance Criteria - The Contractor shall prevent tack coat, binder, aggregate, asphalt or other material used on the work from entering, adhering or obstructing gratings, hydrants, valve boxes, inspection pit covers, kerbs and other road fixtures
label | Standard / Specification - NZTA M10:2020
label | Verifying Document - Environmental Inspections
label | Frequency - Daily
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.03.05 - Ambient Conditions for Placing
label | Acceptance / Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C, for SAC the minimum temperature is 5°C
label | Standard / Specification - NZTA M10:2020
label | Verifying Document - Site Notes
label | Frequency - Pre Seal
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 14.03.06 - Tack Coating
label | Acceptance / Conformance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Prior to Paving
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.07 - Asphalt Production Conformance
label | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass
label | Standard / Specification - NZTA M10:2020 -Table 3.1 & 5.1
label | Verifying Document - Test Results
label | Frequency - 1 per 200T, Min 3 tests per mix
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.09 - Core Thickness
label | Acceptance / Conformance Criteria - The layer thickness determined from measurements on the cores LCV of no less than the specified thickness - refer clause 9.7
label | Standard / Specification - NZTA M10:2020
label | Verifying Document - Lab Report
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.03.10 - Mat Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300m² with a minimum of eight cores representing each lot
label | Standard / Specification - ASTM D5361 NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 14.03.11 - Joint Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100m of joint with a minimum of three representing each lot
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 3 per lot (day) (1 per 100 m of joint)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 14.03.12 - Density Testing
label | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Lab Report
label | Frequency - within 24 hours of them being cut from the pavement
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.13 - NDM Density
label | Acceptance / Conformance Criteria - NDMs are to be completed at the time of placing to ensure compliance when cores are taken
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - IANZ Lab Report
label | Frequency - min 8 per lot (day)
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.14 - Transverse truth of the surface
label | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Post Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.03.15 - Finished Pavement Level, Alignment, and Thickness
label | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements.
label | Standard / Specification - NZTA M10:2020 - 10
label | Verifying Document - Survey
label | Frequency - Continuous thought construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | 14.04 Construction Activity - NZTA M27 - Specification for stone mastic asphalt.
checkpoint | 14.04.01 - Construction Trail
label | Acceptance / Conformance Criteria - Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. SMA manufactured in the production trial can also be used in the construction trial provided that it meets the requirements of the specification.
label | Standard / Specification - PS 21.2.1 NZTA M27:2020 - 7
label | Verifying Document - Test Results
label | Frequency - As Required, two days before the site work is due to commence.
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.02 - Paving Plan
label | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
label | Standard / Specification - NZTA M27:2020 - 8, 9
label | Verifying Document - Construction Work Pack
label | Frequency - 7 days prior to construction of the asphalt pavement.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.04.03 - Preparation of Area to be Paved
label | Acceptance / Conformance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Pre Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.04 - Protection of Services
label | Acceptance / Conformance Criteria - The Contractor shall prevent tack coat, binder, aggregate, asphalt or other material used on the work from entering, adhering or obstructing gratings, hydrants, valve boxes, inspection pit covers, kerbs and other road fixtures
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Environmental Inspections
label | Frequency - Daily
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.04.05 - Ambient Conditions for Placing
label | Acceptance / Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Pre Seal
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 14.04.06 - Tack Coating
label | Acceptance / Conformance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. Where SMA is to be spread over clean, freshly placed asphalt, the Engineer can direct the Contractor to omit the tack coat.
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Prior to Paving
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.07 - Asphalt Production Conformance
label | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass
label | Standard / Specification - NZTA M27:2020 - Table 3.1 & 5.1
label | Verifying Document - Test Results
label | Frequency - 1 per 200T, Min 3 tests per mix
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.09 - Core Thickness
label | Acceptance / Conformance Criteria - The M/27:2020 requirement is LCV of no less than the specified thickness - refere clause 9.7
label | Standard / Specification - NZTA M27:2020 -
label | Verifying Document - Lab Report
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.04.10 - Mat Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot
label | Standard / Specification - ASTM D5361 NZTA M27:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 14.04.11 - Joint Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100 m of joint with a minimum of three representing each lot
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 3 per lot (day) (1 per 100 m of joint)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 14.04.12 - Density Testing
label | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Lab Report
label | Frequency - within 24 hours of them being cut from the pavement
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.13 - NDM Density
label | Acceptance / Conformance Criteria - NDMs are to be completed at the time of pacing to ensure compile when cores are taken
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - IANZ Lab Report
label | Frequency - min 8 per lot (day)
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.14 - Transverse truth of the surface
label | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge.
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Post Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.04.15 - Finished Pavement Level, Alignment, and Thickness
label | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements.
label | Standard / Specification - NZTA M27:2020 - 10
label | Verifying Document - Survey
label | Frequency - Continuous thought construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | 14.05 Roughness
checkpoint | 14.05.01 - For a Chip Sealed Surface
label | Acceptance / Conformance Criteria - Target is an average of 60 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 70 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km.
label | Standard / Specification - PS 21.4.1
label | Verifying Document - Test Report
label | Frequency - Prior to sealing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.05.02 - For an Asphaltic Concrete Surface
label | Acceptance / Conformance Criteria - Target is an average of 50 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 60 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km.
label | Standard / Specification - PS 21.4.1
label | Verifying Document - Test Report
label | Frequency - Prior to sealing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 14.06 Skid Resistance
checkpoint | 14.06.01 - Skid Resistance
label | Acceptance / Conformance Criteria - The surfacing shall meet the requirements specified in the Transport Agency’s T10:2010 Skid Resistance Deficiency Investigation and Treatment Selection, and any other subsequent amendments.
label | Standard / Specification - PS 21.5.1
label | Verifying Document - Prior to Project Completion
label | Frequency - Prior to sealing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT