## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Pavement - Type C - 104.3 - Rev 2 | itp |  |  |  |  | ITP - Pavement - Type C - 104.3 - Rev 2
section | 4.24 AP65 Subgrade Improvement Layer (SIL) - B/2 Materials (Pavement Type A,B,C)
checkpoint | 4.24.01 - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
label | Standard / Specification - PS 20.4.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.24.02 - Crushing Resistance
label | Acceptance / Conformance Criteria - The crushing resistance shall be not less than 100kN when the aggregate is tested in accordance with NZS:4407: Test 3.10
label | Frequency - 10,000m3
checkpoint | 4.24.03 - Weathering Quality Index
label | Acceptance / Conformance Criteria - The aggregate shall have a weathering quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11.
label | Frequency - 10,000m3
checkpoint | 4.24.04 - CBR
label | Acceptance / Conformance Criteria - The material shall have a minimum CBR of 40 when compacted to New Zealand heavy compaction standard in accordance with NZS4402 Test 4.1.2 at water content between 4% and 6% by weight of aggregate. CBR testing shall be in accordance with NZS 4407 Test 3.15.
label | Frequency - 10,000m3
checkpoint | Production Property Test Sampling
label | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
label | Standard / Specification - PS 20.4.1
label | Verifying Document - IANZ Lab Reports
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.24.05 - Aggregate Fractions
label | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 50% by weight shall have two or more broken faces. It shall be free of organic matter.
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.24.06 - Sand Equilavent
label | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 30 when the aggregate is tested according to NZS 4407: 1991: Test 3.6. The sand equivalent test may be neglected if the grading test shows less than 4% passing the 75-micron sieve.
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.24.07 - Plasticity Index
label | Acceptance / Conformance Criteria - The Plasticity Index shall be no less than 8 when the aggregate is tested according to NZS 4407: Test 3.4.
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.24.08 - Clay Index
label | Acceptance / Conformance Criteria - The Clay Index shall be no less than 5 when the aggregate is tested according to NZS 4407: Test 3.5
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.24.09 - Wet Sieving
label | Acceptance / Conformance Criteria - When tested according to NZS: 4407: Test 3.8.1 Standard Method by Wet Sieving or Test 3.8.2 Subsidiary Method by Dry Sieving, the grading of the aggregate shall fall within their respective envelopes defined below or as directed by the Engineer.
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.24.10 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for SIL construction shall be the maximum laboratory dry density using Heavy compaction.
label | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.4.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 4.25 WHAP65 Sub-Base - B/2 Materials (Pavement Type C)
checkpoint | 4.25.01 - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The WHAP65 Sub-Base shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
label | Standard / Specification - PS 20.5.1.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.25.02 - Crushing Resistance
label | Acceptance / Conformance Criteria - The crushing resistance shall be not less than 130kN when the aggregate is tested in accordance with NZS:4407: Test 3.10
label | Frequency - 10,000m3
checkpoint | 4.25.03 - Weathering Quality Index
label | Acceptance / Conformance Criteria - The aggregate shall have a weathering quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11.
label | Frequency - 10,000m3
checkpoint | 4.25.04 - CBR
label | Acceptance / Conformance Criteria - The material shall have a minimum CBR of 40 when compacted to New Zealand heavy compaction standard in accordance with NZS4402 Test 4.1.2 at water content between 4% and 6% by weight of aggregate. CBR testing shall be in accordance with NZS 4407 Test 3.15.
label | Frequency - 10,000m3
checkpoint | Production Property Test Sampling
label | Acceptance / Conformance Criteria - The WHAP65 Sub-Base shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
label | Standard / Specification - PS 20.5.1.1
label | Verifying Document - IANZ Lab Reports
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.25.05 - Aggregate Fractions
label | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 50% by weight shall have two or more broken faces. It shall be free of organic matter.
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.25.06 - Sand Equilavent
label | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 25 when the aggregate is tested according to NZS 4407: 1991: Test 3.6. The sand equivalent test may be neglected if the grading test shows less than 4% passing the 75-micron sieve.
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.25.07 - Wet Sieving
label | Acceptance / Conformance Criteria - When tested according to NZS: 4407: Test 3.8.1 Standard Method by Wet Sieving or Test 3.8.2 Subsidiary Method by Dry Sieving, the grading of the aggregate shall fall within their respective envelopes defined below or as directed by the Engineer.
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.25.08 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for WHAP65 Sub-Base construction shall be the maximum laboratory dry density using Heavy compaction.
label | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.5.11
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 4.26 GAP65 Subgrade Improvement Layer - B/2 Materials
checkpoint | 4.26.01 - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
label | Standard / Specification - PS 20.9.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.26.02 - Production Property Test Sampling
label | Acceptance / Conformance Criteria - The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
label | Standard / Specification - PS 20.9.1
label | Verifying Document - IANZ Lab Reports
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.26.03 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for GAP65 SIL construction shall be the maximum laboratory dry density using Heavy compaction.
label | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.9.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 4.28 TNZ M/4 - AP40 Material Approval (Pavement Type C,D)
checkpoint | Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
label | Standard / Specification - PS 20.8.1 TNZ M/4: 2006 - 3, NZS 4407 : 1991, NZS 4402 : 1986
label | Verifying Document - IANZ Lab Reports
label | Frequency - At least 1 sample every 10,000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.28.01 - Crushing Resistance
label | Acceptance / Conformance Criteria - When tested in accordance with NZS 4407 : 1991, Test 3.10, The Crushing Resistance Test, under a load of 130 kN less than 10% fines passing 2.36 mm sieve size shall be produced.
label | Standard / Specification - TNZ M/4 Spec Clause 3.3.1
checkpoint | 4.28.02 - Weathering Quality Index
label | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11.
label | Standard / Specification - TNZ M/4 Spec Clause 3.3.2
checkpoint | 4.28.03 - CBR
label | Acceptance / Conformance Criteria - The sample shall be:
label | (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand
label | ○ Vibrating Hammer Compaction Test at Optimum Water Content and;
label | (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%.
label | Standard / Specification - TNZ M/4 Spec Clause 3.3.3
checkpoint | Production Property Test Sampling
label | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per PS 20.8.1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
label | Standard / Specification - PS 20.8.1 TNZ M/4: 2006 - 4, NZS 4407 : 1991
label | Verifying Document - IANZ Lab Reports
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.28.04 - Sand Equilavent
label | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407: 1991: Test 3.6.
label | Standard / Specification - TNZ M/4 Spec Clause 4.2.1.1
label | Frequency -
label | – – – – – – – – – – – – – –
label | Quantity ¦¦ No. of Samples
label | – – – – – – – – – – – – – –
label | 1 m3 to 400 m3 ¦¦ 2
label | 400 m3 to 1,500 m3 ¦¦ 3
label | 1,500 m3 to 4,000 m3 ¦¦ 4
label | – – – – – – – – – – – – – –
checkpoint | 4.28.05 - Clay Index
label | Acceptance / Conformance Criteria - The clay index of the fraction of basecourse passing the 75μm sieve shall not be greater than 3 when the aggregate is tested according to NZS 4407 : 1991, Test 3.5 Clay Index Test.
label | Standard / Specification - TNZ M/4 Spec Clause 4.2.1.2
checkpoint | 4.28.06 - Plasticity Index
label | Acceptance / Conformance Criteria - The plasticity index of the fraction of basecourse passing the 425μm sieve shall not be greater than 5 when the aggregate is tested according to NZS 4407 : 1991, Test 3.4 Plasticity Index Test.
label | Standard / Specification - TNZ M/4 Spec Clause 4.2.1.3
checkpoint | 4.28.07 - Broken Face Content
label | Acceptance / Conformance Criteria - The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407 : 1991, Test 3.14 Broken Face Test.
label | Standard / Specification - TNZ M/4 Spec Clause 4.2.2
checkpoint | 4.28.08 - Particle Size Distribution
label | Acceptance / Conformance Criteria - The particle-size distribution of the aggregate shall conform with the envelope limits defined in both Tables 2 and 3 below, when the aggregate is tested according to NZS 4407 : 1991, Test 3.8.1 Wet Sieving Test.
label | ○ If testing has been performed to show that the dry sieving method is not significantly different to the wet sieving method at 95% confidence limit for the same aggregate then dry sieving method may be used.
label | – – – – – – – – – – – – – –
label | Table 2: Particle Size Distribution Envelope Limits for an Individual Sample
label | Test Sieve Aperture ¦¦ AP40 (Max size 40mm) ¦¦ AP20 (Max size 20mm)
label | – – – – – – – – – – – – – –
label | 37.5mm ¦¦ 100 ¦¦ -
label | 19mm ¦¦ 66 - 81 ¦¦ 100
label | 9.5mm ¦¦ 43 - 57 ¦¦ 55 - 75
label | 4.75mm ¦¦ 28 - 43 ¦¦ 33 - 55
label | 2.36mm ¦¦ 19 - 33 ¦¦ 22 - 42
label | 1.18mm ¦¦ 12 - 25 ¦¦ 14 - 31
label | 600µm ¦¦ 7 - 19 ¦¦ 8 - 23
label | 300µm ¦¦ 3 - 14 ¦¦ 5 - 16
label | 150µm ¦¦ 0 - 10 ¦¦ 0 - 12
label | 75µm ¦¦ 0 - 7 ¦¦ 0 - 8
label | – – – – – – – – – – – – – –
label | – – – – – – – – – – – – – –
label | Table 3: Particle Size Distribution Shape Control
label | Fractions ¦¦ AP40 (Max size 40mm) ¦¦ AP20 (Max size 20mm)
label | – – – – – – – – – – – – – –
label | 19mm - 4.75mm ¦¦ 28 - 48 ¦¦ -
label | 9.5mm - 2.36mm ¦¦ 14 - 34 ¦¦ 20 - 46
label | 4.75mm - 1.18mm ¦¦ 7 - 27 ¦¦ 9 - 34
label | 2.36mm - 600µm ¦¦ 6 - 22 ¦¦ 6 - 26
label | 1.18mm - 300µm ¦¦ 5 - 19 ¦¦ 3 - 21
label | 600µm - 150µm ¦¦ 2 - 14 ¦¦ 2 - 17
label | – – – – – – – – – – – – – –
label | Standard / Specification - TNZ M/4 Spec Clause 4.2.3
checkpoint | 4.28.09 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 5,000m2
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 4.30 NZTA M27 2020 - STONE MASTIC ASPHALT MATERIALS
checkpoint | 4.30.01 - Coarse Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, Bulk SG and Density, Absorption, and Particle Size Distribution
label | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.30.02 - Fine Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, Bulk SG and Density, Absorption, and Particle Size Distribution
label | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.30.03 - Mineral Filler
label | Acceptance / Conformance Criteria - Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt.
label | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.2 ASTM D242
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.30.04 - Bitumen
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
label | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.4.1, NZTA M01-A
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.30.05 - Mix Design Approval
label | Acceptance / Conformance Criteria - The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use.
label | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 3.1 , 3.6
label | Verifying Document - Approved Mix Design
label | Frequency - Prior to Use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.31 Tack Coating Materials
checkpoint | 4.31.01 - Bitumen - Quality Testing
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
label | Standard / Specification - NZTA M01: 2022 - 6
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test per grade supplied
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.32 Sealing Chip Supply
checkpoint | 4.32.01 - Sealing Chip - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
label | Standard / Specification - PS 21.1.1 TNZ M/6: 2019 - 4
label | Verifying Document - IANZ Lab Reports
label | Frequency - Before Supply and Every 10,000m3 Thereafter
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.32.02 - Sealing Chip - Production Property Test Sampling
label | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
label | Standard / Specification - PS 21.1.1 TNZ M/6: 2019 - 5
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 500m3
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.33 Bitumen Supply
checkpoint | 4.33.01 - Bitumen - Quality Testing
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
label | Standard / Specification - PS 21.1.1 NZTA M01: 2022 - 6
label | Verifying Document - IANZ Lab Reports
label | Frequency - One test per grade supplied
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.33.02 - Bitumen - Supply Testing
label | Acceptance / Conformance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
label | Standard / Specification - PS 21.1.1 NZTA Q05: 2022 - 6.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Every 200 tonnes supplied.
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.33.03 - Adhesion Agents
label | Acceptance / Conformance Criteria - When used, Adhesion agents must be approved & blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents.
label | Standard / Specification - TNZ M13
label | Verifying Document - Binder Aggregate Adhesion Test
label | Frequency - Each Adhesion Agent and Dosage Rate for a Particular Chip Source
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.33.04 - Sprayer Certification
label | Acceptance / Conformance Criteria - The binder shall be applied with a bitumen distributor, operated in accordance with BCA E/2, Specification for Performance of Bitumen Distributors administered by the New Zealand Bitumen Contractors' Association Inc.
label | Standard / Specification - TNZ P3 TNZ P4
label | Verifying Document - E2 Cert
label | Frequency - Each Sprayer
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 13.02 AP65 Subgrade Improvement Layer Pavement Type A,B,C
checkpoint | 13.02.01 - Material Placement
label | Acceptance / Conformance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.02.02 - Plateau Density Tests
label | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC.
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
label | Verifying Document - MDD and Plateau Reports
label | Frequency - 1 test per 5,000m2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.02.03 - SIL Pavement Layer Compaction
label | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.6
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.02.04 - SIL Layer thickness.
label | Acceptance / Conformance Criteria - The SIL layer shall be monitored for Layer thickness.
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Verification Activity: Activity - W
label | Verification Activity: By - SV / PE
checkpoint | 13.02.05 - Surface Shape
label | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey / Straight edge Report
label | Frequency - Prior to sealing
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.02.06 - Holding Water
label | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey
label | Frequency - Prior to sealing
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.02.07 - Proof Rolling
label | Acceptance / Conformance Criteria - SIL layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass.
label | Standard / Specification - PS 20.5.2.2
label | Verifying Document - Site Records
label | Frequency - Before proceeding with works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.02.08 - Benkelman Beam
label | Acceptance / Conformance Criteria - be ˂ 1.5mm (95th%) and max ≤1.8mm
label | Standard / Specification - B10 Notes
label | Verifying Document - Report
label | Frequency - All Lanes
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 13.03 Construction Of Unbound WHAP65 Sub-Base Pavement Type C
checkpoint | 13.03.01 - Material Placement
label | Acceptance / Conformance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.03.02 - Plateau Density Tests
label | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC.
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
label | Verifying Document - MDD and Plateau Reports
label | Frequency - 1 test per 5,000m2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.03.04 - WHAP65 Sub-Base Pavement Layer Compaction
label | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.6
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.03.05 - WHAP65 Sub-Base Layer thickness.
label | Acceptance / Conformance Criteria - The Sub-basecourse shall be monitored for Layer thickness.
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Verification Activity: Activity - W
label | Verification Activity: By - SV / PE
checkpoint | 13.03.06 - Surface Shape
label | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey / Straight edge Report
label | Frequency - Prior to sealing
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.03.07 - Holding Water
label | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
label | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey
label | Frequency - Prior to sealing
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.03.08 - Proof Rolling
label | Acceptance / Conformance Criteria - Sub-base layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass.
label | Standard / Specification - PS 20.5.2.2
label | Verifying Document - Site Records
label | Frequency - Before proceeding with works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 13.07 Construction Of Basecourse – NZTA M/4 AP40 Pavement Type C
checkpoint | 13.07.01 - Material Placement
label | Acceptance / Conformance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Continuous monitoring.
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.07.02 - Greenfield Sites Plateau Density Tests
label | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.5
label | Verifying Document - MDD and Plateau Reports
label | Frequency - 1 test per 5,000m2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.07.03 - Overlay Sites Plateau Density Tests
label | Acceptance / Conformance Criteria - The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC.
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.5
label | Verifying Document - MDD and Plateau Reports
label | Frequency - 1 test per 5,000m2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.07.04 - Basecourse Pavement Layer Compaction
label | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.6
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.07.05 - Basecourse Layer thickness.
label | Acceptance / Conformance Criteria - The Basecourse shall be monitored for Layer thickness.
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.5
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Verification Activity: Activity - W
label | Verification Activity: By - SV / PE
checkpoint | 13.07.06 - Surface Shape
label | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey / Straight edge Report
label | Frequency - Prior to sealing
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.07.07 - Holding Water
label | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey
label | Frequency - Prior to sealing
label | Verification Activity: Activity - I
label | Verification Activity: By - SV / PE
checkpoint | 13.07.08 - Running Course
label | Acceptance / Conformance Criteria - If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface.
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 10.1
label | Verifying Document - Site Notes
label | Frequency - Prior to sealing
label | Verification Activity: Activity - S
label | Verification Activity: By - SUP
checkpoint | 13.07.09 - Surface Finish post sweeping
label | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.8
label | Verifying Document - Photos
label | Frequency - Prior to sealing
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 13.07.10 - NAASRA roughness
label | Acceptance / Conformance Criteria - The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements.
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.7
label | Verifying Document - Test Report
label | Frequency - Prior to sealing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.07.11 - Presealing Requirements
label | Acceptance / Conformance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 60%.
label | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 12
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 14.02 Chipsealing
checkpoint | 14.02.01 - Sealing Procedure
label | Acceptance / Conformance Criteria - Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, P4, P17, and Q/1.
label | Standard / Specification - M/1, M/6, M/13, P/3, P4, P17, and Q/1.
label | Verifying Document - Methodology / Construction Pack
label | Frequency - Prior to Sealing
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.02.02 - Seal Design / Binder application rate
label | Acceptance / Conformance Criteria - The sealing design including binder application rate to suit the surface conditions shall be approved by the Design Engineer prior to sealing.
label | Standard / Specification - TNZ P3 TNZ P4
label | Verifying Document - Approved Seal Design
label | Frequency - Prior to Sealing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.02.03 - Presealing Requirements
label | Acceptance / Conformance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 60%.
label | Standard / Specification - TNZ B02
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests Per Lot 1000m2 Max Lot Size
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.02.04 - PreSeal inspection
label | Acceptance / Conformance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
label | Standard / Specification - TNZ P3 TNZ B02
label | Verifying Document - Hold Point Release
label | Frequency - A minimum of 24 hours’ notice of intention to seal.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.02.05 - Spray Temperature
label | Acceptance / Conformance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Prior to Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.02.06 - Binder Sampling
label | Acceptance / Conformance Criteria - A minimum of two samples per bitumen distributor load shall be taken. The first of these samples shall be taken at the end of the initial spray run and the other immediately before the final spray run. Bitumen to be tested on Engineers instruction.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Each Worksite
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.02.07 - Quantity of Binder Sprayed
label | Acceptance / Conformance Criteria - The quantity of binder sprayed in any spray run, measured by dipstick reading, shall not vary from the amount directed by more than 50 litres plus 4% of the amount directed.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Every Spray Run
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.02.08 - Chip Application
label | Acceptance / Conformance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - Every Spray Run
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.02.09 - Surplus Chip Removal
label | Acceptance / Conformance Criteria - Surplus chips shall be removed from the sealed surface prior to the removal of the temporary speed restriction signs.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site Notes
label | Frequency - 24 hours of Completion of any Section of Seal.
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.02.10 - Post Seal Inspections
label | Acceptance / Conformance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
label | Standard / Specification - TNZ P3
label | Verifying Document - Engineers Acceptance
label | Frequency - Prior to TM Removal and After Final Sweeping
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.02.11 - Chipseal Repairs
label | Acceptance / Conformance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
label | Standard / Specification - TNZ P3
label | Verifying Document - Approved Repair Methodology
label | Frequency - Prior to Repairs
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 14.03 Construction Activity - NZTA M10 - Specification for dense-graded asphaltic concrete
checkpoint | 14.03.01 - Construction Trail
label | Acceptance / Conformance Criteria - Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. Asphalt manufactured in the production trial can also be used in the construction trial if it meets the requirements of the specification.
label | Standard / Specification - PS 21.3.1 NZTA M10:2020 - 7
label | Verifying Document - Test Results
label | Frequency - As Required, two days before the site work is due to commence.
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.02 - Paving Plan
label | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
label | Standard / Specification - NZTA M10:2020 - 8, 9
label | Verifying Document - Construction Work Pack
label | Frequency - 7 days prior to construction of the asphalt pavement.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.03.03 - Preparation of Area to be Paved
label | Acceptance / Conformance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Pre Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.04 - Protection of Services
label | Acceptance / Conformance Criteria - The Contractor shall prevent tack coat, binder, aggregate, asphalt or other material used on the work from entering, adhering or obstructing gratings, hydrants, valve boxes, inspection pit covers, kerbs and other road fixtures
label | Standard / Specification - NZTA M10:2020
label | Verifying Document - Environmental Inspections
label | Frequency - Daily
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.03.05 - Ambient Conditions for Placing
label | Acceptance / Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C, for SAC the minimum temperature is 5°C
label | Standard / Specification - NZTA M10:2020
label | Verifying Document - Site Notes
label | Frequency - Pre Seal
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 14.03.06 - Tack Coating
label | Acceptance / Conformance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Prior to Paving
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.07 - Asphalt Production Conformance
label | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass
label | Standard / Specification - NZTA M10:2020 -Table 3.1 & 5.1
label | Verifying Document - Test Results
label | Frequency - 1 per 200T, Min 3 tests per mix
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.08 - Core Thickness
label | Acceptance / Conformance Criteria - The layer thickness determined from measurements on the cores LCV of no less than the specified thickness - refer clause 9.7
label | Standard / Specification - NZTA M10:2020
label | Verifying Document - Lab Report
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.03.09 - Mat Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300m² with a minimum of eight cores representing each lot
label | Standard / Specification - ASTM D5361 NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 14.03.10 - Joint Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100m of joint with a minimum of three representing each lot
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 3 per lot (day) (1 per 100 m of joint)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 14.03.11 - Density Testing
label | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Lab Report
label | Frequency - within 24 hours of them being cut from the pavement
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.12 - NDM Density
label | Acceptance / Conformance Criteria - NDMs are to be completed at the time of placing to ensure compliance when cores are taken
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - IANZ Lab Report
label | Frequency - min 8 per lot (day)
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.03.13 - Transverse truth of the surface
label | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Post Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.03.14 - Finished Pavement Level, Alignment, and Thickness
label | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements.
label | Standard / Specification - NZTA M10:2020 - 10
label | Verifying Document - Survey
label | Frequency - Continuous thought construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | 14.04 Construction Activity - NZTA M27 - Specification for stone mastic asphalt.
checkpoint | 14.04.01 - Construction Trail
label | Acceptance / Conformance Criteria - Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. SMA manufactured in the production trial can also be used in the construction trial provided that it meets the requirements of the specification.
label | Standard / Specification - PS 21.2.1 NZTA M27:2020 - 7
label | Verifying Document - Test Results
label | Frequency - As Required, two days before the site work is due to commence.
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.02 - Paving Plan
label | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
label | Standard / Specification - NZTA M27:2020 - 8, 9
label | Verifying Document - Construction Work Pack
label | Frequency - 7 days prior to construction of the asphalt pavement.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.04.03 - Preparation of Area to be Paved
label | Acceptance / Conformance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Pre Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.04 - Protection of Services
label | Acceptance / Conformance Criteria - The Contractor shall prevent tack coat, binder, aggregate, asphalt or other material used on the work from entering, adhering or obstructing gratings, hydrants, valve boxes, inspection pit covers, kerbs and other road fixtures
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Environmental Inspections
label | Frequency - Daily
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.04.05 - Ambient Conditions for Placing
label | Acceptance / Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Pre Seal
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 14.04.06 - Tack Coating
label | Acceptance / Conformance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. Where SMA is to be spread over clean, freshly placed asphalt, the Engineer can direct the Contractor to omit the tack coat.
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Prior to Paving
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.07 - Asphalt Production Conformance
label | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass
label | Standard / Specification - NZTA M27:2020 - Table 3.1 & 5.1
label | Verifying Document - Test Results
label | Frequency - 1 per 200T, Min 3 tests per mix
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.08 - Core Thickness
label | Acceptance / Conformance Criteria - The M/27:2020 requirement is LCV of no less than the specified thickness - refere clause 9.7
label | Standard / Specification - NZTA M27:2020 -
label | Verifying Document - Lab Report
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 14.04.09 - Mat Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot
label | Standard / Specification - ASTM D5361 NZTA M27:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 14.04.10 - Joint Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100 m of joint with a minimum of three representing each lot
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 3 per lot (day) (1 per 100 m of joint)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 14.04.11 - Density Testing
label | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Lab Report
label | Frequency - within 24 hours of them being cut from the pavement
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.12 - NDM Density
label | Acceptance / Conformance Criteria - NDMs are to be completed at the time of pacing to ensure compile when cores are taken
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - IANZ Lab Report
label | Frequency - min 8 per lot (day)
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 14.04.13 - Transverse truth of the surface
label | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge.
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Post Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 14.04.14 - Finished Pavement Level, Alignment, and Thickness
label | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements.
label | Standard / Specification - NZTA M27:2020 - 10
label | Verifying Document - Survey
label | Frequency - Continuous thought construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | 14.05 Roughness
checkpoint | 14.05.01 - For a Chip Sealed Surface
label | Acceptance / Conformance Criteria - Target is an average of 60 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 70 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km.
label | Standard / Specification - PS 21.4.1
label | Verifying Document - Test Report
label | Frequency - Prior to sealing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14.05.02 - For an Asphaltic Concrete Surface
label | Acceptance / Conformance Criteria - Target is an average of 50 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 60 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km.
label | Standard / Specification - PS 21.4.1
label | Verifying Document - Test Report
label | Frequency - Prior to sealing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 14.06 Skid Resistance
checkpoint | 14.06.01 - Skid Resistance
label | Acceptance / Conformance Criteria - The surfacing shall meet the requirements specified in the Transport Agency’s T10:2010 Skid Resistance Deficiency Investigation and Treatment Selection, and any other subsequent amendments.
label | Standard / Specification - PS 21.5.1
label | Verifying Document - Prior to Project Completion
label | Frequency - Prior to sealing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT