## PAVEMENT
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP no: | Z1-WB-PAV
|  |  |  | Project: NZTA 5363 CIP SH30 Te Ngae Road Corridor-Iles Rd to Coulter Rd |  |  |  |  | Associated Docs
|  |  |  | Construction Process: Type A Pavement |  |  |  |  | Rev number: | 0
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 700 - Surfacing
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record Document | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
700 | Pre-construction / Preliminary Compliance Requirements
700.1 | Method Statement Development / Job Safety Analysis / Enviro Site Specific Plans |  | H | Prior to Construction |  | Method Statement and JSEA Completed and signed by relevant authority |  | HP - Downer
700.2 | Drawings and Specification |  | H | Prior to Construction |  | DWG’s and Specifications are of For Construction and latest revision. Reviewed and approved by Designer and Client. |  | HP - Downer
700.3 | Set out |  | H | Prior to Construction |  | Set out as per latest Design Model / For Construction Drawings. |  | R - Designer
700.4 | Material Approvals |  | H | Prior to Construction | Quarry Testing Data | Material approvals to be sent to the Engineer. Refer Project Specs and Drawings; • EME2: o Validation of Mix Design o Grading (Fine and Coarse) o EME2 Binder Properties o Binder Content and Grading + MSG o Air Voids o Mix Discharge Temperature • SMA10: o Validation of Mix Design o Grading (Fine and Coarse) o SMA10 Binder Properties o Binder Content and Grading + MSG o Air Voids o Mix Discharge Temperature |  | HP - Designer
| Paving Plan |  |  | Section 9.5.1 M10 |  | The Contractor shall supply the Engineer with a detailed paving plan to be followed by the paver in placing individual lanes |  | HP - Downer
Construction and Finshing
700.6 | Tack Coat / Membrane Seal (Chip seal) | Membrane | W | Once per lot | QC Sheet | • Tack coat be applied to provide a uniform application rate of residual binder ofbetween 0.2 and 0.6 L/m², depending on the texture and absorption of the substrate. Tack coat application rates shall be within ±0.1 L/m² of the specified rate. • Chip seal to consist of at least 1.0 L/m² of residual binder and sparingly covered with a single layer of sealing chip, normally NZTA M6 Grade 4. | QC Sheet / Photographs | Contractor
700.7 | EME2 | Pavement Density / Compaction | H | 1 test per 300m2 on the mat and 1 test per 100m length on the join. | NDM Testing | Mat: Mean air voids JMF +3,-2Join: Mean air voids JMF +5,-2 | Test Results | Contractor
700.8 |  | Weather Conditions | W | Daily | QC Sheet | • Air and Surface temperature check prior to paving, 5˚c for structural and intermediate layers. | Site Records | Contractor
700.9 |  | Mix Delivery | W | Per Truck | QC Sheet | • Greater than 115 ˚ C at time of primary compaction | Site Records | Contractor
700.1 |  | Paving / Placement | W | Each Shift | QC Sheet | • Thickness, Spreading & Trimming, Joints & Rolling Pattern. Compacted thickness of 160mm paved in two lifts each 80mm thick. • Determine optimum rolling pattern and number of passes to achieve air voids <6% (target 4%) • Measured surface temp shall be 100-175 deg C during compaction | Site records/photos | Contractor
700.11 |  | Production Testing: Binder Content and Aggregate Grading | W | 1 / 200t or maximum of 3 required per production lot | Lab Testing | As per material mix design. Within production tolerances of table 5.3 NZTA M/10. | IANZ Lab Reports | Asphalt Plant
700.12 | SMA10 | Pavement Density / Compaction | H | 1 test per 300m2 on the mat and 1 test per 100m length on the join. | NDM Testing | Mat: Mean air voids JMF +3,-2Join: Mean air voids JMF +5,-2 | Test Results | Contractor
700.13 |  | Weather Conditions | W | Daily | QC Sheet | • Air and Surface temperature check prior to paving 10 ˚c for surfacing layer | Site Records | Contractor
700.14 |  | Mix Delivery | W | Per Truck | QC Sheet | • Greater than 115 ˚ C at time of primary compaction | Site Records | Contractor
700.15 |  | Paving / Placement | W | Each Shift | QC Sheet | • Thickness, Spreading & Trimming, Joints & Rolling Pattern. Compacted thickness of 40mm. Joints to be outside vehicle wheel paths as much as possible. • Determine optimum rolling pattern and number of passes to achieve air voids <6% (target 4%) • Measured surface temp shall be 100-175 deg C during compaction | Site records/photos | Contractor
700.16 |  | Production Testing: Binder Content and Aggregate Grading | W | 1 / 200t or maximum of 3 required per production lot | Lab Testing | As per material mix design. Within production tolerances of table 5.3 NZTA M/10. | IANZ Lab Reports | Asphalt Plant
700.17 | AC14 | Pavement Density / Compaction | H | 1 test per 300m2 on the mat and 1 test per 100m length on the join. | NDM Testing | Mat: Mean air voids JMF +3,-2Join: Mean air voids JMF +5,-2 | Test Results | Contractor
700.18 |  | Weather Conditions | W | Daily | QC Sheet | • Air and Surface temperature check prior to paving 10 ˚c for surfacing layer | Site Records | Contractor
700.19 |  | Mix Delivery | W | Per Truck | QC Sheet | • Greater than 115 ˚ C at time of primary compaction | Site Records | Contractor
700.2 |  | Paving / Placement | W | Each Shift | QC Sheet | • Thickness, Spreading & Trimming, Joints & Rolling Pattern. Compacted thickness of 40mm. Joints to be outside vehicle wheel paths as much as possible. • Determine optimum rolling pattern and number of passes to achieve air voids <6% (target 4%) • Measured surface temp shall be 100-175 deg C during compaction | Site records/photos | Contractor
700.21 |  | Production Testing: Binder Content and Aggregate Grading | W | 1 / 200t or maximum of 3 required per production lot | Lab Testing | As per material mix design. Within production tolerances of table 5.3 NZTA M/10. | IANZ Lab Reports | Asphalt Plant
Close Out
700.22 | Collate above documentation | Document review | H | Each ITP | Review |  | N/A | Contractor
700.23 | As-built drawings | Survey | H | At completion of construction | Asbuilts to be submitted at the completion of construction | - As-built to be submitted at the completion of construction - Information to be captured: - Maintain Redline drawings through works. | N/A | Contractor
700.24 | RAMM Data | Drawing | H | At completion of construction | Info to be submitted by the completion of project construction | - Information to be captured: | N/A | Contractor
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [5 empty] | Date: _____________________________ | H | Hold Point
Contractor's Rep Name:_____________________________________________ | [5 empty] | Date: _____________________________ | W | Witness Point
BBO Engineers Rep Name:____________________________________ | [6 empty] | M | Monitor Point