## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Surfacing | itp |  |  |  |  | ITP - Surfacing
section | Pre-construction / Preliminary Compliance Requirements
checkpoint | 700.1 - Method Statement Development / Job Safety Analysis / Enviro Site Specific Plans
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority
label | Responsibility - HP - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 700.2 - Drawings and Specification
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - DWG’s and Specifications are of For Construction and latest revision. Reviewed and approved by Designer and Client.
label | Responsibility - HP - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 700.3 - Set out
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - Set out as per latest Design Model / For Construction Drawings.
label | Responsibility - R - Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 700.4 - Material Approvals
label | H
label | Minimum Test Frequency - Prior to Construction
label | Inspection / Test method - Quarry Testing Data
label | Acceptance Criteria - Material approvals to be sent to the Engineer. Refer Project Specs and Drawings;
label | – EME2:
label | ○ Validation of Mix Design
label | ○ Grading (Fine and Coarse)
label | ○ EME2 Binder Properties
label | ○ Binder Content and Grading + MSG
label | ○ Air Voids
label | ○ Mix Discharge Temperature
label | – SMA10:
label | ○ Validation of Mix Design
label | ○ Grading (Fine and Coarse)
label | ○ SMA10 Binder Properties
label | ○ Binder Content and Grading + MSG
label | ○ Air Voids
label | ○ Mix Discharge Temperature
label | Responsibility - HP - Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Paving Plan
label | Minimum Test Frequency - Section 9.5.1 M10
label | Acceptance Criteria - The Contractor shall supply the Engineer with a detailed paving plan to be followed by the paver in placing individual lanes
label | Responsibility - HP - Downer
section | Construction and Finshing
checkpoint | 700.6 - Tack Coat / Membrane Seal (Chip seal)
label | Detail of Activity - Membrane
label | W
label | Minimum Test Frequency - Once per lot
label | Inspection / Test method - QC Sheet
label | Acceptance Criteria - Tack coat be applied to provide a uniform application rate of residual binder ofbetween 0.2 and 0.6 L/m², depending on the texture and absorption of the substrate. Tack coat application rates shall be within ±0.1 L/m² of the specified rate.
label | ○ Chip seal to consist of at least 1.0 L/m² of residual binder and sparingly covered with a single layer of sealing chip, normally NZTA M6 Grade 4.
label | Record Document - QC Sheet / Photographs
label | Responsibility - Contractor
checkpoint | 700.7 - EME2
label | Detail of Activity - Pavement Density / Compaction
label | H
label | Minimum Test Frequency - 1 test per 300m2 on the mat and 1 test per 100m length on the join.
label | Inspection / Test method - NDM Testing
label | Acceptance Criteria - Mat: Mean air voids JMF +3,-2Join: Mean air voids JMF +5,-2
label | Record Document - Test Results
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 700.8 - EME2
label | Detail of Activity - Weather Conditions
label | W
label | Minimum Test Frequency - Daily
label | Inspection / Test method - QC Sheet
label | Acceptance Criteria - Air and Surface temperature check prior to paving, 5 °C for structural and intermediate layers.
label | Record Document - Site Records
label | Responsibility - Contractor
checkpoint | 700.9 - EME2
label | Detail of Activity - Mix Delivery
label | W
label | Minimum Test Frequency - Per Truck
label | Inspection / Test method - QC Sheet
label | Acceptance Criteria - Greater than 115 °C at time of primary compaction
label | Record Document - Site Records
label | Responsibility - Contractor
checkpoint | 700.10 - EME2
label | Detail of Activity - Paving / Placement
label | W
label | Minimum Test Frequency - Each Shift
label | Inspection / Test method - QC Sheet
label | Acceptance Criteria - Thickness, Spreading & Trimming, Joints & Rolling Pattern. Compacted thickness of 160mm paved in two lifts each 80mm thick.
label | ○ Determine optimum rolling pattern and number of passes to achieve air voids <6% (target 4%)
label | ○ Measured surface temp shall be 100-175 °C during compaction
label | Record Document - Site records/photos
label | Responsibility - Contractor
checkpoint | 700.11 - EME2
label | Detail of Activity - Production Testing: Binder Content and Aggregate Grading
label | W
label | Minimum Test Frequency - 1 / 200t or maximum of 3 required per production lot
label | Inspection / Test method - Lab Testing
label | Acceptance Criteria - As per material mix design. Within production tolerances of table 5.3 NZTA M/10.
label | Record Document - IANZ Lab Reports
label | Responsibility - Asphalt Plant
checkpoint | 700.12 - SMA10
label | Detail of Activity - Pavement Density / Compaction
label | H
label | Minimum Test Frequency - 1 test per 300m2 on the mat and 1 test per 100m length on the join.
label | Inspection / Test method - NDM Testing
label | Acceptance Criteria - Mat: Mean air voids JMF +3,-2Join: Mean air voids JMF +5,-2
label | Record Document - Test Results
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 700.13 - SMA10
label | Detail of Activity - Weather Conditions
label | W
label | Minimum Test Frequency - Daily
label | Inspection / Test method - QC Sheet
label | Acceptance Criteria - Air and Surface temperature check prior to paving 10 °C for surfacing layer
label | Record Document - Site Records
label | Responsibility - Contractor
checkpoint | 700.14 - SMA10
label | Detail of Activity - Mix Delivery
label | W
label | Minimum Test Frequency - Per Truck
label | Inspection / Test method - QC Sheet
label | Acceptance Criteria - Greater than 115 °C at time of primary compaction
label | Record Document - Site Records
label | Responsibility - Contractor
checkpoint | 700.15 - SMA10
label | Detail of Activity - Paving / Placement
label | W
label | Minimum Test Frequency - Each Shift
label | Inspection / Test method - QC Sheet
label | Acceptance Criteria - Thickness, Spreading & Trimming, Joints & Rolling Pattern. Compacted thickness of 40mm. Joints to be outside vehicle wheel paths as much as possible.
label | ○ Determine optimum rolling pattern and number of passes to achieve air voids <6% (target 4%)
label | ○ Measured surface temp shall be 100-175 °C during compaction
label | Record Document - Site records/photos
label | Responsibility - Contractor
checkpoint | 700.16 - SMA10
label | Detail of Activity - Production Testing: Binder Content and Aggregate Grading
label | W
label | Minimum Test Frequency - 1 / 200t or maximum of 3 required per production lot
label | Inspection / Test method - Lab Testing
label | Acceptance Criteria - As per material mix design. Within production tolerances of table 5.3 NZTA M/10.
label | Record Document - IANZ Lab Reports
label | Responsibility - Asphalt Plant
checkpoint | 700.17 - AC14
label | Detail of Activity - Pavement Density / Compaction
label | H
label | Minimum Test Frequency - 1 test per 300m2 on the mat and 1 test per 100m length on the join.
label | Inspection / Test method - NDM Testing
label | Acceptance Criteria - Mat: Mean air voids JMF +3,-2Join: Mean air voids JMF +5,-2
label | Record Document - Test Results
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 700.18 - AC14
label | Detail of Activity - Weather Conditions
label | W
label | Minimum Test Frequency - Daily
label | Inspection / Test method - QC Sheet
label | Acceptance Criteria - Air and Surface temperature check prior to paving 10 °C for surfacing layer
label | Record Document - Site Records
label | Responsibility - Contractor
checkpoint | 700.19 - AC14
label | Detail of Activity - Mix Delivery
label | W
label | Minimum Test Frequency - Per Truck
label | Inspection / Test method - QC Sheet
label | Acceptance Criteria - Greater than 115 ° C at time of primary compaction
label | Record Document - Site Records
label | Responsibility - Contractor
checkpoint | 700.2 - AC14
label | Detail of Activity - Paving / Placement
label | W
label | Minimum Test Frequency - Each Shift
label | Inspection / Test method - QC Sheet
label | Acceptance Criteria - Thickness, Spreading & Trimming, Joints & Rolling Pattern. Compacted thickness of 40mm. Joints to be outside vehicle wheel paths as much as possible.
label | ○ Determine optimum rolling pattern and number of passes to achieve air voids <6% (target 4%)
label | ○ Measured surface temp shall be 100-175 °C during compaction
label | Record Document - Site records/photos
label | Responsibility - Contractor
checkpoint | 700.21 - AC14
label | Detail of Activity - Production Testing: Binder Content and Aggregate Grading
label | W
label | Minimum Test Frequency - 1 / 200t or maximum of 3 required per production lot
label | Inspection / Test method - Lab Testing
label | Acceptance Criteria - As per material mix design. Within production tolerances of table 5.3 NZTA M/10.
label | Record Document - IANZ Lab Reports
label | Responsibility - Asphalt Plant
section | Close Out
checkpoint | 700.22 - Collate above documentation
label | Detail of Activity - Document review
label | H
label | Minimum Test Frequency - Each ITP
label | Inspection / Test method - Review
label | Acceptance Criteria -
label | Record Document - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 700.23 - As-built drawings
label | Detail of Activity - Survey
label | H
label | Minimum Test Frequency - At completion of construction
label | Inspection / Test method - Asbuilts to be submitted at the completion of construction
label | Acceptance Criteria - - As-built to be submitted at the completion of construction
label | ○ Information to be captured:
label | ○ Maintain Redline drawings through works.
label | Record Document - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 700.24 - RAMM Data
label | Detail of Activity - Drawing
label | H
label | Minimum Test Frequency - At completion of construction
label | Inspection / Test method - Info to be submitted by the completion of project construction
label | Acceptance Criteria - Information to be captured:
label | Record Document - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | BBO Engineers Rep Name:
signoff | Add Signature