## Enabling Works
[9 empty] | Approved | Signature
|  |  | Contract Name: | Devonport Town centre Safety Improvement |  |  |  |  | FH Engineer | GS
|  |  | Procedure: | Enabling Works - Footpath, Kerb and channel |  |  |  |  | FH Quality Manager | BL
Inspection & Test Plan / Checklist
Job No: 2095295 |  |  | Corresponding Work Instruction: |  | Documentation Required |  | Compliance with Work Instructions and Specifications
Detailed Location: Devonport
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
Pre-construction
1 | Permits & Services | Records | Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space) | Prior to any construction commencing | Document Review | Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority | Permit attached or permit number noted. | Site Engineer |  | Date
|  | Site Record | Locate and mark out all existing services | Prior to any construction commencing | GPR & Document | B4u dig procedure - follow utility protocols | B4u dig plans & GPR report attached | Site Engineer |  | Date
2 | Pre-Construction Sign Offs | Records | Sub-Contract and Supplier Agreements | Prior to commencement. | Document Review | Sub-Contract and Supplier Agreements to be agreed and signed | Subcontract and Supplier Agreements | Site Engineer |  | Date
3 | Design | Construction drawing | Design is approved and Drawings are of the latest revision. | Prior to commencement. | Document Review | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Drawing Register. | Site Engineer | Engineers Rep. | Date
4 | Survey Setout | Records | Kerb & Channel set out, catchpit, bottom of ramp, table top, streetlight, HFS extent, footpath extent, street furniture Verify existing levels vs. design Verify grades | Prior to commencement. | Survey | As per the Drawings: T18092 - R1-001 & Setout files HOLD POINT | Survey Receipt. | Site Engineer |  | Date
6 | Locate Existing Services by Hand Digging / Hydro Vac | Site Record | Ensure all services conflicting with the line of trench have been exposed by hand digging. | Prior to commencement. | Potholing / Survey | All conflicts have been located. New services and / or conflicts to be advised to Project Manager. | GPR report Photos | Site Engineer |  | Date
Kerb & Channel
2 | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Everysite | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level >1% fall | Inprocess Inspection | FH concrete QA sheet | Site Engineer |  | Date
Footpath & Berm Construction
3 | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m Intervals | Basecourse - 100mm min. thickness Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish | Inprocess Inspection HOLD POINT Prepour inspection | FH concrete QA sheet. Concrete delivery Dockets Scala | Site Engineer | Engineers Rep. | Date
4 | AC Footpaths | QA FORM | TDM Technical Standards - FP0003 | 10m Intervals | Subgrade -(CBR > 3) Basecourse - 150mm min. thickness GAP40 Clegg CIV > 13 DG10/Fine asphalt mix used 25mm | Inprocess Inspection HOLD POINT | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer | Engineers Rep. | Date
5 | Paver type FP | QA FORM | TDM Technical Standards - FP0004 | 10m Intervals | 80mm concrete Pavers,30mm compacted bedding sand,150mm Gap 40 compacted | Inprocess Inspection | Photos | Site Engineer | Engineers Rep. | Date
6 | Concrete Vehicle Crossings (VX) | QA FORM | TDM Technical Standards - VX0103 | Each VX | Basecourse - 100mm min. thickness Clegg CIV > 36 Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish 665 mesh placed centrally | Inprocess Inspection HOLD POINT Prepour inspection | FH concrete QA sheet. Concrete delivery Dockets Scala | Site Engineer | Engineers Rep. | Date
7 | Pram Crossing | QA FORM | TDM Technical Standards - FP006 | Each Xing | Tactiles Directional & Dot - 60mm 1500mm min width; 600mm flares Slope as per criteria | Inprocess Inspection HOLD POINT Prepour inspection | Photos | Site Engineer | Engineers Rep. | Date
8 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | 10m Intervals | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones. | Inprocess Inspection | Photos | Site Engineer |  | Date
9 | Service Covers and Street Furniture | Visual | AT Contract Specification 14000 | Everysite | Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works. | Inprocess Inspection | Nil | Site Engineer |  | Date
Asbuilts
10 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Site Engineer |  | Date
11 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Site Engineer |  | Date
ITP APPROVAL
Prepared By |  | Genald Sebastian | Initial | GS |  |  | Date: | 2023-06-07
Approving Delegate |  | Ben Lin | Initial | BL |  |  | Date: | 2023-06-07
Engineer's Rep |  |  | Initial |  |  |  | Date:

## Stormwater Drainage
[7 empty] | Approved |  | Signature
|  |  |  | Contract Name: | Devonport Town centre Safety Improvement |  | FH Engineer |  | GS
|  |  |  | Procedure: | Stormwater Drainage |  | FH Quality Manager |  | BL
Inspection & Test Plan / Checklist
Job No: 2095295 |  |  |  | Corresponding Work Instruction: |  | Documentation Required |  | Compliance with Work Instructions and Specifications
Detailed Location: Devonport
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
Pre-construction
1 | Permits & Services | H | Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space) | Prior to any construction commencing | Document Review | Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority | Permit attached or permit number noted. | Site Engineer |  | Date
|  | H | Locate and mark out all existing services | Prior to any construction commencing |  | B4u dig procedure - follow utility protocols | B4u dig plans & GPR report attached | Site Engineer |  | Date
2 | Pre-Construction Sign Offs | H | Sub-Contract and Supplier Agreements | Prior to commencement. | Document Review | Sub-Contract and Supplier Agreements to be agreed and signed | Subcontract and Supplier Agreements | Site Engineer |  | Date
3 | Design | H | Design is approved and Drawings are of the latest revision. | Prior to commencement. | Document Review | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Drawing Register. | Site Engineer | Engineers Rep. | Date
4 | Survey Setout | H | Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design | Prior to commencement. | Survey | As per Drawings: T18092 - R1-001 & Setout files | Survey Receipt. | Site Engineer |  | Date
5 | Pipe and Manhole Material Compliance | H | Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards | Prior to commencement. | Document Review, Visual Inspection | Pipe shall be Check for freshyly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP | Manufacturers Data Sheets, Delivery Dockets | Site Engineer |  | Date
6 | Locate Existing Services by Hand Digging / Hydro Vac | H | Ensure all services conflicting with the line of trench have been exposed by hand digging. | Prior to commencement. | Potholing / Survey | All conflicts have been located. New services and / or conflicts to be advised to Project Manager. | GPR report Photos | Site Engineer |  | Date
Stormwater Construction
7 | Trenching & Excavation | H | Excavation methodology | Daily | Prestart review | The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016) | Prestart RCP | Site Engineer |  | Date
|  | M | Trench Profile - Width | Daily / as trenching takes place. Different depth methodology | Visual Inspection, Excavation methdology | Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing | Construction Photos | Site Engineer |  | Date
|  | W | Trench Profile - Depth | Daily / as trenching takes place. | Visual Inspection, Measurement | Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings | FH Drainage Line Record / Construction Photos | Site Engineer |  | Date
8 | Bedding for Concrete Pipe Laying & Manhole & Cesspit | W | Placing and compaction of Bedding Material. | Inspected continuously during placing and compaction of Bedding Material. | Visual Inspection | Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725 | FH Drainage Line Record / Construction Photos | Site Engineer | Engineers Rep. | Date
10 | Trench Backfill - Placing & Compacting | M | Placing and compacting of Trench Backfill Material | Throughout Trench Backfilling operation. | Visual Inspection | Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm | Construction Photos | Site Engineer |  | Date
14 | Trenching | H | Inspect trench profile and ensure it is 0.300m wide | 10m intervals | Visual inspection and measurement | Record levels of base of trench on dip sheet | Photo / subsoil log | Site Engineer |  | Date
|  | H | Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings. | 10m intervals | Visual inspection and measurement | Ensure trench line and levels match the design drawings | Photo / subsoil log | Site Engineer |  | Date
15 | Catchpit Connection | W | Ensure minimum entry point 150mm above soffit of outlet stormwater pipe | As required | Visual inspection | Consistency with Subsoil Details | Photo | Site Engineer | Engineers Rep. | Date
|  | W | Perforate Catchpit and epoxy grout pipe from inside to completely seal connection. | As required | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer | Engineers Rep. | Date
16 | Gradient | W | Ensure water falls in intended direction | Throughout | Visual Inspection | Grade >1% No undulation in subsoils | Photos | Site Engineer | Engineers Rep. | Date
17 | As-Built Drawings | W | Red pen marked-up As-Builts of every 'Issued for Construction' AT / drawings | Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure. | Drawings / Visual Inspection | As Built and GIS Data | Redline As-Built Drawings, scanned as .pdf files. | Site Engineer | Engineers Rep. | Date
Subsoil Construction
17 | Subsoil Material Compliance | H | Ensure Subsoil Drainage pipe complies with TDM RD0010 | Upon delivery to site | Ensure delivery docket matches materials delivered | 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock | Delivery docket | Site Engineer |  | Date
|  | H | Ensure Material for Bedding, Side support and backfill F6 filter sand drainage aggregate | Throughout Subsoil | Visual inspection | Ensure clean drainage aggregate - F2 Spec | Delivery docket | Site Engineer |  | Date
| Subsoil construction Compliance | H | Inspect trench profile and ensure it is 0.300m wide Located below 300mm below subgrade | 10m intervals | Visual inspection and measurement | Record levels of base of trench on dip sheet | Photo / subsoil log | Site Engineer |  | Date
18 | Bedding, pipe installation and Backfill. | W | Ensure 50mm thick F6 Drainage aggregate bedding is placed in base of trench. | 10m intervals | Visual inspection | Record levels of top of bedding on dip sheet | Photo / subsoil log | Site Engineer | Engineers Rep. | Date
|  | W | Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | 10m intervals | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer | Engineers Rep. | Date
|  | W | Backfill by tipping F2 Sand into the trench | - | Visual inspection | Ensure good coverage | Photos | Site Engineer | Engineers Rep. | Date
|  | M | Ensure water falls in intended direction | Throughout | Visual Inspection | Grade >1% No undulation in subsoils | Photos | Site Engineer |  | Date
Asbuilts
8 | As built information |  | Drawings | Every Site | As built drawings | In Process Inspection | Asbuilt records | Site Engineer |  | Date
9 | RAMM DATA |  | RAMM DATA SHEET | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Site Engineer |  | Date
ITP APPROVAL
Prepared By |  | Genald Sebastian | Initial | GS |  |  | Date: | 2023-06-07
Approving Delegate |  | Ben Lin | Initial | BL |  |  | Date: | 2023-06-20
Engineer's Rep |  |  | Initial |  |  |  | Date:

## Raised Table
[5 empty] | Process Control Plan |  |  | Approved |  | Signature
[5 empty] | Contract Name: | Devonport Town centre Safety Improvement |  | FH Engineer |  | GS
[5 empty] | Procedure: | Raised Table |  | FH Manager |  | BL
Inspection & Test Plan / Checklist
| Job No: 2095295 |  |  |  | Corresponding Work Instruction: |  | Documentation Required |  | Compliance with Work Instructions and Specifications
Detailed Location: Devonport
Chainage:
| No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer/MSQA Engineer Initials (Grey if not required) | Date(s)
| 1 | Permits | H | Obtain Permits | As required | Document Review | Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer |  | Date
| 2 | Pre-construction sign offs | H | Ensure that Sub-Contract and Supplier Agreements are signed | Prior to commencement | Document Review | Signed Subcontractor and Supplier Agreements | Subcontract and Supplier Agreements | Site Engineer |  | Date
| 2.1 |  | H | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS | Prior to commencement | Document Review | TMP is approved by CAR manager for each site and works are only completed within the approved dates.. | TMP on MyWorksites/On Site | Site Engineer |  | Date
| 2.2 |  | H | Ensure all Sub-Contractors and Suppliers go through FH induction | On site daily | Induction | Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation | Hazard ID and Pre-starts to safety team | Site Engineer |  | Date
| 3 | Design | H | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Prior to commencement | Document Review | IFC drawings have been received by Contractor | Check Drawing Register | Site Engineer | Design Engineer | Date
| 4 | Installation of Erosion and Sediment Controls | H | Ensure that Erosion & Sediment Control in place | Prior to commencement | Visual Inspection | Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence | Environmental Controls Audit | Environmental Manager/Site Engineer |  | Date
| 5 | Survey Setout | H | Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations) | Prior to commencement | Survey + Smart Level | Consistency with Construction Drawing | Site Photos post surveying | Site Engineer |  | Date
| 6 | Locate Existing Services by Hand Digging | H | Ensure all services conflicting with the line of trench has been exposed by hand digging | Prior to commencement | Potholing | All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services | Digging and excavation checklist, service planes,As-Built Drawings Doc. Review | Site Engineer |  | Date
| 7 | Material Compliance | H | LESA dowels to be used at all construction joints | Prior to pouring concrete | Document Review | Photos + Delivery Docket added to QA folder | Delivery Dockets / Photos | Site Engineer |  | Date
| 7.1 |  | H | 0.25mm polythene layer placed across all surface area at bottom of raised table | Prior to pouring concrete | Visual Inspection, Document Review | Photos + Delivery Docket added to QA folder | Delivery Dockets / Photos | Site Engineer |  | Date
| 7.2 |  | H | 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer. | Prior to pouring concrete | Visual Inspection | CIV >32 | Delivery Dockets | Site Engineer |  | Date
| 7.4 |  | H | All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder and 19mm aggregate chip size RadForce Fibre | Prior to pouring concrete | Concrete Delivery Dockets | Delivery Docket added to QA folder | Concrete Delivery Dockets | Site Engineer |  | Date
Raised table Construction
| 8 | Temporary Works (Formwork) | W | Formwork to be set to correct line and level | Prior to pouring concrete | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer | MSQA Engineer | Date
| 8.1 |  | H | Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer |  | Date
| 8.2 |  | H | Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer |  | Date
| 8.3 |  | H | Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp Swedish table ramps to be 1.125m across for entry and 4m for departure ramp | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer |  | Date
| 8.4 |  | H | Raised Table ramps to be 1:15 gradient for entry and exit Swedish table ramps to be 1:15 gradient for entry and 1:40 for exit | Prior to pouring concrete | Measurement | Tolerance +0.5% -1% | Site photos / Concrete Formwork Checklist | Site Engineer |  | Date
| 8.5 |  | H | The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured | Prior to concrete pour | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer |  | Date
| 9 | Reinforcing | H | All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Speed basket system 260mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint | Prior to pouring concrete | Measurement | Concrete Inspection Record | Site photos/Concrete Formwork Checklist | Site Engineer | MSQA Engineer | Date
| 10 | Concreting | H | The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required | Prior to concrete pour | Visual inspection | Engineer will be notified via email/SMS at least 24 hours before required for inspection | Email / SMS | Site Engineer | MSQA Engineer | Date
|  |  | W | Vibrator to be used throughout concrete pour | When pouring concrete | Visual Inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer |  | Date
| 11 |  | W | Concrete ramp surfaces shall be U5 broomed finish & Table will be exposed | At completion of pour | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer |  | Date
| 12 | Curing | M | Concrete will be left for 48 hours minimum to cure before traffic is allowed on it. / 36hrs with 50Mpa | Post Pour | Monitoring the time allowed for curing | 48 hours minimum have passed/ 36hrs with 50Mpa | Concrete Formwork Checklist | Site Engineer |  | Date
| 13 | Remove formwork | W | Remove formwork after 48 hours/ 36hrs with 50Mpa | Post Curing | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer |  | Date
| 14 | Asphalt- Concrete extension slab/ Toe | H | Two rows of Lesa diamond placed mid depth @600mm C/C along construction joint as per R5-004 | Prior to pouring concrete | Measurement | Pre pour Inspection Checklist, Concrete Inspection records | Site photos,delivery dockets | Site Engineer | MSQA Engineer | Date
|  |  | H | 250mm thick 40/50MPa Concrete with two layers of 663 mesh, 60mm cover | Prior to pouring concrete | Measurement | Pre pour Inspection Checklist, Concrete Inspection records | Site photos,delivery dockets | Site Engineer | MSQA Engineer | Date
|  |  | W | Tack Coat between DG10/AC14 and Concrete slab | Post Curing | Visual inspection | Photos + Delivery Docket added to QA folder | Site photos | Site Engineer |  | Date
|  |  | W | 50mm thick DG10/AC14 | Post Curing | Measurement | Photos + Delivery Docket added to QA folder | Site photos, QA records,delivery dockets | Site Engineer |  | Date
| 15 | Lot Number QA File | W | Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file | At completion of Lot | Document Review | All QA files compiled and sumbitted to client | QA records | Site Engineer |  | Date
|  |  | W | Delivery Dockets to be included in QA file | At completion of Lot | Document Review | Delivery Dockets to be included in QA file | QA records | Site Engineer |  | Date
Asbuilts
| 8 | As built information |  | Drawings | Every Site | As built drawings | In Process Inspection | Asbuilt records | Site Engineer |  | Date
| 9 | RAMM DATA |  | RAMM DATA SHEET | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Site Engineer |  | Date
ITP APPROVAL
| Prepared By |  | Genald Sebastian | Initial | GS |  |  | Date: | 2023-06-07
| Approving Delegate |  | Ben Lin | Initial | BL |  |  | Date: | 2023-06-20
| Engineer's Rep |  |  | Initial |  |  |  | Date:

## Ducting
|  |  |  | ITP |  |  | Approved |  | Signature
|  |  |  | Contract Name: | Devonport Town centre Safety Improvement |  | FH Engineer |  | GS
|  |  |  | Procedure: | Ducting |  | FH Project Engineer |  | BL
Inspection & Test Plan / Checklist
Job No: 2095295 |  |  |  | Corresponding Work Instruction: |  | Potholing and traffic signal installation |  | Compliance with Work Instructions and Specifications
Detailed Location: Devonport
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
Pre-Construction
1 | Permits | H | Obtain Permits | As required | Document Review | Authorisation to work, dig permit and first gas permit obtained | This ITP signed | Site Engineer |  | Date
2 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer |  | Date
3 | Survey Setout | H | Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor. | Prior to commencement | Survey | Consistency with Drawings and Specifiactions | Survey Records | Site Engineer |  | Date
|  | H | Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation. | Prior to commencement | Visual Inspection | Consistency with Drawings and Specifiactions | Photos / Engineers approval documentation | Site Engineer |  | Date
4 | Locate existing services by hand digging/ hydrovac | W | Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation | Prior to Installation | Potholing | All conflicts have been located and survey as built recorded | Digging/Excavating Control Checklist | Site Engineer |  | Date
5 | Material Compliance | H | Ensure duct pipes and poles are as per drawings and specification | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | Site Engineer |  | Date
|  | H | Ensure all concrete used is 20MPa mix | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | Site Engineer |  | Date
Ducting
6 | Trenching | H | Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing) | 10m Intervals | Visual Inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer |  | Date
6.1 |  | H | Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs | 10m Intervals | Measure | Ensure trench alignment and levels match the design drawings | Stringline records & Photos | Site Engineer |  | Date
7 | Duct Installation | W | Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct. | Prior to Installation | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer |  | Date
7.1 |  | H | Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer |  | Date
7.2 |  | H | Asbuilt Survey | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Survey Records | Site Engineer |  | Date
8 | Bedding | H | Lay min. 150mm gap20 or finer for bedding and haunching | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer |  | Date
9 | Warning Tape | H | Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines. | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer |  | Date
Asbuilts
8 | As built information |  | Drawings | Every Site | As built drawings | In Process Inspection | Asbuilt records | Site Engineer |  | Date
9 | RAMM DATA |  | RAMM DATA SHEET | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Site Engineer |  | Date
ITP APPROVAL
Prepared By |  | Genald Sebastian | Initial | GS |  |  | Date: | 2023-06-07
Approving Delegate |  | Ben Lin | Initial | BL |  |  | Date: | 2023-06-20
Engineer's Rep |  |  | Initial |  |  |  | Date:

## Traffic Island
Devonport Town centre Safety Improvement
Site Location |  |  | Devonport |  |  |  | Job No: 2095295
Traffic Islands
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Materials
1 | Mountable Kerb | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Everysite | Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint | Inprocess Inspection | FH concrete QA sheet, photos. | Site Engineer
Construction
2 | Survey Setout | Survey | Setout Kerb Alignment required to construct to design | Prior to commencement. | Survey | As per Construction Drawings HOLD POINT | Survey Receipt. | Site Engineer
3 | Concrete Island | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | Kerbs to be haunced with 20MPa Concrete | Inprocess Inspection | Photos | Site Engineer
|  | QA FORM | TDM Technical Standards - IS0001 & IS0003 | Each Site | Basecourse to be 150mm min thickness of GAP65 | Inprocess Inspection | Photos | Site Engineer
4 | Concrete Infill | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
Asbuilts
5 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Supervisor and Engineer
6 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Genald Sebastian | Initial | GS |  |  | Date: | 2023-06-07
Approving Delegate |  | Ben Lin | Initial | BL |  |  | Date: | 2023-06-20
Engineer's Rep |  |  | Initial |  |  |  | Date:

## Signage
Devonport Town centre Safety Improvement
Construction Works - Signage & E-Signage
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Signage Construction
1 | Survey Setout | Records | Signage set out, check for clearance and sight distances | Prior to commencement. | Survey | HOLD POINT | Survey Receipt. | Site Engineer
1 | Signage Foundation | In Situ | MOTSAM Technical Standards | Each sign | Boxed Foundation of dimension 300x300mm. Depth 600mm | Inprocess Inspection | Photos. Concrete Bag Spec. | Site Engineer
2 | Signage Foundation | In Situ | MOTSAM Technical Standards | Each sign | Put up sign on 60mm or 76mm steel galv pole. Angle sign towards traffic at 15 degrees. | Inprocess Inspection | Photos. | Site Engineer
Asbuilts
3 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Supervisor and Engineer
4 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Genald Sebastian | Initial | GS |  |  | Date: | 2023-06-20
Approving Delegate |  | Ben Lin | Initial | BL |  |  | Date: | 2023-06-20
Engineer's Rep |  |  | Initial |  |  |  | Date: