## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Enabling Works - Footpath, Kerb and channel | itp |  |  |  |  | Devonport Town Centre - ITP - Enabling Works - Footpath, Kerb and channel
section | Pre-construction
checkpoint | 1 - Permits & Services (1)
label | VERIFICATION ACTIVITY: Records
label | METHODS OR REFERENCE: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | FREQUENCY: Prior to any construction commencing
label | ACCEPTANCE CRITERIA: Document Review
label | HOLD POINT: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority.
label | RECORDS: Permit attached or permit number noted.
checkpoint | 1 - Permits & Services (2)
label | VERIFICATION ACTIVITY: Site Record
label | METHODS OR REFERENCE: Locate and mark out all existing services
label | FREQUENCY: Prior to any construction commencing
label | ACCEPTANCE CRITERIA: GPR & Document
label | HOLD POINT: B4u dig procedure - follow utility protocols
label | RECORDS: B4u dig plans & GPR report attached
checkpoint | 2 - Pre-Construction Sign Offs
label | VERIFICATION ACTIVITY: Records
label | METHODS OR REFERENCE: Sub-Contract and Supplier Agreements
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Document Review
label | HOLD POINT: Sub-Contract and Supplier Agreements to be agreed and signed
label | RECORDS: Subcontract and Supplier Agreements
checkpoint | 3 - Design
label | VERIFICATION ACTIVITY: Construction drawing
label | METHODS OR REFERENCE: Design is approved and Drawings are of the latest revision.
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Document Review
label | HOLD POINT: Ensure that Design is approved and Drawings are of the latest revision.
label | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
label | ○ HOLD POINT of not issued to IFC.
label | RECORDS: Drawing Register.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Survey Setout
label | VERIFICATION ACTIVITY: Records
label | METHODS OR REFERENCE: Kerb & Channel set out, catchpit, bottom of ramp, table top, streetlight, HFS extent, footpath extent, street furniture
label | ○ Verify existing levels vs. design
label | ○ Verify grades
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: As per the Drawings: T18092 - R1-001 & Setout files, HOLD POINT
label | RECORDS: Survey Receipt.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | VERIFICATION ACTIVITY: Site Record
label | METHODS OR REFERENCE: Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Potholing / Survey
label | HOLD POINT: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | RECORDS: GPR report, Photos
section | Kerb & Channel
checkpoint | 2 - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level >1% fall
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet
section | Footpath & Berm Construction
checkpoint | 3 - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness
label | ○ Clegg CIV > 12
label | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | HOLD POINT: Inprocess Inspection, HOLD POINT, Prepour inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets, Scala
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - AC Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0003
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
label | ○ Basecourse - 150mm min. thickness GAP40
label | ○ Clegg CIV > 13
label | ○ DG10/Fine asphalt mix used 25mm
label | HOLD POINT: Inprocess Inspection, HOLD POINT
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Paver type FP
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0004
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: 80mm concrete Pavers,30mm compacted bedding sand,150mm Gap 40 compacted
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
checkpoint | 6 - Concrete Vehicle Crossings (VX)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX0103
label | FREQUENCY: Each VX
label | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness
label | ○ Clegg CIV > 36
label | ○ Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | ○ 665 mesh placed centrally
label | HOLD POINT: Inprocess Inspection, HOLD POINT, Prepour inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets, Scala
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Pram Crossing
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP006
label | FREQUENCY: Each Xing
label | ACCEPTANCE CRITERIA: Tactiles Directional & Dot - 60mm
label | ○ 1500mm min width; 600mm flares
label | ○ Slope as per criteria
label | HOLD POINT: Inprocess Inspection, HOLD POINT, Prepour inspection
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
checkpoint | 9 - Service Covers and Street Furniture
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AT Contract Specification 14000
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Nil
section | Asbuilts
checkpoint | 10 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
checkpoint | 11 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Genald Sebastian
note | Approving Delegate: Ben Lin
textbox | Engineer's Rep
checklist | ITP - Stormwater Drainage | itp |  |  |  |  | Devonport Town Centre - ITP - Stormwater Drainage
section | Pre-construction
checkpoint | 1 - Permits & Services (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | FREQUENCY: Prior to any construction commencing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority.
label | RECORDS: Permit attached or permit number noted.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1 - Permits & Services (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Locate and mark out all existing services
label | FREQUENCY: Prior to any construction commencing
label | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols
label | RECORDS: B4u dig plans & GPR report attached
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-Construction Sign Offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Sub-Contract and Supplier Agreements
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
label | RECORDS: Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Design is approved and Drawings are of the latest revision.
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
label | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
label | ○ HOLD POINT of not issued to IFC.
label | RECORDS: Drawing Register.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Survey Setout
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
label | CONFORMANCE CRITERIA: As per Drawings: T18092 - R1-001 & Setout files
label | RECORDS: Survey Receipt.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pipe and Manhole Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
label | CONFORMANCE CRITERIA: Pipe shall be Check for freshly formed pipes and return if required
label | 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058
label | 2). All Concrete RCRRJ pipes to be fitted with Rubber rings
label | 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
label | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | RECORDS: Manufacturers Data Sheets, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
label | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | RECORDS: GPR report, Photos
holdpoint | AUTHORITY HOLDPOINT
section | Stormwater Construction
checkpoint | 7 - Trenching & Excavation (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Excavation methodology
label | FREQUENCY: Daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
label | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | RECORDS: Prestart RCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (2)
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Trench Profile - Width
label | FREQUENCY: Daily / as trenching takes place. Different depth methodology
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methdology
label | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | RECORDS: Construction Photos
checkpoint | 7 - Trenching & Excavation (3)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Trench Profile - Depth
label | FREQUENCY: Daily / as trenching takes place.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
label | CONFORMANCE CRITERIA: Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | RECORDS: FH Drainage Line Record / Construction Photos
checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Placing and compaction of Bedding Material.
label | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | RECORDS: FH Drainage Line Record / Construction Photos
checkpoint | 10 - Trench Backfill - Placing & Compacting
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Placing and compacting of Trench Backfill Material
label | FREQUENCY: Throughout Trench Backfilling operation.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | RECORDS: Construction Photos
checkpoint | 14 - Trenching (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Inspect trench profile and ensure it is 0.300m wide
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
label | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet
label | RECORDS: Photo / subsoil log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Trenching (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
label | CONFORMANCE CRITERIA: Ensure trench line and levels match the design drawings
label | RECORDS: Photo / subsoil log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Catchpit Connection (1)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photo
checkpoint | 15 - Catchpit Connection (2)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photos
checkpoint | 16 - Gradient
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure water falls in intended direction
label | FREQUENCY: Throughout
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Grade >1%, No undulation in subsoils
label | RECORDS: Photos
checkpoint | 17 - As-Built Drawings
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction' AT / drawings
label | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
label | CONFORMANCE CRITERIA: As Built and GIS Data
label | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
section | Subsoil Construction
checkpoint | 17 - Subsoil Material Compliance (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Subsoil Drainage pipe complies with TDM RD0010
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials delivered
label | CONFORMANCE CRITERIA: 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
label | RECORDS: Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Subsoil Material Compliance (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Material for Bedding, Side support and backfill F6 filter sand drainage aggregate
label | FREQUENCY: Throughout Subsoil
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Ensure clean drainage aggregate - F2 Spec
label | RECORDS: Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Subsoil construction Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Inspect trench profile and ensure it is 0.300m wide
label | ○ Located below 300mm below subgrade
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
label | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet
label | RECORDS: Photo / subsoil log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18 - Bedding, pipe installation and Backfill. (1)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure 50mm thick F6 Drainage aggregate bedding is placed in base of trench.
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Record levels of top of bedding on dip sheet
label | RECORDS: Photo / subsoil log
checkpoint | 18 - Bedding, pipe installation and Backfill. (2)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photos
checkpoint | 18 - Bedding, pipe installation and Backfill. (3)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Backfill by tipping F2 Sand into the trench
label | FREQUENCY: -
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Ensure good coverage
label | RECORDS: Photos
checkpoint | 18 - Bedding, pipe installation and Backfill. (4)
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Ensure water falls in intended direction
label | FREQUENCY: Throughout
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Grade >1%, No undulation in subsoils
label | RECORDS: Photos
section | Asbuilts
checkpoint | 8 - As built information
label | DETAIL: Drawings
label | FREQUENCY: Every Site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): As built drawings
label | CONFORMANCE CRITERIA: In Process Inspection
label | RECORDS: Asbuilt records
checkpoint | 9 - RAMM DATA
label | DETAIL: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): RAMM SHEET
label | CONFORMANCE CRITERIA: In Process Inspection
label | RECORDS: Asbuilt records
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Genald Sebastian
note | Approving Delegate: Ben Lin
textbox | Engineer's Rep
checklist | ITP - Raised Table | itp |  |  |  |  | Devonport Town Centre - ITP - Raised Table
section | Details
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Obtain Permits
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS: Permit attached or permit number noted
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Sub-Contract and Supplier Agreements are signed
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Signed Subcontractor and Supplier Agreements
label | RECORDS: Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | RECORDS: TMP on MyWorksites/On Site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all Sub-Contractors and Suppliers go through FH induction
label | FREQUENCY: On site daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Induction
label | CONFORMANCE CRITERIA: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | RECORDS: Hazard ID and Pre-starts to safety team
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Design is approved and Drawings are of the latest revision.
label | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: IFC drawings have been received by Contractor
label | RECORDS: Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of Erosion and Sediment Controls
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Erosion & Sediment Control in place
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | RECORDS: Environmental Controls Audit
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Survey Setout
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey + Smart Level
label | CONFORMANCE CRITERIA: Consistency with Construction Drawing
label | RECORDS: Site Photos post surveying
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
label | CONFORMANCE CRITERIA: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | RECORDS: Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: LESA dowels to be used at all construction joints
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.1 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 0.25mm polythene layer placed across all surface area at bottom of raised table
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Document Review
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: CIV >32
label | RECORDS: Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.4 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder and 19mm aggregate chip size RadForce Fibre
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Concrete Delivery Dockets
label | CONFORMANCE CRITERIA: Delivery Docket added to QA folder
label | RECORDS: Concrete Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
section | Raised table Construction
checkpoint | 8 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Formwork to be set to correct line and level
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 8.1 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.3 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp
label | ○ Swedish table ramps to be 1.125m across for entry and 4m for departure ramp
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.4 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to be 1:15 gradient for entry and exit
label | ○ Swedish table ramps to be 1:15 gradient for entry and 1:40 for exit
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Tolerance +0.5% -1%
label | RECORDS: Site photos / Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.5 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | FREQUENCY: Prior to concrete pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Reinforcing
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Speed basket system 260mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Site photos/Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Concreting (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | FREQUENCY: Prior to concrete pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | RECORDS: Email / SMS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Concreting (2)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Vibrator to be used throughout concrete pour
label | FREQUENCY: When pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 11 - Concreting
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Concrete ramp surfaces shall be U5 broomed finish & Table will be exposed
label | FREQUENCY: At completion of pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 12 - Curing
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Concrete will be left for 48 hours minimum to cure before traffic is allowed on it. / 36hrs with 50Mpa
label | FREQUENCY: Post Pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Monitoring the time allowed for curing
label | CONFORMANCE CRITERIA: 48 hours minimum have passed/ 36hrs with 50Mpa
label | RECORDS: Concrete Formwork Checklist
checkpoint | 13 - Remove formwork
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Remove formwork after 48 hours/ 36hrs with 50Mpa
label | FREQUENCY: Post Curing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 14 - Asphalt- Concrete extension slab/ Toe (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Two rows of Lesa diamond placed mid depth @600mm C/C along construction joint as per R5-004
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
label | RECORDS: Site photos,delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Asphalt- Concrete extension slab/ Toe (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 250mm thick 40/50MPa Concrete with two layers of 663 mesh, 60mm cover
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
label | RECORDS: Site photos,delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Asphalt- Concrete extension slab/ Toe (3)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Tack Coat between DG10/AC14 and Concrete slab
label | FREQUENCY: Post Curing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Site photos
checkpoint | 14 - Asphalt- Concrete extension slab/ Toe (4)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: 50mm thick DG10/AC14
label | FREQUENCY: Post Curing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Site photos, QA records,delivery dockets
checkpoint | 15 - Lot Number QA File (1)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | FREQUENCY: At completion of Lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: All QA files compiled and sumbitted to client
label | RECORDS: QA records
checkpoint | 15 - Lot Number QA File (2)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Delivery Dockets to be included in QA file
label | FREQUENCY: At completion of Lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Delivery Dockets to be included in QA file
label | RECORDS: QA records
section | Asbuilts
checkpoint | 8 - As built information
label | DETAIL: Drawings
label | FREQUENCY: Every Site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): As built drawings
label | CONFORMANCE CRITERIA: In Process Inspection
label | RECORDS: Asbuilt records
checkpoint | 9 - RAMM DATA
label | DETAIL: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): RAMM SHEET
label | CONFORMANCE CRITERIA: In Process Inspection
label | RECORDS: Asbuilt records
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Genald Sebastian
note | Approving Delegate: Ben Lin
textbox | Engineer's Rep
checklist | ITP - Ducting | itp |  |  |  |  | Devonport Town Centre - ITP - Ducting
section | Pre-Construction
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Obtain Permits
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Authorisation to work, dig permit and first gas permit obtained
label | RECORDS: This ITP signed
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA:
label | RECORDS: Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Survey Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos / Engineers approval documentation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Locate existing services by hand digging/ hydrovac
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
label | FREQUENCY: Prior to Installation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
label | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
label | RECORDS: Digging/Excavating Control Checklist
checkpoint | 5 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure duct pipes and poles are as per drawings and specification
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
label | CONFORMANCE CRITERIA:
label | RECORDS: Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all concrete used is 20MPa mix
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
label | CONFORMANCE CRITERIA:
label | RECORDS: Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
section | Ducting
checkpoint | 6 - Trenching
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing)
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1 - Trenching
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
label | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
label | RECORDS: Stringline records & Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Duct Installation
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
label | FREQUENCY: Prior to Installation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
checkpoint | 7.1 - Duct Installation
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - Duct Installation
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Asbuilt Survey
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Survey Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Bedding
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Lay min. 150mm gap20 or finer for bedding and haunching
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Warning Tape
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
section | Asbuilts
checkpoint | 8 - As built information
label | DETAIL: Drawings
label | FREQUENCY: Every Site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): As built drawings
label | CONFORMANCE CRITERIA: In Process Inspection
label | RECORDS: Asbuilt records
checkpoint | 9 - RAMM DATA
label | DETAIL: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): RAMM SHEET
label | CONFORMANCE CRITERIA: In Process Inspection
label | RECORDS: Asbuilt records
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Genald Sebastian
note | Approving Delegate: Ben Lin
textbox | Engineer's Rep
checklist | ITP - Traffic Islands | itp |  |  |  |  | Devonport Town Centre - ITP - Traffic Islands
section | Materials
checkpoint | 1 - Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, photos.
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 2 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: As per Construction Drawings, HOLD POINT
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | HOLD POINT
checkpoint | 3 - Concrete Island (1)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Island (2)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Infill
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide
label | ○ Cross Fall of 2% or max rise in centre of 180mm
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 3 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 4 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Genald Sebastian
note | Approving Delegate: Ben Lin
textbox | Engineer's Rep
checklist | ITP - Construction Works - Signage & E-Signage | itp |  |  |  |  | Devonport Town Centre - ITP - Construction Works - Signage & E-Signage
section | Signage Construction
checkpoint | 1 - Survey Setout
label | VERIFICATION ACTIVITY: Records
label | METHODS OR REFERENCE: Signage set out, check for clearance and sight distances
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: HOLD POINT
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | HOLD POINT
checkpoint | 1 - Signage Foundation
label | VERIFICATION ACTIVITY: In Situ
label | METHODS OR REFERENCE: MOTSAM Technical Standards
label | FREQUENCY: Each sign
label | ACCEPTANCE CRITERIA: Boxed Foundation of dimension 300x300mm. Depth 600mm.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos. Concrete Bag Spec.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2 - Signage Foundation
label | VERIFICATION ACTIVITY: In Situ
label | METHODS OR REFERENCE: MOTSAM Technical Standards
label | FREQUENCY: Each sign
label | ACCEPTANCE CRITERIA: Put up sign on 60mm or 76mm steel galv pole. Angle sign towards traffic at 15 degrees.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos.
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 3 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 4 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Genald Sebastian
note | Approving Delegate: Ben Lin
textbox | Engineer's Rep