## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-150-CIV-PSDS-Rock Beaching
ITP Description: |  | PSDS-Rock Beaching
Discipline (e.g. CIV/STR/RAIL: |  | 150-CIV
Revision Number: |  | 0
Revision Date: |  | 2024-04-17
ITP created by: |  | Jonathan Kogan
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Progress St
Inspection & Test Plan - Rock Beaching
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-04-17
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | VicRoads Specification and Melbourne Water approval | VicRoads Section 713 April 2017 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Beaching Material | 713.03 Section 713.03(a) IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CBR-5613 | All rock beaching materials shall: - comply with the material requirements for ‘sound’ rock in Section 801 and -the Los Angeles Value (LAV) requirements of Table 801.033. and - The rock shall have a minimum apparent particle density of 2.5 t/m3 and - the rock beaching shall have a minimum wet strength of 100 kN and a wet/dry strength variation not exceeding 45% The rock beaching material shall be Type 5 - Melbourne Water waterway beaching and comply with criteria set out in IFC Drawings Enter: Teambinder Material Approval number [free text box] | Document Review | Prior to each use unless previously approved | HP | Nominated Authority | ConQA Hold Point Release
2.2 | Bedding Material | 713.03 Section 713.03(b) | The rock used for the granular filter layer is to be well graded and where a granular bedding is required, limited to 0-100 mm in size. Enter: Teambinder Material Approval number [free text box] | Document Review | Prior to each use unless previously approved | HP | Nominated Authority | ConQA Hold Point Release
3 | Preliminaries - Procedures & Documentation
3.1 | Beaching Placement Approval | 713.05 Sect (a) | Prior to commencement of any work where placement of rock beaching is proposed, a detailed job safety assessment shall be undertaken by a suitably qualified and experienced professional and a suitable Safe Work Method Statement developed to cover all necessary elements. The completed job safety assessment and the Safe Work Method Statement shall be submitted to the Superintendent for review. | Document Review | Each Lot | IP | Site Safety manager | ConQA Hold Point Release
4 | Pre-construction Activities
4.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP
4.2 | Confirmation of rock sizing | Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613) | Ensure rocks being used are Type 5 with a minimum D50 of 400mm. | Document Review Measure | Each Lot | IP | SE/Supervisor | Delivery Dockets and test reports to be attached to this ITP
4.3 | Confirmation of rock sizing | Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613) | Toe rocks to be Type 5 with a 1m minimum diameter. | Measure | Each Lot | IP | SE/Supervisor | Delivery Dockets and test reports to be attached to this ITP
5 | Construction Activities
5.1 | Preparation of Underlying Surface | 713.04 | Areas on which beaching is to be placed shall be compacted and trimmed as required to provide a finished surface level of beaching in accordance with the drawings. Any scours or hollows in the surface shall be filled with compacted Class 4 crushed rock. Trimmed material shall be removed from the site. For treatment of scours and hollows on or near Melbourne Water assets, contact Melbourne Water for the necessary treatment. | Visual | Each Lot | IP | SE/Supervisor | This ITP
5.2 | Toe Rock embedment | 713.07 Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613) | Perimeter and toe edge rocks shall be trenched into in situ ground before bedding placement. Such rocks shall have 2/3 of the rock diameter embedded. | Visual Measure | Each Lot | IP | SE/Supervisor | This ITP
5.3 | Bedding Placement | 713.03 (b) IFC (MRP-091-C-BEC-DRG-00-DNG-CBR-5613) | Bedding to be placed as specified in IFC Drawings: -PSDS: 150 mm | Measure | Each Lot | IP | SE/Supervisor | This ITP
5.4 | Beaching Placement-Thichness | Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613) | Thickness of placement to be 2 x D50. Rocks have min D50 of 400mm | Measure | Each Lot | IP | SE/Supervisor | This ITP
5.5 | Beaching Placement-embedment | 713.05 Sect (a) | Beaching materials shall be firmly bedded on the prepared embankment and/or bedding if required and laid in courses commencing from the bottom of any slope. Un-grouted beaching and armour stone when placed shall form a tight ‘interlocking grid’, which shall prevent the removal of individual rocks. | Visual | Each Lot | IP | SE/Supervisor | This ITP
5.6 | Type 5 Rock Beaching Placement-Surronding | 713.05 Sect (f) | Rocks shall be placed to - allow for the formation of a tightly interlocked rock mass in which the larger rocks are not free to move. - All voids are to be sealed with smaller graded rock for stability and sufficient for water to flow over the top and not within or underneath the beaching. - All leading and edge rocks shall finish flush with the surrounding ground level. | Visual | Each Lot | IP | SE/PE | This ITP
5.7 | Type 5 Rock Beaching Placement-Surface | 713.05 Sect (a) | The general surface of the finished beaching shall not vary from a 3 metre straight edge laid across the surface of the beaching by more than: - 75 mm for Type 5 Beaching (unless otherwise specified by Melbourne Water Authority) | Visual | Each Lot | IP | SE/PE | This ITP
6 | Post-construction Activities
6.1 | Cleaning | 713.09 | On completion of the work, the beaching shall be cleaned to remove all foreign materials and discolouration from the beaching surface. | Visual | Each Lot | IP | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /