## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-087-CIV-PSDS-Type A Fill-Road | itp |  |  |  | Yes | ITP-087-CIV-PSDS-Type A Fill-Road Rev 0 | 0f81a8e1-cfbd-4940-b1bf-bd7943c0759e
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | d8c503cc-839b-544a-a8df-faa1b287df0d |  | note | Document Title: ITP-087-CIV-PSDS-Type A Fill-Road
label | 3d2bef9a-7313-5136-b025-a84d65f35379 |  | note | ITP Description: PSDS-Type A Fill-Road
label | 0df140b5-db5d-507d-8e30-f8361ee76c24 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 01295a75-323e-5a66-9618-61c5b26fb24a |  | note | Discipline (e.g. CIV/STR/RAIL): 087-CIV
label | 04affd15-e2fb-5f15-8e71-885dc0366f2c |  | note | Revision Number: 0
label | 1e82c968-39c2-51ee-9771-ce070e651e85 |  | note | Revision Date: 21/12/2023
label | a967ba78-99e8-5405-b43a-f17eea504c15 |  | note | ITP created by: Victor Mira
label | 0b1c9520-355a-5fcb-83a6-cdab517bd5e4 |  | note | ITP approved for use by: Victor Mira
label | 79f80e26-a0a8-507d-88e0-6fadf601a6a6 |  | note | 1.1 Non Dependent
label | 2bebb49b-79a4-5317-8e22-118aed780f04 |  | note | Reference: IFC Drawings
label | b34f7f31-a5c6-5918-8b4c-753083784d29 |  | note | VicRoads Standard Section 176 (Sept 2008)
label | d0c3c679-3a18-5b46-8bd0-eed396e13a2f |  | note | VicRoads Section
label | 854b458e-2b5f-56a8-aad3-d0669d31d5b3 |  | note | 204 (Dec 2015)
label | 7c40b2df-4139-5405-8242-653d7094e1f1 |  | note | Code of Practice RC500.20
label | 47b748b3-876d-5c00-96f9-93e8c9202405 |  | note | Code of Practice RC500.5
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Material Conformance
label | 70e21d28-c039-56c0-a0b4-5c37137bf699 |  | note | REFERENCE: Section 204.04 b) Table 204.041
label | fce10395-13e6-5e11-b3e7-18201c6806d8 |  | note | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | 18461f61-fadc-515f-9734-7ffed1e24708 |  | note | ○ Assigned CBR≥10%
label | b51baf55-c73f-5a23-9f18-6eb2c597eab5 |  | note | ○ Swell ≤ 1.5%
label | 97c083c4-9365-5b3c-b623-cc71171714e8 |  | note | ○ Permeability ≤ 5X10-9 m/s
label | 1a24131b-e922-5cbe-96eb-9f7f4be9a12a |  | note | Grading:
label | 8d1e1e62-89ef-5e08-8463-9d95d4672e37 |  | note | ○ 75.0mm 100%
label | 48b4bb9f-318c-59b1-a908-4ae35b28ea0b |  | note | ○ 4.75mm 40-80%
label | 68653841-982c-5cf5-a01e-1706611ff7e2 |  | note | ○ 0.075mm 10-40%
label | 26fb8062-17c5-53db-b961-de671332210d |  | note | Reference: Material approval in Teambinder:
label | 2bf6f867-cbd1-529e-98a8-b7f0231d7619 |  | note | METHOD: Document Review
label | e50fc0c7-ca5a-53c2-a500-990e1760d184 |  | note | FREQUENCY: Once, for each material type
label | 88f1b364-8fb0-50e9-987b-e6da9daff75b |  | note | CATEGORY: HP
label | 39523a05-60e9-503c-a859-e4d13079bd38 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 6dcd4859-336f-5ab3-8f9c-977c76180656 |  | note | VERIFYING DOCUMENTS: Supplier Material Conformance Certificate
date | 4de70f69-ba89-51b8-92ad-e977130b0d19 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 Pre-Commencement of Fill Works
label | 7d9c38c3-31fa-517d-adf2-207406192fb5 |  | note | REFERENCE: Section 204.10 (b)
label | a59162b0-7f91-5559-a1bb-a8ebe0a6a5b7 |  | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | 0acb5e00-5f2d-5354-9fd4-0bc7daedb27b |  | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | b99027bd-55a8-5be8-9fcb-d7adb34d79f0 |  | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
label | 7e26cae3-931b-5fe5-bba6-406ed808fe60 |  | note | Reference: Subgrade Preparation Lot Number:
label | 7a1ec4cb-66db-5b9a-aedb-dd7659cb5fe1 |  | note | METHOD: Visual Inspection
label | 6dca032d-e34b-554f-8407-83d1e6634ca3 |  | note | FREQUENCY: Prior to commencement of fill works
label | 67d12b29-b36d-5eee-9feb-6e6e5953cca9 |  | note | CATEGORY: HP
date | 067c0bd1-feb0-5573-8902-17ffbb4a3a43 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set Out
label | 34f92b05-ac40-5354-be83-cbfc21e26fd1 |  | note | REFERENCE: Design Drawings
label | 18066e2f-555c-5454-9499-c560bfd60b40 |  | note | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
label | 0c9c25d9-c3c6-532a-9ec1-fc29af8638ec |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | 5d8860d9-cf46-5e14-a9f9-ebdbb53274b2 |  | note | METHOD: Visual Inspection
label | aac5f72a-1491-5eed-97b4-5f4fb7c0b714 |  | note | FREQUENCY: Each lot prior to commencement
label | 6bb98a5e-6657-5287-a06f-5f8505f2cdd5 |  | note | CATEGORY: HP*
label | 87b9ff9a-c14c-55f8-b950-e7c705e96075 |  | note | RESPONSIBILITY: PE
label | 748269d0-45fa-57e4-a4e6-cf6d373ccf65 |  | note | VERIFYING DOCUMENTS: Signed ITP, Lot Map
date | e2b4482b-4a6b-5ffe-a21d-3fb1bdc4699b |  | date | Date Completed:
checkpoint-group |  |  | section | Type A Fill/Verge Activities
checkpoint-status |  |  | checkpoint | 5.1 Placing of Fill
label | 27801d2f-e829-5b1f-9f70-71ba569adbf8 |  | note | REFERENCE: Section 204.10
label | 6e25f0c8-3057-5538-8626-24380af842ee |  | note | ACCEPTANCE CRITERIA: Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | 43a18ab6-4572-521d-814b-270cec4922db |  | note | METHOD: Visual
label | b60cc1c5-62eb-5e16-a8f5-32ae6f82663c |  | note | FREQUENCY: Each Lot
label | c0c61884-10df-5817-b211-c3135a219c65 |  | note | CATEGORY: WP
label | 8cd8fb34-aa88-5ed6-b3f2-0b5274be0bd6 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 35478f95-d8fc-553f-b259-40f5ea01c17b |  | note | VERIFYING DOCUMENTS: Sign ITP
date | dc072b4f-8681-5c69-8d17-b32dd171eadb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Test Roll
label | ec8e069c-9b32-5ae0-b0f4-add19eef6122 |  | note | REFERENCE: Section 173.03, Section 204.12
label | b7da5c2b-310f-5b27-b31e-e09afe7bf24f |  | note | ACCEPTANCE CRITERIA: Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | f692e437-1b93-517b-9396-695710c0a6c7 |  | note | METHOD: Test Roll as per 173.03
label | 37d3b29a-be86-54c0-bce7-5546d1336022 |  | note | FREQUENCY: Each Lot/Layer
label | 55012926-785e-500a-be3e-58f5cac76a49 |  | note | CATEGORY: HP
label | c15e60b6-a596-5cf4-8b4b-c18614213d2c |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 5ef3cd9d-5661-5a32-a473-0f2c740ec330 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 12763c3a-8cd6-518d-b38c-99a471a7de1f |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Compaction Testing
label | b3364d57-ddb4-53e9-be3d-6e6df9337896 |  | note | REFERENCE: Table 204.131 Section 204.14 c) Table 204.142
label | e2db3875-9b97-586b-94ee-23c3ffbd7c47 |  | note | ACCEPTANCE CRITERIA: Testing as per 204. Ensure testing is tracked and reports available.
label | 1135fd80-47d9-5a95-994c-bc7bca7ce2f1 |  | note | Standard Compactive Effort
label | 7d865066-31d6-5426-8ef9-4d0efb703f2f |  | note | ○ For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
label | 3051f2cc-3bc2-5259-b3de-d28ccecaabb9 |  | note | ○ For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | c1ed7d82-2cef-5659-bbf8-4e8cd63b4764 |  | note | Compaction and Moisture content
label | a29e9dfe-f350-5648-a8fe-e33425a42fda |  | note | ○ Scale A: Characteristic Density Ratio 99%.
label | aa490aab-cf80-599e-b494-c225b3aa0e18 |  | note | ○ Scale B: Characteristic Density Ratio 98%.
label | a38618b9-404b-52da-b5ae-55d3f33cf637 |  | note | ○ Scale C: Mean Value of Density Ratio: 100%
label | 081eca3f-f62d-5d85-b20c-41cadeb18fed |  | note | Lot size - the leser of one day's production or 5,000sqm
label | 21e194f8-5c42-5ff3-8762-9ec80c4a2550 |  | note | ATTACH: COMPACTION TEST RESULTS
label | 2e685b9c-de82-557b-abdf-ebd81fe7bbe7 |  | note | METHOD: Review Document
label | de1cd64a-ff83-55ed-90b5-d7c2225a47c5 |  | note | FREQUENCY: Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | 74ad15d4-ef2a-51a0-b43e-faa31fc8c1ec |  | note | CATEGORY: IP
label | fdd0d825-f6e7-5234-ac27-5dc6ed95b939 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 09266928-6d82-5606-a17c-739b7aeb5e71 |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Compaction Test Report
date | d150fde9-653d-54e4-9e85-5a03edf7acd4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Preparation of final surface
label | 8eec47d8-b3a2-5d6e-80a4-3cc161c4ef3c |  | note | REFERENCE: Section 204.15, 204.03 (g)
label | 7e880842-8e5e-5393-bbbf-bfb275510ca7 |  | note | ACCEPTANCE CRITERIA: The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | 13ea9b41-26dd-5bc7-b3ae-54d16409d328 |  | note | METHOD: Measure
label | 46628d2b-663b-51d3-81ce-45e365e714d4 |  | note | FREQUENCY: Top layer
label | b6673f4a-a8a8-5318-aae3-e455c7122ab5 |  | note | CATEGORY: IP
label | be528ef2-f016-5044-9086-73633d0a7cbe |  | note | VERIFYING DOCUMENTS: Signed ITP
date | d6d4e38e-ce69-54b4-8b66-cfb6f8fe84fb |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Post Compaction Material Property Testing
label | 0f522fae-c87a-5eb9-b64c-d21f872bb542 |  | note | REFERENCE: Table 204,041, Table 204.141 Section 204.14 a) or b)
label | 213854c4-bed5-51b4-9b28-771f6c4041a9 |  | note | ACCEPTANCE CRITERIA: Material Properties (Not Applicable for Scale C):
label | 8ef2d5b2-7e61-5a7e-9c6a-0db1ff573ec4 |  | note | ○ CBR ≥ 10% and Swell ≤ 1.5%
label | 957f2a43-09c3-547c-81aa-54a106e966ce |  | note | ○ Max Permeability = 5X10-9 m/s
label | e18b0092-1e29-542d-9271-f87b764ad43a |  | note | Grading:
label | cd36077b-ab85-5a9c-96c9-21250c75a7ee |  | note | ○ 75.0mm 100%
label | 97e36a1c-f955-5ae2-bb49-0652a50a3285 |  | note | ○ 4.75mm 40-80%
label | 6f3c7cb9-fc70-5192-9023-78bbe2986771 |  | note | ○ 0.075mm 10-40%
label | 3d2fc21a-74e5-57ac-8625-e10c2711b500 |  | note | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 23be3e5f-bd65-5e9e-8e45-9de5de477cb1 |  | note | Scale A:
label | 802c9b72-0bc8-597d-bb7f-07faf3617cf2 |  | note | CBR & Swell
label | c48c7fd3-90ed-5ab1-b145-ae6f153bc4f3 |  | note | ○ Initial - 1 Lot Test to determine Assigned CBR and swell
label | b328e556-de03-57a3-ac99-9da49bdedeed |  | note | ○ Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | bb1234fe-67f9-5013-885d-056e40065a10 |  | note | ○ Max Permeability
label | 0aa49c2b-2210-5c0d-bf52-b8bdb5f2278a |  | note | ○ Initial - 1 test per 2 lots
label | 17de055e-af2e-588e-bab8-7e4d66a816c8 |  | note | ○ Reduced - 1 test per 4 lots
label | 39ee7e5b-00ed-5bdf-8a62-f1e104f92bad |  | note | Grading:
label | 91b66d5a-42db-5165-aa8e-3e2c9691d73c |  | note | ○ Initial - 1 test for each lot tested for compaction
label | 1520c416-f275-58dc-8190-31f72acdf99f |  | note | ○ Reduced - 1 test for every second lot tested for compaction
label | bca267ee-501d-5f2d-8290-64b49d7bc7fd |  | note | ○ Max. PI x%Passing 0.425mm & PI
label | a746f0f7-7570-5cc6-992a-4d650ad2e6f4 |  | note | ○ Initial - 1 test per 2 lots
label | 269a7f31-b697-5290-8474-05d27b4cc432 |  | note | ○ Reduced - 1 test per 4 lots
label | 16a52ca2-7ee7-5f9d-9399-c41d02fc580e |  | note | Scale B:
label | 997ead02-415b-59bc-8cab-87b0b2f51389 |  | note | ○ 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | f7e5c1d6-f3e4-5fcf-8a04-03a92c9df28d |  | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | fc52edab-56de-524a-9736-ccfb8e49d1b7 |  | note | Attach: Post compaction test results:
label | f0dc556f-458e-5310-a55a-32426c4c20a9 |  | note | METHOD: Review Document
label | 997f8ae8-ceda-580d-b0e1-6abb545ba062 |  | note | FREQUENCY: Refer to Section 204
label | 838c83fa-cc77-5f1a-8a81-79b62a4cac31 |  | note | CATEGORY: IP
label | e709013c-f0a1-5fec-b822-0f37d3826413 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ee672198-701b-5ff5-9e31-c6618a6e27dc |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Material Property Test Report
date | 9b0dd658-da8f-54de-a92c-2f6980fbba8c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Survey Conformance
label | 4260f1c1-3c07-5e2e-bb5a-71ffa18f0f88 |  | note | REFERENCE: VicRoads 204.03f,g and h
label | f6ac3f76-cd60-5d5d-b9e0-4fb323c9e645 |  | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 365a2fc4-acdd-56f0-af59-119079625ac3 |  | note | Level tolerances Scale A:
label | 8a76ad16-8891-5463-9238-b960841db647 |  | note | ○ Range x = +5, -15mm
label | f3aa0dc7-8cae-5382-bd7a-7a2eb193c018 |  | note | ○ Max S = 12 mm
label | a34bed6a-23b1-5ae2-9825-78c6ab7ba561 |  | note | ○ 80 measurements per lot
label | 2fa44353-c35d-54e6-b2ae-e69bed023fe8 |  | note | Level tolerances Scale B:
label | efce45fe-b728-5b04-9845-5076be6ae1fd |  | note | ○ Range x = +5, -25mm
label | 19026b68-f093-5669-859c-f653df8306a7 |  | note | ○ Max S = 15 mm
label | 407bc8f3-b892-55da-a1a2-c3fd9a430a74 |  | note | ○ 40 measurements per lot
label | 50aa2ba0-d1e0-5542-a20f-8a348649ad6f |  | note | Level tolerances Scale C:
label | 95fc868b-7e15-58cd-be22-40273244a061 |  | note | ○ Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | 98b1d2ce-cddc-5e20-817d-498cdd3de4bc |  | note | METHOD: Document Review
label | 166597c7-8f5e-53f2-b462-e74da4241c13 |  | note | FREQUENCY: Top of Type A/Verge
label | dcbba2e6-3215-5f50-b3b1-1476ddac2f58 |  | note | CATEGORY: IP
label | 6b184051-8baa-5f27-93eb-cdf9b46e7843 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 2b129928-22b7-5b86-84d5-18c7886fb9bc |  | note | VERIFYING DOCUMENTS: This ITP, Survey Conformance Report
date | de3f508d-0f71-554a-86d3-19e1f1bff601 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | c7cd8969-1bd3-5b27-b9e4-6f9fe658185b |  | note | REFERENCE: MRPA Quality Management Plan
label | e6ea9d0c-acf2-53a0-a087-f6ec0fa8a2e7 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 8a3fae7a-3ed0-52b1-bc40-9bec712fc8a0 |  | note | METHOD: Document Review
label | 8e5002b1-7b11-5e67-8544-f49b635ea062 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | e8cee319-8daf-5fe8-83c7-301e205bc980 |  | note | CATEGORY: HP*
label | 6eceb162-f4f0-50c7-af63-270f6fb5021a |  | note | RESPONSIBILITY: SE/PE/SPE
label | 304c7ea7-3a37-5e0f-8203-245166688d08 |  | note | VERIFYING DOCUMENTS: This ITP
date | 4d03c647-3e58-50b6-8f94-a7b666e81815 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | f214a374-e344-5920-93be-2a7007c4815d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 69de427b-1752-55f2-9e9e-453478eb0020 |  | textbox | Name:
text | 832ab578-ec67-538a-a8dc-b82b1ded6015 |  | textbox | Position:
date | 1179106e-1f40-5517-a00d-9600cb3a98c3 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-090-CIV-PSDS-Site Clearing and Grubbing | itp |  |  |  | Yes | ITP-090-CIV-PSDS-Site Clearing and Grubbing Rev 0 | 209ca522-e2e2-48e9-8278-8f0e401dc427
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 2dc18d0a-e369-56e9-8029-57b43deeda4e |  | note | Document Title: ITP-090-CIV-PSDS-Site Clearing and Grubbing
label | 580bc6cb-80ec-5970-94cb-b6a86bfaa7b3 |  | note | ITP Description: PSDS-Site Clearing and Grubbing
label | f7c9af2a-1d90-5ce9-b578-6953bdaa722e |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 4d091128-4c98-5d39-af3f-d236b9368f15 |  | note | Discipline (e.g. CIV/STR/RAIL): 090-CIV
label | e6263147-312e-59c5-882b-ad27f7f5b6aa |  | note | Revision Number: 0
label | 39174801-064b-55ae-b452-c8565c383c09 |  | note | Revision Date: 28/02/2023
label | 9d32b3a6-c641-5735-92a6-e2218d0ea475 |  | note | ITP created by: Jason Lee
label | bfda0bbe-84b0-5712-947c-80ccc4d7a010 |  | note | ITP approved for use by: Jon De Castro
label | 429245e9-ca1b-52e9-9198-c9ce8b51197e |  | note | 1.1 Non Dependent
label | 7c93ddde-066b-57bc-b56e-141d7ad5a8c8 |  | note | Reference: VicRoads Section 201 (Feb 2023)
label | 4cc87ada-9671-5256-9ab1-9a7748fa9fad |  | note | 1.2 Non Dependent
label | 6f5a9a10-d2fd-50ad-ac1b-5b24d5f769ef |  | note | Reference: VicRoads Section 204 (Dec 2015)
label | 0c40eb66-6c59-5a3e-8608-48beda0d5016 |  | note | 1.3 Non Dependent
label | ee10b73c-62ba-5007-995c-ab3dbc381e03 |  | note | Reference: IFC Drawings
checkpoint-group |  |  | section | Preliminaries - Documentations
checkpoint-status |  |  | checkpoint | 3.1 Environmental Controls
label | ea9218c6-1df8-5966-8814-67c2fba59169 |  | note | REFERENCE: MRPA Environmental Management Plan
label | 0b302b3f-07de-513a-9f80-3da0bb2de65e |  | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities.
label | 1dab666c-593f-5ce8-80b9-eb03a5f0cc6a |  | note | ○ Sediment control measures to be installed and protected vegetation to be clearly identified.
label | 919725d4-9645-5161-a31e-26b86c4f0337 |  | note | METHOD: Visual
label | 893aa6b8-5609-53dd-8166-e26590c10013 |  | note | FREQUENCY: Where applicable, prior to starting Works
label | 44e129e5-686b-594b-bc7d-c285e87f88bb |  | note | CATEGORY: WP
label | bf1a3e58-141b-5b25-a0db-92a7f10561e1 |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | f24bd01a-cf6f-50b7-9fff-1f2386ac6822 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | e3db71fd-4d4a-5905-854d-4f7c0d278440 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Vegetation Removal Permit
label | f582f725-0e22-5c06-871e-967e877fc0db |  | note | REFERENCE: MRPA Environmental Management Plan
label | 15724757-7307-5547-9fad-0b3860ea3c5b |  | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat:
label | c8aa2627-4510-583f-8a47-8189e5ae0739 |  | note | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
label | 27b13eff-98ef-5dee-aed9-2190d80dddc8 |  | note | A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
label | 640c17b6-a930-57e9-aab5-631886f159b2 |  | note | ii. fence and sign all sites nominated as No-Go Zones.
label | c2403a41-7842-54e7-9e22-a398416c29e4 |  | note | Attach: Vegetation Removal Permit
label | 5dab51c8-a239-55f6-a6c5-2250c9dcee2a |  | note | Attach: Ecologist's Report
label | d33e7c57-d4fc-565f-b52f-5151c3012212 |  | note | METHOD: Document Review, Visual
label | f2c89450-0ae6-5099-9bd1-e9e0710afa90 |  | note | FREQUENCY: Where applicable, prior to starting Works
label | b24280d3-bf0e-5f59-8a48-336c30860626 |  | note | CATEGORY: HP*
label | 1a7b2582-a7fc-516d-ae77-73d63f50f62d |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 0780cfd2-ae87-537d-aa52-77df85a949de |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 318be9d8-cf01-5dfa-a135-675c52282de6 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out / Limits of Work
label | 1c77958e-d0f2-5de5-a403-30d7a8f95c5b |  | note | REFERENCE: IFC Drawings Section 201.03
label | 1137455d-d66a-5561-83dd-6d54d0c61795 |  | note | ACCEPTANCE CRITERIA: The limits of clearing and grubbing shall be:
label | 0176eae2-401a-551c-ba0f-8917087751fb |  | note | a. the limits defined on the IFC drawings
label | 3def38aa-ff7a-5844-ad04-80afc6dd52ee |  | note | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
label | fbee31e3-82b0-565e-a569-42c20b01c43f |  | note | c. no more than the width required for completion of the Work under the Contract.
label | 0509db5d-a07a-5020-a4a2-22ff78a0d83c |  | note | METHOD: Measure, Visual
label | 0af7eed4-aff0-509b-a403-71d4525f1fc9 |  | note | FREQUENCY: Once, prior to starting Works
label | 9f54eb71-437a-55ae-83fe-f46db301ed14 |  | note | CATEGORY: IP
label | 197b5d0d-9688-5f19-acf2-ae959706b383 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | c3f22741-b86a-5bb1-a726-41a6444cdfc7 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | c9bc782f-9d74-53bd-b868-bcad0a231568 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Cultural Heritage and Areas of Significance
label | b124b9eb-0e65-531c-bb35-14ac0f506b78 |  | note | REFERENCE: MRPA Environmental Management Plan Section 201.10
label | 019b3125-1f78-581b-8140-53af78174986 |  | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | add7cf5b-c142-58a6-9d1d-43081c3da586 |  | note | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
label | df5ef560-94fb-5011-9f5d-0d44bad70d8a |  | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | f930f183-5e00-55bf-b935-fb04188fa22a |  | note | Attach: Cultural Heritage Report
label | 417dd0d6-eed7-5609-a043-7d16879c9b5d |  | note | METHOD: Document Review, Visual
label | 974d2104-3074-57b7-908b-1b129b57d212 |  | note | FREQUENCY: Where applicable, prior to starting Works
label | d051bb65-b7db-5300-b32f-d1e6e95446cd |  | note | CATEGORY: HP*
label | 101fe6a7-72be-5a7b-ae2e-a863fb3e77a6 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 3280fef2-9e74-558d-bddb-cd25cf5216b8 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 07631dbc-6dd7-52d1-a3fd-614589c84327 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Stripping of Topsoil
label | 9f3ad103-909b-5ee5-91bb-ac46964e1185 |  | note | REFERENCE: IFC Drawings Section 204.05
label | 43dc5218-e34e-5183-ba81-f49b7c138d5a |  | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation.
label | 2cb488d5-a582-5f58-97ec-f73a99717e09 |  | note | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
label | df15be73-6823-5623-a272-38d327cbf1fb |  | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
label | 98dbe752-a124-57c0-902c-a4bca6d97983 |  | note | METHOD: Visual
label | a7e847ae-4449-5a58-9b75-830cf27bd9cd |  | note | FREQUENCY: Each Site
label | 641f2ca6-8af7-5426-aea4-d59ae2717ca5 |  | note | CATEGORY: IP
label | 34d65b5d-ba7d-5b1d-af97-dd164abb6cdd |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | e45a37b8-f4f0-5e85-99e2-bc9963005010 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | e0aecd8a-5796-5752-80cb-36e8a822bae1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Stockpiling
label | 664f8807-3b65-593e-8ae6-651c776a9cbb |  | note | REFERENCE: MRPA Environmental Management Plan Section 204.05
label | c0a5ddea-3c91-5719-9017-6a5c73899ce6 |  | note | ACCEPTANCE CRITERIA: Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
label | 465b0db2-bc34-5ca7-831d-3504fab51d3f |  | note | ○ If this clearance is not possible,additional protection shall be provided.
label | d9f72fde-35a9-5fce-8511-4911719c7807 |  | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
label | 6834a746-e4db-505d-a0e9-532cabf305bd |  | note | ○ Topsoil shall be re-spread as soon as practicable.
label | a1c2f0cf-ae4a-546b-8d03-710b095ca289 |  | note | METHOD: Visual
label | c99a7c7d-7831-56fc-8b66-c41171f86066 |  | note | FREQUENCY: Where applicable, each Site
label | 40cee9f3-96d6-52ae-919b-3068e77789d6 |  | note | CATEGORY: IP
label | c0858729-3a16-5027-a77b-089f3fa2aa46 |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 00b04db8-dfa8-529a-8597-5a3b007d185e |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 7307bb6e-8a7d-5883-84d1-0fb1e5e9d886 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Abandoned Services
label | b147027c-3513-507f-8548-6c2868b95d02 |  | note | REFERENCE: IFC Drawings Excavation Permit Section 201.05
label | 68dca96c-bde1-5e60-80b2-2aaf13386d0e |  | note | ACCEPTANCE CRITERIA: Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
label | ac30d8c5-e369-5ea4-8421-837b0b58673a |  | note | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
label | 74b7ca2d-1a54-5a36-81f4-01b0e84c69c5 |  | note | ○ Decommissioned services to be disposed of in a suitable manner.
label | 1b3a58d3-e481-5342-b52a-eed95472b1ae |  | note | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
label | 5d4072a2-81d4-5627-bc2f-10943e9baa75 |  | note | METHOD: Visual
label | 80df4e50-db99-5a0d-8db3-1fb203ee1136 |  | note | FREQUENCY: Where applicable, each Site
label | 31bc7c41-5b8e-58ef-b64b-20c77a6232b3 |  | note | CATEGORY: IP
label | 98b2e9e6-8e8c-5c8e-b469-74e8e767ae30 |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 1289b4f5-76e4-57a6-b84d-ce272012bce1 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 1e3e1fdd-c9ec-5df0-8fb8-bfb1d597d812 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Clearing of Trees and Vegetation
label | aa4aa639-08fa-53f9-b3ea-1629dde32606 |  | note | REFERENCE: IFC Drawings Section 201.04
label | 513be186-9ec9-54e5-813a-e5ed456f7c65 |  | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertaken outside of the specified limits of work.
label | 3c083e60-222f-5f6b-9df1-3375238f0541 |  | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | e12b29a3-3871-5f64-baa4-938d201b8cae |  | note | METHOD: Visual
label | f78c842d-546c-5a47-ba12-7c0b722bada7 |  | note | FREQUENCY: Where applicable, each Site
label | 0086b6b3-fc35-55d4-bfa3-e9c6a184d681 |  | note | CATEGORY: IP
label | 3e1e86d2-917e-557e-95a5-aceb7f31d54b |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | e6de8a83-29ad-5767-9386-cecda7254c9d |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 7750fac7-da01-5518-b712-dec6ce6a7eb6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Grubbing of Vegetation
label | 9ad91a23-9dbf-588f-a549-6982ef7097b0 |  | note | REFERENCE: IFC Drawings Section 201.05, Section 201.06
label | c3dc66dd-77e6-59c8-9776-4c22ae9cd9ae |  | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
label | 541a3b39-04c7-509f-a208-2322d2a997e8 |  | note | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
label | 93997030-0db3-5b19-ab19-e0133f7badae |  | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
label | 07294389-a019-52b7-ad3d-9e5539b2e0e6 |  | note | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
label | f10b1534-1c37-551f-8f5f-d22d10874d6d |  | note | METHOD: Visual
label | b27f5c64-222c-5a63-9ee1-6a4b301434be |  | note | FREQUENCY: Where applicable, each Site
label | 39c2f70b-9a87-51b5-8639-e304bc238334 |  | note | CATEGORY: IP
label | eaa5b6ec-ded6-538d-a0c1-c3286ced397b |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 27cbb7ec-8797-5ba0-8a03-3f65bc4f8e46 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 009308da-9187-5465-8b6f-a3b0b686ca56 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Disposal of Materials & Vegetation
label | bc2b59ce-8171-5644-8cdd-5ae91d1d5c82 |  | note | REFERENCE: Section 201.07
label | 68385a44-42ab-5d82-8d21-3158d326ec3b |  | note | ACCEPTANCE CRITERIA: Salvagable material to be used wherever possible, the remainder is to be remove from site.
label | 4413e017-bc62-565c-88bb-9198fddbcbe8 |  | note | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
label | 004354ee-76ce-575f-a6fa-ac96f31684c4 |  | note | ○ Tree trunks and large branches shall be removed from the site.
label | 9bac7ff1-4800-593a-8ea6-731aca98510a |  | note | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
label | d46218cb-8ca1-5e7b-ac6d-c29da7106d4b |  | note | Attach: Delivery Dockets (for Items sent off Site)
label | 99268393-3958-5c33-9b5c-9e4ec75eb457 |  | note | METHOD: Visual
label | b2c2467c-19d2-50bc-8b13-5cddf0db2dbd |  | note | FREQUENCY: Where applicable, each Site
label | d8655c99-9e8a-5dae-8b0d-f4ffd89ad9a9 |  | note | CATEGORY: IP
label | c0581f8b-d32d-5fe8-a6f3-cc0081eff1ba |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 205fbd8e-20b1-50d4-b5dd-e545839c4f44 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
date | 9e585868-7bea-5665-830d-e000f3ed0887 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 474c9552-a0eb-578a-a4f8-f9c69a272b26 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d7135bc4-8fc1-5b80-99c2-61a9a12de519 |  | textbox | Name:
text | f4134ac6-9921-5e7b-afd0-74c52884ae4f |  | textbox | Position:
date | 3eb3294a-1953-55f6-8222-9df25e8e5efb |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-091-CIV-PSDS-Conduit & Pits-MTM | itp |  |  |  | Yes | ITP-091-CIV-PSDS-Conduit & Pits-MTM Rev 0 | 2967b10f-ba1a-4be6-b9f7-ee41481e6886
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | b0aa64dd-79eb-56dd-a21f-d825229e344c |  | note | Document Title: ITP-091-CIV-PSDS-Conduit & Pits-MTM
label | 69eb7c74-b5a5-52c3-b15a-1632d6c303ba |  | note | ITP Description: PSDS-Conduit & Pits-MTM
label | b8282235-496f-5af3-ad9e-4e705950bfb7 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 27c7939a-fe8f-59d8-adf6-d669dcf73fb8 |  | note | Discipline (e.g. CIV/STR/RAIL): 091-CIV
label | dab0b4a6-75b0-532d-a63b-b8a02c58d347 |  | note | Revision Number: 0
label | 60f477fb-1a1f-5216-bf40-a32160b879d1 |  | note | Revision Date: 13/01/2023
label | 93a6f5ae-2f8a-57c2-b0bc-79f118112e0c |  | note | ITP created by: Shubham Bajaj (Sammy)
label | bb6cd3c8-02a0-5d93-b292-c5f3c6a77e3a |  | note | ITP approved for use by: Jon De Castro
label | 9292a766-a262-5791-bc10-73d470998ae4 |  | note | 1.1 Non Dependent
label | 23731fcb-f8ee-508b-986b-2810d60b13cc |  | note | Reference: IFC Drawings
label | 42fad78a-d4b6-54ae-bc78-cab06b81a20e |  | note | L1-CHE-STD-043 (VRIOGS 012.2.1)
label | 49dea0ea-ad91-5961-a779-36022aa7b0ae |  | note | L1-CHE-SPE-070
label | a5535252-a17a-5969-8ba8-559386516a0a |  | note | Australian Standards
label | 7bfdc0ae-38d6-5e4c-93e3-187b4d5a0965 |  | note | MRPA Standards
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Conduits
label | cb0c21a8-747f-57c1-a227-d81fe8824030 |  | note | REFERENCE: HV Conduit: AS 2053
label | f25930cf-ba05-54b6-ad95-ba10e50e8cf1 |  | note | ○ HV Conduit (boring): AS 4130
label | ee6f46a3-af15-5730-b39a-3cd053d8b056 |  | note | ○ Comms Conduit: AS/ACIF S008:2006
label | 6b17d3f1-0880-57ae-8840-cf570656cae4 |  | note | ○ LV Conduit: AS/NZS 3000 - 2000.
label | ad96fd2e-a5d8-5c6b-8317-7277b1d93bae |  | note | ○ L1-CHE-STD-043
label | 1a3a256d-cab8-5b6d-b854-2c58ac92ad21 |  | note | ○ L1-CHE-SPE-070
label | 3d703d37-2303-5719-a816-70e28afdde2e |  | note | ACCEPTANCE CRITERIA: LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
label | 4f5fadb2-33d9-54a6-a775-2f4de90f1461 |  | note | ○ LV & COMMS CONDUITS TO HAVE A MIN 600mm BENDING RADIUS
label | bdc36042-ccec-54ec-a75e-3b013c54cc43 |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | cf061803-304a-5a2f-aba8-5da69fe36a6f |  | note | METHOD: Visual, Document Review
label | 22800182-21cf-5451-a9a8-5d5ceccea388 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 9cdbb40a-76d9-5e3e-b880-5cd3995f88fc |  | note | CATEGORY: IP
label | 41b582f4-f92d-5225-abce-d416796704f4 |  | note | RESPONSIBILITY: SE/PE
label | f910cf08-ba99-5961-9201-51abe0de8dec |  | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
date | 2cf9678a-770c-575b-89bd-5160485afa90 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Pits and Pit Lids
label | 5a2186f6-45c6-50aa-947e-d3fc28f054b5 |  | note | REFERENCE: IFC Drawings VRIOGS 012.2.1 Section 6.15-16, VRIOGS 012.2.1 Section 6.9, VRIOGS 012.2.1 Cl.6.7 (c), L1-CHE-SPE-070 Cl.10 AS1289
label | 24d45b36-c750-5e1b-ad8d-39365888369f |  | note | ACCEPTANCE CRITERIA: Pits:
label | 32005582-ef40-5b79-8a66-d3d31a07b5ae |  | note | ○ Pits located within 1.5m of nearest rail, pit to be 300LA Railway loading
label | 615cc7a0-e057-565e-9382-ae4e9765d48f |  | note | ○ Pits 900x900mm or greater, multipart pits lids to be used.
label | 3c92cec0-404f-589d-87af-837b956a3499 |  | note | Pit Lids:
label | 2aaab00a-d39d-5788-ab91-d2b0ded588b4 |  | note | ○ Pit Covers shall comply with AS3996-2006
label | b146551c-cd74-5c20-8bc3-0f101c7b7485 |  | note | ○ Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
label | 796b9297-b966-5c0e-87fd-06e9b4a4450b |  | note | ○ LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
label | 43bd2b8c-0ab5-5301-85df-3ac131f3c464 |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | 506499a0-a91a-5390-9195-6fd201fd84ef |  | note | METHOD: Visual, Document Review
label | 9e73bca8-24f7-573e-86d0-cc53c5129f55 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 78747d53-d2f3-546f-bb18-eb42f1744baf |  | note | CATEGORY: IP
label | 34197545-92e0-5486-ae3a-d50010bf931e |  | note | RESPONSIBILITY: SE/PE
label | 97087625-7a87-5484-923d-7bc512d6ff0b |  | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
date | 427a43e8-2470-55e8-bf60-f0e4bd466e60 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Warning/Marker Tape
label | fb9dddf6-3102-5180-881e-3434701a6acd |  | note | REFERENCE: IFC Drawings AS/NZ 2648.1, TS-SP-013, L1-CHE-STD-043 6.4
label | f36d6c1a-01a1-54d7-8ceb-cea9dc8f4619 |  | note | ACCEPTANCE CRITERIA: Warning/Marker Tape:
label | 3fb2cc9a-1ba5-5594-93cb-34daa4d0c6be |  | note | Above LV:
label | ef7d5b60-f01b-58a6-ad83-4405bc4556ae |  | note | ○ 150mm minimum wide orange coloured PVC
label | 4f1fea3c-6b16-5ec6-b145-3ba6a63411e8 |  | note | ○ ‘DANGER RAILWAY SIGNALLING CONDUITS’
label | 9dcf05e4-f629-5afa-99ce-7b1890db5e4f |  | note | Above Comms:
label | 72f70429-8363-5e6c-af65-5dde4ec83a7a |  | note | ○ 75mm minimum wide white coloured PVC
label | 90722e60-7cc5-5da8-a59b-54456b26b682 |  | note | ○ ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire to be laid directly above trenched VicTrack assets
label | 26b0b155-90d1-5309-9f1c-4714fb2f595f |  | note | Above HV:
label | fe88022c-2209-52e4-aa38-8181b2a64dce |  | note | ○ 300mm minium width orange coloured PVC 'Danger - Electrical Cable Below'
label | 397379e5-d929-5fdf-968f-455c9fdabd65 |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | 97cdf769-0c9a-5316-b7f1-af758e7d9cbe |  | note | METHOD: Visual, Document Review
label | 43a5343e-5dfa-58dc-9026-31118e35d102 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | eb45f8d7-10b8-5fd6-9f91-52f3a34561c3 |  | note | CATEGORY: IP
label | bda9770b-ef3e-5c8d-ab7e-8746bbdea9e8 |  | note | RESPONSIBILITY: SE/PE
label | 0fe7b806-d205-505e-b0fd-086eb495866f |  | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
date | 3dee491a-cd42-5a52-8c22-56b92b39a83e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Protection Barriers
label | d3b00733-d9a1-57d3-a845-8651dbbea107 |  | note | REFERENCE: IFC Drawings L1-CHE-STD-070 10.3.3 AS4702
label | 77f6b3c0-07eb-5c12-a734-cfaedd11a070 |  | note | ACCEPTANCE CRITERIA: Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days
label | a241f246-4abd-5dc3-981a-3fcb0d539835 |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | f4376df3-5538-581e-b592-3a3bc98a16a3 |  | note | METHOD: Visual, Document Review
label | 0248775d-67bf-562c-a272-147251cb0e62 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 10bbffe8-293a-5b11-a2d8-b33b5dddc7ec |  | note | CATEGORY: IP
label | dfc09fdf-e7b9-5abf-8f74-63d89fdf4fdf |  | note | RESPONSIBILITY: SE/PE
label | dd13f8d2-7ef1-584b-a6d5-1bfb4ee28674 |  | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
date | b4ff9a0a-fc24-58dc-9c3d-31f94e75fb51 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Backfill Material (stabilised sand)
label | 5567bf84-c5d7-5876-9638-9c67b0e61959 |  | note | REFERENCE: IFC Drawings L1-CHE-STD-043 Section 2 Table 1
label | ac817eaf-446e-5f24-96f5-211c52f31695 |  | note | ACCEPTANCE CRITERIA: Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could dmanage the conduits.
label | eb35d5fc-5be6-5376-8da8-9d192f78dcab |  | note | ○ Inspect backfill material.
label | d9c7a733-ebc1-5ab1-a055-cc6d47ade521 |  | note | ○ Attached delivery dockets (if applicable).
label | 61a480b2-8c5f-57b0-ab21-ba91f843734d |  | note | METHOD: Visual, Document Review
label | 8fc48ec9-1368-5b89-9e39-02a1085ebc0b |  | note | FREQUENCY: Each Material Type, Each Delivery
label | c88514e6-8948-5ce8-ae09-4fbecd953792 |  | note | CATEGORY: IP
label | 9073cb15-bfaf-5478-a0d9-4a8f3d84c2ba |  | note | RESPONSIBILITY: SE/PE
label | 8b2d342f-9f80-5b7f-943b-841f465f7f04 |  | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
date | 6d915142-7041-50c6-83c1-6a58f06339dd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Bedding Sand
label | 03e2f977-3463-526f-b471-59ce79c31eaf |  | note | REFERENCE: IFC Drawings AS2758.1
label | 89bde411-dd2f-53a9-9ac7-4bab43f788fc |  | note | ACCEPTANCE CRITERIA: Bedding Sand shall be a clean sand that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
label | a5c7b82b-5022-5447-8fa6-09fb018b6eb4 |  | note | METHOD: Visual, Document Review
label | 68b126fe-16c4-547f-a6e6-7f21859609eb |  | note | FREQUENCY: Each Material Type, Each Delivery
label | e9b684bf-1424-5bce-ae1a-5af0a8a2060c |  | note | CATEGORY: IP
label | 123809c2-1c18-5c21-9832-71bee486c00f |  | note | RESPONSIBILITY: SE/PE
label | b2eaa0a5-deb1-5293-8505-350767f1ee6f |  | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
date | cae859a2-4046-5257-8ae7-69fbb5f248f6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Draw Wires
label | 5fa0724d-f3ec-5db7-841e-6ca8688380ee |  | note | REFERENCE: TS-SP-013, AS 4142
label | be284cd0-6e99-56dc-8d68-09b681e42385 |  | note | ACCEPTANCE CRITERIA: 6 mm diameter polypropylene blue/yellow
label | fec3307e-dfdc-5cbd-828f-ea84b0713295 |  | note | METHOD: Document Review
label | 1dde2de4-2e8f-53bf-9a37-8f57757665b7 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 0098074e-7a1a-544f-9441-b094a0dec7f3 |  | note | CATEGORY: IP
label | 7e6d9ad5-89a2-5a15-a32a-8cb0499fc190 |  | note | RESPONSIBILITY: SE/PE
label | a3ebcc5c-b9ec-5aed-8390-c298631005e4 |  | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
date | 6e6df19f-41e4-5a14-84f5-2ef01cf543e2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 Concrete Mix - Trench
label | 3ea0c6a0-2d7f-5e1d-960e-a2714f5802e2 |  | note | REFERENCE: L1-CHE-STD-043
label | 72bc0bca-c0ce-5ce4-b8b5-4d1728a0f107 |  | note | ACCEPTANCE CRITERIA: Concrete strength at 28 days shall be not less than 25MPa.
label | f0f3bf25-a085-552f-b9c7-b0dc187dc412 |  | note | ○ Chemical admixtures or fly ash shall not be used
label | 2832f9fa-9064-5cea-bb51-e0e2e8a3dd2e |  | note | METHOD: Document Review
label | 367416e8-def6-5758-b773-8860711f816f |  | note | FREQUENCY: Each Material Type, Each Delivery
label | f5aa180a-ffaf-512a-9785-3b43a9012df9 |  | note | CATEGORY: IP
label | 83012c2b-9421-5d71-9be3-95a53ba39d8b |  | note | RESPONSIBILITY: SE/PE
label | 0ab4aff9-f872-5c5a-90bb-a29609cfec16 |  | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
date | b90b6b3a-2dfa-5706-9db5-5c1896c5deeb |  | date | Date Completed:
checkpoint-group |  |  | section | Prelimnaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Services
label | 60e9d061-c8ae-56ef-adf7-ae4cba57b184 |  | note | REFERENCE: Services CAD file
label | af2573dd-8b9a-539b-9e2e-fbc4fae4502f |  | note | ACCEPTANCE CRITERIA: All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit).
label | 37744404-4b14-50bf-9c82-bcb09fd0ebfd |  | note | ○ Survey to mark out existing services.
label | e5502a9f-28cd-51fb-91c0-d8394ce5597c |  | note | METHOD: Visual
label | e1371372-89f7-55d6-8832-de12949efdc0 |  | note | FREQUENCY: Prior to commencement of works
label | 818dfd37-a908-5c54-83a7-e99c125fe90c |  | note | CATEGORY: IP
label | ceb66d53-ba67-56bb-8645-3f4236e5e017 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 628dce13-5641-54de-8728-725792e4d0d9 |  | note | VERIFYING DOCUMENTS: This ITP
date | e7641f01-6dd8-59f3-a776-65721d08074e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 CSR Works Procedure
label | 52e264aa-6bc2-52a6-89c2-eb122738806e |  | note | REFERENCE: WAP_BRU_201
label | de6b5ce3-792a-5caa-877b-b44940cff492 |  | note | ACCEPTANCE CRITERIA: WAP to be reviewed and signed by all relevant stakeholders along with Rail Safety highlighting works proedure with in the Rail Corridor
label | 7c40fa3a-02c7-5a44-8feb-4f811637acd3 |  | note | METHOD: Document Review
label | 128336a4-2ac9-5b35-a051-8c2d65c81bd3 |  | note | FREQUENCY: Prior to commencement of works
label | 81dd8a2f-c584-5da8-9d9d-9deb244192f2 |  | note | CATEGORY: HP*
label | 909ccfb2-05c9-5694-9f77-5dbd7f6daa8b |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3219e64c-0664-57c1-8f8f-d9beaec423a2 |  | note | VERIFYING DOCUMENTS: This ITP
date | fdabcc66-0d7e-552e-9d68-5e9918bd4dd3 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out
label | 39069863-5d34-5f86-a3d4-78e9ee692231 |  | note | REFERENCE: IFC Drawings
label | e989f423-8e9c-5214-ad67-142a848ed797 |  | note | ACCEPTANCE CRITERIA: Survey to set out trench alignment and pits, and establish construction control (alignment and level).
label | bbec44af-b245-523d-b304-8a48e7aab0a5 |  | note | METHOD: Measure, Visual
label | 257e720b-5fc2-5b8f-a865-84a8c68b9649 |  | note | FREQUENCY: Each element
label | 992a1095-6d6c-5bd4-97c2-9ae6b7065b2e |  | note | CATEGORY: IP
label | 0cb0d1b2-b650-5180-a1d3-ab7274d5d1dc |  | note | RESPONSIBILITY: Surveyor, SE/Site Supervisor
label | 9d00d5ee-65bc-5a3f-bd6c-48e434131e99 |  | note | VERIFYING DOCUMENTS: This ITP
date | 17cfb9df-d6b5-5ff7-a8d2-eadf247482d6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 IFC Drawings
label | 0b3277fb-9fe2-503d-80e8-442beaa55cba |  | note | REFERENCE: IFC Drawings
label | e9a43790-7809-5dc6-bd94-f2680ce11be7 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | ddaefefc-6825-53a5-bb52-651bdf18fa4f |  | note | METHOD: Document Review
label | 9f34680b-8b5c-5a70-bf53-a04b1eac7772 |  | note | FREQUENCY: Prior to commencement of works and at regualr intervals
label | 633d160d-3360-505c-b03d-3ca3937709f1 |  | note | CATEGORY: IP
label | d1192729-0fd9-5561-80a2-295def5768f3 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 84e029a3-55f1-5e29-8d5a-62c23306dcfe |  | note | VERIFYING DOCUMENTS: This ITP
date | 3bb03b1c-e894-5a5d-81ee-c49982ae9ee0 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Trench Excavation
label | 530ec0a3-0145-5ebd-904d-296313f93f6c |  | note | REFERENCE: IFC Drawings L1-CHE-SPE-070 7.3 Table 2, L1-CHE-STD-043, L1-CHE-STD-070 7.1c
label | e64d84cd-7ddc-592a-bc4b-cb4a09db0ea4 |  | note | ACCEPTANCE CRITERIA: Trench profile and depth as per IFC drawings.
label | 61d18464-c4c7-533a-9b05-475678ef3b92 |  | note | ○ Edge of trenching to be a min. 2m from strucutres/pile foundation (unless it is mounting the structure) and a min. 4m from the rail for HV and 3m from the rail for LV & Comms
label | cd805c92-42e1-5599-80fe-116ab3e5e495 |  | note | ○ The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
label | 2693faf2-61db-5dfd-ab7d-964be4e27da1 |  | note | ○ The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
label | 9c49aa78-215e-5f85-9e1f-8829d9908d4a |  | note | METHOD: Measure, Visual
label | 4d02b7af-5f5e-5ce5-a4c6-5ac8c4327aa8 |  | note | FREQUENCY: Each lot
label | 4564eb17-accc-5e17-b571-9c10c3f28c11 |  | note | CATEGORY: IP
label | d5b03b7e-1db4-533b-805a-642aa950e962 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fcf7c160-d9a7-54bc-94e8-add23d76f011 |  | note | VERIFYING DOCUMENTS: This ITP
date | b39768e3-c2b8-50b8-b56f-cd957b3fad94 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Trench Stability
label | a11e1530-89b4-5cc2-ab66-748289d3f78e |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings MRPA Standards
label | 7b272644-a1a4-5fc7-8c98-e41cc0d9191a |  | note | ACCEPTANCE CRITERIA: Trench stability check:
label | 4a5bb328-b2d3-5170-a886-060adff8ecc4 |  | note | – Shoring,
label | 1fd159f6-59d5-5ad7-a0c0-79d5bef3f998 |  | note | – benching
label | c6f89c97-7a69-5e70-b556-bf55d0e6276f |  | note | – geotech signoff
label | 863f31a3-c58d-5139-87b3-4f7ad4ed84e7 |  | note | Attached Geotech Report
label | 39f22e15-16c3-5fd9-995f-9d49ea913396 |  | note | METHOD: Visual, Document Review
label | 5dae644d-9ae4-5a83-a791-657990079bd8 |  | note | FREQUENCY: Each lot
label | ce1d51ad-a96a-5ed9-b856-6c981f98c7ea |  | note | CATEGORY: IP
label | 062b74cc-80da-5490-8b8d-fe6851ea0823 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9d01ccc7-7eaa-5e70-bc08-dd6b75df8c94 |  | note | VERIFYING DOCUMENTS: This ITP
date | 75058eb1-d7a6-54e2-97e7-17ed71a362c5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Placement of Bedding Sand for Conduits
label | f174d590-7860-5c1b-b33a-c9524b3418a9 |  | note | REFERENCE: IFC Drawings L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070
label | 5c1d321a-a94c-5eb8-97f5-dc6755aeb78c |  | note | ACCEPTANCE CRITERIA: 100mm of bedding sand/crusher dust to be places at the base of trench.
label | a8c48100-3d5a-5eb5-8230-6e043cd2cd80 |  | note | METHOD: Measure, Visual
label | 3682af5d-c08d-5aa1-9119-031d55840eb7 |  | note | FREQUENCY: Each lot
label | 984d3ba8-2971-5513-b0b2-04e5eb921286 |  | note | CATEGORY: IP
label | f44328a3-c0eb-592c-8c80-501f2b4e35cb |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b222585f-e61a-5e72-8b03-2fb6a40d8281 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9d2fcdb6-a9c8-5e0b-84a8-1d21a00b2c6d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Conduit Placement & Configuration
label | 79171b55-8a74-5367-8e5c-240f524b04c5 |  | note | REFERENCE: IFC Drawings L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070, L1-CHE-STD-077
label | 7baad5e5-0a58-5df2-b067-a02e651c9066 |  | note | ACCEPTANCE CRITERIA: Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
label | 32290e10-7a4c-5d2d-a3cd-a3cf107b2e72 |  | note | Min Cover
label | fc0c540c-c0b4-5e26-8f7f-00c6ee361085 |  | note | – HV: 1000mm
label | 7a47a9c4-99ce-55c0-8bb8-c8c0d898e728 |  | note | – VicTrack: 650mm
label | cb65a474-fec4-58fa-a513-a9e010a2633c |  | note | – Signalling: 800mm
label | 2ff23918-34a3-51be-adac-cc4fec9523ee |  | note | – LV: 800mm
label | ca54b1e7-c7f4-5b1c-881b-e2ae4dfcbf0a |  | note | – Electrolysis: 800mm
label | 25672c16-e8b9-5011-b960-cfe020fce9fa |  | note | – SCADA: 800mm
label | 9a20de99-7037-5d39-a618-20d498edbb10 |  | note | – MTM Comms: 600mm
label | c13ca5a0-c10e-5ae9-9bc3-af12a0c5cacb |  | note | – 800mm below water coarses (stab sand encasement)
label | 9cb08112-73fd-5494-92ab-d8a81c6aec62 |  | note | – 1200mm Under VicRoads Roads & top of Rail
label | c70f653d-bd88-5119-878e-a11064579142 |  | note | – 900mm below council roads
label | 47ca82b7-218c-596f-b2b3-c5817e2a71fc |  | note | METHOD: Measure, Visual
label | eb347824-4d07-5e61-9f13-d219dbed8f8c |  | note | FREQUENCY: Each lot
label | b3a6cc8d-5cb0-53f4-8506-375fb2e7bdd3 |  | note | CATEGORY: IP
label | 284d5926-899d-5dca-a1dc-260dc30c9403 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 298d8fd6-5573-5cb3-96fb-3fe6e2bcc7bb |  | note | VERIFYING DOCUMENTS: This ITP
date | 6ed84b40-9d7e-5686-8bd8-e497bb9f34b3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Separation of Services
label | 542deb7b-4aec-5eb9-bfc7-eb0c83fced8a |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070, L1-CHE-STD-077 IFC Drawings
label | 6d1dd2bd-108c-505c-a822-86fbc6e1c7b4 |  | note | ACCEPTANCE CRITERIA: Separation of services
label | e02d0b21-fee7-5b27-bcb2-fca30e72f999 |  | note | – HV: Min. seperation distance between HV conduits at least 50mm
label | 237b9a9d-cc62-5ff5-8798-f94d4fcbb695 |  | note | – VicTrack: fiber 300mm from HV
label | a0b450dd-ac64-55a7-a8cd-b17aa08d10ac |  | note | – Utility: 300mm to utilities
label | 83e3fba1-82fe-5131-9618-4d6ab3b117a1 |  | note | – Rail: When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 164fbaf6-9954-5045-a7f9-07ed0cbc39ac |  | note | METHOD: Measure, Visual
label | f396906c-3387-5e33-b74b-41dad97cee63 |  | note | FREQUENCY: Each lot
label | 04273a28-5303-5fc4-9429-ac14118cb544 |  | note | CATEGORY: IP
label | 2891aa21-d01b-53c0-b3a3-8378943cb637 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 6abc363b-f52f-5c3e-a995-74a35e81b86c |  | note | VERIFYING DOCUMENTS: This ITP
date | 8db40914-40c6-596a-b43c-448e69a2ae68 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Joints
label | 8a1e77a5-a1b4-5d7b-94e1-aeb9627c953a |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | 4bfa4627-5858-524c-98b1-db17924fce79 |  | note | ACCEPTANCE CRITERIA: All conduit joints shall be made by utilising the spigot and socket ends.
label | 8926bbca-66d0-5df1-ae09-6a0b604f5c96 |  | note | ○ Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer.
label | cac6af79-71cc-5f03-bcdb-dd706fe95d5e |  | note | ○ The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer.
label | 4e66016d-5083-587a-9d36-df02729fec10 |  | note | ○ Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
label | 29bb7401-6195-5a26-8671-e249b977bdef |  | note | METHOD: Visual
label | 7db5fc00-b53d-5560-ad16-80d6cfa3589a |  | note | FREQUENCY: Each Joint in each trench
label | 756aee3d-918c-5cfe-b27d-7735ae535181 |  | note | CATEGORY: IP
label | fcf8f793-ae63-544d-b789-67210a76d5bf |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8a2e35d7-8fb1-5d80-af90-5b6320874580 |  | note | VERIFYING DOCUMENTS: This ITP
date | fcb16f55-1ae5-504f-8454-6b126d097992 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Conduit Inspection
label | 356b7afe-8337-5a42-9557-639dfa9fbae5 |  | note | REFERENCE: L1-CHE-STD-070 16
label | 44ab4d23-032a-5767-8e6e-bf58b76041ae |  | note | ACCEPTANCE CRITERIA: Provision shall be made for inspection of cable routes by NA, MTM/VicTrack representatives prior to backfilling.
label | a5eba1cf-bef2-582a-94ca-156f810d9409 |  | note | METHOD: Visual
label | c86658da-32fb-5153-891e-b52101e92cb1 |  | note | FREQUENCY: Each lot
label | af0f5ab7-a5bf-5ff2-bc8b-bd0aa3084785 |  | note | CATEGORY: HP*
label | 7691b9f5-5da9-58da-8d87-9ceb2a008871 |  | note | RESPONSIBILITY: SE / PE MTM / VicTrack Rep.
label | db9f2740-a1ef-5f47-82aa-6c11d4697a85 |  | note | VERIFYING DOCUMENTS: This ITP
date | 4cca3388-f724-5a1f-b477-f0134de0326f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Bedding Sand Installation
label | 2c9d5624-baec-5470-ae66-bbd207bfdf1e |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 CL13.1 IFC Drawings
label | 1416be2c-98a2-5e9c-a5ec-fee4d5ec1db6 |  | note | ACCEPTANCE CRITERIA: Bedding sand/crusher dust extends 50mm past edge of conduits.
label | 8410d5ae-427f-52d2-8141-2859773957b0 |  | note | ○ Bedding sand/crusher dust extends 100mm above conduits.
label | 46764d1a-8076-51a8-a8db-ae667163c0e4 |  | note | ○ Attach Delivery Dockets
label | baf4c657-bdc3-5a87-94c6-96a6a1b8e2c7 |  | note | METHOD: Visual
label | 0e9d3cba-728f-5554-96b6-fb6dedda4744 |  | note | FREQUENCY: Each lot
label | 2cb34320-ff40-598c-ad94-a39654f796e8 |  | note | CATEGORY: IP
label | 336c5438-cf95-5c58-ae42-23e01832378d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 783ac3a5-7291-57a5-bce8-5fdb2ad6a479 |  | note | VERIFYING DOCUMENTS: This ITP
date | a84dc77d-313f-5dc5-a50f-d35d9706372e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Marker Tape
label | d8e1bf85-060b-53cf-8b94-d9d29e895618 |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-SPE-070 Cl10.3.3
label | b740b100-d0d8-5e63-96b8-446961b2a429 |  | note | ACCEPTANCE CRITERIA: Warning Tape installed a min. 300mm above top conduit or a min. 300mm above HV protection barrers.
label | d7d11d21-2392-5dba-838f-e25a88039ff1 |  | note | ○ Tape to be one continuous length.
label | d8eaf905-350e-52a6-94dc-3fca881cd294 |  | note | ○ VicTrack to inspect the Marker Tape placement..
label | 4df3164e-a4b4-5275-a494-acd361a406dd |  | note | METHOD: Visual
label | ef244d7d-96fa-5f6b-87d7-e70620e1b0dd |  | note | FREQUENCY: Each lot
label | 7d5f05d1-b14d-5991-a9fe-ee735ac1152c |  | note | CATEGORY: HP*
label | 7ae286ff-f601-5c09-9ddf-05ea32343b7d |  | note | RESPONSIBILITY: SE/PE, MTM / VicTrack Rep
label | d78cca81-674d-5a3e-9514-3ef00209366c |  | note | VERIFYING DOCUMENTS: This ITP
date | a9f18dc3-113e-5c4b-9898-cc32f035ca10 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Backfill Installation for Conduits
label | 3c0d9281-2739-58e1-8551-6074e22822b2 |  | note | REFERENCE: IFC Drawings L1-CHE-STD-043 clauses 6.15 and 6.16
label | f2c4631a-03a9-5004-b149-87fe2f7afa80 |  | note | ACCEPTANCE CRITERIA: Backfill per trench profile
label | 1dc94e01-2b1c-573f-8e6e-52b5ae57f0e0 |  | note | ○ 150mm layers of 3% stabe sand
label | 9ec06418-7569-5272-ae3c-193ca05229e0 |  | note | ○ conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
label | ebe077fa-7e9e-53b2-a7d5-05a5240c9492 |  | note | ○ The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
label | 3c981d79-8864-56d3-8eb4-eb656097ff6e |  | note | ○ Trenches under road pavement - backfill to be same material as the road formation material.
label | 2cdddc8e-fbed-50d1-b37c-a02fe3d0857a |  | note | ○ Trenches immediately adjacent to footing shall be 3% stab sand. To be thoroughly placed to fill all voids without placing undue strain on or cause displacement of conduits.
label | 9950c272-cf2a-5c32-99f3-dd67b525196d |  | note | ○ When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | d72cbecd-1322-5318-bb3a-adb3017e9610 |  | note | ○ VicTrack to be notified and witness the first layer of backfilling.
label | 51549555-056c-5b99-816b-4fed237653d7 |  | note | ○ Attached Delivery Dockets
label | 31b5c386-5191-52df-b1b2-39cae961a836 |  | note | METHOD: Visual
label | cc2b7b86-0ed0-53c0-b138-d2121e34aa57 |  | note | FREQUENCY: Each lot
label | 24137a8d-e0ed-53f1-9b8b-66d0c22259fb |  | note | CATEGORY: HP*
label | fd375785-849c-5a30-9895-9953434b325f |  | note | RESPONSIBILITY: SE/PE, MTM / VicTrack Rep
label | 77d7862c-480d-50d3-a2c8-2e9de127fac2 |  | note | VERIFYING DOCUMENTS: This ITP
date | a982f2b7-eeb8-5c7c-8335-b6b6a230f6f0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Signalling Pits, LV Pits, Electrolysis Pits, SCADA Pits, MTM Comms Pits
label | 5218c639-2055-5840-9753-d3fa35cde5e1 |  | note | REFERENCE: L1-CHE-STD-043 Cl7.14.o, Cl7.14.g
label | 3d9219be-1669-57a2-9230-de6dfa849cd4 |  | note | ACCEPTANCE CRITERIA: intervals no greater than 400m (electrolysis 190m)
label | c38b604e-cd87-577a-ab8e-b7d2bd4638b3 |  | note | ○ 3m from rail
label | 93ed4ed3-aa0c-5343-92e9-920c9f731272 |  | note | ○ Access Roads, Class D lids
label | 1ddd36db-1361-5d5c-9f59-d2a5d881c7c1 |  | note | ○ Footpaths and non traffiacl areas, Class C Lids
label | c73795aa-0aec-5492-adb5-12df11782d3b |  | note | METHOD: Visual, Measure
label | 269ccd52-bdcf-5172-abcd-c265566968ee |  | note | FREQUENCY: Each Pit
label | 0544bf50-24a2-5fed-b627-baf7205c1d68 |  | note | CATEGORY: IP
label | e79e61fb-e8d0-5bc1-b86c-1e0a9c77b410 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 049f1aa0-8fa2-5945-af21-0ecfe994f974 |  | note | VERIFYING DOCUMENTS: This ITP
date | 7b2474b0-465a-5d88-a336-267d6202e7e4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Additional Considerations
label | d72d5104-9167-59a0-8299-e78a1fb6d9e2 |  | note | REFERENCE: IFC Drawings
label | cfd93b2f-1de6-5604-b695-4642c163a6d1 |  | note | ACCEPTANCE CRITERIA: Access tracks to pits
label | 628b7f05-797e-5573-bc07-f458c8ab31aa |  | note | ○ Safe access and egress (i.e. lid doesn't open up with workers back to the rail)
label | 9c631ff0-6cc0-541f-a10d-96719afe7167 |  | note | ○ Hand rail & retaining wall installed as required
label | eaba00c8-bd7f-5958-b5ad-e6dffe78d0eb |  | note | METHOD: Visual
label | 61969190-fc79-5095-9b01-fbb2a7a0abb2 |  | note | FREQUENCY: Each Pit
label | adf0ad7c-c96f-5e7d-85a2-f3e82d440ace |  | note | CATEGORY: IP
label | d965a625-f903-5258-b4d2-14ad62c54238 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 930ac6d3-cc47-54e4-b796-8ddd299bc3a2 |  | note | VERIFYING DOCUMENTS: This ITP
date | f97c49ec-1847-5257-902f-300cd9a41ef3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Bedding for Pit Installation
label | 93d01f06-7251-50b0-ab40-81ba61a1a126 |  | note | REFERENCE: L1-CHE-STD-070 Cl 7.21.u, L1-CHE-STD-043
label | 1f0744ef-44ba-5005-aed9-ac369a71cdfb |  | note | ACCEPTANCE CRITERIA: 150mm of crushed rock under pit extending 500mm past the pit
label | f2a37646-077e-531a-b00a-cf9eeb8c9a39 |  | note | ○ Drainage arrangements shall be provided at the base of each pit.
label | c2a2a390-c48f-5260-aa29-89e0a850bf72 |  | note | ○ Attach Delivery Dockets
label | b11905e2-c4d1-58c8-898d-c1a249c6e1fd |  | note | METHOD: Visual, Measure
label | 092f9633-61c1-5bd3-810e-01e388f3d9b2 |  | note | FREQUENCY: Each Pit
label | 646602c6-02ef-588c-a2c5-101c7d4d9804 |  | note | CATEGORY: IP
label | 6eb43bdd-3e4b-510c-a3af-4b950ecc5415 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fbe0cb30-eb5b-56c8-b112-4a0f28f32140 |  | note | VERIFYING DOCUMENTS: This ITP
date | ef10e5f7-b8ae-5f9f-844c-be7d005b6cfb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Pit Orientation
label | 0e6c0c9c-afad-5829-8c34-2563ded7a13a |  | note | REFERENCE: IFC Drawings
label | 5c709462-bee5-54e8-9cab-fabc5fa7d815 |  | note | ACCEPTANCE CRITERIA: Pit to be parallel to track and parallel to conduit route.
label | 88978cf6-8f19-5f9a-bb23-aeeecbb7ee13 |  | note | METHOD: Visual
label | 5ac8252c-51eb-5f04-86e1-efc7b6c43557 |  | note | FREQUENCY: Each Pit
label | 5a2746bf-aa4f-5a0a-b3a2-83235e173e35 |  | note | CATEGORY: IP
label | 6bb38415-5b34-52aa-ac7b-faeaaeaaacdd |  | note | RESPONSIBILITY: SE/Site Supervisor
label | e73b32ee-a781-582b-8771-8150bba62482 |  | note | VERIFYING DOCUMENTS: This ITP
date | 04585113-9778-523b-aaab-72244099d780 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Pit Installation
label | 2cc78682-36ac-5ba4-bd86-f3cbc83ad1ff |  | note | REFERENCE: IFC Drawings
label | c04b0b56-46d2-59fe-b792-4db0046605ed |  | note | ACCEPTANCE CRITERIA: Pit installed to design specifications
label | dcabe336-1a03-5abb-b2e8-77fabefa21a2 |  | note | ○ Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
label | 48e3db38-2b55-50a0-a65e-fe8a335c3e6f |  | note | METHOD: Visual
label | 01859ce4-96a8-58cc-a840-3b8adbc1065c |  | note | FREQUENCY: Each Pit
label | ffc9428d-6396-52a8-87eb-04bb5ba8020b |  | note | CATEGORY: IP
label | 34bedc70-9c27-51e2-b460-d1026300c9f6 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3998d324-5d28-573f-bf46-4474c036d428 |  | note | VERIFYING DOCUMENTS: This ITP
date | b6b4cb41-48dd-5839-be51-10e8c5aca13c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Conduit Entry onto Pits
label | 99ba90a0-7693-588a-89e6-86b88f272288 |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | 8b78a58a-52e3-5303-8968-69fd7b6a5bbe |  | note | ACCEPTANCE CRITERIA: Lowest conduit 100mm from the pit chamber floor.
label | 327eed41-3bd5-5fcf-8a6d-6a8dae3b3d65 |  | note | METHOD: Visual, Measure
label | 2e929625-a2c7-5a8b-bf03-8ea7bfb61948 |  | note | FREQUENCY: Each Pit
label | 4edb8c49-ce2d-51aa-ab30-0f0209dad09e |  | note | CATEGORY: IP
label | 3a56e5d4-c2bb-530d-b5ea-bcb2fb1f7023 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b3dce4df-2d22-51b2-8cd0-0d91f7a7856a |  | note | VERIFYING DOCUMENTS: This ITP
date | 269a6da8-2674-5235-8ba5-f0e4c95bc510 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Tracer Wire
label | ae5e1d17-d3aa-5a93-b721-e08db6179e51 |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | 04158a8c-079a-5f42-8111-f6623b6a8ee1 |  | note | ACCEPTANCE CRITERIA: Warrning tracer wire for Vic Track routes to be drilled into pits and crimped off.
label | f56178fd-caac-5d36-a318-34dfb44355b7 |  | note | ○ If tracer wire broken needs to Crimped
label | b335b81f-a727-56a5-a84f-d84b7d271ac7 |  | note | METHOD: Visual
label | e8b6c624-1a2b-5e10-b828-d729cc4e2ffe |  | note | FREQUENCY: Each VicTrack Pit
label | ad7558b3-47d7-5935-b52e-5776784bf8ef |  | note | CATEGORY: HP*
label | f73159d8-ee9c-5794-bf5c-ba8bf365882d |  | note | RESPONSIBILITY: SE/PE, MTM / Vic Track Rep
label | 921b9e2b-e036-5d87-8834-0346598fe5a1 |  | note | VERIFYING DOCUMENTS: This ITP
date | 47a24740-cf3b-5ab1-ba92-7e6460e6ff01 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Spigots and Bell Mouths
label | 8ce5ff8e-32b3-59a9-bcfe-97d0eb2f7f03 |  | note | REFERENCE: L1-CHE-SPE-070_9.3.4
label | 8c84e389-54fa-532a-bb41-b5891fc32d13 |  | note | ACCEPTANCE CRITERIA: All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigots.
label | 28f53404-bdec-5e67-ad00-0c240abbf431 |  | note | ○ HV Conduit entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
label | b8c4f5a0-baa9-5777-82a9-1f10d5936918 |  | note | METHOD: Visual, Measure
label | 04cee6cd-d876-58e9-948e-c40e451ebf54 |  | note | FREQUENCY: Each Pit
label | 90678a2a-5d19-52e0-999e-55fa43884945 |  | note | CATEGORY: IP
label | 494367b5-e5ca-5ff9-a5bb-18c41a5fb10f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1f345f4a-224c-59bb-b19a-dd96c23946c9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9ed1bdb5-00fe-5662-9de2-f4d10608561e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 Draw Ropes
label | 4260b33b-1ccc-54aa-aa2f-6dc38451739d |  | note | REFERENCE: VRIOGS 012.2.1
label | c6b80c47-bea5-5b73-9f76-57887241a8ac |  | note | ACCEPTANCE CRITERIA: The draw wire shall be continuous for the complete length of the conduit run.
label | a3bc7c58-81e6-54bf-a453-d32f2d3e8ce4 |  | note | ○ The draw wire shall have a minimum of 2 metres of slack within every pit.
label | 980bdf9b-efee-569a-b6a5-cecab1d34789 |  | note | METHOD: Visual
label | 14240aa3-8847-5b07-91be-47e81c86bac6 |  | note | FREQUENCY: Each Pit
label | d7caa487-5fc5-5cc8-b504-6a95b03265e4 |  | note | CATEGORY: IP
label | fd8d3b65-729c-5332-a248-a2e54ec6428d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3845978c-c4dd-5b08-bde0-ede7454fbce8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5ce8b6e4-8d4f-5d11-93d7-707ef82d4ed5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 Backfill and Compaction Testing (if applicable) arouns Pits
label | 99d077c9-1a2f-5058-aaae-0080d6854a19 |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | ad391d66-dd63-5ad6-b1d6-ec7e164c34b5 |  | note | ACCEPTANCE CRITERIA: Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
label | 663231da-fc55-51bc-9e64-729ce0554801 |  | note | ○ Sand within sand pits to be compacted in layers no more than 250mm layers
label | e7d11807-1cbc-5959-ad17-12988242b05f |  | note | ○ Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
label | 755fcb60-3ab7-53c3-8544-099242757f35 |  | note | ○ Attach Test Report
label | deec2004-1246-5886-8c20-3d785ee79359 |  | note | METHOD: Document Review, Visual
label | 764aa750-fd3f-54fb-9c38-98250ed0103e |  | note | FREQUENCY: Each Pit
label | b147eb79-fe0f-5632-b070-1dccb0bbfc75 |  | note | CATEGORY: IP
label | 9f94dbc3-eb65-54b3-81c7-8a3c7238ff2d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8f851a7b-759b-5be7-a9db-00696a8514db |  | note | VERIFYING DOCUMENTS: This ITP
date | c92f6202-10a8-5a54-90e3-85ddcda7bd54 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.21 Spare Conduits
label | 69034040-247e-566c-b9d6-69691c9118c3 |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | a141062b-5e71-5c05-8121-0f327d40d1c5 |  | note | ACCEPTANCE CRITERIA: Spare conduits to be sealed and to be included on survey report.
label | 6758ff2c-eb0f-55f8-a9f4-c87c64bc2359 |  | note | METHOD: Visual
label | 371de5d8-8542-5454-b112-5c76fe48fa64 |  | note | FREQUENCY: Each Pit
label | e05cb314-a55a-5484-96b2-b288f2bc1301 |  | note | CATEGORY: IP
label | 48f983aa-b6c2-5a59-8aba-1a9d4075c32b |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8732663a-6493-5fa0-9773-30ee8b49e84b |  | note | VERIFYING DOCUMENTS: This ITP
date | d228b58d-3dda-5229-a445-a39b50761dd4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.22 Pit Labels
label | 11039533-9e05-5cab-a111-3e2c2c232e1b |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | 01121451-b87d-575c-bc73-8e06e983e8fc |  | note | ACCEPTANCE CRITERIA: Pit labels Brass Label (30mm x 150mm)
label | 739023ac-fd41-5e68-b13b-ddf51360fa92 |  | note | – HV: DANGER - Railway High Voltage
label | cd912f2d-b3d8-5d84-a5b0-23366d5d5a84 |  | note | – VicTrack: Victrack Comms
label | fb5e1bac-4100-5e02-874c-37ed215c0987 |  | note | – Signalling: Rail Sign Comms
label | 916d2744-33de-5919-9e82-776bd4c7cec6 |  | note | – LV Pits: Electrical
label | d982417a-c23d-5256-b931-e9c3259a31e1 |  | note | – Electrolysis: Electrolysis
label | 42efec68-e96c-575f-a2c6-5a11e20c573c |  | note | – SCADA: Rail Sign Comms
label | 28ccc759-d1f4-5594-9a50-ecaa433aedcc |  | note | – MTM Comms: Rail Sign Comms
label | 1cc70578-0041-5010-8272-c36afbcfbfb5 |  | note | METHOD: Visual
label | 33d82225-9a72-5da1-b945-d64fa7d849e6 |  | note | FREQUENCY: Each Pit Lid
label | e2e52c6c-e619-547a-9da9-7664345eb89d |  | note | CATEGORY: IP
label | ad4f4132-a2cb-5013-b6d6-d9230a2702ba |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 212e65d0-bd4f-57a8-9ff7-571d1dfffe57 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9a32a0e5-b8a2-5f63-b24d-972826244be7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.23 Pit Numbers
label | 513b16b0-a4e9-5159-848c-31a4461bb470 |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | cbaf1e41-1c6e-55a4-b171-71a589d1c0b8 |  | note | ACCEPTANCE CRITERIA: Pit Number Brass Label (30mm x 150mm)
label | 2090f8df-220e-5dfd-a8ef-5cbca9cf903e |  | note | – HV (22kVV Feeders): ###HV
label | 9e55c501-ff12-53a5-b097-49795edc9d65 |  | note | – DC (HV Feeders for OHLE): ###DC
label | 836083e5-89e1-5f9f-9ad9-a41ba5481c89 |  | note | – VicTrack: ###C
label | 6c7918ec-e7c6-578b-9833-2562fa87ee87 |  | note | – Signalling LV: ###SL
label | cf173a66-0dd1-5a0e-8379-325d7a1dcb63 |  | note | – Signalling HV (2.2 or 3.3kv): ###SH
label | 5fbd8e25-be84-5f64-bf84-0e1d4cd84347 |  | note | – LV Pits: ###L
label | 0fbedc0d-4a09-5cf3-9341-16205477b159 |  | note | – Electrolysis: ###E
label | 4a406ad8-13a9-5a0b-8469-42115c59593b |  | note | – SCADA: ###MS
label | 619d8fdd-6fce-57d9-880a-a0fcbe9581c3 |  | note | – MTM Comms: ###M
label | 8ca4aeb9-737b-56d6-8931-c17384d2ace2 |  | note | METHOD: Visual
label | 65e3c8f7-2480-5611-986e-b3f926b88e98 |  | note | FREQUENCY: Each Pit Lid
label | 9e4493a5-91c6-5ed3-ae6d-7086374eda3d |  | note | CATEGORY: IP
label | f4922314-a52b-590f-a965-c721bca899ea |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 645dbca6-7559-55f0-b20f-f40a8d03ba51 |  | note | VERIFYING DOCUMENTS: This ITP
date | 37d3c94a-d0b5-5069-8476-4f448f94e3a8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.24 Cable Route Markers
label | 6ee50af3-a402-531a-a6a0-a1a54996f6e5 |  | note | REFERENCE: L1-CHE-SPE-070_13.2, STD_E0169 and STD_E0170, AS 4799, STD G0003 and STD G0004
label | 123e2320-5c03-504b-915b-e4adaf40a4f1 |  | note | ACCEPTANCE CRITERIA: Cable Route Markers
label | d8dcf363-53a6-55f9-8232-5212b6e10b3f |  | note | – points entering & leaving the rail corridor
label | b56ec145-0fa4-58ec-9a54-a60ab3c3903b |  | note | – no greater than 100m spacing
label | a770701e-216c-561d-92da-2b4b68ef0ad8 |  | note | – Change of direction (more than 5 degrees)
label | d0e5f72d-9289-5d77-9c8d-97e76dd6b1bd |  | note | – White posts with marker plates for conduit runs
label | 02d02c0c-5e13-559b-aaa9-a4f826dd5d69 |  | note | METHOD: Visual
label | 78619c73-9406-5080-a0ba-c7aede3a9b59 |  | note | FREQUENCY: Per Cable Route
label | 280eb45a-b2de-5477-a25e-003b5d62f093 |  | note | CATEGORY: IP
label | 728a14eb-6f77-52a2-84ed-16ce67c0c5f0 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 6c7998df-be64-546d-bec5-fd7f2052c385 |  | note | VERIFYING DOCUMENTS: This ITP
date | ceeb4639-0cfc-5bc7-9677-32a8d733addd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.25 Cable Pulling
label | a7f62723-c0c9-5d6d-9c77-a7e6ffaabee3 |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | 6c7f6e0b-1eb1-5316-886c-4af899afffe9 |  | note | ACCEPTANCE CRITERIA: Cable pulling to be witnessed by MTM/Vic Track and to be signed off.
label | db0cb5d8-a1dc-5c1a-8330-61f4fce3584c |  | note | METHOD: Visual
label | cca8bc22-960f-5d35-bd1c-fa85607165f3 |  | note | FREQUENCY: Per Cable
label | 1839e8bb-08e4-5e51-abd3-d03c1d2fed5c |  | note | CATEGORY: HP*
label | 92aeba12-b3fb-5392-a102-8ff31b542ad1 |  | note | RESPONSIBILITY: PE, MTM/VicTrack Rep
label | 9ec21f6b-6aae-546e-8d8c-f3eba15c2a02 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9b4e6fbe-2b46-5285-bf93-0d55678f533e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.26 Cable Labels
label | 5a774c10-4d54-5ed3-a4f1-e3973dc7914e |  | note | REFERENCE: L1-CHE-SPE-070 Section 13.3
label | edaf4e8d-428a-521e-a35f-e7a9f0ffb4cf |  | note | ACCEPTANCE CRITERIA: All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints.
label | 248a2120-dfad-5e23-8ae4-e86e36112d2b |  | note | ○ The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
label | 80f1e92a-75f4-580f-881a-7f03ca289273 |  | note | METHOD: Visual
label | 1a36bc33-e748-5cd2-b97d-4e0824f2e7b6 |  | note | FREQUENCY: Per Cable
label | 3549893a-9e2d-5ea8-831b-1c582fa1db10 |  | note | CATEGORY: HP*
label | 9c194d1b-73ee-5bc4-8e51-8bc226950572 |  | note | RESPONSIBILITY: PE, MTM/VicTrack Rep
label | 8694ad37-fe4f-5ff7-ba39-8a03ae965174 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3f894f5d-8806-5817-a6e9-8c4276afb655 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.27 Cable Joints
label | c3b5dfb8-ed9c-5470-91c7-ef4d72554bc9 |  | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | fd231ced-4492-5b7f-ada0-157918007ef3 |  | note | ACCEPTANCE CRITERIA: Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
label | 8f7a433c-2cab-592b-a587-248832620b6a |  | note | METHOD: Visual
label | d913e6e3-aff8-508e-b6df-2fe7373c0a90 |  | note | FREQUENCY: Per Joint / Termination
label | 321cf65a-8684-5b2f-9087-a6e276673650 |  | note | CATEGORY: HP*
label | 14211237-f0f9-5576-807b-cfc20ae928ab |  | note | RESPONSIBILITY: PE, MTM/VicTrack Rep
label | 17a68fd4-3ed4-5281-b0e4-f32524154579 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6a081a85-cafa-5f66-87a5-2038001cfb06 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey
label | 66d1e62c-22c9-5d91-b090-c80bffe5468b |  | note | REFERENCE: IFC Drwings L1-CHE-SPE-070 Section 13.1
label | e53f70f3-7f65-5815-9c0c-862c146ec936 |  | note | ACCEPTANCE CRITERIA: Survey report to include but not limited to:
label | 8b2123b9-b87f-5215-90dd-6229e89cd206 |  | note | – Cable joint locations.
label | 34f9a9e1-2ce6-5446-a9b1-cecf86482566 |  | note | – Cable pit locations (Corners)
label | ec80c736-b3d2-563f-aea8-ab068d48bc44 |  | note | – Pit dimensions & pit lid type
label | 7db45838-94be-5bd9-b01d-f4034e323cae |  | note | – Under line crossings
label | e79a90e8-07c0-5eef-8aa2-013db166d5c9 |  | note | – Under road crossings
label | 0b137d3e-2672-58b0-8686-286a8ca4d2b0 |  | note | – Changes of direction
label | bbcc1bb4-c47d-5959-ba96-1a1c2f44a392 |  | note | – Spare Conduits
label | 9b3ba0cb-9117-5f7d-9e70-5570c13ea47e |  | note | – Conduits labelled as per trench profile
label | 9b3be22b-9b95-5e3a-9c6f-ba859ea68c7c |  | note | – every 10m
label | baa77a76-83bb-5c0c-b036-80631fd25a88 |  | note | – Other significant points of the cable route
label | a7a3c834-6d7b-58c6-8cac-4a6fb8f2e438 |  | note | ○ Attached Survey Report
label | 82e4e4cf-418d-5554-bd71-3e869e3aad8a |  | note | METHOD: Document Review
label | f874931a-e08e-570f-824f-274efa23174d |  | note | FREQUENCY: Each Lot
label | 6eb27fdb-3e57-57df-9cdc-35167d4002d0 |  | note | CATEGORY: IP
label | 71283e86-5e82-59a3-88bf-0cf2b52c214a |  | note | RESPONSIBILITY: SE/PE
label | 0aacc399-f0c5-5722-b736-de494f1790f5 |  | note | VERIFYING DOCUMENTS: This ITP
date | e25c8f76-a41a-50c5-b377-092ff97d7c62 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Handover Check
label | e666f92c-4756-55d4-bcbf-3e8351eadd79 |  | note | REFERENCE: IFC Drawings
label | 2176bcff-76b0-5150-9ddc-f2ee92a132d1 |  | note | ACCEPTANCE CRITERIA: Handover check completed for Testing and Commisioning.
label | 9f060cae-c41e-58bc-a7a2-436f67e7ee61 |  | note | ○ Attach MTM/Vic Track Check Sheet (Signed-off)
label | f2e1063f-26b8-5a6e-8381-43599d7098d7 |  | note | METHOD: Document Review
label | a0f2d367-01dc-56eb-a4dd-b861015b8a9b |  | note | FREQUENCY: Each Lot
label | 7386a227-bb23-5da6-b014-80cdb864f5ef |  | note | CATEGORY: HP*
label | 4dda6aed-fc9d-5b27-a5eb-953b10d27605 |  | note | RESPONSIBILITY: PE, MTM/VicTrack Rep
label | 60a55a59-32c4-5c62-a2f6-185931f6619a |  | note | VERIFYING DOCUMENTS: This ITP
date | c32c4c13-28a6-50fb-8fe6-79ac85f3272e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Testing and Commissioning
label | fa4ca134-bcff-5d20-ba2b-fa3a14535347 |  | note | REFERENCE: IFC Drawings
label | 88196051-8110-5ee9-9dbe-23bc835180e3 |  | note | ACCEPTANCE CRITERIA: Testing and Comminsiong to be completed
label | 2b2fd64f-173b-54a2-9f8d-b9ff82f6355c |  | note | ○ Attach Testing and Comminsiong Report
label | 2507b3c0-410c-5c38-b812-2779fddb1459 |  | note | METHOD: Document Review
label | 2d885c79-367d-5d09-bb5e-a058ff99d8b1 |  | note | FREQUENCY: Each Lot
label | 12e8ee34-63ef-5865-bfe7-36d3b5726c1c |  | note | CATEGORY: HP*
label | 7ff3e05d-ca11-571d-b2b3-352c375952e5 |  | note | RESPONSIBILITY: PE, MTM/VicTrack Rep
label | 76af0b18-e86a-5175-ad39-4b2a86771e3a |  | note | VERIFYING DOCUMENTS: This ITP
date | e4a9c679-3a79-591c-bac2-0f8c7edb390a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | 03176dcf-ce5a-597e-a9a5-330a3f5c1db6 |  | note | REFERENCE: MRPA Quality Management Plan
label | fe4cb5d3-e5b5-569d-8018-c30743523f7e |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 5e5e4708-1977-5910-bcdd-50dea287f70d |  | note | METHOD: Document Review
label | 2fdc2027-5f9a-51ca-999f-99953f452520 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 05eec57c-d289-5e2d-8d3c-c2d6ec2396e7 |  | note | CATEGORY: HP*
label | 66dc9642-a9f4-5451-9f8e-c4604a7454c0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | bd3068cf-987e-5c59-82b5-51a0d88a2e37 |  | note | VERIFYING DOCUMENTS: This ITP
date | e01c50b5-157b-5d2c-9c05-8cd969db49b2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | f5f0dda7-8ed4-59f0-b0ac-ab1a773c8aa7 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 1c90f279-519f-533f-9f1f-1254a5c2179b |  | textbox | Name:
text | bcb84c9b-615b-566d-bb7a-632b8c2767fd |  | textbox | Position:
date | 7d7a778c-f75b-52da-b777-60e1d71a72fe |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-077-CIV-PSDS-Subgrade Preparation-Road | itp |  |  |  | Yes | ITP-077-CIV-PSDS-Subgrade Preparation-Road Rev 0 | 488e1df5-291e-44b1-b81d-ee5185a4ad71
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | a48d66c0-894e-5948-bcf0-f12038958b0d |  | note | Document Title: ITP-077-CIV-PSDS-Subgrade Preparation - Road
label | e4625747-28d3-5d68-97e8-94c26c9addeb |  | note | ITP Description: PSDS-Subgrade Preparation - Road
label | e07b4132-2d59-5588-8116-6299a6a41330 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | a1fb18e9-1b6e-5b6a-9795-0ae974c79ab5 |  | note | Discipline (e.g. CIV/STR/RAIL): 077-CIV
label | c4e99df4-6dc6-5da0-89d7-544f5ac74162 |  | note | Revision Number: 0
label | d4ac226b-638e-5029-97e8-5c0a1b35f9d9 |  | note | Revision Date: 21/12/2023
label | cf9c0afe-e511-52bc-8c79-02d58d2aa527 |  | note | ITP created by: Victor Mira
label | 7d696924-d706-5012-9ac7-8926a1377758 |  | note | ITP approved for use by: Victor Mira
label | 01659c66-156d-5fb1-87da-bc4ecf55b634 |  | note | 1.1 Non Dependent
label | 68322612-12a9-54e4-845f-99f754678b3b |  | note | Reference: VicRoads Section 204
label | a5a168a6-6025-53a3-a2a9-d38e8151352f |  | note | 1.2 Non Dependent
label | 030abb92-c8a0-593c-87ce-ff1dac02e5d1 |  | note | Reference: VicRoads Section 173
checkpoint-group |  |  | section | Mater
checkpoint-status |  |  | checkpoint | 2.1 Material Approval
label | cc15bfa8-a92a-528f-b683-b763359bbc9d |  | note | REFERENCE: VR 204.04 (C) MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage,Barriers,Pavements & S&L)
label | 2f808ccf-5ed5-5ae1-9e34-6a85b1c92459 |  | note | ACCEPTANCE CRITERIA: Material used for subgrade preparation shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
label | 9acf7b0b-7f5d-5be3-bb6a-5736d53ea27e |  | note | ○ Material shall have a minimum Assigned CBR as indicated in IFC Drawings, and Assigned Percent Swell less than the value indicated in the IFC drawings.
text | fac73c56-d541-5da3-9530-9d2e76868063 |  | textbox | Enter: Teambinder Material Approval number
label | 850f6036-ff71-5106-88b2-58b289e536e6 |  | note | METHOD: Document Review
label | 074c6e03-92ca-5500-b0c7-ae8691924f13 |  | note | FREQUENCY: Once, for each mix material
label | 15181c2e-91d2-5488-ac25-5467450cc34d |  | note | CATEGORY: HP
label | 1bbbe49b-49fc-5037-a64a-7af98851e402 |  | note | RESPONSIBILITY: Nominated Authority
label | 89ab2191-180c-5228-a77b-fcdea24433af |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 234388bc-6245-592c-8bed-5debae54122e |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 Non Dependent
label | 1ff798c2-cded-59c0-9e6a-9cab0dfb8de9 |  | note | REFERENCE: N/A
label | ddc9dc8e-8164-5966-826a-f6be59044572 |  | note | ACCEPTANCE CRITERIA: N/A
label | 1762311f-f4e4-5d4d-989c-9b787bf86bef |  | note | METHOD: N/A
label | df5b8439-1a06-5e21-ac3c-ff41faea2956 |  | note | FREQUENCY: N/A
label | 2627712e-b1b3-5100-bedf-25f806ef4c74 |  | note | CATEGORY: N/A
label | 1ec6e44e-8c08-51ae-a5ff-53e60a8dbb82 |  | note | RESPONSIBILITY: N/A
label | fe104d15-102f-5866-96e2-603b689e1ffb |  | note | VERIFYING DOCUMENTS: N/A
date | 5739eac9-a4cf-529c-8a51-c6d511b644a8 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-Out
label | 19635583-96de-5188-8ed6-8fcf1a175ee4 |  | note | REFERENCE: IFC Drawings
label | ca61ebc4-1b11-537c-ac02-6ae5c8bf310e |  | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | ac3f2fb2-ea7a-538f-a165-a971e03f8b0d |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | 22f0bb1f-257f-5524-ab8a-c15d26e087ad |  | note | METHOD: Verify
label | 8ef44350-162d-5450-b89e-12e250451eb2 |  | note | FREQUENCY: Prior to commencement of excavation
label | 8a7e0f6d-4d8b-504e-9c31-517d0fc5278a |  | note | CATEGORY: IP
label | f9989393-29e5-5a82-ac88-4bc452bc2655 |  | note | RESPONSIBILITY: SE/Surveyor
label | 8aef91a2-1c2f-5ba2-8075-8b3b94123e86 |  | note | VERIFYING DOCUMENTS: This ITP
date | a11ebe6a-e07c-531b-8640-b466849e24ea |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Inspection of Subgrade Material-Subgrade Material Properties
label | 8b49d3ee-1485-59b1-8ab7-7d4a4122d2ef |  | note | REFERENCE: Section 204.06 (c), Section 204.06 (e), IFC Drawings: MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage, Barriers, Pavements & S&L)
label | 7fcba309-6c96-55e3-a0fb-3354dbda15e6 |  | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | bb592932-f611-535d-8124-031b734afc9e |  | note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | 50c70d7b-31d9-56f5-a8e0-820092814215 |  | note | ○ Assigned CBR and swell as per MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage,Barriers,Pavements & S&L)
label | bd37584b-7ac8-5b2e-8bf9-b2030955bdfb |  | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
label | d1d0db08-e4d9-533d-8374-614421c81848 |  | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming fill material.
label | 79002180-6cb4-5127-a239-42b3dd31d7d9 |  | note | Attach: Laboratory testing Verification:
label | d783471c-e79c-5c40-8c5e-d50b43dfb6f2 |  | note | METHOD: Verify-Document Review
label | 1090dbbe-8389-545f-a516-a9aa6d504999 |  | note | FREQUENCY: Each lot
label | 287341f8-6704-55c6-904d-26beccd89343 |  | note | CATEGORY: HP
label | 3ad806cb-6e5f-5b61-8c93-0e2a7f48e8fd |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 8af4e62f-1690-50f6-9b4f-7345e9493022 |  | note | VERIFYING DOCUMENTS: This ITP/Test Report/Referenced Lot number
date | ef611fa3-a1b8-521a-bcf3-40e923678645 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 Material classified as silt
label | cb416677-a3ac-5900-9358-ac3816737845 |  | note | REFERENCE: Section 204.04 b)
label | c18d3959-9e28-57a1-b333-e2ab2f5f6cc3 |  | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | 4d981136-0c33-52d6-892a-9d662d45051b |  | note | METHOD: Document Review
label | 0d7eb51b-2703-5b11-8a5e-140235a12efe |  | note | FREQUENCY: Prior to commencing
label | e0347212-d188-5189-9f4b-42cc9808f345 |  | note | CATEGORY: HP
label | 5cd2bd63-77a3-5912-a566-59f4d1af3cb3 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 018d11ce-2fa0-5f41-b52e-d994a892ef35 |  | note | VERIFYING DOCUMENTS: Superintendent satisfied with Stabilisation, Signed ITP/ records
date | 36c02dea-1c81-5758-99c6-4e524afb6b91 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Acceptance of Rock Subgrade (where applicable)
label | a415de54-5414-5e28-b921-bab68b677b37 |  | note | REFERENCE: Section 204.06 f)
label | fb3fa1aa-ec7c-56ba-a16f-8f3465d546d5 |  | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | 28c010bb-e311-519b-8890-8ebda4e7c879 |  | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | a24d7df8-eb75-516c-b24d-c8d4a4eb2830 |  | note | METHOD: Site Inspection/ Document Review
label | 6117c7fb-35f8-5346-9a66-d05e8a8a2ae0 |  | note | FREQUENCY: Prior construction of the regulating layer
label | e3265566-ae82-55a5-ba1a-d475618d7878 |  | note | CATEGORY: HP
label | 46d25171-3039-54d1-9e6c-c592a9751adb |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 33ae55b9-af72-51db-8c54-cd9e93d8336a |  | note | VERIFYING DOCUMENTS: This ITP
date | b2f5c12c-ec3c-5119-a27d-0ff876128f8c |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Unsuitable Material
label | 6c34d66f-33b3-5f39-8c74-0b121909e397 |  | note | REFERENCE: Section 204.07 d)
label | 175b4207-c731-5c4e-8076-f3221ace154f |  | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | 79a574d6-67d3-54de-bad6-137030f79c75 |  | note | METHOD: Visual inspection
label | 9f4212d5-1fda-56df-ad8e-a4b54e61f662 |  | note | FREQUENCY: Each lot
label | 4664e2d1-1d52-5e3d-a1be-7c46d05eff75 |  | note | CATEGORY: HP
label | 64d6a90f-0f2e-58d8-be79-aeac97d97b49 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | cf580054-16ca-521d-bb28-35a2e9cfb12f |  | note | VERIFYING DOCUMENTS: This ITP
date | 9a7ae309-1678-5d9e-815b-2c825f562eb7 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 Groundwater
label | 6374f297-f20c-5080-ae6e-1d972ad71967 |  | note | REFERENCE: Section 204.06 h)
label | 777f3cd5-2834-5b62-acf1-d79e9a666d13 |  | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | 1ff029de-f2d0-5be5-ad96-c018104ccc0e |  | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | a8a85504-b511-52b9-9f4e-781d1b80027b |  | note | METHOD: Visual inspection
label | d02b1dd3-570c-5d5d-9e19-5301cbb10969 |  | note | FREQUENCY: Each lot
label | 33399df5-fb99-5621-9290-8190cc1c8e28 |  | note | CATEGORY: HP
label | bff287bf-2c2f-5692-8487-fbaa299bb1ea |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 7aa007fe-0304-589a-871c-74777fc61d33 |  | note | VERIFYING DOCUMENTS: This ITP
date | 7e61b246-c266-5d09-bd7f-474e03f50a85 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Cut to Fill Zones
label | b66ca4b7-c5dd-5c68-89f5-dd2a85077d42 |  | note | REFERENCE: Section 204.06 g)
label | f6197293-7543-5b44-953a-c8a4c15aacf2 |  | note | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
label | cc9054fc-a599-58e8-8501-a625d1fe38d5 |  | note | METHOD: Site Inspection
label | a2c52e45-0c33-5e0b-a346-fc8b00816d6b |  | note | FREQUENCY: Each lot
label | 0b4c5976-3380-5b5d-91f3-ff75d6551cb7 |  | note | CATEGORY: IP
label | c793e3cb-704b-55fc-8b27-68f4b8c30e9f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 482c74f1-14ab-587d-b896-b9f55b3e4dcc |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 7b814770-6342-525f-9f0d-9ecb4f235c24 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Proof Roll
label | 58413b66-18bd-5f48-9205-57cf85e897e9 |  | note | REFERENCE: Section 173
label | 40b47644-8cdc-5737-ba28-efbf10387014 |  | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | d852f588-d496-5015-ad9f-c51b229ea7a4 |  | note | METHOD: Visual inspection
label | d823eca5-496c-5ad2-807a-e13f2077fcbd |  | note | FREQUENCY: Each lot
label | 877c4d70-462a-58c1-a37c-5d5c89044ab4 |  | note | CATEGORY: HP
label | 33cbee85-1ee1-555f-89d1-0c0b7bf59ed3 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | f9971d4c-b3e7-5d97-9801-0883591c37bb |  | note | VERIFYING DOCUMENTS: This ITP
date | a76c35ab-61a3-5393-a4ec-e1fb448bec22 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Compaction Testing
label | a7563933-9f7c-5de5-aa4d-117f3ea7bfa3 |  | note | REFERENCE: Table 204.131
label | 87ded265-10e3-5b1e-b30c-7f8a0222ec44 |  | note | ACCEPTANCE CRITERIA: All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
label | d8219a23-6d62-5ad7-9885-931ce5f1b2ff |  | note | ○ Ripped and re-compacted material below Cut Floor Level
label | c9d20ddc-12c8-5418-b20b-ebb2566b122c |  | note | ○ Scale A: Characteristic Density Ratio 99%.
label | 43e332ec-aa2e-50ee-94fd-fce70971b523 |  | note | ○ Scale B: Characteristic Density Ratio 98%.
label | 6d2ec4fe-9495-5fe7-b701-4ceb2b07bcdc |  | note | ○ Scale C: Mean Value of Density Ratio: 100%
label | 8a527c56-27d4-5bae-8991-29cb988e94e7 |  | note | Attach: Compaction Test Result:
label | d9227e81-6b5a-55b7-9dce-d6d4cdb6c434 |  | note | METHOD: Document Review
label | ef9e40c4-a03c-559d-9f68-b51224da58d3 |  | note | FREQUENCY: Each lot
label | 05e255b5-c832-5dd9-9f92-1f9db2a2b9d1 |  | note | CATEGORY: IP
label | 9515a711-81ed-51aa-965e-cf7b42d3b2ef |  | note | RESPONSIBILITY: PE/SE
label | b84415de-0e85-5672-9b8a-cc3f214f463d |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Test Report
date | a59bf131-f58b-5594-9f99-c266cae7be01 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Post Compaction Material Property Testing
label | 83c24d6d-6edf-5454-b90c-5f00b8970753 |  | note | REFERENCE: Section 204.04 (c), Section 204.14 (a) and Table 204.141 For Scale A, Section 204.14 (b) for Scale B, IFC Drawings MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage,Barriers,Pavements & S&L)
label | 4513759f-40d4-5e16-aca3-8848d0aa3b16 |  | note | ACCEPTANCE CRITERIA: Material Properties (Not Applicable for Scale C):
label | aeee463a-3202-5656-864f-854d8499493e |  | note | Scale A:
label | b4e0bcb8-f56c-59f9-9478-659a5917e9ac |  | note | ○ CBR and Swell as per IFC for design packge:
label | a3b3620c-4e4d-5790-9e28-88f099a2129e |  | note | – MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage,Barriers,Pavements & S&L)
label | f4a1b736-1d4f-5a44-9062-268913f29c7a |  | note | – as per table VR 204.141
label | 64a75462-a4ba-516e-9542-40995a6f2add |  | note | Scale B:
label | ee35fdc8-1e6f-50d7-9299-57f888379ebe |  | note | ○ CBR and Swell as per IFC for design packge:
label | 3d381e3f-1707-5333-af5e-2d4b067b7216 |  | note | – MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage,Barriers,Pavements & S&L)
label | 8a99a9fd-4297-590e-911e-eca277aee5d2 |  | note | First Lot for Max Particle Dimension:
label | d4a9cb62-b3d5-5d27-9905-1b7bfdcb83c2 |  | note | After compaction Type B material shall have a maximum particle dimension of not more than:
label | 4699934c-8c0b-52c4-9754-fe33e7cdf35c |  | note | ○ 150 mm within 400 mm of the top of Type B material and 400 mm at depths greater than 400 mm below the top of Type B material.
label | 10e55403-a23e-5b3f-a682-90d2650b5e65 |  | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | c6cd8e80-76f0-5a20-9c4a-bf3cc7722451 |  | note | Attach: Post compaction test results:
label | a072a3c3-154d-5eee-873f-3e2da5c24086 |  | note | METHOD: Review Document
label | 57189ab2-8ce6-54bc-94c3-74d0d8e81100 |  | note | FREQUENCY: Refer to Section 204
label | 6ee5ce3f-ea17-58e8-9a35-2d61ad511855 |  | note | CATEGORY: IP
label | 84dc2d14-f7a7-56f7-9fb2-9735a3b727d8 |  | note | RESPONSIBILITY: PE/SE
label | 511f3356-2368-56c3-8a87-8c4a77cb41ac |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Material Property Test Report
date | 941d41e2-6a88-5824-ac7d-82169fef9861 |  | date | Date Completed:
checkpoint-group |  |  | section | Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Survey Conformance
label | 5a406530-61a9-5247-9109-90eec95d2b05 |  | note | REFERENCE: VicRoads 204.03f,g and h
label | fca6c499-fe25-59ab-bd4f-05f260d22fae |  | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 02f12284-dfb6-58a1-ba8e-e58a7d8271d8 |  | note | Level tolerances (Scale A):
label | 165d2c6a-fcf9-58f0-ab8e-d5d2fed45bce |  | note | ○ Range x = +5, -15mm
label | bf1e2a7e-ea85-5c05-912a-5fc5d6edcf0c |  | note | ○ Max S = 12 mm
label | 5dd1a84a-57f1-513b-ba72-12444be54cc9 |  | note | ○ 80 measurements per lot
label | fb0b64f9-1d4c-5ae0-bfbe-977129c3a54c |  | note | Level tolerances (Scale B):
label | 92aeb724-e952-52c4-ba55-796f7c5eca1c |  | note | ○ Range x = +5, -25mm
label | 279c416c-0739-5ab0-8238-f4409b69b0c1 |  | note | ○ Max S = 15 mm
label | a864de12-9ec7-5317-92ab-800b6225559d |  | note | ○ 40 measurements per lot
label | b9ed6cc3-4ef2-5d1e-9a93-5a2f2462c685 |  | note | Level tolerances (Scale C):
label | 0605a1a8-0bf6-5f5f-97bf-9de7e486f2b6 |  | note | ○ Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | 0a702658-aa91-56af-b22f-73a5eed4a1f0 |  | note | METHOD: Review Document
label | 6f405732-181f-5912-af9e-f768f3c2a297 |  | note | FREQUENCY: Each lot
label | c71441ce-19c6-59ae-85eb-cabda9870374 |  | note | CATEGORY: SCP
label | da7a3dbe-255c-55fc-af6b-1dc31f2d80ba |  | note | RESPONSIBILITY: SE/Surveyor
label | a974f132-7fea-5068-9989-7a95245cfedc |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Survey Report
date | 549435f2-495e-55cc-9461-2ab4e97a76e6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | e02fcc19-7986-50aa-9623-f47b937e70a4 |  | note | REFERENCE: MRPA Quality Management Plan
label | a11bc5b8-c03f-5afc-9e10-e2f8ba9c9412 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 0683969d-e99a-53db-b774-cb7be0265a0c |  | note | METHOD: Document Review
label | 1cfcfa69-c388-5ce5-b94d-9c8ada9bac6c |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | e7f556e5-4d70-5cd2-af6a-b9544a532576 |  | note | CATEGORY: HP*
label | c8436153-1bab-5a54-8bb7-2c1ac17620dc |  | note | RESPONSIBILITY: SE/PE/SPE
label | 75b20c93-82d1-5bff-878f-3a9ac8f29084 |  | note | VERIFYING DOCUMENTS: This ITP
date | 78df3ccf-4bbe-5eb8-9210-9bc2293d7a04 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | b5f226f4-b1aa-55e0-a96b-67a6aa964c59 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 79dec377-2a1c-5241-aa25-a58106f5368b |  | textbox | Name:
text | 4d13ad8d-410e-58aa-a92b-18ab98f0cce8 |  | textbox | Position:
date | 3f4cceea-b968-5b0a-963f-d2498404fa23 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-092-CIV-PSDS-Private Property Fencing | itp |  |  |  | Yes | ITP-092-CIV-PSDS-Private Property Fencing Rev 1 | 5aeb5a02-a825-4ad5-a219-9267f083e13a
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | bcfee22c-2443-507c-ac38-1e726e76d709 |  | note | Document Title: ITP-092-CIV-PSDS-Fencing
label | 131ccf07-a8b4-5e87-86e6-4491ed2be6aa |  | note | ITP Description: PSDS-Fencing
label | 6f68c1ff-c5de-598b-ae70-b3ac2f7af2ee |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 59f1b3c4-20cb-5e5e-bb9d-a870f7861be2 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 2fe77d48-3738-52b8-831e-8867df86a18c |  | note | Revision Number: 1
label | ee869a03-2b87-57d7-9ab0-ac2bfee5e74f |  | note | Revision Date: 26/02/2024
label | 3bcf41dc-1ea4-5910-95a8-93a5d943323b |  | note | ITP created by: Nathan Cooper
label | a0c04f1f-b3c0-5562-bb1f-276a53f441ae |  | note | ITP approved for use by: Victor Mira
label | fb58cc97-c089-5006-a0fa-01febde89eeb |  | note | 1.1 Non Dependent
label | dfcfc7c3-a0b5-5aba-875a-187672859e49 |  | note | Reference: IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025, VicRoads Section 610, VicRoads Section 630
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete
label | 78501596-b09f-5cb2-8f30-73aa489e251e |  | note | REFERENCE: IFC Drawings Section 610.07 Table 610.071
label | a54ac429-ea63-533c-8cd3-718da254fd38 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads. 32MPa concrete to be used as per IFC drawings.
label | f0d5d953-31b6-5435-bcf9-5115cdab8fa9 |  | note | METHOD: Document Review
label | 326871f6-b05e-5b8b-9c36-9b5139615bb6 |  | note | FREQUENCY: Each Mix
label | c1f2bac4-48b9-5087-8edd-414336092cdb |  | note | CATEGORY: HP
label | 8f2e293a-bda0-5d42-80b2-abc58ce2a03e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 283505d9-966b-5cae-8265-6a270e492bc1 |  | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | 29248fa6-f6ba-568a-9298-0ecd27cf3362 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Steel Columns, Cladding, Handrails, etc
label | 300ad61d-d91d-50a4-ad4a-ab9cb7098172 |  | note | REFERENCE: IFC Drawings AS41000, AS1163
label | ba47aa9b-4626-5e5f-be14-5ad1113dd3fc |  | note | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | 7f7bf3d0-ffbc-548b-b1f1-09e064c11541 |  | note | ○ Steel section sizes must be checked on site.
label | b88589a1-e221-5fde-971c-fe4d3b475f6d |  | note | ○ Steel posts to be CHS with a grade of C250
label | 4c250280-fe37-5115-ad21-fd22ae91d655 |  | note | METHOD: Document review, Visual and Measure
label | 5eddbbec-caa4-5627-8e2a-9380977ddcb4 |  | note | FREQUENCY: All elements
label | 68c55aa9-c2e7-5d32-93be-20fb63f0f70f |  | note | CATEGORY: IP
label | 597c9685-0d64-5c8a-9920-dca23d1c4e81 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9c09d7c5-56fa-5630-b0e6-05beb2856384 |  | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | 70f06ec2-1d12-582a-96af-75d66b95ce55 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 8f1d304b-5fa2-5dd6-9232-1f5ab45720c5 |  | note | REFERENCE: IFC Drawings
label | f3397189-fb11-5a8f-adad-d893da95fae5 |  | note | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | bdad203e-ac5d-57e9-bb96-3bc3ac86c988 |  | note | ○ Offset checked against the running edge prior to installation of posts.
label | 566b9c3b-ff51-5ade-a919-0622daeeab06 |  | note | METHOD: Measure, Visual
label | 54692f09-8a9f-5486-8467-bd6604ab7b77 |  | note | FREQUENCY: Each element
label | fe7e9824-e5e2-532f-99f9-d227b7775f15 |  | note | CATEGORY: IP
label | 299283fc-4aa9-56f0-8f2e-ae969af7c0c7 |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | b5ef011d-2248-59e4-92f2-b4b60d054fbd |  | note | VERIFYING DOCUMENTS: This ITP
date | d7440c57-bca3-523f-ac69-4bf10ce0c2ba |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Excavation works
label | 7cb9a474-e1d5-5eb3-992b-0f8022eee35f |  | note | REFERENCE: IFC Drawings
label | ab014a4d-900e-51e0-8338-50c0d3354f53 |  | note | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine footing of existing structures.
label | 85c89dad-f818-5848-a2aa-ceff3586a04a |  | note | ○ Follow asset owners guidelines for work around their service.
label | ea09ad65-040f-501a-9925-d6f69c9445fe |  | note | METHOD: Visual
label | d57caab8-8833-5234-bb17-1a861ad9190c |  | note | CATEGORY: IP
label | 722fd217-277d-59f3-b810-a1ef1d842a1c |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 987f67f5-ef76-5207-adfb-0aa2b63090c4 |  | note | VERIFYING DOCUMENTS: This ITP
date | af50346b-c0fe-5b5f-b51d-52395042abb4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Ground Conditions
label | 44788d42-6444-518b-8d46-0a9dc78ba351 |  | note | REFERENCE: IFC Drawings
label | ebd96176-393f-5600-820e-b9e49bc22e61 |  | note | ACCEPTANCE CRITERIA: All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | 529a37e6-e4d2-5e12-a653-0c1ff248a058 |  | note | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | ee75b060-1eec-5076-a14a-6e5405712388 |  | note | METHOD: Visual
label | 0e7fb7af-c709-5105-8419-5dcdb1b91ccc |  | note | FREQUENCY: Each post
label | 211d166f-140d-5391-96dd-bbaa5f6cf7be |  | note | CATEGORY: IP
label | 598246b9-386a-50cb-a1ff-31bfe511d381 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3edc6626-5cab-5035-8c50-a27907c0775f |  | note | VERIFYING DOCUMENTS: This ITP
date | a39b5057-6969-5f3f-a345-f96c64d00b8f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Fence Post Foundation
label | 7e707588-d013-5b7b-b54d-aba299bc1cb9 |  | note | REFERENCE: IFC Drawings
label | 1a15f5f5-92a9-5b82-befb-bfcb1871568a |  | note | ACCEPTANCE CRITERIA: 32MPa concrete.
label | afaeca32-a2ee-5140-a806-4f3f88809bc3 |  | note | ○ Footings as per IFC drawings or standard design to match existing.
label | fe6ef4ba-9959-55c7-baa2-2e3012a3a209 |  | note | ○ Refer to IFC drawing for reinforcement details.
label | 3a3e6ecb-7df0-5ec6-9a74-bcfcd6db33d8 |  | note | METHOD: Measure
label | 25768b57-b0bc-56b4-a413-811158179a98 |  | note | FREQUENCY: Each footing
label | ef87bca7-582a-5072-8d45-1da476ee5f64 |  | note | CATEGORY: IP
label | af94314f-c8ff-5519-82c2-087e84e81f04 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9035e9ef-3f58-565d-bba0-6d12d6394471 |  | note | VERIFYING DOCUMENTS: Post and concrete dockets
date | c1098ea4-e59c-5bbe-85d5-761c86626cf2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Fence Post Installation
label | df26cfd6-9944-51ac-8ca9-7d5ae464e967 |  | note | REFERENCE:
label | 50dfc27b-9efa-56d3-8553-808a5eb761b4 |  | note | ACCEPTANCE CRITERIA: IFC Drawings
label | c48543ec-1669-56fd-9355-099c5a07bda2 |  | note | METHOD: Maximum post spacing to be 3.25m ± 250mm.
label | fe7547c4-5073-582a-a2d3-6a8284031e88 |  | note | FREQUENCY: Measure
label | 39c6ba19-ad71-5401-92f6-92e64e759cd9 |  | note | CATEGORY: Each post
label | 37c6a6cd-3c5f-5eeb-b94c-602d61d2c85e |  | note | RESPONSIBILITY: IP
label | 938a054a-5d27-533e-b00e-747972ab49a3 |  | note | VERIFYING DOCUMENTS: SE/Site Supervisor
date | ffd1581d-2b11-5221-b986-88b8dc96a667 |  | date | Date Completed:This ITP
checkpoint-status |  |  | checkpoint | 4.6 Chain Wire Mesh Installation
label | 47cb2698-0308-58a8-9eb8-345c1d0ba4af |  | note | REFERENCE: IFC Drawings
label | b5689626-eea9-5e8d-882b-93abfc34d3bb |  | note | ACCEPTANCE CRITERIA: Chain-wire mesh to match existing and or IFC drawings
label | 50b2a7f7-08d3-5e21-ae35-aadc5a7329c6 |  | note | METHOD: Visual
label | edbd0886-c65c-564c-9b41-b6293177f7c8 |  | note | FREQUENCY: Each element
label | 833cd6df-a61d-500f-9604-502e40abcba7 |  | note | CATEGORY: IP
label | e9accff2-7e9c-5542-89b6-7aba7aeaeb20 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | bda1fd75-feeb-54cd-8a52-5d1ae05c5e64 |  | note | VERIFYING DOCUMENTS: This ITP, Delivery dockets
date | 376f57b7-f8c1-5a09-8733-c5d4f2c661cc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Gate Post Foundation
label | 52d80363-180f-5efc-bfdb-506f839b2b67 |  | note | REFERENCE: IFC Drawings
label | f583bc0a-3ab3-54b8-9a2c-8b0ea6d54193 |  | note | ACCEPTANCE CRITERIA: As per standard drawings and or IFC drawings
label | 441fac10-7cbb-5383-a24e-25447e13aaef |  | note | METHOD: Visual/Measure
label | eefa7e49-909c-57bf-9ef6-c9feba4f9a50 |  | note | FREQUENCY: Each footing
label | 81ca5066-b0fb-57be-90dd-c14ccf347373 |  | note | CATEGORY: IP
label | b5d1f8f6-40cf-5e25-b4d1-2d71e996643f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4b24222b-d41b-5f85-a2dc-a24a9aebd9bb |  | note | VERIFYING DOCUMENTS: Post and Concrete Dockets
date | bd78b44f-65c2-5db2-be1d-0937fd2df802 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Gate Installation - Post
label | bf920a40-ac6e-58a6-922a-18793b604a92 |  | note | REFERENCE: IFC Drawings
label | aef59f0e-ed59-5260-be37-7d863d879bb5 |  | note | ACCEPTANCE CRITERIA: As per standard drawings and or IFC drawings
label | 6ae88ab3-b79a-586f-865a-c67239938516 |  | note | METHOD: Measure
label | a35abd11-5e5a-504a-b7d3-1b3a16e63f2d |  | note | FREQUENCY: Each Post
label | 3881cae8-bd19-56b7-918b-e7b14ea0beb9 |  | note | CATEGORY: IP
label | c5a14780-2cc7-538e-a058-0577c6e3ae1f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 546cbceb-1aea-5471-ab79-fa652cef9db7 |  | note | VERIFYING DOCUMENTS: Delivery Dockets
date | 78cab5a4-7d8e-5541-9267-85109d54f7fb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.11 Gate Installation - Gate
label | f3a3d63b-27aa-5c2f-b4a9-21481080faae |  | note | REFERENCE: IFC Drawings
label | c95c5049-1b7e-5508-b458-6a7b78a658d5 |  | note | ACCEPTANCE CRITERIA: As per standard drawings and or IFC drawings
label | 9a090227-5e81-5f8b-b4d9-5330b4b4daa8 |  | note | METHOD: Measure
label | cd07af45-f2b9-59f2-b111-c8203639f13b |  | note | FREQUENCY: Each Gate
label | 520b17a6-f304-5c88-9e4b-1c03dabaf26a |  | note | CATEGORY: IP
label | bab1440f-e6ea-548b-b653-bc349f17ddd9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 07574356-4227-5172-91c5-ea5a4f81d84e |  | note | VERIFYING DOCUMENTS: Delivery Dockets
date | af27c8fa-2535-581a-a18a-6c6193a9b26d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 5a5ec471-3e59-542c-922e-53f89b06291b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8196ccf4-894f-57c4-a35c-89375c896b21 |  | textbox | Name:
text | fd9a66d1-2069-5dc0-8d4e-47ddcc3021c7 |  | textbox | Position:
date | e0be5ae8-0cbf-50ff-979a-9d4fa8a3d4d0 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-137-STR-PSDS-Structural concrete | itp |  |  |  | Yes | ITP-137-STR-PSDS-Structural concrete Rev 0 | 5c887c79-71db-44d0-9f72-34979af99431
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 48a37867-445e-5f61-8615-7bb3be5ffd64 |  | note | Document Title: ITP-137-STR-PSDS-Structural Concrete
label | 3e1a2a50-7465-590d-b712-df4c3693f804 |  | note | ITP Description: Structural Concrete
label | 4ad6017e-b824-5ca7-8b57-dc45dd858856 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | da5e4b15-08d0-5f20-b689-eb1b6da65f0f |  | note | Discipline (e.g. CIV/STR/RAIL): 137-STR-PSDS
label | 9b7935f0-eac1-5df5-8ea8-3e6bce3f58e9 |  | note | Revision Number: 0
label | 04cef9f9-6c4c-5538-9b75-8bbe410fd3ab |  | note | Revision Date: 22/02/2024
label | bceb11ff-03a1-5604-b6b9-922dea858964 |  | note | ITP created by: Mathew Velcek
label | 6128d632-32bb-51c1-b160-6469a23bc4bd |  | note | ITP approved for use by: Victor Mira
label | c6221acb-23b5-5922-9770-34adfff5d9b3 |  | note | 1.1 Non Dependent
label | 367c6d38-1382-5df2-a7f9-10aabb71ba4c |  | note | Reference: VicRoads Section 602 October 2007
label | ec8e537c-5e0d-58e8-b11a-a54bd94dc9e5 |  | note | 1.2 Non Dependent
label | a6b17e13-c81d-533c-8a14-9000c04db92a |  | note | Reference: VicRoads Section 610 February 2020
label | 0171e6f5-ca1c-5cce-b88e-f79bdcadef5f |  | note | 1.3 Non Dependent
label | d9a771ed-617b-50a9-b52f-d679b31399c2 |  | note | Reference: VicRoads Section 611 November 2018
label | c8c2b75a-a301-5ed3-8999-b5f31a22b77b |  | note | 1.4 Non Dependent
label | e6ab4ef5-9ee6-546e-83d0-9f0a8d1d8afa |  | note | Reference: VicRoads Section 614 June 2017
label | 9c0570a3-4094-55e8-b297-727e1e6118e4 |  | note | 1.5 Non Dependent
label | 309a84ce-c6f5-5528-a186-71ec168701e9 |  | note | Reference: AS3810.1 2018
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 78b20ae1-63a5-540a-95ca-d93780af0afb |  | note | REFERENCE: 610.07 Table 610.071 IFC Drawings
label | b3e3dc01-92b5-59c3-b308-a9fe88410ea2 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | 34569e10-65c8-55ba-a75d-a9a2f6d3a93c |  | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 2aa071fa-8316-5f22-80ba-0bc17f9fabe0 |  | textbox | Enter: Teambinder Material Approval number
label | c2c3b474-831d-55a4-9be8-4f55e8f7010a |  | note | METHOD: Document Review
label | 58814631-4da8-5508-9b28-5f771b623ebc |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 293b4e9f-2954-5e0d-9e9b-093490464704 |  | note | CATEGORY: HP
label | dee4be3f-1883-5471-928b-8f304d885cd6 |  | note | RESPONSIBILITY: Nominated Authority
label | c4815363-6c36-5768-ace5-1117bb65e3a5 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | a6d12268-af4f-50e1-a5d0-6796364e7de6 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 006676c1-6d90-5882-ad29-f8ac97161663 |  | note | REFERENCE: 611.05 (a)
label | 2bdfb7e3-c53f-53dc-b50c-f1f95537b4af |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | 0f657101-e8fe-506d-81fa-c7a10952e5ac |  | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | ff9c9a72-fc0c-5fbe-b923-14189cbc5eca |  | textbox | Enter: Teambinder Material Approval number
label | 4ed7bb95-821d-50c5-989f-f2f50ebcf908 |  | note | METHOD: Document Review
label | 894ca53d-c229-53c6-aa32-ac8c3001a18c |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | cce69068-04d3-5f71-b6ac-bf65d8c14b66 |  | note | CATEGORY: HP
label | e9add410-3ad3-5893-9ee8-7c89c239d5fd |  | note | RESPONSIBILITY: Nominated Authority
label | 9b91c09b-f2da-5304-8416-9d49cb97fc7b |  | note | VERIFYING DOCUMENTS: This ITP
date | 3a1947dc-f775-57d1-853d-1ce152d77789 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 50bf5c07-262d-5245-8c53-d9d5c0cbee90 |  | note | REFERENCE: 610.26 (a)
label | 1ffb80ae-ad23-58c8-83c4-faff39bb0c19 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | b62dcc87-c546-523e-bffa-1d7d1646cbb8 |  | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 47c11224-1c6c-5a76-8f01-187cf0c2d788 |  | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 7dd9c8d4-48fa-5428-8a7a-9deb5755fa93 |  | textbox | Enter: Teambinder Material Approval number
label | 50ae08a6-2fff-5cef-a7b7-47455d574c19 |  | note | METHOD: Document Review
label | 062c23e0-1ecb-5490-ac58-eeb561a56bb1 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 6ee2660c-387a-525c-b8f5-f6414b34a1ad |  | note | CATEGORY: HP
label | f4472654-7567-5fc4-9d86-8a436717695c |  | note | RESPONSIBILITY: Nominated Authority
label | 80f80b76-c015-54dd-bb22-4a7a599ae0fb |  | note | VERIFYING DOCUMENTS: This ITP
date | de4e55d4-1777-5b12-8050-9fc5285ea2c3 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Evaporative Retardant
label | 95c17965-9db8-538e-8f49-68d42fb6d14d |  | note | REFERENCE: 610.17 (f)
label | b83ac77e-27b6-5e45-8796-0f3c75d79d63 |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 6d0579e1-4203-5ef1-a3b4-65dfb12fd080 |  | textbox | Enter: Teambinder Material Approval number
label | 39cd6bad-d690-5fe9-8870-83d0a2567776 |  | note | METHOD: Document Review
label | 92bbe2a4-eff2-5c07-b389-3f476f867653 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | be914ab1-1c99-5ba7-91f4-bd1035b9a27c |  | note | CATEGORY: HP
label | dc46b5b7-70db-5a04-b01a-05b8b3b9a7dd |  | note | RESPONSIBILITY: Nominated Authority
label | b99fb48c-a91c-5151-a70a-c5d02647c6a5 |  | note | VERIFYING DOCUMENTS: This ITP
date | 46d26814-c3d3-5232-ad1b-ff16cd8fa341 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | a35c12df-3a67-5b21-abb9-7d7f7ad489af |  | note | REFERENCE: 610.23 (d)
label | 7e118efe-c360-5e33-a996-cd749f6a06e9 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | 91d05db3-71a4-5052-9e92-2f2ef5d6b547 |  | textbox | Enter: Teambinder Material Approval number
label | 2d6cea99-4be0-5a14-9423-ec6922b6d569 |  | note | METHOD: Document Review
label | e9d41fd5-1e2e-5e82-9571-676e3ca646fc |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | fb269b69-89fa-58f8-82df-56c1c44a2ffe |  | note | CATEGORY: HP
label | c78e8f86-a35f-5883-a62b-f45e9fb9a465 |  | note | RESPONSIBILITY: Nominated Authority
label | 7db5aee7-d4a8-54a3-b361-b584d0663ba8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 100e3b7c-a054-5939-b433-665496b415f0 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
label | 6e91258a-4dfd-5a1d-bb44-67916855fc72 |  | note | REFERENCE: 610.18 (a) (i)
label | 380a378e-1be3-5804-a9f8-3b62ffc77d7d |  | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
text | 9332ebfa-7b4d-51b4-99ef-5664d037f721 |  | textbox | Enter: Teambinder Approval number
label | 72214396-ae29-521b-a280-5b8d7e4fba8c |  | note | METHOD: Document Review
label | c95a071a-34b0-5891-9888-f92afd9ed971 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 65cabe31-2124-590b-b099-2364615199da |  | note | CATEGORY: HP
label | 208d22ef-d923-529a-8771-74991bc57b73 |  | note | RESPONSIBILITY: Nominated Authority
label | f2ed0892-adb6-54ea-994f-a54a4325576f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 78d9d504-7d1a-5802-80da-c324fd837d1f |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Concrete Sampling and Testing Procedure
label | 3ca0ab6b-293b-5875-a6c2-ac29350403cd |  | note | REFERENCE: 610.18 (a) (v)
label | 4f8ae491-3a7f-5ed6-ae02-b852e563d2cd |  | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
text | 4b83c0f8-9dc8-51e1-8e41-73193d6abfe7 |  | textbox | Enter: Teambinder Approval number
label | 7bb86482-f46d-51b7-81ed-1801bab70d39 |  | note | METHOD: Document Review
label | edc29478-b629-5233-aab8-d670000a45be |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 01df8587-9d39-5aff-9746-ec3d63c8c274 |  | note | CATEGORY: HP
label | 58b4c558-e6be-5589-b19c-2b36b7ee19ee |  | note | RESPONSIBILITY: Nominated Authority
label | 021441d4-10ef-513a-ad42-f0282c169643 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 78b3cd94-6035-5fb8-8f30-29b53a85a0e8 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
label | b0b017c2-7bc6-5cf7-aae5-850fe5d6a087 |  | note | REFERENCE: 610.18 (a) (iv)
label | 2247496b-728a-5e63-b6e2-7ece3e239eda |  | note | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | c929b29f-9529-57e6-88e2-d80cf0dbd8dd |  | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
text | 2f4c9ad0-f99a-56f6-b85d-0f0ae2e44a27 |  | textbox | Enter: Teambinder Approval number
label | e2786f67-4339-51ac-a0dc-f83e69cf132d |  | note | METHOD: Document Review
label | d74aa5f4-e4b1-54c8-99b0-6809d4c8d7ef |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 2f392c6a-ca44-5be2-9fc7-13a0e3a4ffd0 |  | note | CATEGORY: HP
label | 09497351-9563-5325-b4b1-d5cc18f0d537 |  | note | RESPONSIBILITY: Nominated Authority
label | e1542e51-f1c6-5ca0-b485-7b4ede298d15 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 24a378c9-acfd-50a4-9867-361690b24a03 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
label | 3007903f-94ce-5c94-b5d1-45447afba44a |  | note | REFERENCE: 610.17 (a)
label | 2fa3e953-83ed-5b5d-a921-b2d09aecf7b5 |  | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
text | dd2de02b-2ad6-5b8a-8695-6ee659414ef7 |  | textbox | Enter: Teambinder Approval number
label | 6c236726-e03a-5412-ae42-ac64df9a69c1 |  | note | METHOD: Document Review
label | cb81c107-675f-5cd3-89ff-1fc98ba3d7e6 |  | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
label | fd2c61a3-a394-5092-ba4b-79eae22315b6 |  | note | CATEGORY: HP
label | f1b5781a-4d28-51dd-85db-fb900dff069e |  | note | RESPONSIBILITY: Nominated Authority
label | d82bf127-6ede-5acf-acf9-d108c35329b4 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5f180382-76ed-592f-9351-225725ba685c |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
label | e2e5e209-7c63-5698-909e-ec432f96ec7c |  | note | REFERENCE: 610.23 (a)
label | 5e19b961-cf55-5c0a-8be7-8a08c942eb3f |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
text | 8d49a449-64c3-5d3e-8876-da9d6e178f23 |  | textbox | Enter: Teambinder Approval number
label | c6ece6fe-af68-5175-8351-f9b2b2d5fbc3 |  | note | METHOD: Document Review
label | e5efc0d4-6785-5d9e-959d-d86bde933873 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | ee60cd66-6889-540f-aac3-f9f2ad36e523 |  | note | CATEGORY: HP
label | 32b31899-a6c7-50b2-93b4-558a775fcb55 |  | note | RESPONSIBILITY: Nominated Authority
label | 8824c402-f80f-5f6e-b9bc-ff001cc7a5ac |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 663fe1f0-67d2-52a3-bc02-61f7ddad02f2 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Concrete Drilling Procedure
label | 7040c9e3-da83-59a7-8803-69428fd2dd9a |  | note | REFERENCE: 610.46
label | 0f2e4719-f0b1-502a-85f1-5ebd121f4f78 |  | note | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | faf72bac-9625-589a-bebb-aa273975121a |  | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
text | b9fea75a-e0ff-5dad-aac4-f5a7b3825dd2 |  | textbox | Enter: Teambinder Approval number
label | 8b6e4626-5086-55f3-ab45-8ec7acb6cb6e |  | note | METHOD: Document Review
label | e29fccc4-994c-58e3-bee2-7719acd3e8a0 |  | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
label | 9549c89f-49bc-5042-99a2-cdf74c008aba |  | note | CATEGORY: HP
label | 321ab5cd-4b90-56eb-970f-33216ab86ad8 |  | note | RESPONSIBILITY: Nominated Authority
label | eb339755-3c96-5f90-a245-938d14b3ead6 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 5f8f1d63-129c-54ee-b1cc-45a0c0b210d9 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Temprature difference measuring-Calibration
label | 11329de4-6dbb-5515-9c53-c2bd85618b81 |  | note | REFERENCE: MRPA Quality Management Plan
label | 3a678f47-e8de-57af-9db5-31d0fda83d5c |  | note | ACCEPTANCE CRITERIA: Calibration records are valid and up to date.
label | 0cd25656-a09a-593e-bf85-346ce734702c |  | note | Attach: Calibration certificate
label | 4206ef2a-67f5-5b5f-b6a5-9875ed465b37 |  | note | METHOD: Document review
label | 4557a4a4-2877-52b6-9215-ff999f8759cd |  | note | FREQUENCY: Where applicable
label | 53d3c6a6-3f06-534c-a410-becee309de24 |  | note | CATEGORY: HP*
label | 62df030e-eec9-56f2-bea7-aecd8dd1f573 |  | note | RESPONSIBILITY: PE
label | 8af81bf4-6517-5261-b0ee-f1fc1922a403 |  | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
date | 7841a1ed-d81e-5762-a59a-8ad23e911e24 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | f762b9fb-09ed-5015-a996-83f8b41818b6 |  | note | REFERENCE: MRPA Quality Management Plan
label | 2f0b823f-706d-54a6-a469-cc71c5fd14ca |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 09aa2e01-3f49-5476-8be5-5c1ee18a9280 |  | note | METHOD: Document Review
label | 00a6fdf2-b527-5ff6-9cbe-2948c86cff82 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 8ffd8aff-526e-5d10-aa7b-5e56e6263de1 |  | note | CATEGORY: HP*
label | 916d2d31-b0d9-56c9-b552-c70a3df69375 |  | note | RESPONSIBILITY: All
label | 9a2ddfb5-e823-5b1d-bd71-71d08bd84ab9 |  | note | VERIFYING DOCUMENTS: This ITP
date | eaf7f487-912a-5516-a767-fc4414b9b013 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | a882ab04-5cf2-56fc-8ec3-84e6e2b21867 |  | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472
label | 5b238228-4397-5184-a664-8d77f809e65c |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | edb8aec7-7fff-5d81-95b3-2f393f99b022 |  | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | 41368af7-cb50-5bde-a382-801cacbd28c0 |  | note | METHOD: Measure, Visual
label | f85aee46-0dd2-57f5-984e-aa0b3e384323 |  | note | FREQUENCY: Each element
label | f8c2e71a-cb5e-58fa-8b71-8d7d6c874409 |  | note | CATEGORY: IP
label | bf4c05c3-3c70-53cc-bc22-f8764a408590 |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | 8bb963cb-772c-5208-98d7-3566970f0910 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1610f893-453f-5c4a-8ee3-ff377185f0ff |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Excavation support
label | ab85e0f8-7f12-5610-ba4b-9869af0b365d |  | note | REFERENCE: 602.02
label | 4a893a43-5c89-5405-ba32-f72beafcfee0 |  | note | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
text | 74144183-36e3-554a-b1eb-be594a5aef78 |  | textbox | Enter: Teambinder Approval number
label | 2bcaa7c3-6c8b-5421-8de4-05bf5b2ea7f3 |  | note | METHOD: Document Review
label | d9613f4a-fe1c-5cbb-b34c-ef2a920957d3 |  | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
label | 00a2925a-b265-579c-b3c4-aa2b56d99a82 |  | note | CATEGORY: WP
label | 93d20014-ded8-5e9f-8cf4-5b04a7440bc7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 489a925a-9e5d-5b62-a808-73942f4405a2 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | b53b6321-107e-5426-bb3f-8206c149af37 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Excavation Inspection
label | 499b4fb6-8ee8-5263-aa60-f179ca95f779 |  | note | REFERENCE: 602.03
label | 379dfe3a-0f95-56e5-b7c8-a1f883c13634 |  | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | bf8cf939-956c-51aa-8a07-669cf707468a |  | note | METHOD: Visual
label | 8cd5bd33-2362-5463-ad9f-73b031e1d867 |  | note | FREQUENCY: Where applicable, prior to placing blinding concrete
label | 56b9d25f-d216-5277-8708-4a8dfb1d3665 |  | note | CATEGORY: HP
label | 86d67415-d3f6-5f36-949b-27619a1b4427 |  | note | RESPONSIBILITY: Nominated Authority
label | c80e8954-e62c-59d3-ab1d-285230afa21f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 00f95435-1712-5b1e-85c3-d7061752cc98 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Formwork Design and Construction
label | ac411c8b-f6ae-5e94-b314-fb85b2033464 |  | note | REFERENCE: IFC Drawings 614.04, 614.05, 614.06
label | 0c403a63-15dd-5a52-b2f4-089e10d0eb0c |  | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | 69a03307-46fc-5f6c-82e6-08241afb7eea |  | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | a4b285ea-7e9f-5996-abf6-1b0f0211ee4d |  | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | f1f7ab10-1112-5ec3-8bdc-a73c784ac6b3 |  | note | METHOD: Document Review, Visual, Measure
label | 32229d91-390b-5fbe-8b95-91af42a0225b |  | note | FREQUENCY: Each type of element
label | 50955bea-238c-5f69-b870-ec78d9ae82fa |  | note | CATEGORY: IP
label | 4f93f5d5-f63c-545c-962c-6bf5cf6e8ddd |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | d265eff4-f2aa-5229-b689-ad9e5b4e09e6 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8a15be88-8dfc-534b-9ad4-b0b975208522 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | bb84e584-20ff-5e97-9ceb-10e3a16210ea |  | note | REFERENCE: 614.08
label | 010ab915-f7d2-5390-8c31-2d1f72916e89 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | 95e09125-41ae-536b-ab81-6e20f444002c |  | note | ○ Walls with heights greater than 2.0 metres
label | 7d24156e-9a81-5231-9c9c-fca928158f42 |  | note | ○ Any member for which self-compacting concrete is proposed.
label | 1e18dff5-32cd-5c24-9aa0-1fab4fe62db7 |  | note | Attach: Attachment A
label | fb737f20-a908-537d-8559-4e4c9e897660 |  | note | Attach: Attachment B
label | 50245ed1-c42b-56ec-9709-d1b71024f7fd |  | note | METHOD: Document Review, Visual, Measure
label | 4d4564de-27e5-5232-8a53-27c7e75f9bd9 |  | note | FREQUENCY: Each element (where greater than 2m)
label | 19caee64-9516-5f05-8fb9-ee380241b402 |  | note | CATEGORY: HP
label | e68e5b9f-d626-5c08-817b-0c8d57c467d3 |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | f1c61ce2-254a-5c47-bc97-98683c6b3a6f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 8cb1827b-5680-5f16-a02e-d10fcaf1aea5 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | 67ba62e8-23ac-58ce-8af7-27eb29844803 |  | note | REFERENCE: 614.08
label | 58eded0b-92b0-586d-83a3-c01777808561 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | dff5f1aa-ccc2-59b6-8f1f-1825f9bd84fd |  | note | ○ Walls with heights less than 2.0 metres
label | a3b4ee9e-e1d2-55e8-9d8b-b8330e2a7322 |  | note | Attach: Attachment C
label | 4217ad5f-7aa0-5c6c-b98e-26aaa25aef41 |  | note | METHOD: Document Review, Visual, Measure
label | 7b5442fa-d8c1-5ed5-a0e8-14e660ba5707 |  | note | FREQUENCY: Each element (where 2m or less)
label | ec51b777-4a69-5ef2-a659-346370e6497c |  | note | CATEGORY: HP
label | 07fe32d9-5145-564b-8701-5e0c39914a27 |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | 36b3c291-c4dc-5a8a-8358-0354e7767995 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 736f98e9-2f88-5837-b67f-2341889c441a |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Pre-pour Survey
label | c0e95b3b-b8c5-5de3-b80e-6666097a509e |  | note | REFERENCE: 610.47 (a) Table 610.472
label | 60872c36-2d95-522a-b1de-9313d4e60b4b |  | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
label | 7f9257ca-4cdb-5eb3-83b7-a8850938a796 |  | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | cf548554-9968-537e-96f1-e11c41bb0c38 |  | note | METHOD: Measure, Visual
label | 0995faf1-48d9-505c-a721-be255ee6e893 |  | note | FREQUENCY: Each element
label | ad1a2381-2a54-582c-afaa-62c0d6fe49e9 |  | note | CATEGORY: HP*
label | aa08a970-02af-5e6b-be75-2dcc025cc2b2 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 58b83609-c045-5ddb-8614-1e1ce280223d |  | note | VERIFYING DOCUMENTS: This ITP
date | 0887f110-4694-5e29-a07a-ab10076b9298 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement Placement
label | ef5578b8-64af-5ae3-bd02-30e7d91407ff |  | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | 5d9c0d91-989b-5615-828b-1c3c85a8f315 |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 1a46d952-0323-5ef1-bedf-5ba38add2880 |  | note | ○ Projecting reinforcement is the correct length and location.
label | 02fd0ff4-2d66-5914-9ed2-06b5c3a8be8b |  | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | 32e27238-df5b-506c-b980-c72fa6bea5ad |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | 774b9341-5480-545e-a756-0d447352ed94 |  | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | d7a87f0b-0fb3-59b6-8fdf-b3ebb22328c8 |  | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | c698252b-5fb3-5d13-b19d-433b7d168906 |  | note | METHOD: Measure, Visual
label | 94729b30-b4e7-59b8-8ba4-a61db4cb872e |  | note | FREQUENCY: Each element
label | 7761c8b0-b573-5382-818f-71d7c6ff6214 |  | note | CATEGORY: IP
label | 6d36785a-addd-5e93-aeeb-b8522b1444b1 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 8d5a274a-71c6-5aa2-ad33-becf363a358a |  | note | VERIFYING DOCUMENTS: This ITP
date | 71c5d3f6-6c60-5410-bae3-74774684762f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | 2e1a7f69-5e98-50a2-9fc2-431276630233 |  | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | 267d8bdd-0fa9-5317-8adc-707c705a9d00 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | ab9d8e66-54f7-5fcd-9415-fb0a6bad076c |  | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 0102d4b4-be91-5a8d-b21c-98c3f0f098f9 |  | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | cc1a63e9-dd93-5400-a5b7-d095ea81446d |  | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 7767602e-a95f-506c-830d-d9f652e57825 |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 6fb0634d-9ef1-515a-b7b1-69c94e35c6e2 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | bbf32c55-fba8-5916-85a9-c51ba6ba968f |  | note | ii. Running dimensions of a group of the above = ±6mm
label | acc84001-317f-528f-b4a0-2c51e8e3ef43 |  | note | iii. Ducts and conduit location = ±12mm
label | 88afca78-4e57-5402-b979-36466f8924fa |  | note | iv. Diameter of ducts and conduits = ±3mm
label | f3262ae6-ebe4-5c38-8d40-df9608bb508e |  | note | METHOD: Measure, Visual
label | 7d3dcd28-ffd6-5ac1-8caf-4201cd40d27b |  | note | FREQUENCY: Where applicable, each element
label | d658aca6-2e9c-58a7-8c8d-5c88bfb3da95 |  | note | CATEGORY: IP
label | 863741d9-e7a9-5ccc-a8e3-71ed5f8a062f |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 1dcda6fa-3bc2-5773-92ee-a8403193ec92 |  | note | VERIFYING DOCUMENTS: This ITP
date | b0455395-6176-5f81-9ea7-2d29fe4043ae |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Thermal Differential Monitoring
label | ff17f1c5-53de-5acb-baed-27d10e60624b |  | note | REFERENCE: 610.22
label | 8e5032f7-76b7-5262-9ed5-51e40d9867d7 |  | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
label | 951ef0af-a58b-5ff5-90f8-b3949cb0ae8b |  | note | Only applicable if the element has:
label | f65ce090-7921-5158-a3a7-0ff8010c9b88 |  | note | i. the smallest sectional dimension exceeding 500mm
label | cc94943b-8b73-52e3-883f-b984bde69515 |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | 8e581407-5236-5d51-8299-ca1934cec9b4 |  | note | METHOD: Measure
label | 35482c5e-d86c-51df-8ffb-5e55e35a83ed |  | note | FREQUENCY: Where applicable, each element
label | c40b6554-5683-5c85-9a7b-4d396fe93cc2 |  | note | CATEGORY: IP
label | bc1d111c-a197-5e82-b4ae-8963e9dcab81 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | dfa80979-d295-5e6d-b9f7-2406f95d0b95 |  | note | VERIFYING DOCUMENTS: This ITP
date | 05631a22-54d7-58b6-bd1d-75c0e3602946 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pre-pour Inspection
label | 85cc9a72-ab42-5377-b9ce-d8fe7b8ed524 |  | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
label | 32312840-9fd8-5b7b-ba7b-35a546c1a4da |  | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 4ba57218-d7a3-5054-8034-ef04654ddc26 |  | note | ○ All foreign material has been completely removed from the forms.
label | 67a98274-f023-52b7-89cc-145270896243 |  | note | ATTACH: Pre-Pour Checklist
label | d81254ce-6f2a-5c10-b846-e015a4510973 |  | note | METHOD: Measure, Visual
label | f1ca7c07-e48b-529a-ab36-5063349dea44 |  | note | FREQUENCY: Each element
label | 4d4716e8-946e-578a-8b25-741ed05bfa9f |  | note | CATEGORY: HP
label | b926ad55-eb55-5d01-956f-5eefe78cd31e |  | note | RESPONSIBILITY: Nominated Authority
label | 5589f9f3-eb3a-54e3-a553-6c029fa4e116 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
date | c3a56ab8-623f-5eac-aa05-7bcbd33dc690 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.9 Weather Conditions & Evaporation Limits
label | 52b95cf7-0ab7-5f73-950a-aca0f3832f75 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | 73d8104d-70f7-590d-9a7b-6b5b7e84355c |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 80a68c37-95c8-504d-aa00-6d408770c0dd |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 038b2e13-63f6-50de-a695-9e0b0c06e1d9 |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 7d569abb-fd97-5370-b525-cb4ebc314a06 |  | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | c41aeff1-b544-5391-92ce-607648826086 |  | note | Record: Required information on the Concrete Pour Record.
label | fe584986-9580-5519-ac54-ad5995ef5e00 |  | note | METHOD: Measure, Visual
label | 0479f38e-5f5e-58ae-8e92-ccc7a04574bb |  | note | FREQUENCY: Each element
label | 9b5f0985-3a6d-5fbd-845c-a27fb9d41fa6 |  | note | CATEGORY: IP
label | 209d4a6c-bd9b-56b1-b061-b3c12eb9512f |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 6f1cbb61-3b20-5895-8ea7-3c61b0534691 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | f7a830e0-39c6-5e5e-b06e-3167d4d9c2cb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Sampling Frequency
label | 70d646e3-b498-5cd5-bc84-f7f2a846bd11 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
label | ea4901cc-d27b-50a5-9004-9f8acab1952f |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | bcc2fbb5-d2c1-50f4-8b20-740358ec02f7 |  | note | 0m³ to 10m³ = 1 sample
label | 0638878b-45d3-507f-b3a1-5cc4d9b8bbb1 |  | note | 10m³ to 25m³ = 2 samples
label | d4beeacd-1e5d-5533-bb91-4ff8edd02bc2 |  | note | 25m³ to 50m³ = 3 samples
label | 0d8a7479-8d77-5924-ab2d-8aff98b9e9a9 |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 83b96ac3-5668-54dc-a893-b4f005a72328 |  | note | ○ For each additional 50m³ and additional sample shall be taken.
label | 3570d254-62ac-5c37-a834-dfe932b88559 |  | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | 107c8492-a32f-59bd-9d45-bdc73a99acd1 |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 1892a383-62e0-51f6-919c-c2c8ddc3b631 |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 30f6a7f0-0e07-53ad-8d58-bb880714e36f |  | note | ○ Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | e4684260-8c30-5a99-9d6a-8ff058727a94 |  | note | Record: Required information on the Concrete Pour Record.
label | 998ad40f-be4a-5ff6-a843-3e7db0bb8706 |  | note | METHOD: Test
label | ddbfd493-854e-50fe-aedb-3c4a00cb83e0 |  | note | FREQUENCY: Each element
label | 92ef3c17-eba6-558c-9e8a-5c84de5d2396 |  | note | CATEGORY: IP
label | df307976-d854-5198-86f9-e79c1db0d1da |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | 4e0b8c23-d50a-576e-b8dc-ad83fcc69229 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | e73ed433-7c07-5704-9b81-649fdbeb4d20 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Slump
label | 810846ec-f736-57dc-b07c-adec3d037724 |  | note | REFERENCE: 610.16 (c)
label | 9063bf9a-7da4-5e7a-961e-5cddbb4724ea |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | 57c75ae2-3201-5cae-9bc8-12f66dec87c3 |  | note | <60mm = ±10mm
label | 2df01aea-418e-503c-b86a-58c8a5c9448a |  | note | ≥60mm to ≤80mm = ±15mm
label | 06d50ff0-dd35-5576-be99-34baf19100d7 |  | note | >80mm to ≤110mm = ±20mm
label | ba2e4b3c-2fff-5603-b7e9-24b4ba071159 |  | note | >110mm to ≤150mm = ±30mm
label | a3c9b718-4168-585a-8d61-dffbd320a4ee |  | note | >150mm = ±40mm
label | c2e69ad6-8e1e-5b3f-ad88-c218ac4ae0d5 |  | note | Record: Required information on the Concrete Pour Record.
label | 3ce788c2-7fd1-5afb-8f23-0b61a865e29a |  | note | METHOD: Test
label | 558f3f8c-35f0-5f32-b741-e0c2c2b32d6a |  | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
label | 484e70c3-d0f9-53c9-b059-09f169faf755 |  | note | CATEGORY: IP
label | acdce024-df68-5079-97e7-0a08a7d9440a |  | note | RESPONSIBILITY: Concrete Tester
label | deadaf34-0ca7-5491-bc77-d45d0aa3bac5 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 71eb8556-82e6-50d1-bf40-e973c729938c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Concrete Testing - Spread, Passability & Viscosity
label | 76601688-9cb5-5901-af8f-0f6760806bd9 |  | note | REFERENCE: 610.13 (b)
label | 0c709607-69f7-5169-9c79-0c64178db33f |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | dbd5fae9-a5c7-573d-abf4-cbe412c5f47a |  | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 3a3410cc-fc3f-594d-8609-39ed5ff32bca |  | note | ○ Passability = ≤10mm (aggregate height differential)
label | 4d7dc640-fd70-5f52-9516-1aaada5e5415 |  | note | Record: Required information on the Concrete Pour Record.
label | cf3223d1-d6de-5e3f-9dbc-9bc35dc1013c |  | note | METHOD: Test
label | 1296c40a-eb5c-59aa-bd39-a353e1331513 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 0d277f46-7076-53ec-abeb-aaef5c64deaa |  | note | CATEGORY: IP
label | 926a11ca-9d5c-589c-9397-6326a4f34615 |  | note | RESPONSIBILITY: Concrete Tester
label | a024f50c-abff-599d-b698-fc80eb219387 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 2ae97e4a-5b74-55fc-9f8f-278118a691f4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Concrete Testing - Compressive Strength Cylinders
label | af1e9a61-a7c2-5193-aa2e-e59bc7200351 |  | note | REFERENCE: Site Sampling & Testing Procedure
label | a1611d2e-352c-5c82-881f-555c5cca0f37 |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | df0674db-2e51-57e3-b869-0314024ecfec |  | note | Record: Required information on the Concrete Pour Record.
label | dcfead24-1b46-58b4-b467-bdf6f4ab0eed |  | note | METHOD: Test
label | b6244837-2f32-54e1-a296-6d590c8dfe04 |  | note | FREQUENCY: Each sample
label | fb1c81e6-3f94-585a-9022-18ef2f2e8be8 |  | note | CATEGORY: IP
label | 2a1dd9e8-1235-5a32-ab87-3a77214b1f17 |  | note | RESPONSIBILITY: Concrete Tester
label | 3a4058e4-6b59-581f-bddc-2f3960994a44 |  | note | VERIFYING DOCUMENTS: This ITP
date | 712ec909-1501-5fbb-97a1-75cb96db0201 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Supply & Discharge Rates
label | 8059d8ff-a1a1-5f34-ac7a-62c86fe7fe05 |  | note | REFERENCE: 610.13 (a) & (f)
label | 1f4be852-0422-52d2-93f9-72f9629d7602 |  | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | fc5c4470-bb23-511d-94fa-64f16738c79f |  | note | ○ No water is to be added once discharge commences.
label | f2a7e314-fe2e-5af6-9fbd-b402c66a902d |  | note | ○ Maximum time between batching trucks is 25 minutes.
label | 95003075-4798-5148-9b56-d86011d09729 |  | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | 7cf401e9-12b5-58e8-996e-c3fb06e2084c |  | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
label | ebac800f-bcfc-52b7-96cf-2c8ac6b8a4c5 |  | note | Record: Required information on the Concrete Pour Record.
label | eed3b20c-198c-5545-9c31-c0c9d00d99f1 |  | note | METHOD: Measure, Visual
label | 37df5e6a-3ac8-552b-9504-461e0ffd1167 |  | note | FREQUENCY: Each load
label | 1ce52d0c-4c12-5a9e-885c-082c99afac13 |  | note | CATEGORY: IP
label | 0b5851f0-baba-5549-ad77-d4e60fc95844 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 76d4daa3-0818-594a-bd3a-cc23e9a4be0f |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | e487e5be-4d9b-566f-a5bb-3d0accac182b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Placement & Compaction
label | f1c8c4c5-66cf-57da-bcaa-8824cc59135b |  | note | REFERENCE: Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
label | c5d0e827-b9f2-5c68-97a0-1c0ca084704d |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | 4752d7a2-95e4-575d-89ef-b15764162262 |  | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | b164f2a9-1495-5c45-8b18-fe9c2b5af907 |  | note | ○ Concrete is not dropped freely from a height exceeding 2m.
label | da8e1105-da60-5851-969a-daa45245457c |  | note | ○ Concrete is not moved horizontally by use of vibrators.
label | 80e5f3e6-c46b-54d3-a278-80179ac7db32 |  | note | ○ Adequate compaction is ensured
label | 779a4d91-52a7-5bdd-9c6d-1a92a4bb285f |  | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | 2fd90353-de7e-5786-9c27-2ecda12b9e2f |  | note | ○ Concrete layers are not more than 350mm
label | 4764cec1-a177-5d0b-adea-6e40636b8a84 |  | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | 93acd8ca-a7f5-57e8-b8dd-0966de3e5dfd |  | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | 63061f49-6a76-5934-83c0-da845ea5a35f |  | note | Record: Required information on the Concrete Pour Record.
label | 6378c2bc-1056-5847-936f-9722baa61031 |  | note | Attach: Concrete Pour Record
label | eaf2a9a5-481b-5145-bdb7-15ceb36a035e |  | note | Attach: Concrete Dockets
label | 7f8d66bb-b201-50b7-81d7-2a390210d2b5 |  | note | METHOD: Visual
label | 53d6010e-fb2f-51f6-b2ee-3c26ea1f7564 |  | note | FREQUENCY: Each load
label | c33eae2d-84ce-57c4-a9bf-de65e0129cc1 |  | note | CATEGORY: SP
label | 0dc31f4e-463e-5960-a484-d557c16bf34f |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 1e971a9a-1f8a-5bab-b5d2-2ca494f7a8ac |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | ec7e949b-1580-5d70-b813-e2cce67b5ba7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Surface Finishes
label | 7d1110bc-a7b0-5ba2-8319-16db30c25111 |  | note | REFERENCE: IFC Drawings 610.31, 610.20
label | 7e7e513d-cbd6-52a8-876a-621fe3a71b57 |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | 8dd2f674-4aab-5c68-80af-a467cab1cc2e |  | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 59d40032-476b-5944-8ccf-0a9204dffd8f |  | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 8fed469c-d9d3-5431-9afa-1e41c410a394 |  | note | METHOD: Visual
label | ab35bc79-4f7f-52f9-bc29-60fdc3cc9348 |  | note | FREQUENCY: Each element
label | 20303314-1c06-5731-bf3e-f292d2b8c841 |  | note | CATEGORY: IP
label | 1efdc7ab-16e4-5a24-a259-f8bbea025751 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 62eab483-dc86-54d8-9589-a9ccf82f3e9c |  | note | VERIFYING DOCUMENTS: This ITP
date | 320aca79-8db6-5ce4-bf0f-ecd7c15bdd8c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Curing-Top Surface
label | 4486d3bd-8cdb-5523-901f-140ce5e5166f |  | note | REFERENCE: IFC Drawings
label | 6aecdd21-1f2d-57ce-b349-c4e30de59250 |  | note | ACCEPTANCE CRITERIA: Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | 42674716-18ea-5af8-9633-7087a4eead07 |  | note | METHOD: Visual
label | 99d5daef-2bef-550c-b3ba-88571cef580e |  | note | FREQUENCY: Each element
label | 775df6b0-edb3-5fca-b4c4-b12d55c867a4 |  | note | CATEGORY: IP
label | e94d7885-a4aa-5f8d-859f-23ce907a5620 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 29159a4b-2c71-57fb-b247-0317cc14e124 |  | note | VERIFYING DOCUMENTS: This ITP
date | 89f279da-f449-5cf0-943e-f601e85a9986 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Curing after formwork removal
label | ce13fe23-8f87-55fe-9bbe-4bb571894fec |  | note | REFERENCE: IFC Drawings
label | e08aa63f-01c8-5bc5-93c7-b534392a342f |  | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | 3a78fafb-a3fe-5dc4-b76d-dca1380f1306 |  | note | METHOD: Visual
label | d1d08fff-3439-5260-a2c7-da17cc87e72b |  | note | FREQUENCY: Each element
label | b1a739bc-eb16-5d55-9b09-03484d78a4ac |  | note | CATEGORY: IP
label | 9f3b091e-dc40-5a53-9c58-5944f19befdb |  | note | RESPONSIBILITY: SE
label | fcb16fcf-9df9-5a28-b5a8-b96ab4aaadb3 |  | note | VERIFYING DOCUMENTS: Thip ITP
date | 36c1cdbe-7351-5ef5-9229-1f6b18e7578d |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Thermal Differential Monitoring
label | ab730aa8-f165-5459-a08c-2e12eea0c4b1 |  | note | REFERENCE: 610.22
label | f513e9ed-b6f0-5ef4-af03-1cfcae2f2a4b |  | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | b8be5f3e-c2dc-5d02-8dc7-14c634c70727 |  | note | Only applicable if the element has:
label | 291f9293-ff55-5b5e-9d92-1311aca65753 |  | note | i. the smallest sectional dimension exceeding 500mm
label | c6f57acd-78c6-5e88-8fe2-b50c158e61d3 |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | c66036d5-64cb-5e95-8c1c-2d1d177c4211 |  | note | Attach: Thermal Monitoring Report
label | d56a96f4-567f-5c20-8415-1045922899d7 |  | note | METHOD: Document Review
label | b68f3020-d045-5ff7-9b70-8751ccc59370 |  | note | FREQUENCY: Where applicable, each element
label | 6bb84073-3694-5e83-b3eb-3a1f0179dee6 |  | note | CATEGORY: IP
label | c41b85c6-6700-564b-ade6-17c0e6db4ec5 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 0259593c-e19b-5105-bd96-b48eef3593f2 |  | note | VERIFYING DOCUMENTS: This ITP
date | e93b48e1-cec0-5e85-8843-17f4de44e4e6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Early Age Compressive Strength Test Results - Removal of Formwork
label | 8a6273c5-41e1-57cb-bab9-593bb21b5c4f |  | note | REFERENCE: IFC Drawings
label | 0a178370-cedd-518c-8601-c6279886cea3 |  | note | ACCEPTANCE CRITERIA: Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
label | 8d9545bb-4f7c-51f6-85c4-e0270093566c |  | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | d5bdceec-4d9c-556b-aaef-da12a1b62bed |  | note | METHOD: Document Review
label | f8d12fa1-3ff5-5974-a53b-667e1a2ee77e |  | note | FREQUENCY: Where applicable, each element
label | 54758895-9010-5eff-91a4-e32bab307e2a |  | note | CATEGORY: IP
label | 8e8ee779-c317-5b43-88dd-cfea7784b0cd |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 0f87e0e1-1ac7-5e48-a35c-7102956162f8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3daca89c-d878-53b6-a433-f8630ed686b0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Surface Inspection - Cracks
label | 1cbc80bf-7ea8-5fef-86a2-2a88d1e888eb |  | note | REFERENCE: 610.24
label | 9e2b5f6e-77d6-5ad3-9057-cb442ba84d8d |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1)
label | 8ae3a60c-f7e2-510a-a290-a638fd4ff423 |  | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | a0b44f11-396b-55c5-9c00-a87f85645831 |  | note | METHOD: Visual, Measure
label | e1b28460-87c2-56a2-82c5-cb311e5bf7bb |  | note | FREQUENCY: Each element
label | 28e8ebf7-ac95-593c-9882-3080ae81b528 |  | note | CATEGORY: IP
label | 8e67cb79-e224-5f98-9f0d-3f2ca5bf6ef5 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3836baa7-3216-58f3-ac42-86ddd7f8ddf9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8cf3029f-e705-56a5-b9ec-f530a83688ba |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Surface Inspection - Surface Finish
label | 2b7373f3-8e1f-50f8-8bdf-ea16278086d5 |  | note | REFERENCE: IFC Drawings 610.31 (a) - (n), 610.32
label | 4d1e63b0-9ef7-58c8-8c09-6b15be52c0d1 |  | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
label | 59ba086d-77c4-5e30-a645-36c2eacad78a |  | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | f3b1f179-38e9-5b93-a63a-368fae846c78 |  | note | METHOD: Visual
label | 83205327-b449-5e3a-af1d-6cd73bcff0d3 |  | note | FREQUENCY: Each element
label | 9bdd523c-cfbe-5335-9fb0-20332a047a10 |  | note | CATEGORY: IP
label | 5d9e2b74-dd81-527c-9e08-82f7ffb2d51a |  | note | RESPONSIBILITY: SE/PE/SPE
label | fb7ce9ef-f49c-589e-ad24-4448559e7bf0 |  | note | VERIFYING DOCUMENTS: This ITP
date | e82b290e-2967-5ab2-aee9-ac6b4b943011 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Measurement of Concrete Cover
label | 548e6cae-749e-59a4-8d6a-9f4f9ccfd948 |  | note | REFERENCE: 610.34
label | e2e18b75-ee33-53d8-88c1-421a86908604 |  | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | a371d0ab-af59-5a37-b071-a3bc538d9e80 |  | note | ○ Minimum 10 no. measurements recorded in each area.
label | 14a571da-e2bd-58c1-b063-01877ef9539b |  | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | 0885a184-c3e7-53d0-865a-fd2f347bdcab |  | note | Attach: Covermeter Check Record
label | c9ab0d13-fb7a-5f30-9f81-e48bcb3aab11 |  | note | METHOD: Measure
label | e1fd2d18-14e2-586b-9162-75c9106b51e2 |  | note | FREQUENCY: Each element
label | 455b73ec-10ab-5d48-a45d-5221cf1041dc |  | note | CATEGORY: IP
label | 2e5b1788-b421-512f-9ecf-fb2f50f95e6d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 08372b93-19be-5b1f-8c07-7578a5bd5d30 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6172afa8-5643-5998-8eca-e219f3076c24 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | fe28427c-bf52-511d-be33-209f68ba1121 |  | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
label | dd2b8086-1bb9-5d0b-ba83-7f324fdb850a |  | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
label | e04606cd-313d-54a6-b767-8a5bc65bdb8f |  | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
label | afbe2790-41f2-507a-8994-18dcc1c6f2fd |  | note | Attach: Concrete Test Results or Maturity Test Results
label | 3337681d-1307-5f45-bbfd-5030cfae2428 |  | note | METHOD: Document Review
label | 29f96889-f5d4-52b9-aff6-db98a3438304 |  | note | FREQUENCY: Where applicable, each substructure element
label | 601e13bd-8464-5419-aa93-43e649a12bcc |  | note | CATEGORY: SP
label | 9d74fbd6-aa20-5dbd-9597-012853d94e46 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 4525b4bc-38a1-5937-8aaf-19be12768ad9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 514e94ae-3024-5915-b62c-57ddf2e020fb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Compressive Strength Test Results
label | 6e085b77-bbf8-513a-a0f1-bbeb64dcd016 |  | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
label | 11c6caba-ba1e-5db5-ae9d-bc6120fa31b1 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | de469aef-f083-5196-9c46-ec6c5d71c995 |  | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 1a3351bd-cc6f-5241-b6a6-aedcc0912c22 |  | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 6eee60be-0574-5c1c-b330-73c62a193087 |  | note | Attach: Compressive Strength Test Results
label | f98e2d12-b874-5363-b2b5-901e76c81380 |  | note | METHOD: Document Review
label | 9e5896d8-0643-58fc-afbb-93c38b4c64bd |  | note | FREQUENCY: Each cylinder
label | f06d4bd3-480a-562c-86cc-3311ca43424d |  | note | CATEGORY: IP
label | c46cb896-dc35-5396-91d9-696b3223427e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 50dd208b-83c1-5aec-9e9f-f67a1e753e9d |  | note | VERIFYING DOCUMENTS: This ITP
date | d8ee0b87-5d5d-5625-9088-34dccf642327 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 As-built Survey
label | 7bb5b4d0-cfff-5c77-8f09-c415e8620e4c |  | note | REFERENCE: IFC Drawings 610.47 Table 610.472
label | 3bcf07ad-e62c-5d08-9c00-1c722fe20051 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | eb4582c1-f6bc-5093-bc5c-baf6319caae9 |  | note | Attach: Survey As-builts / Survey Report
label | 86033720-5c45-5269-b6cb-a2a53d421bfb |  | note | METHOD: Document Review
label | 432d7f3e-c2c9-5dd1-8565-3c36485b651a |  | note | FREQUENCY: Each element
label | 2a30ff7f-c114-59c2-b7c6-8c4159852975 |  | note | CATEGORY: IP
label | 36edd975-3c7f-5bb8-b37d-bc838cc78091 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 5da77fd7-da47-5fad-9cea-d83e0627b9e9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 800de3ec-d2e6-5186-a240-93ef9706c263 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Non-conformance Report (NCR) Closure
label | 1c0db92e-9a55-515a-b2b4-cf8440ef0db0 |  | note | REFERENCE: MRPA Quality Management Plan
label | e72564f1-7470-5399-9060-9633a8718f5f |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | b6cf15b2-d66b-50fd-aa81-1129f95dd684 |  | note | METHOD: Document Review
label | 922836fa-f05d-50d3-aac6-e282888b7f9b |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 576431d3-e8ec-5bbd-b830-74836cae8543 |  | note | CATEGORY: HP*
label | e617ec60-067b-5302-a623-e0fd26e531ef |  | note | RESPONSIBILITY: SE/PE/SPE
label | c6e1ccf3-3dba-5ae4-ac8b-568a422f625d |  | note | VERIFYING DOCUMENTS: This ITP
date | 66d2a70c-0a88-56e6-b2a2-b44e27b637a3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 2b043501-4e61-52cf-b8df-d6a6e661afa7 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 4655f156-9b90-5347-aa36-a8b0920b10d9 |  | textbox | Name:
text | 9dbcbd76-7179-5721-8aab-5cdc2aff3463 |  | textbox | Position:
date | bb085d81-3d0e-591a-81cb-c236afbb4279 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | CHK-002-CIV-Stormwater Drainage Pit Installation | itp |  |  |  | Yes | CHK-002-CIV-Stormwater Drainage Pit Installation Rev 2 | 6cce7d99-4222-45fb-a483-afc97e114c9e
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 1059b5dd-322e-5f33-8128-e1503fb29acb |  | note | Document Title: CHK-CIV-CAMMS-Stormwater Drainage Pit Installation
label | e2cc06ed-68f3-5ce0-8c54-9667e3faf1a6 |  | note | ITP Description: CAMMS-Stormwater Drainage Pipes Installation
label | 0b1c8c27-715a-5535-b71e-c34282f8c3bb |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 01af07ba-8a0e-5b4a-bc46-d153421a6234 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 2744e92b-4729-5b7c-b859-992bc31eac15 |  | note | Revision Number: 2
label | 88cf025b-7341-5612-84b3-a32d245e445c |  | note | Revision Date: 6/12/2023
label | 9dd9946b-a8e4-5159-acee-f343bcd6fe37 |  | note | ITP created by: Victor Mira
label | 3905a3d1-8b6e-5ab5-824a-56846384204a |  | note | ITP approved for use by: Victor Mira
label | 541e4ad2-1e7b-5b46-ac4f-27534d5bcda0 |  | note | 1.1 Non Dependent
label | a26d74fa-72d8-5007-9ffc-672a7cfb911b |  | note | Reference: VR 701
label | 736d0272-15d3-5945-a59c-cb35488ad7fa |  | note | 1.2 Main ITP
label | 5d5fcd0e-4ba1-5dc8-bc5a-6730db80d40c |  | note | Reference: Project Storm water Drainage Main ITP
label | b9ed2c67-5868-5f41-90ef-bbfc7f55562b |  | note | Acceptance Criteria: This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0
text | 972e75a1-6fca-5b87-a005-2b9a1c100c21 |  | textbox | Enter: Main ITP Lot Number
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Bedding
label | 1f6d8c56-2959-5348-afe1-e36e9aa9722f |  | note | REFERENCE: VR 701
label | a13fa797-fba4-5fb3-af44-6451d973fe7d |  | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
label | e1b36fe7-cb2c-5dfe-b29d-415fc35d56ec |  | note | METHOD: Document Review
label | 5420bf31-0fcb-59a8-a2aa-86e8cd822a9f |  | note | FREQUENCY: Each Lot
label | 57dbf6d4-52ce-5b51-9a9e-8c8c47521c8b |  | note | CATEGORY: HP*
label | badfcd8a-e9e1-58c1-802e-04ba8e384842 |  | note | RESPONSIBILITY: SE
label | f8f19f5d-4244-5b95-8f97-f9b9c8e6d394 |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
date | 04ec41dc-d554-58bf-bfe2-09f259d857d5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Backfill Material
label | 39f7f10a-d625-5b6b-8648-46a064593462 |  | note | REFERENCE: VR 701
label | 36d2907d-44f3-59cf-a6a8-47a3ae904bd3 |  | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
label | d6fc9a17-a65c-5e71-b32f-457126b2c2bb |  | note | METHOD: Document Review
label | 35ab21ae-84a1-5ddb-acd9-6d9c467feddf |  | note | FREQUENCY: Each Lot
label | 7e48bacd-d9fa-5dbb-a3d6-51afa87be37d |  | note | CATEGORY: HP*
label | d234bc48-2817-50c4-959c-5b3c08d6e5e7 |  | note | RESPONSIBILITY: SE
label | 9ac22a2c-deee-5bac-8023-53a6938c1a62 |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
date | baeadcd2-b733-553d-a3ef-c906bc31d2b7 |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Subcontractor QA Submissions and ITP
label | e625595c-4e07-5605-a395-9c61f46435ca |  | note | REFERENCE: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
label | 82046a45-8a6d-5734-952e-4dded890a124 |  | note | ACCEPTANCE CRITERIA: Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications..
label | 50e15413-630f-50dc-a7e4-609456aaa596 |  | note | ATTACH: Subcontractor Signed ITP
label | 5e4a13c5-74b1-53c0-a71d-2a1cd4189f7e |  | note | METHOD: Document Review
label | 01fddb99-91d0-5089-abf8-9523249652ed |  | note | FREQUENCY: Each Lot (in case undertaken by subcontractor)
label | 374233fb-6d54-537f-8c01-11b8af368d84 |  | note | CATEGORY: HP*
label | e8a16dae-7948-5fa9-8ccf-4195baf159a6 |  | note | RESPONSIBILITY: SE
label | 8842c718-b322-53f3-974d-786e1a6e3618 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 341424e0-6da0-56c5-aac1-fd1050f29500 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set Out
label | 95090731-2672-530e-9b11-ce618974a790 |  | note | REFERENCE: VR 701.10
label | bf54edec-cb70-59e1-84c6-6cbc686c8198 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
label | 031c0c4d-8f8f-5e14-9eff-7e2087f8916e |  | note | METHOD: Visual inspection
label | 0626a794-60bf-52da-860d-5a7c9c4a45e6 |  | note | FREQUENCY: Each Lot
label | 093dec7e-5951-5cc3-b314-103b66cd46ba |  | note | CATEGORY: HP*
label | a335cde0-427c-51fa-8b23-c27296d4f355 |  | note | RESPONSIBILITY: SE
label | 325fd8e8-163a-5a9f-9fb0-52633219f4ea |  | note | VERIFYING DOCUMENTS: This ITP
date | 746d2174-d9b3-5563-9ccf-ea684a674ca4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Pit Excavation
label | f1d17630-c86c-5eeb-8a82-945ca448f6b5 |  | note | REFERENCE: VR 705.05
label | 93689cd3-0bc3-5cde-aa71-5292e0e1eb60 |  | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
label | f9c8b174-6945-5df0-b490-0c3ea9a4980f |  | note | METHOD: Visual inspection
label | 360339a1-6cef-5c29-9229-6d8ecd4203d0 |  | note | FREQUENCY: Each Lot
label | 112051c7-b560-5064-8367-3cf2a9ea60bf |  | note | CATEGORY: IP
label | 60d88eed-d574-5ddc-8d69-8ee09b0cb94d |  | note | RESPONSIBILITY: SE
label | e2ece3dc-3972-5b37-b869-e21b3fd9dfc5 |  | note | VERIFYING DOCUMENTS: This ITP
date | d1bff01a-a105-55d7-bade-9506c810c533 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Excavation Foundation
label | 8edd3bb3-89d2-5579-9b51-cab83d5ac43d |  | note | REFERENCE: VR 705.05
label | 79a022d7-a1e6-53c7-9f21-ff72343efe34 |  | note | ACCEPTANCE CRITERIA: Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
label | b817ca89-5200-57a7-a7e7-d0552008bc66 |  | note | > 80mm for clay foundations
label | 8da2fbea-a14c-542c-ae87-e8acfff3b7a7 |  | note | > 150mm for rock foundations
label | f0b822e5-6c4f-52a5-a0f2-c418ea734399 |  | note | METHOD: Visual inspection
label | 5b7e0648-11f6-594e-827a-a573ed3ae77e |  | note | FREQUENCY: Each Lot
label | 4724b2d3-beff-57b9-ba65-35eaefdbac40 |  | note | CATEGORY: IP
label | 961e3b25-e5d9-5e3a-9f27-f92f8ed5346e |  | note | RESPONSIBILITY: SE
label | 054393d0-58da-52f2-a5af-e5dd1a25028e |  | note | VERIFYING DOCUMENTS: This ITP
date | 0573c1b3-add8-5c43-870c-eae160198830 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Jointing
label | b6b71a95-cd37-5e09-a730-8b5ab7820b82 |  | note | REFERENCE: VR 705.11
label | 9f9ae5a4-564a-51af-9b77-9f461a7c5421 |  | note | ACCEPTANCE CRITERIA: All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
label | ddd2bfce-97c7-57b1-96e0-9e8197d8ef9b |  | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
label | 098ddcb3-63c4-57f7-b5dc-22005942ad0e |  | note | METHOD: Visual inspection
label | 87c72705-e162-5805-9baa-52b3dd359a19 |  | note | FREQUENCY: Each Lot
label | 89f641e9-8cf1-503f-8129-40072b1b189d |  | note | CATEGORY: IP
label | 9e4f424d-e4be-5bc4-90dc-2c58091dfadb |  | note | RESPONSIBILITY: SE
label | cba1d4c5-1330-5c94-b5be-019f76f21310 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9c45999b-ffd9-5c9f-9a72-a15b40d7b097 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Shaping of Floor
label | 9d9f6745-d765-5de4-8eea-6b0497b3a2d0 |  | note | REFERENCE: VR 705.13
label | 8e34bb91-1c87-5b4b-9b00-752998b68e09 |  | note | ACCEPTANCE CRITERIA: Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
label | 14748ec2-f1e3-585d-ac6f-fe87645a913e |  | note | METHOD: Visual inspection
label | c10a2d91-2a60-5972-b471-0e894e9e3d96 |  | note | FREQUENCY: Each Lot
label | 43504930-5091-514a-b812-d0fb63b08f3e |  | note | CATEGORY: IP
label | 8e7968d3-aa23-5cc9-9763-2d48daa8369b |  | note | RESPONSIBILITY: SE
label | 1757c5de-8312-5381-a3eb-cca15ee15c8a |  | note | VERIFYING DOCUMENTS: This ITP
date | 68dcdc2c-38da-5112-a880-c2f89e89d7ce |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Step Irons
label | 2d50c676-09ac-5a41-a525-b071b0a5178a |  | note | REFERENCE: VR 705.12
label | b06af494-85c6-5ec8-82da-7c4d0fd44939 |  | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
label | 2ebea370-6686-5cc0-94f5-7aa92bf8b42c |  | note | METHOD: Visual inspection
label | d2d309a2-9e8c-5073-bca2-e6defad0f237 |  | note | FREQUENCY: Each Lot
label | 1b444b30-905b-5002-82e7-3c8db8cb38a6 |  | note | CATEGORY: IP
label | 01037711-359e-5898-b7d5-0d591caa7fcf |  | note | RESPONSIBILITY: SE
label | 822b2a8e-970b-587b-9f93-6f39a07253a3 |  | note | VERIFYING DOCUMENTS: This ITP
date | 84d3e685-18e5-5d6c-a72b-d4e274952b66 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Fitting of Covers
label | 5330c520-7349-5c20-a4d9-6acd4861ccfd |  | note | REFERENCE: VR 705.17
label | d040e1a8-104a-5ce9-93a7-be3986651bfb |  | note | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
label | 96cebb8e-c83e-5e90-aecb-4614eaf5ef0e |  | note | ○ Height shall be within 10mm of the design level
label | e830d3cc-0374-52d2-ac8d-1b61709c147e |  | note | METHOD: Visual inspection
label | ed5e2a0d-c26e-5c84-950f-f919c10545ca |  | note | FREQUENCY: Each Lot
label | 39a7633b-9aad-518b-a406-3abd528ca50d |  | note | CATEGORY: IP
label | 2aa60c86-76b5-554f-a39c-1841bbaffa30 |  | note | RESPONSIBILITY: SE
label | 63854145-da0c-5cc3-9335-29a8a575f0ff |  | note | VERIFYING DOCUMENTS: This ITP
date | 92b18ea5-1d7d-50d9-871c-7e0d6c14a4a4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Backfilling Around Drainage Pits
label | 99449984-7ef5-55c4-bed1-2b2e4c6eee8d |  | note | REFERENCE: VR 705.18
label | 98c05316-785b-5a0b-97cd-05042bed1e1a |  | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
label | 4c3cd8bd-3f44-565d-a5e3-f635f75b4d4a |  | note | METHOD: Visual inspection
label | 506b5cf2-3b16-517b-a60c-d4bddd38a0a0 |  | note | FREQUENCY: Each Lot
label | ac79961c-75dc-5a1f-9296-2f6afeed61bb |  | note | CATEGORY: IP
label | 4f366c07-0275-5a30-9cfb-dddb22cae1eb |  | note | RESPONSIBILITY: SE
label | 9306df1c-acc2-5800-b696-8a0bfaf8ac8a |  | note | VERIFYING DOCUMENTS: This ITP
date | c27a24ef-cf2f-5138-8c45-55ee11934b3f |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Placement of Pit-Conformity with drawings
label | 2d5a5548-3d32-50e0-8260-a3ca84560c46 |  | note | REFERENCE: VR 701.10
label | 982dcd11-c865-5129-b9c0-0f65357d56ef |  | note | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
label | c2c576e5-01c4-51b6-8f53-0330bc6e48a3 |  | note | Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | 6849767f-ee2f-5c2b-8464-9e7d3b012739 |  | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | 20aa2a37-9cea-5cc9-87b0-961c47c986a2 |  | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | 1f42dd70-9f13-58f9-9fc4-38d47466d360 |  | note | (c) invert level of pipes at pits ±50 mm
label | 9fb8b063-e730-55c3-878a-d75907c3da71 |  | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | f73e87ed-ff0c-5f0a-9098-63c5a316b624 |  | note | ATTACH: Survey Report
label | 89b1ae99-5e67-5ffc-8567-d502e8adc381 |  | note | METHOD: Measure
label | 6efc8eff-d2ee-5d1b-be3e-f2516ffe7e0b |  | note | FREQUENCY: Each Lot
label | 87343b12-b3b3-5fbf-b779-5fd4049021ef |  | note | CATEGORY: HP*
label | c5036daf-cdc5-57df-bc9b-00c8ba2c42b6 |  | note | RESPONSIBILITY: SE
label | a8647564-923a-53a0-8520-4d60fdff406e |  | note | VERIFYING DOCUMENTS: Survey Report
date | 241ba779-cb1f-5804-abaa-7d40f05e982f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 CCTV Inspection
label | 7bcd0375-d644-5be7-a40e-6def36da4fe0 |  | note | REFERENCE: VR 701.30
label | 184755e6-84d3-551e-97a4-fbc3f6c1e9a0 |  | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | 44a4a3ff-0537-5214-b738-08c862f723bc |  | note | ATTACH: CCTV Report (PDF):
label | f75b31b0-1ba7-5374-8f5c-753c7e939afd |  | note | METHOD: Document Review
label | d3fa30b7-2538-54bb-838f-bef6b139f004 |  | note | FREQUENCY: Each Lot
label | fb549aef-76af-5873-b110-80537fbefdb7 |  | note | CATEGORY: HP
label | b2edbf57-a43b-5f91-8450-5a868ee2425a |  | note | RESPONSIBILITY: Nominated Authority
label | 8f65017c-ca9b-5c74-9def-f13708e6d70b |  | note | VERIFYING DOCUMENTS: CCTV Reports
date | f368172f-f26c-5e4f-8330-8ea86a18e590 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | fac3e35c-b455-5910-bc21-6892b3de02b6 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c5b73a63-fc06-5829-a78f-7eaf7288db6a |  | textbox | Name:
text | ba690567-9f64-520e-9e7b-abb3460ae5b0 |  | textbox | Position:
date | e78e7ba8-0989-5dbb-ad68-d64aad9fc1d0 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | CHK-001-CIV-Stormwater Drainage Pipes Installation | itp |  |  |  | Yes | CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 2 | aa8cf543-13db-40aa-b7c2-844f6f7c80f6
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | b1dece8b-320e-5f03-bea4-d6cc7e86dbcf |  | note | Document Title: CHK-CIV-CAMMS-Stormwater Drainage Pipes Installation
label | 5b2e91cb-7fc8-5608-b824-210769628860 |  | note | ITP Description: CAMMS-Stormwater Drainage Pipes Installation
label | 89cbc121-9693-5a66-8fda-83497881e5ca |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 45883644-3603-524d-8db0-a2073837a0f8 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 784756f4-439a-52d4-b873-db7269832303 |  | note | Revision Number: 2
label | 8ba7c0fa-ab61-5cfa-a35e-15afdcc71cc7 |  | note | Revision Date: 7/12/2023
label | 9bfd0648-f500-5441-92fd-35f422f19210 |  | note | ITP created by: Victor Mira
label | e3e462ac-bde1-5ac0-b474-ef8fe5be88d4 |  | note | ITP approved for use by: Victor Mira
label | a3d11e14-7f99-5a81-bb52-7314d4559336 |  | note | 1.1 Non Dependent
label | 0d6661d2-cf07-5a31-8893-8e85c559eb40 |  | note | Reference: VR 701
label | f5d661f7-b46e-51f8-8c50-e0a4a55713a7 |  | note | 1.2 Main ITP
label | 20a126bc-d9e0-53d3-9da6-4a4b7108a8d4 |  | note | Reference: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
label | 64e644a3-35a0-5e40-a7ed-4d6b16429d06 |  | note | Acceptance Criteria: This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0
text | adf430eb-788e-5e7b-89f8-587a5b058061 |  | textbox | Enter: Main ITP Lot Number
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Bedding
label | 0b36b268-ce3a-5cda-8fcf-fa70e495a207 |  | note | REFERENCE: VR 701
label | 543eebfc-3791-526e-9bd5-5dabe41fb58a |  | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
label | 04ae4900-0c63-5594-8a56-4b21aa86b749 |  | note | METHOD: Document Review
label | debf6564-dc10-58cc-a1a9-a55bd6c85b30 |  | note | FREQUENCY: Each Lot
label | 63cdf1d6-7f22-55ec-8f42-08c0ea74d824 |  | note | CATEGORY: HP*
label | ae64a7f4-bf32-5f8e-a8c9-ae9ec4d140f7 |  | note | RESPONSIBILITY: SE
label | f72dd6b9-a78d-5f17-9295-8862c78327f5 |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
date | d219760d-6f0b-5c8e-909b-81c8c7798338 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Backfill Material
label | 46a5e3e0-6dc6-5182-b358-e0a9deb6726d |  | note | REFERENCE: VR 701
label | 03dafda0-6f04-5a8a-bc31-7744df2836de |  | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
label | 6978dab9-1199-5b6d-ad4f-915b7f002336 |  | note | METHOD: Document Review
label | 9750fd14-2393-5539-b9b8-8f8cc35dce2d |  | note | FREQUENCY: Each Lot
label | 0b2e1404-d737-5ffa-99b3-a31fac2ca0b3 |  | note | CATEGORY: HP*
label | d8710aec-e1f6-5b7b-8652-96382e6a711a |  | note | RESPONSIBILITY: SE
label | e8c5bb31-21d8-5246-b0e1-9765c56a080f |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
date | affadd9d-a024-5bea-86cf-e54802dbfd64 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Stabilized Sand
label | 2b0f8474-58af-5d8b-a796-97651902a889 |  | note | REFERENCE: VR 701
label | b68c8441-b1f1-5382-8ec6-f08ed513e248 |  | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
label | 57fcf703-7548-5dac-a028-3d6eca268362 |  | note | METHOD: Document Review
label | 8f7f82ae-703b-595b-b726-7b86e5898211 |  | note | FREQUENCY: Each Lot
label | 3abd029e-227c-5703-86a1-c82ac928cb64 |  | note | CATEGORY: HP*
label | 8fc47305-3a6a-5f05-9c1d-b0c16e503894 |  | note | RESPONSIBILITY: SE
label | 5358996e-e0f6-5131-bb20-8c717caa968d |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
date | b713a6e3-bb0f-57fd-bc59-c3955dc3a3d1 |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Subcontractor QA Submissions and ITP
label | dd0f2d9b-9b24-5294-9026-a1a0b1e8006e |  | note | REFERENCE: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
label | 24a2dcc5-4fc6-5dec-8c1e-96c7dbbf94de |  | note | ACCEPTANCE CRITERIA: Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
label | 8ed531b7-f0e5-5ca4-862d-4d81f6e4de70 |  | note | ATTACH: Subcontractor Signed ITP
label | b78644bb-ea40-5caf-b586-362ddd1f6b64 |  | note | METHOD: Document Review
label | 60eb5fd9-bf4b-5333-b07d-21cf723dc9d1 |  | note | FREQUENCY: Each Lot (in case undertaken by subcontractor)
label | 9eff7623-9631-5b95-9fa3-72acacef1d8d |  | note | CATEGORY: HP*
label | b5ad3ee9-b878-5e4e-832a-fea8e0ab8f1d |  | note | RESPONSIBILITY: SE
label | 4ec0b7af-5239-5fa0-956f-343c6cc539f6 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | dc431774-7ae0-5dc6-8c8d-2c528867f646 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-Out
label | c2282f5a-b8ea-570c-aee2-9703ecb62b4d |  | note | REFERENCE: 710.10
label | 797659a0-a56c-59ab-93ea-2b1dbb174f0e |  | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | b917af37-64bb-59b8-aad6-e0e232e224c9 |  | note | ○ The culverts constructed shall be constructed true to line and level.
label | 024aca26-882f-5325-bcc9-37b0df477294 |  | note | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
label | 964653f2-652d-5507-9251-e6c47ac43a23 |  | note | METHOD: Survey, Measure
label | 1d9028c6-00d2-5cf8-b6ff-cdd7dc2fde53 |  | note | FREQUENCY: Each Lot
label | 7c0f39a8-f269-575b-820e-c57a4a7f8d38 |  | note | CATEGORY: HP*
label | 4ba07a9c-d680-5525-9c11-ba78e2246b5d |  | note | RESPONSIBILITY: SE
label | 5a2d5334-a3cc-5c9b-95ff-33dd6e068858 |  | note | VERIFYING DOCUMENTS: This ITP, Main Lot Map
date | c8980374-fa54-5422-9909-08477bf60a9b |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Trench Excavation
label | 10dd7a34-1d21-55d2-b7cd-8d4cd37bf18f |  | note | REFERENCE: VR 701.15
label | e0655f80-0382-5de7-988f-d81dabb0ce05 |  | note | ACCEPTANCE CRITERIA: For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
label | 20932b62-5589-5c94-b4a2-e6dd4f18d430 |  | note | Horizontal Clearance to wall of trench
label | 4527244d-624e-5e5e-8cc8-4a158980a91a |  | note | Pipe Culverts:
label | 595b112e-b94b-5885-aaf6-80edc5c90d28 |  | note | ○ 300mm<Horizontal clearance for corrugated metal culverts<1000mm
label | aaa5c6bf-66ad-54cc-affd-2b94ed8edc35 |  | note | ○ 300mm<Horizontal clearance for other Pipe culverts<600mm
label | d1fa284f-a7da-5b8c-8d06-8302019c8a49 |  | note | Box Culverts:
label | 65475937-292f-55cc-bfa3-9bafe43e6afb |  | note | ○ 0.5 times the height of the culvert<Horizontal clearance<overall height of the culvert
label | bb7235f2-8eab-50ff-b5eb-2a39d82c36bc |  | note | METHOD: Measure
label | de709c6c-b62b-56fd-b2f1-076f2509ae1f |  | note | FREQUENCY: Each Lot
label | 36df3b93-313d-57a1-b249-85bf880074ac |  | note | CATEGORY: IP
label | b163b685-34e7-5df1-9d80-13644e42cb28 |  | note | RESPONSIBILITY: SE
label | 86dfd443-441c-533d-a939-52cb9d76c0d6 |  | note | VERIFYING DOCUMENTS: This ITP
date | 329ff529-9fd2-5440-9734-19e832980e4c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Trench Base
label | 728aa9c6-3096-51fd-8b9a-ed6555932494 |  | note | REFERENCE: VR 701.15
label | 2905db11-bf18-50dd-85e6-2031ae3da4d8 |  | note | ACCEPTANCE CRITERIA: The base of the trench shall be compacted to refusal using mechanical plant
label | f04d3520-6320-5527-ab07-d2745ae118f0 |  | note | METHOD: Visual
label | 83076747-457b-53a3-8abd-d6587098b0b0 |  | note | FREQUENCY: Each Lot
label | 2aa165b4-5951-5a84-9850-93961eb0a8f0 |  | note | CATEGORY: SP
label | 8cac7e92-88b9-50c6-9ec8-6b360b0dd5a0 |  | note | RESPONSIBILITY: SE
label | 4a0343ec-eebd-507b-83eb-416418fa870e |  | note | VERIFYING DOCUMENTS: This ITP
date | 03056e4a-d680-5677-a8e2-d622baed0187 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Bedding-Placement and compaction
label | c43bfa13-6741-5a50-811d-b4a44537efc5 |  | note | REFERENCE: VR 701.16, VR 701.20 (a)
label | 6e2c384e-7dd0-5b82-8298-04ae68b6e721 |  | note | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
label | c6c013f3-a164-5519-9bd0-c5b23a5e37e1 |  | note | ○ 100 mm where D < 1500 mm
label | f77b0413-5d8c-5628-b554-7e17763e48ba |  | note | ○ 200 mm where D ≥ 1500 mm
label | ac3bccc1-3bb9-5904-9ab1-fefbbbb1b388 |  | note | Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer
label | 5c437689-3c90-5975-b8ed-0674c3bad6a9 |  | note | METHOD: Visual, Measure
label | 218a8726-1adb-58ec-a25b-a885c167e781 |  | note | FREQUENCY: Each Lot
label | f5855308-fc28-5eb6-9d49-c06f5d7eb424 |  | note | CATEGORY: SP
label | 6a976c88-861e-567d-982e-ba48bc265375 |  | note | RESPONSIBILITY: SE
label | 730f87f3-fe60-544d-b196-bf3d2c0fd733 |  | note | VERIFYING DOCUMENTS: This ITP
date | 7ffd5247-cd6b-59e4-890a-ee46fcdb0d8e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Laying pipes-Bedding conformity
label | adaaeaef-0d63-580d-911e-f1a823c41046 |  | note | REFERENCE: VR 701.17
label | 07c0b3c9-4ebb-5d75-8e9e-b7ed43799328 |  | note | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged.
label | 45942d14-cfad-5283-b9c8-f7048465f74c |  | note | ○ Laying of pipes or box culverts shall commence from the downstream end.
label | 1daec5e1-086f-554a-bd47-1f2017d83012 |  | note | METHOD: Visual
label | 7c51c851-065f-51cc-9594-f288604d115e |  | note | FREQUENCY: Each Lot
label | 9cc827cf-0cd7-5f5a-b5cf-fa3301472b33 |  | note | CATEGORY: HP*
label | 26c1ab6f-a11c-51c5-8e0a-13ec54e8ac01 |  | note | RESPONSIBILITY: SE
label | c886ac85-7ead-5c90-9b95-6ec063e62a8d |  | note | VERIFYING DOCUMENTS: This ITP
date | 01082f63-d017-503e-a6f5-f9dc64601db0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Pipe Laying
label | c6530a39-e7d5-53a0-a093-fc6b643b28b1 |  | note | REFERENCE: VR 701.16, VR 701.17
label | 6f75ec44-aa8c-5076-b75c-964807424665 |  | note | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall commence from the downstream end.
label | 78931b84-52b8-5c34-a45d-3cb155d7cf22 |  | note | ○ Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
label | 56305124-9c8c-505d-a02f-45d7376edd66 |  | note | ○ The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
label | c420ed5e-2259-5388-b26c-87f9cd310719 |  | note | ○ The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
label | da8e9a7e-eaa0-5fdf-af18-ce266ec554e7 |  | note | ○ When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
label | 68c292f3-65a6-5333-805c-a795a0e337ec |  | note | METHOD: Visual
label | 13267c4d-9933-51eb-9c6e-a1f2793e7e88 |  | note | FREQUENCY: Each Pipe
label | b99c9766-ae86-5c70-93c1-48a08a149b90 |  | note | CATEGORY: SP
label | 2236b5fa-f32c-58bd-a65f-1c3da00850ca |  | note | RESPONSIBILITY: SE
label | 668a2d1c-4519-5287-bb2a-f084bc7e1026 |  | note | VERIFYING DOCUMENTS: This ITP
date | b19e6b85-ba2f-5ff6-a70d-797644cb7bea |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Pipe Joints and rotation
label | 94c40845-1252-5b4c-91bb-934d825ce561 |  | note | REFERENCE: VR 70.18
label | cef64d7d-888c-54cf-a4dc-b94a7c4eb1bf |  | note | ACCEPTANCE CRITERIA: All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
label | 590ec354-7414-53d0-8586-640db5f1970e |  | note | ○ Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
label | 0097a504-1ada-589c-b608-c0dc33141781 |  | note | METHOD: Visual
label | d1cf2ee8-7ba6-594a-b1f1-7e538d7afce9 |  | note | FREQUENCY: Each Pipe
label | e7b1eb92-8f19-5713-973e-a75cdcccf4ee |  | note | CATEGORY: SP
label | b24b35cf-f618-55ac-9a4d-7a347ed5398a |  | note | RESPONSIBILITY: SE
label | 625b21cb-eec5-5434-914e-47d294f7c2b1 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5cbd7178-b531-53e7-b961-5836f0d7309b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Conformity with drawings
label | 96ef94ea-e8bc-5318-8e68-53d342b5aba1 |  | note | REFERENCE: VR 701.10
label | c5e5cb9e-e17a-5a7e-8223-bebb90e0825d |  | note | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
label | 5942c81a-5773-5bee-ae01-89c28ccc2173 |  | note | Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | 2e6051a1-7fed-556d-aae9-4ed09d64c194 |  | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | 0854e21a-6b84-5772-ad9b-98135fa1a1e8 |  | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | fb2d99a1-0ed9-51e0-828c-04c225300b4e |  | note | (c) invert level of pipes at pits ±50 mm
label | c70957fc-51dd-5a71-b588-1c60fa2b8496 |  | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | 52e47aa6-0178-52bc-a654-bb12b22f9c87 |  | note | ATTACH: Survey Report
label | a9759810-a442-5f01-bfe1-85a9ccb9fb90 |  | note | METHOD: Measure
label | bca36410-8d53-5f24-8102-21b7239c6cad |  | note | FREQUENCY: Each Lot
label | 61b66fb8-e260-5d52-a1fa-d6d73d930c0c |  | note | CATEGORY: HP*
label | 679c50ee-a545-5f8f-a2e1-263e08fd7776 |  | note | RESPONSIBILITY: SE
label | 74d28269-9384-5762-92b8-8950cbc1d145 |  | note | VERIFYING DOCUMENTS: Survey Report
date | 708df606-2739-5184-b46b-882e3ac1b0ec |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Backfill-Under area to be paved
label | 0ecfe407-8db6-545f-a954-00fe87a16d73 |  | note | REFERENCE: VR 701.19 (a) i
label | f6aee447-b8dc-59f6-a0b4-7f4c90956082 |  | note | ACCEPTANCE CRITERIA: Culvert under area to be paved
label | 991aa84b-f2ab-5878-9b8a-bf98adca5955 |  | note | ○ Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
label | c00400a7-8db9-5897-8019-60178e89c355 |  | note | ○ Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
label | 8ba2f810-cf7d-5568-bcb1-abbfccea86ed |  | note | METHOD: Visual
label | c0a5f155-255b-577f-948e-8df8ad73ef61 |  | note | FREQUENCY: Each Lot
label | acbc417d-5b41-5662-9229-f8a5d1cf0b94 |  | note | CATEGORY: SP
label | 94f14696-6bbb-5a4b-a084-bd4d35668f13 |  | note | RESPONSIBILITY: SE
label | 9bad6892-1740-57a1-9a48-7e81deccd206 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1940ff1e-2a2b-5d0e-9d05-cf8043d39b9b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Backfill-Under area not to be paved
label | ac587971-4c0b-51a4-bd83-4592cfa97cc5 |  | note | REFERENCE: VR 701.19 (a) ii
label | c71159a1-7b74-5aca-810c-a71bfb0a1e1b |  | note | ACCEPTANCE CRITERIA: The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level
label | 6b577fe6-95f9-56d1-91f7-4885ae7aeeb9 |  | note | METHOD: Visual
label | 2b5e8070-7bc2-5ee6-8f56-5c591762484b |  | note | FREQUENCY: Each Lot
label | fa1fb367-088f-509d-b75b-d92cb64adbdd |  | note | CATEGORY: SP
label | f8b9344b-b7d3-52e3-b6f3-fc7cc18e81a1 |  | note | RESPONSIBILITY: SE
label | a2e2b509-da64-5a19-849b-6d32f9025b28 |  | note | VERIFYING DOCUMENTS: This ITP
date | 59a28c4b-0c13-50d8-84c1-c5e2220d3f2c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Backfilling with cement stabilised sand
label | 88341e2b-4839-55ba-a81d-b3b3ab568d63 |  | note | REFERENCE: VR 701.19 ( c)
label | afb641fe-9078-5011-b03a-379c2e3b74a8 |  | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height
label | 09092c86-6254-50e7-8ce6-c776ad5c9918 |  | note | METHOD: Visual
label | d2d59e25-7b53-5740-85c2-8a2f7402cf3c |  | note | FREQUENCY: Each Lot
label | 7951f93b-0ae7-5c0e-a888-53b74fc4d123 |  | note | CATEGORY: SP
label | 8f36aeff-5b47-56f7-a72b-2428c370108f |  | note | RESPONSIBILITY: SE
label | a2eeb583-01da-5564-88b8-feb03692a3fe |  | note | VERIFYING DOCUMENTS: This ITP
date | 9325fbac-7ef4-5bfb-a739-daca94562d80 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Backfill Placement
label | edecb0cf-aae3-5c0d-ad34-0c15674d69a5 |  | note | REFERENCE: VR 701.20
label | 038b2690-c2e2-5de8-90ff-d1791bc50a7d |  | note | ACCEPTANCE CRITERIA: backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | 09f4d551-fc44-55f9-87ea-5aaed635ee61 |  | note | METHOD: Visual
label | e364fff4-6a63-5396-82aa-52cfc02ef50a |  | note | FREQUENCY: Each Lot
label | 15f651ba-6563-503c-b902-59c2a26c62d3 |  | note | CATEGORY: SP
label | 0f15d7bd-5e1d-56c7-af27-9958846c219c |  | note | RESPONSIBILITY: SE
label | c33285cd-b014-5a61-8446-9a434a38eaa7 |  | note | VERIFYING DOCUMENTS: This ITP
date | cf8eeb18-c1f3-5620-8458-1feb9d9e527a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Backfill Compaction
label | c5aa5f67-f0a9-538e-8abf-6eba37d0ca24 |  | note | REFERENCE: VR 701 (b)
label | 5322690b-d6e5-58c4-b203-198356c782b0 |  | note | ACCEPTANCE CRITERIA: 20% of all bedding/Backfill layers for each culvert shall be tested.
label | 731340ed-fc80-5770-8c1b-fd8ea75385f5 |  | note | ○ Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
label | 18306498-39d5-5408-96ec-b929b341ef4c |  | note | ○ Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | 550ff429-84d7-54c6-b3c8-b02462be8a02 |  | note | METHOD: Test
label | e79190dd-315c-555b-a1f2-f434fb1a1a7e |  | note | FREQUENCY: Each Lot
label | 4ffcff48-b178-5ff7-9ad3-a60697e7f575 |  | note | CATEGORY: HP*
label | 23504c87-8e9f-5abc-8844-93742a1d3d52 |  | note | RESPONSIBILITY: PE
label | f91e49dc-925e-50ce-9c94-804933a1f750 |  | note | VERIFYING DOCUMENTS: This ITP
date | 955ad31b-4fc5-50ac-831f-809b20a2a7b4 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Compaction and Moisture content tests
label | bd303d66-8d57-55de-ac3c-ed77fc013a6b |  | note | REFERENCE: VR 701.20
label | aa737218-0400-5d7a-984e-64b6ac5a7422 |  | note | ACCEPTANCE CRITERIA: Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
label | 12f35f77-925b-53f1-b105-0ef630c49e2b |  | note | ATTACH: Compaction and Moisture content test results:
label | 93c730a8-a809-57dd-9be5-560fc1fbe2be |  | note | METHOD: Document Review
label | 1548800b-1468-5023-8228-6a6a8326f1c8 |  | note | FREQUENCY: Each Lot
label | 0b1f7f6f-531d-5579-9071-251fe20c7511 |  | note | CATEGORY: IP
label | bdb1bb63-4019-53fb-a291-52d37a943cd8 |  | note | RESPONSIBILITY: SE/PE
label | 6d6d0f4a-97ae-51c6-96e1-ce8a8307f1fe |  | note | VERIFYING DOCUMENTS: Test Results
date | 43f261e5-2ac2-5ea7-9e55-ae730c8bfcee |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | c6a8f0c4-3161-5b5b-a149-53a60062a9ba |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 4a45ca88-857d-54b5-898c-7f4cba7ba9ce |  | textbox | Name:
text | b442326f-2cdf-5483-9aa6-d6a9ffdd8aee |  | textbox | Position:
date | edf7353b-649c-57a9-a958-5bcc5efacea9 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-083-CIV-PSDS-Footpath-Industrial Crossover-Traffic Island | itp |  |  |  | Yes | ITP-083-CIV-PSDS-Footpath-Industrial Crossover-Traffic Island Rev 0 | b8e26a58-6649-43a3-9f00-9748bd8f6eab
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 4e26ffba-03c6-5642-8764-602bff3be227 |  | note | Document Title: ITP-083-CIV-PSDS-Footpath-Industrial crossover-Traffic island
label | bad55f8a-7afb-5835-946b-56752dfefb9e |  | note | ITP Description: PSDS-Footpath-Industrial crossover-Traffic island
label | 3c85ecd5-3e2d-5885-9fc1-27fdfa14d781 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | d77622b4-6463-5af6-8a7f-c49794f7ae2f |  | note | Discipline (e.g. CIV/STR/RAIL): 083-CIV
label | 86668c5e-67a4-556c-9c11-d12589069298 |  | note | Revision Number: 0
label | 33602419-082b-5d3a-b6ce-707359d6e4f1 |  | note | Revision Date: 21/02/2024
label | 1912c470-bf25-517a-90cb-f6f809cdfa97 |  | note | ITP created by: Abhi Patil
label | 84f754c1-5b83-5a91-9845-aca5f158cda5 |  | note | ITP approved for use by: Victor Mira
label | 1f1e08ab-4700-5551-b647-c9ecabd6ddd0 |  | note | 1.1 Non Dependent
label | d8d3205a-b962-5010-96ee-2b8409bf4ff1 |  | note | Reference: VicRoads Section 304 August 2013
label | 9ea7a373-d0c5-5140-9b6d-4623f1e11a7b |  | note | 1.2 Non Dependent
label | da148009-5366-5fe2-ac03-2e9c6f672821 |  | note | Reference: VicRoads Section 703 April 2019
label | 235e27db-2b86-5a62-8e3c-28e0c636f335 |  | note | 1.3 Non Dependent
label | 7f0fca8c-05b1-5c69-861f-16b993eb21aa |  | note | Reference: Council CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | 7474ecba-1b00-5d85-9341-988d4c9f3869 |  | note | 1.4 Non Dependent
label | c2ba7a52-0eb1-5c15-a20e-714db234adb4 |  | note | Reference: AS 1379-2007
label | fcd17006-dcb4-5c86-8779-ecd63479292d |  | note | 1.5 Non Dependent
label | bb69cdf0-051b-54e7-979a-90f61e2d3d57 |  | note | Reference: VicRoads Section 812 July 2016
label | 1fe4df38-c115-5f70-b89b-685f02943c82 |  | note | 1.6 Non Dependent
label | 3dcc8ed6-bd8b-5b79-8368-d37e3e30a6a4 |  | note | Reference: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Bedding Material Placement & Compaction
label | ad3139a2-0745-52cb-98e9-a3921cf7190c |  | note | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 812.04, 703.21
label | 5186c6f4-7f2e-5f53-9962-3c5662f66841 |  | note | ACCEPTANCE CRITERIA: Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
label | 764a8924-facc-5faf-a8b6-75309742d818 |  | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
text | 49365a2e-9711-5d9d-8de9-2890ab3689bc |  | textbox | Enter: Teambinder Material Approval number
label | 00b7d399-8984-5787-b260-82ff9515e3d3 |  | note | METHOD: Document Review
label | 53219220-452c-5150-b88e-af59c4d93cb1 |  | note | FREQUENCY: Each Lot
label | eac2e012-6b2d-5402-8f64-6cd10016897a |  | note | CATEGORY: HP
label | 70212c48-5100-57aa-bb4a-8acc42822287 |  | note | RESPONSIBILITY: Nominated Authority
label | 2fda8e62-91d2-54e9-9e7d-e11ae529f2da |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 7450adec-9d77-567a-87de-eaf70d9f64f3 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Concrete Mix
label | 28da9624-c447-564e-bf9f-622f482c7072 |  | note | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.05 (a), 703.07
label | 254fdd86-6150-5bc1-b96c-6879e98e2c60 |  | note | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
label | d52aa123-742f-5385-9eec-eb3959133ca1 |  | note | Footpaths (Pavement Type 7):
label | 6bdcb154-ff9f-5d81-be71-0dd1ba7b8183 |  | note | – Concrete Strength: 25Mpa
label | cb4906a3-cc93-5f2e-ae4f-a45e9a5eaa89 |  | note | – N25 with eMesh (Macro Synthetic) Fibres Applied at 5.6kg/m3
label | 7c7c6c1d-d5e4-5eb4-bda4-99f1d4381fa7 |  | note | – Min 30% SCM
label | a0139f58-f0b6-5ed6-b458-3a38e4f4cf07 |  | note | Industrial Vehicle Crossings (Pavement Type 8):
label | cc07f253-c5e0-5c28-92f9-1353f993e037 |  | note | – Concrete Strength: 25MPa
label | 35086c01-cd3c-56f5-8613-6b98951e093e |  | note | – Min 30% SCM
label | bd0ee2c4-cf59-5376-9e30-87a299c1f5f2 |  | note | Raised Concrete Median / Traffic Island on Remnant Pavement (Pavement Type 4)
label | 7e92a7bc-dd22-54b0-b747-280f2e702ab4 |  | note | – Concrete Strength: 25MPa
label | e6e73323-19a7-55a8-928e-30378c79223d |  | note | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
text | 946372ab-0bd1-5cd9-a449-5f166d846437 |  | textbox | Enter: Teambinder Material Approval number
label | 41c710d8-680f-5b40-9cae-b74dd80ca9b5 |  | note | METHOD: Document Review
label | ed52977a-446a-572a-b4e6-52e268640e14 |  | note | FREQUENCY: Each Lot
label | 0fe34eaf-987f-5984-a222-e39b77937e71 |  | note | CATEGORY: HP
label | 57bc92e2-48cc-5a20-b172-b6d2abc52486 |  | note | RESPONSIBILITY: Nominated Authority
label | e622c55c-f46a-520a-aa54-63b54bcd309f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 2bbabd10-d171-5ca3-b962-8cbe4d84de31 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Reinforcement
label | aeba8d86-584e-5bdf-b983-d2a81f10019c |  | note | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.16
label | 4a41a3b4-0778-562b-a3ce-38b87685afc2 |  | note | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
label | 24b0b3f2-3851-53cf-a633-512e390333bd |  | note | Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification) following steel mesh requirements shall apply as per IFC Drawings:
label | 74853313-2fe7-5bbb-a104-b71da40eaab0 |  | note | Footpaths (Pavement Type 7):
label | ba6faa57-8ad4-5c26-9a92-5c784e3d7003 |  | note | – eMESH Fibres Applied at 5.6kg/m3
label | 8407506a-5516-5b6b-b444-48c3815ae740 |  | note | Industrial Vehicle Crossings (Pavement Type 8):
label | 196f4e91-2a91-530f-a664-f4b98b1ef49a |  | note | – SL82 Mesh (Centrally Placed)
label | bfaf579b-2109-5a1d-95bf-3123d190b196 |  | note | Raised Concrete Median / Traffic Island on Remnant Pavement (Pavement Type 4)
label | a110d79c-0d70-59a4-a2c1-1a42b402830e |  | note | – SL72 Mesh (Centrally Placed)
text | 872d5ffb-3eec-50f8-a9e0-776fbd91cf0f |  | textbox | Enter: Teambinder Material Approval number
label | cce98823-40e8-514a-b035-dbe9ff5c1d19 |  | note | METHOD: Document Review
label | e7be3383-1415-588f-bdb3-89efbfbaeaf1 |  | note | FREQUENCY: Each Lot
label | 29c9019f-5cdf-5001-936a-e08fd6577592 |  | note | CATEGORY: HP
label | cae70c2e-a4fe-5564-b734-164bcc397fb0 |  | note | RESPONSIBILITY: Nominated Authority
label | 71a638d1-7d93-5c0f-a662-ad4c975497bb |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 81172436-12db-5861-bd30-c068bf93b573 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Evaporative Retardant
label | e0bc67a4-75f7-59aa-93f4-08b92379edf2 |  | note | REFERENCE: 703.09, 610.17 (f)
label | 157df81a-7417-5da1-a7cc-99736c109dc4 |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 033458a4-cb20-51d3-bba3-41c20be920d0 |  | textbox | Enter: Teambinder Material Approval number
label | 9c6da5dc-2f00-5f6c-8427-5dbe906651f9 |  | note | METHOD: Document Review
label | bfdb8ed4-5d7a-5450-8fa9-cd885737601d |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | bdf8798a-1ada-561d-bb21-9e8a5cc197d7 |  | note | CATEGORY: HP
label | 76b70af7-3c0a-5b77-a644-317078e7502f |  | note | RESPONSIBILITY: Nominated Authority
label | 1cecad8d-722a-503d-8b57-1768c072f4e4 |  | note | VERIFYING DOCUMENTS: This ITP
date | 154b377e-8e6c-5081-b879-ff9a95f0d243 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | f4290ab4-4d51-5da6-885f-9c9762371ede |  | note | REFERENCE: 703.10 (a), 610.23 (d)
label | cfdae339-2a7c-5f6c-b675-d4befe12f1de |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | 6e39f2b6-0e40-5b99-9503-2492e1838dc1 |  | textbox | Enter: Teambinder Material Approval number
label | c8dbff0b-5663-5dad-b3d6-0ec698a17c6b |  | note | METHOD: Document Review
label | 78f33c87-4cd8-599b-927b-f4d36183d432 |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | 740652f1-871f-5b34-89fa-01af76c012b5 |  | note | CATEGORY: HP
label | dfdda8e2-afc9-5a84-b01e-b8ea117198f9 |  | note | RESPONSIBILITY: Nominated Authority
label | 706fe65e-f8aa-5c3c-8eb7-1ff3991574ca |  | note | VERIFYING DOCUMENTS: This ITP
date | 4faa9e2f-3d74-57c2-8cd9-bb3b60d88b08 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Documents
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | fdb23812-ff5d-5104-b7d3-a4323220ec7c |  | note | REFERENCE: IFC Drawings MRP-BEC-TRANS-000131-091-CRG, 703.17
label | 86cc9950-68a1-5e57-bea7-b57f5040bb4e |  | note | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | dc900a2c-0aff-5bf0-930e-63a028bc70b2 |  | note | ○ The Nominated Authority will review and confirm the set out.
label | 6f37dba7-af1b-5b25-94af-de916550a73c |  | note | Attach: Survey Report
label | 33e25196-169a-5a91-88ee-4e2681c72733 |  | note | METHOD: Document Review, Measure, Visual
label | 4e7f1ac5-c8e9-5101-a1db-c89bfeecf0e8 |  | note | FREQUENCY: Each lot
label | 8e941e89-7122-50ce-a74f-e1977b124086 |  | note | CATEGORY: HP
label | 6d7cca15-f924-5756-b756-182ffcc9458a |  | note | RESPONSIBILITY: Nominated Authority
label | e5eb45f3-b6f3-5fec-b8e3-d3726d749de0 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | bdbf97fe-6fc2-5724-9a97-f0327111bffc |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Lot Map
label | 625340b9-8d5a-57f9-b48c-1f6ccc125822 |  | note | REFERENCE: MRPA Lot Management Plan
label | 8b6a14a8-31e4-52e3-a6b3-956696e3393e |  | note | ACCEPTANCE CRITERIA: Attach Marked drawing indicating the location of this Lot
label | a1c3f7a8-b252-5e01-a0d1-f4f11ad69337 |  | note | Attach: Lot Map
label | c94d35ea-d2ea-5f09-a53f-d4a6b19c6317 |  | note | METHOD: Document
label | 4b804730-c6c2-5c17-932c-0a8f09d8f6ed |  | note | FREQUENCY: Each Lot
label | 96e426eb-4fe5-5f0a-9715-3a7bcf3e965c |  | note | CATEGORY: HP*
label | 06cdc695-674e-5efb-8bff-e6c22d3f7261 |  | note | RESPONSIBILITY: SE/PE
label | 8914a7ee-0b5c-5e2d-a0d0-bb5f01575fe9 |  | note | VERIFYING DOCUMENTS: Attached Lot Map
date | 2aa9fc93-af00-5c45-be34-48f38cf9a068 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Site Clearing & Grubbing
label | ce39a6fb-0ccb-5caa-a719-3b473d7035e3 |  | note | REFERENCE: IFC Drawings
label | da420ed2-e538-5a91-bdfd-58bfc388ffe2 |  | note | ACCEPTANCE CRITERIA: If not completed during the site establishment, the work area needs to be cleared and grubbed.
label | 45cef61c-b56b-5abb-84e4-945f8956bdfb |  | note | ○ Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
label | 9e03eeb2-7c9e-5726-b7f9-c5484fbbb2db |  | note | METHOD: Visual
label | 565b6993-2882-57b0-ae0f-d944c6682847 |  | note | FREQUENCY: Where applicable
label | 560c0f89-79d2-5e4f-ae14-17bb8b1f96ac |  | note | CATEGORY: IP
label | 94efdd9f-5481-5474-a606-29bcca8ce2a2 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9b3bb9ca-d595-5222-b187-e46dd7d38822 |  | note | VERIFYING DOCUMENTS: This ITP
date | b06dec8e-148b-50be-b3d4-1223e7778dbd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 IFC Drawings
label | c53a93c0-42e7-5fa2-a489-25beee94ec31 |  | note | REFERENCE: MRPA Quality Management Plan
label | 7a657049-c397-5a01-b09d-76ac6c035c41 |  | note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
label | 6083128e-ddcd-56a8-b38e-3f89058f014d |  | note | – Using the correct and complete set of drawings
label | e636d3c8-5974-571a-8a95-a2474d5586ab |  | note | METHOD: Document Review
label | 8726facb-ad11-53ab-8ff0-ca8068fb3322 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | a1d11053-bf92-54fe-b01d-b7fd04e06abe |  | note | CATEGORY: HP*
label | 2e011b18-21c6-5f7f-bc3d-8e1dd4ebb62e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 76c04d81-6d38-590a-89c0-20810ac16add |  | note | VERIFYING DOCUMENTS: This ITP
date | cb9b0e9d-6587-5286-93f5-32f4a741f17d |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Excavation
label | c674d4e1-d380-5b1f-b448-34a646a1d0be |  | note | REFERENCE: 703.20 IFC Drawings
label | 2478dd2c-8f69-56da-b2b6-d59c658f71e9 |  | note | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
label | c439d0f4-bdae-5981-967a-d477b754e88e |  | note | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
label | 93e1d570-d31c-5ea1-ac9d-36e913822e99 |  | note | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
label | b8df9b90-9d90-5718-be33-df7bf6c0f75a |  | note | METHOD: Visual, Measure
label | 57e80157-20b1-5c86-a464-0d9e19bd19e5 |  | note | FREQUENCY: Each lot
label | 92fd1485-2f78-5ba4-8220-83271ca60660 |  | note | CATEGORY: IP
label | e453f4aa-4db0-5ed8-b7e5-8035ea6a65b9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d0f71159-d277-5439-ba71-6d81645f2fc0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 41c68ede-e99b-5cf1-9a9e-23e8dfbca874 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Excavation-Pavement Thickness Increases for Crossings
label | d7f8ca0c-b32a-550a-9b65-3b3faf02cdf9 |  | note | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | b7ba1034-002b-5247-8a81-88d7dccf8f9f |  | note | ○ Relevant Council drawings: CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | 97221ab5-49b1-5fa3-af77-ef03d3e53375 |  | note | ACCEPTANCE CRITERIA: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
label | 2479cb6f-ea53-5b18-8914-6e36af387db8 |  | note | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | 6251cff6-a9d2-5f99-bafb-b2246b60c391 |  | note | METHOD: Visual, Measure
label | fc8f6580-00e5-5a5b-b6f4-22febf72926d |  | note | FREQUENCY: Where applicable, each lot
label | abd138fe-5bbf-5a0d-8a75-d998bd064a86 |  | note | CATEGORY: IP
label | c85504f7-9c34-5b81-aa4a-9998d308b843 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4e837cb4-b0f8-5289-ad1d-1e9f039deb6d |  | note | VERIFYING DOCUMENTS: This ITP
date | e5dd5e44-fcbe-5674-89d2-66e6ef5bac98 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Bedding Material Placement & Compaction
label | 1d8471f9-d550-5387-9dc3-3362e27b2fbd |  | note | REFERENCE: 703.21 IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | ddea3e8a-ed92-576b-a462-87b3a7bedd51 |  | note | ○ Relevant Council drawings: CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | 8aa70893-c4fc-5ce9-bb87-aa06a445c4bb |  | note | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings :
label | f4869004-d160-552a-a508-d954a7f911ca |  | note | Footpath (Pavement Type 7) / Industrial Vehicle Crossing (Pavement Type 8):
label | 38344c9f-b943-58c7-9e16-ce2fc102f3e7 |  | note | – 20mm Class 3 Crushed Rock or Crushed Concrete
label | 5f0b9771-a0a2-59ff-8b74-afe2b98d4a9f |  | note | – Bedding shall be 50 mm compacted thickness
label | 10bc280b-0ec9-550a-9a75-439f44db4ab8 |  | note | Raised Concrete Median / Traffic Island on Remnant Pavement (Pavement Type 4):
label | 65de545c-3aec-510c-8e3f-f3b2a4f4d6f7 |  | note | – Remnant pavement in SGH or minimum 100mm Class 3 Crushed Rock or Crushed Concrete)
label | ab1c9d0c-0122-50a6-bfb8-013bccedb307 |  | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
label | bf4983c1-7e97-5cca-a36f-7250b03e8c85 |  | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
label | 2b6f498e-aabe-5ed0-9c9a-cb8c42c2eab3 |  | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
label | 231cf9f9-7e9e-5669-a959-c5ab960cdde1 |  | note | Attach: Bedding Material Delivery Dockets
label | 4431ec28-a9da-5e1a-a9b4-06a4968e6ba7 |  | note | METHOD: Visual, Measure
label | f00d7a03-dd7d-5ede-888b-ea0f410c1858 |  | note | FREQUENCY: Each lot
label | 80f626d6-9c62-5760-a913-20576bfc1fef |  | note | CATEGORY: IP
label | fc8a1c39-ccb3-53c2-ab2b-64050e898147 |  | note | RESPONSIBILITY: SE/PE/SPE
label | be819f7f-0447-5617-8d30-acb2fc2c70b2 |  | note | VERIFYING DOCUMENTS: This ITP
date | a2d22608-a460-59e9-b5d3-fe7aa09d8d48 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Compaction Testing
label | 1c802f9b-78a6-5abd-9d4d-7d7da39d1543 |  | note | REFERENCE: 703.21, 304.08 (a) & (b), 304.11 (a)
label | be607efb-d61e-5ea1-ab8f-63dd1961acec |  | note | ACCEPTANCE CRITERIA: Compaction shall meet the following requirements:
label | b7573a34-578e-5661-abdc-1635b0418642 |  | note | ○ Scale of Surface Level Measurement = Scale C
label | 3caf6532-bc85-51ad-9d33-973f8374b5ed |  | note | ○ Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
label | 58ead751-cb6b-5500-a825-4f6760637cb4 |  | note | ○ Mean Value of Density Ratio % (3 tests) not less than 100%
label | 2f126c6f-5998-5682-9b31-fba438a761cc |  | note | Attach: Moisture Content Test Results
label | e327a0ea-c1ad-51c2-b125-9e973317330d |  | note | Attach: Mean Value of Density Ratio
label | baec22a0-e1ec-5bd5-9952-f1010a02433d |  | note | METHOD: Document Review, Visual
label | d039e5f2-2b7b-5644-b3b4-93414173fc65 |  | note | FREQUENCY: Where applicable, each lot
label | 26fc2d65-2c5e-5856-b547-5c1c728a7ed2 |  | note | CATEGORY: IP
label | b8b9c6ba-8b9b-5d7a-8a4f-4bbcb23824b6 |  | note | RESPONSIBILITY: SE/PE/SPE
label | dc6c34b4-439d-5c7a-975e-af5e2fe07dff |  | note | VERIFYING DOCUMENTS: This ITP
date | 4e90ad11-d24b-5858-8946-df6a1574fefd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Formwork Construction & Placement
label | aadeb3a9-f38d-53eb-aa5d-1b6bc1c25239 |  | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.12
label | 9ae80755-80f0-54a3-be7a-708f24444420 |  | note | ACCEPTANCE CRITERIA: Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
label | d5322e46-d6fd-5afd-9ec3-8f044a4443c1 |  | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
label | 6bf5a9e7-2532-58bc-90e9-646b07d0b831 |  | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
label | ae8d077b-af6e-5b4b-901f-20c4707cfe11 |  | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | af066d6e-13cd-527e-93c9-86156f84c453 |  | note | METHOD: Visual, Measure
label | 7b0c79c6-4cd1-5c2c-a504-0fa8413430e4 |  | note | FREQUENCY: Each lot
label | 9b4a4ec0-bfdb-5e7c-ba64-e055006299b5 |  | note | CATEGORY: IP
label | 65a706e7-45f6-55cf-98d9-d7effb2e7c63 |  | note | RESPONSIBILITY: SE/PE/SPE
label | fea790b1-6686-548b-9f29-f0511bdecf35 |  | note | VERIFYING DOCUMENTS: This ITP
date | e4e7fb93-942f-5c5b-a807-ff45d2d7b211 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Construction Joints & Matching Existing Surfaces
label | 82de5737-6b1f-556c-8f01-674d2abc5815 |  | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.24
label | fe1adc32-37d6-574d-a5e1-0fbf279d22f2 |  | note | ○ Relevant Council Standard DrawingsRelevant Council drawings: CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | a7055fc3-f1d0-5d3c-84e6-1b2d694b813b |  | note | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
label | e0143f6b-ba3d-5bc7-a07a-f2d30a8169d6 |  | note | Consult the relevant Council Standard drawings for the joint detail, these may require:
label | 3ed44e56-4491-53ca-8a2e-2e464ef1463c |  | note | i. Concrete cutting of a shear-key
label | fa7e50fb-2dfa-5b47-bdd1-4340c85dac6b |  | note | ii. Surface roughening
label | e7d839aa-7aa7-55bf-ab63-f5cd6dd4c4d4 |  | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
label | 2f89ad39-69ed-5a62-a785-44194a0226e9 |  | note | iv. Cutting a groove for sealant
label | a29b895d-0fc8-5e6e-82e5-af9ea595642a |  | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | 87ed83f7-38d5-5751-920d-c8d5144ef191 |  | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
label | e1049e30-d594-5e0c-8334-f5bb81b1d250 |  | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
label | 1ed1f024-2d21-5ff8-acb7-01fcdf907b89 |  | note | METHOD: Visual, Measure
label | 8599e3ad-1e47-51c8-83c1-9fbd7d31b205 |  | note | FREQUENCY: Where applicable, each lot
label | 66b6d219-c378-5257-bde0-4f0c060a7681 |  | note | CATEGORY: IP
label | fd7d3294-2017-5aca-a408-4a0249e7c767 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0487b1d7-f38c-5187-8bd0-21848a74c1e5 |  | note | VERIFYING DOCUMENTS: This ITP
date | fa52de06-3b6e-524e-9b9f-26a9292da47e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Isolation Joints
label | acaa7cd9-8760-504d-84fd-3d9cb50f4d7f |  | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.26 (c)
label | f20dc6f6-d471-5ce8-86f1-7e89e1a200f1 |  | note | ○ Relevant Council Standard Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | 1caa3938-9114-502a-9390-01755c60b017 |  | note | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
label | 881e9128-dede-5772-bd1d-a18635e07882 |  | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
label | f08c67a5-ebe7-5fc4-b9f0-73c190db01da |  | note | ii. at any location marked on the drawings
label | c49839b4-e94a-5ab7-bf7b-4cdbdccff781 |  | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 7d08bc8e-f070-5da0-b079-53d09ed9eb0f |  | note | METHOD: Visual, Measure
label | 88b52edd-6545-54c8-a83a-955f9d05aa4d |  | note | FREQUENCY: Where applicable, each lot
label | 39afa697-8702-5c18-b8be-07194cf0aa00 |  | note | CATEGORY: IP
label | 5a9c6dd3-78b7-55d9-a3c5-1dc1cfe05a38 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 34d846b8-2fac-51bc-ab6f-18d4fc015691 |  | note | VERIFYING DOCUMENTS: This ITP
date | 40fb8294-4440-5462-9e03-87a72dfc854e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Expansion Joints
label | 66225ecb-5acd-5da2-bd29-2a6592d7a223 |  | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.26 (a) (ii) & (b) (i)
label | a8dcaf2b-ab1b-5b79-9bfd-5fa5613ccc55 |  | note | ○ Relevant Council Standard Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | e3a1fa8a-415e-5527-a7c4-4badcdbc7281 |  | note | ACCEPTANCE CRITERIA: Where applicable, expansion joints shall be placed:
label | b8534d2f-f209-5288-96b0-4a022aaac870 |  | note | i. on either side of vehicle crossings
label | 499a1af9-8f1b-5a98-af48-126840fe8075 |  | note | ii. at junctions with existing footpaths and shared use paths
label | c673b6bf-4d7b-585c-9a40-da16995309aa |  | note | iii. at junctions with bridges
label | c9feb0d3-8314-5c06-99d3-7b872eb3a7a6 |  | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
label | 6b2248a2-1c7b-5222-b0f4-aaea768c6280 |  | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 4d8bf207-d26b-5158-a787-7c220b183d5f |  | note | ○ Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
label | c139202f-9ba6-5170-a6a4-8618f116127e |  | note | ○ Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
label | 1779de7f-dcea-5555-8dbe-cada07fd8763 |  | note | METHOD: Visual, Measure
label | 070e311b-fc09-538a-a277-b3bf12d8a044 |  | note | FREQUENCY: Where applicable, each lot
label | b6fb170e-812b-5ab6-bcaf-b47a18e631d2 |  | note | CATEGORY: IP
label | ad22ca89-ed68-5997-b140-2c5470e0b188 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 519749e1-56d5-5653-9b44-ec8ed64159e3 |  | note | VERIFYING DOCUMENTS: This ITP
date | 69018f68-9650-5d25-bc2b-c75434ce83c9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Reinforcement Placement
label | 35e19cee-9d4c-591b-98d2-ef0a974a827c |  | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.13
label | af96dfaa-cb8f-5065-975b-124b4d8e1de1 |  | note | ○ Relevant Council Standard Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
label | 77b50c5c-1089-5358-af6f-29d4fed2dce5 |  | note | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
label | 4b8a60f1-9f78-5956-8bd4-07e136d808dd |  | note | Footpaths (Pavement Type 7):
label | b61ebcdc-0cde-50f7-8693-21c19bede4df |  | note | – eMESH (Macro Synthetic) Fibres Applied at 5.6kg/m3
label | 29b983b0-8cb0-5b6d-857d-18eee04752bc |  | note | Industrial Vehicle Crossings (Pavement Type 8)::
label | dcdb07ab-8058-5615-ad37-ef7855546884 |  | note | – SL82 Mesh (Centrally Placed)
label | 271ffa39-a9a5-566a-aa57-c6498324fbd3 |  | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
label | 27dadb88-2d12-50e8-b352-057f06e02bc2 |  | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
label | b7137be1-9eb8-5879-ad37-e9c7a3b5a4df |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | 86f48dc4-37d6-5110-ab61-17f15c92c463 |  | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
label | b60eda47-2dad-56d7-8064-9388891a1c5b |  | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
label | d19b05e3-a7a0-5f72-86e1-ee3db020a13d |  | note | METHOD: Measure, Visual
label | 849e53d6-5450-5155-875d-0c89ed6ab3f0 |  | note | FREQUENCY: Each element
label | 29dfa952-af42-5ce6-b9a0-ebfcae8b117d |  | note | CATEGORY: IP
label | 36d9c293-6be0-580a-9b83-299ab81f28c6 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 22b05c21-05d4-5bcc-8e5a-9c6b79a1121b |  | note | VERIFYING DOCUMENTS: This ITP
date | 1294f2f1-abd7-532f-a546-8acc70f29c9d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Pre-pour Survey
label | e372ce33-8923-5edc-879f-825e1aa2dd2e |  | note | REFERENCE: IFC Drawings MRP-BEC-TRANS-000131-091-CRG, 703.15
label | 91aac27b-1cc1-51e2-a411-b8fc826fbf9b |  | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor. Erected formwork and base layer within the tolerances below:
label | edf04979-a8ba-5b60-8f44-3d84a38b3ebb |  | note | ○ Departure from RL = ±10mm
label | 09e6a103-60f2-51ca-80da-7931f715e2df |  | note | ○ Departure from alignment = ±10mm
label | b98f08bd-ca9b-5c32-8245-2ce20603fdc3 |  | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
label | 9ab4ec1e-4e8e-514a-afa0-5d724d1a1f16 |  | note | ○ Irregularities in alignment = 5mm in 3m
label | dc2cbbb9-334e-5856-a863-84b589175789 |  | note | ○ Section dimensions = ±5mm
label | 1c05a738-7bac-59a7-84cb-7880e3193d00 |  | note | ○ Section dimensions (less than 25mm) = ±3mm
label | 05332485-3bf3-56d2-afbc-3074f52fbde4 |  | note | ○ Width of pavement = -5mm, +15mm
label | 71e3b615-078f-5c7b-bfc7-e50a7ea0e86c |  | note | Attach: Survey Report
label | 8f1260bb-c0fe-589f-9a74-aafef140d1d0 |  | note | METHOD: Measure, Visual
label | cadae1fc-dc51-56c0-9f80-5ca85944185c |  | note | FREQUENCY: Each lot
label | 78c041c7-73ab-5178-8576-0cb86915d6a1 |  | note | CATEGORY: HP*
label | 6fd8da17-ac04-52e2-a200-f2d9d483fc61 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 78e952be-cda1-5330-9217-201f2f990292 |  | note | VERIFYING DOCUMENTS: This ITP
date | f795ca23-9c4f-59f5-a1e4-8cbaefd897e8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Pre-pour Inspection
label | 34b3d9e3-3dd6-5cc9-a1b4-49aa87c170c9 |  | note | REFERENCE: Section 703.09, Section 703.21 Section 610.17a), b) & c)
label | 161d37ec-ada4-5f15-bb1f-12cecf971a44 |  | note | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
label | cd594241-2ce7-5f95-820a-3414c654851a |  | note | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | 214f1271-1fae-55c1-a8e5-476e1c003a79 |  | note | METHOD: Measure, Visual
label | 077b67ff-3137-5be8-aa6c-7081c1124ad5 |  | note | FREQUENCY: Each lot
label | ded009dd-73a8-5f46-815e-d1b1fd5cf1c8 |  | note | CATEGORY: HP*
label | f59373eb-a856-567b-8f0c-3c4d12290331 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a6b1fc1c-0eb2-5c26-a512-f799f788a50c |  | note | VERIFYING DOCUMENTS: This ITP
date | e5990b67-729b-5b27-8629-9d5490d3ed23 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Weather Conditions & Evaporation Limits
label | f6475b6c-5d65-5bf0-879f-a4de9afe72bb |  | note | REFERENCE: 703.09, 610.17 (a - f) Table 610.171
label | 74fc7209-8811-534c-a773-5e859fe98bc5 |  | note | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
label | beb6df1d-c57c-58e4-942d-53ad4afc8aab |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 345bd725-1d62-5b43-871f-868990607146 |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | b06337ef-b557-5eab-b28d-913f76788d58 |  | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 2eafdedf-2b7a-5a32-b358-3142f1e4f220 |  | note | Record: Required information on the Concrete Pour Record.
label | 178325fa-6a8f-5df9-8c95-2dcffc9ee663 |  | note | METHOD: Measure, Visual
label | 6604d31b-44d3-5fc2-809e-728273772ed4 |  | note | FREQUENCY: Each lot
label | dad1d179-4b66-5cd5-b032-3cbe2f5938ae |  | note | CATEGORY: IP
label | eb445298-81e0-5682-bf55-076d55be211a |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 2aad06ff-7bfa-5e5a-8cd4-8933a5706168 |  | note | VERIFYING DOCUMENTS: This ITP
date | fb0eee52-068a-5c6b-84d2-425451fba1f4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Concrete Testing - Sampling Frequencies, Footpath, Industrial Driveway, Traffic Island
label | 2f8eeced-b63f-5700-acb3-4ba9eba5b82d |  | note | REFERENCE: 703.11, 610.16 (b) AS 1379-2007 Cluse 6.2
label | 0bac76c8-7ab0-593e-88b6-9e6193ac08ff |  | note | ACCEPTANCE CRITERIA: The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
label | 3a24736b-cc5d-538c-bb66-f56a332720bf |  | note | ○ Correct quantity of cylinders manufactured per sample.
label | 85cc2aa4-e644-5bf7-aca2-bbdaa15cac17 |  | note | Record: Required information on the Concrete Pour Record.
label | 7e2c32fc-1e97-58b1-b002-6726637624d0 |  | note | METHOD: Test
label | 2ebb6602-0680-59e3-92a1-019e07e830e3 |  | note | FREQUENCY: Each lot
label | 66873bcb-9519-5463-a677-9501d2d36a63 |  | note | CATEGORY: IP
label | ffcf4563-f462-56f0-8834-0e10a467c46a |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | 8df0169d-4ee6-55d0-96aa-67e1c1c67040 |  | note | VERIFYING DOCUMENTS: This ITP
date | 89669457-23ce-5676-84c9-b0e1202db49a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Concrete Testing - Slump
label | 03cc68be-7d6c-51fc-8bf7-fea518ab6bb3 |  | note | REFERENCE: 703.11, 610.16 (c)
label | 0cb85eda-d6d2-521d-9f81-fee4fe7ccadc |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | e266a8db-eacc-58be-b262-4ac9c5362583 |  | note | <60mm = ±10mm
label | 3efa41e9-437d-5c63-9da6-36049ca75128 |  | note | ≥60mm to ≤80mm = ±15mm
label | e6f40b30-a775-564f-a760-e0b25706f16d |  | note | >80mm to ≤110mm = ±20mm
label | c811701c-a0ec-5dd0-a690-a2513422d0c4 |  | note | >110mm to ≤150mm = ±30mm
label | 45fa0b88-1c65-5315-83d8-9a894fffb029 |  | note | >150mm = ±40mm
label | 6f913174-e291-5099-8fe8-ca53adfcc775 |  | note | Record: Required information on the Concrete Pour Record.
label | 15c1bfcf-ae4c-5d24-b31a-af063ceb8024 |  | note | METHOD: Test
label | 344302a6-7627-5e6e-9275-90fc3e3868c5 |  | note | FREQUENCY: Each sample
label | 12581612-74d1-50e7-8295-e0513ef6c5bb |  | note | CATEGORY: IP
label | 6671bd60-90da-5373-91d2-e383cc51c44b |  | note | RESPONSIBILITY: Concrete Tester
label | 03eaaaec-bbe6-57c9-a1c8-889a4e5050ea |  | note | VERIFYING DOCUMENTS: This ITP
date | 53a341cb-f1e9-52cd-a880-258c8872be84 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Placement & Compaction
label | 33dc26a6-0c95-59e3-9217-ccc7cd7a655c |  | note | REFERENCE: 703.08
label | 9e0338c7-d68f-5ced-bfeb-d383cc58b3c8 |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | 7516cd2e-c7b5-5f9c-b817-4c726a0ae6df |  | note | ○ Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
label | a8e0b1da-55ab-5361-baae-2090929483ca |  | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | e1e41d1f-8d20-52ec-87f2-0b75b061324d |  | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | c9ca6130-b7b2-50d5-a226-9e9f2801718b |  | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
label | 632662b2-70e9-5615-8dc3-ed0d1eec47cc |  | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | 388540f9-8d24-5496-ab85-5acd1ec8a1de |  | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
label | ecc11998-9a8d-50a3-a4e8-5e430e819d2e |  | note | Record: Required information on the Concrete Pour Record.
label | 9fb18074-20b8-591c-bf38-233633f29217 |  | note | Attach: Concrete Pour Record
label | 477243ae-932e-53ca-af46-9fa92eb4bc74 |  | note | Attach: Concrete Dockets
label | 05b28115-65e2-52fc-a835-dd116fb33fbb |  | note | METHOD: Visual
label | f7fb0cb5-e5f0-568c-b108-5130b3943db9 |  | note | FREQUENCY: Each load
label | 5ad24efe-31e1-5ca8-955f-b8b47869fe95 |  | note | CATEGORY: SP
label | 8825fb70-5064-52b2-9696-fbf6449dfde7 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
date | cc64b45c-c6d1-52e8-a482-54dc98668596 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Surface Finishes
label | 3b404280-a40b-5489-b844-2e9aa5b76e7e |  | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | 3a9d429e-24b4-5808-87f6-42d88eb8ff84 |  | note | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B, 703.25
label | 280463a3-3b89-57d0-87bc-a282426527c1 |  | note | ACCEPTANCE CRITERIA: Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
label | 4c4badba-a492-5242-bd82-17d6cf7b2bf9 |  | note | ○ After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
label | ced06453-2aca-55af-8ee4-acd2a813f943 |  | note | ○ Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
label | f1d9f35d-497d-5a1e-8dcb-21aee89ae4fc |  | note | ○ All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
label | d0bae9e3-1b14-5046-a58a-aa218c7a7856 |  | note | METHOD: Visual
label | c9a60337-4f2f-5106-8fb3-ed278d153bb9 |  | note | FREQUENCY: Each lot
label | 222886b1-870c-5a2a-bd45-682bff260c5e |  | note | CATEGORY: IP
label | 611691cf-7c08-504f-a715-647f872179df |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 599f7bde-01fc-5cdd-9a12-52ca3ac150bd |  | note | VERIFYING DOCUMENTS: This ITP
date | a2243563-2c4c-569c-8f65-70c635e9c86e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Crack-control Joints / Weaken Plane Joints
label | 0195d76a-da36-51fb-88d3-3b091a87beda |  | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | e2dd8529-1a49-571f-88f7-358066eef8ce |  | note | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B, 703.26 (b) (ii)
label | d24d5719-135f-5fa2-a464-4e621f93e8c4 |  | note | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
label | a960b2ed-2bd0-5fa0-9460-583249089d8b |  | note | METHOD: Visual
label | d1227381-4b8e-54a0-a0e0-7d999d55ca33 |  | note | FREQUENCY: Where applicable, each lot
label | 8668d251-9b1b-5223-a894-f69f1ffd4a4c |  | note | CATEGORY: IP
label | f599f4fa-29a1-50da-8186-964b9dc23f5d |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | fe720b4d-2a13-5b67-a4f9-1ea5bd1c81ad |  | note | VERIFYING DOCUMENTS: This ITP
date | 64a9e453-5e3f-5c6a-a446-97a208f85b98 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Curing
label | 882ecb4b-1635-5cbd-a063-3392f8e24334 |  | note | REFERENCE: 703.10
label | bb0c55e9-fbd0-5c55-8ef2-7e3b3ecc86a5 |  | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | 7eb4610d-e62c-511b-86b8-5e69e6f746f5 |  | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
label | f0506576-8eaf-5385-8b43-d0a1f70f74fc |  | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
label | d837d132-ff9f-56f1-bd2f-14e45c4c78a5 |  | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
label | b7e13689-beb9-5b12-9667-118fe4bb1e2d |  | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
label | ef04f531-7ac2-5b37-97b2-57ee8e8e39dd |  | note | METHOD: Visual
label | 18f65b6d-e168-550c-aaa2-04ec22a62b4e |  | note | FREQUENCY: Each lot
label | 7c1ab2b1-6b1d-5349-9d24-4336abb05cec |  | note | CATEGORY: IP
label | 19de72d6-013e-5aea-ad35-0cace25033ea |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | cf1e6376-26cb-5fb3-8a58-a29b19826f9c |  | note | VERIFYING DOCUMENTS: This ITP
date | 91c650bf-b904-5e2d-a0dc-83c748819fbf |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Crack-control Joints / Weaken Plane Joints
label | a68aa0ac-b5a3-51b9-a9da-a7288b1e640f |  | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | faeef5fa-43d7-5db8-9345-0b71041d1f32 |  | note | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B, 703.26 (b) (ii)
label | c3477859-daf9-58cb-9c16-708b4ac0bfcc |  | note | ACCEPTANCE CRITERIA: Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
label | ad839319-1beb-5727-95e1-3f9448e3234b |  | note | <20°C = within 24 hours of finishing operations
label | d193052a-a6b3-5583-9924-f84508d89c76 |  | note | ≥20°C - 35°C = within 4 hours of finishing operations
label | 60cdd52a-7f64-554e-b6f9-bf1dac324bc9 |  | note | METHOD: Visual
label | 5826da7c-1a6c-5616-a526-74c92a954821 |  | note | FREQUENCY: Where applicable, each lot
label | 220992d0-46ba-517a-b302-bff71682f0bc |  | note | CATEGORY: IP
label | 14bba591-6430-56d9-9d4e-55c6aabb098c |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 8a74f785-1dc4-5bb1-9971-733008de6d93 |  | note | VERIFYING DOCUMENTS: This ITP
date | b54e73e5-9432-5fe1-8468-cb7e791de982 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Protection of Newly Poured Concrete
label | d8e6ecba-ca80-5f30-b579-222213a9b614 |  | note | REFERENCE: 703.27
label | fa00d0bf-a33e-5141-8630-bfb5164a9390 |  | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | c1392798-a49a-582c-a2e1-9cbd10186da0 |  | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | 285c6209-05cf-5177-a6fc-8023d1987c6e |  | note | METHOD: Visual
label | d4f542c0-1156-51df-af3b-7ec734d2fd30 |  | note | FREQUENCY: Where applicable, each lot
label | 4db25502-7fbf-5dd5-bb34-de208f7ea17c |  | note | CATEGORY: IP
label | 121aa3e4-2940-5390-9ac8-b2ed3ff16c05 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 152e2e7c-7997-5f16-bf22-d7c22ee38048 |  | note | VERIFYING DOCUMENTS: This ITP
date | 10f37618-d665-51ee-ab5b-8ff32c9a9d93 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Stripping Formwork
label | 487b8993-5cc5-5656-a263-3e3a61f85a5d |  | note | REFERENCE: 703.12 AS3610 Table C2
label | e65ecd02-bdb1-5f05-9821-907f8ab8729f |  | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | e71b3d27-e9e9-565c-be20-409cba057fba |  | note | i. 2 days for vertical formwork on external surfaces; and
label | 9e57a27d-86c7-5da4-b5a4-da6ab7287dfa |  | note | ii. 1 day for vertical forms on permanently hidden surfaces
label | 52eadf41-24a2-576a-b0ca-ff7202701971 |  | note | METHOD: Visual
label | d5fb040a-5354-5800-af31-5e0767ef520b |  | note | FREQUENCY: Each lot
label | c7cb76af-ba44-5841-bc08-d04f22ea644a |  | note | CATEGORY: IP
label | 98c4372b-0637-5ef4-9e62-5a3ae49a65c2 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 55d7eb1c-55c9-5f42-854f-8aa734c08740 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1f466dd8-8f4c-58ff-99aa-31602d188705 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Backfilling & Pavement Restoration
label | 4f9876d9-3c7c-520d-b114-a5c20734bdf7 |  | note | REFERENCE: 703.29
label | a91b9264-a5a4-5317-ad10-824474be37c0 |  | note | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
label | cdf9ca87-b742-59b0-95ea-c492bb7c150e |  | note | METHOD: Visual, Measure
label | 4467d8ae-aa15-5b1a-a685-7a8b6f444d2e |  | note | FREQUENCY: Each lot
label | a38b90fc-d0d8-517d-aa12-3641d160ca06 |  | note | CATEGORY: IP
label | 76b2ef3f-f9d7-5a62-9866-bf3836a085ff |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 458d740e-9204-5803-bfaf-3d6dde672f8f |  | note | VERIFYING DOCUMENTS: This ITP
date | 9b506ea7-f3f5-5cd8-9710-1625ecd8fa53 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Surface Inspection - Cracks
label | 6d49261d-0657-5b81-8d1e-841ad8533278 |  | note | REFERENCE: 703.3
label | 9accbd90-a2de-5067-8714-7aaec9e78215 |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
label | 0ecab4a8-8538-59ea-bb47-f84e3c361abd |  | note | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 8a7e1752-801f-5a0f-86a7-87d799407704 |  | note | METHOD: Visual, Measure
label | 6bca73c3-bd71-5320-84c4-1c6ab4d9f019 |  | note | FREQUENCY: Where applicable, each lot
label | 8c4a4aa3-51f6-5d08-9612-5213d6588fa5 |  | note | CATEGORY: IP
label | b73f6b96-c587-595f-99e6-a74a91d22085 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 04de9326-8b7e-5ce5-abf3-489cea109f7b |  | note | VERIFYING DOCUMENTS: This ITP
date | 60033343-a573-51ca-a491-a5fa8f206ed6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Surface Inspection - Surface Finish
label | e96e7eb5-fa35-5466-bdb7-a6b1a01e53f8 |  | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | 7b5e101f-d5f1-5163-b01f-1b590c69bb53 |  | note | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B 703.25, 703.10 (a) AS3610 Clause 3.2
label | b09c4f4e-3108-581d-beae-3345554f9d67 |  | note | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
label | cc70f582-00c2-5a49-ba0d-c4f4dedbd2cf |  | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
label | 573b8066-4c4e-5789-a382-eeba19da54a2 |  | note | Class of finish:
label | 0eda494e-d311-5ee6-a363-07ad2a59ad5f |  | note | – Permanently hidden surfaces = Class 4
label | f3880f4e-66b6-5e5c-896c-400de43b7cf0 |  | note | – All other surfaces = Class 3
label | 18367678-9917-5958-9adb-7d7b9c8f39cc |  | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
label | 5c8fb5c1-c52e-5ee0-908a-0a9e6bca3ab7 |  | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | 154dbaf4-2057-5371-a851-8e547c85b82b |  | note | METHOD: Visual
label | bf4b0b50-b9c2-57ee-939a-203eac70650e |  | note | FREQUENCY: Each lot
label | 29b15251-d73f-5273-be7f-57767cf0986c |  | note | CATEGORY: IP
label | 0fd52cc4-9c20-5d3f-be5f-4d298da9d715 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7c90356c-3dde-583d-9ebc-b7f9909aadba |  | note | VERIFYING DOCUMENTS: This ITP
date | a04b5809-6e79-54c2-804a-69461618166a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Compressive Strength Test Results
label | 2d42bdc0-7b17-52f0-a229-fef1a843a34d |  | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
label | bda3c81d-1958-5e5a-a570-56ccb2d2dd99 |  | note | ○ Relevant Council Drawings 703.11 Table 703.111
label | 2fafc145-fd99-51ef-ac4a-474283764c94 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | fcb83308-a792-5303-8c70-797e26fca304 |  | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 12c4ead0-6e74-5c22-ba72-2ec45f8a1790 |  | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 0c4722f2-0a25-538f-878e-2bd1e6f67eed |  | note | Attach: Compressive Strength Test Results
label | c16e3d5a-56ba-5fef-8f32-6ceb423c20ce |  | note | METHOD: Document Review
label | f333d0e1-09e1-5e77-a187-1113e37c967c |  | note | FREQUENCY: Each cylinder
label | dee714bc-1dae-514c-a4be-b0aa160b364a |  | note | CATEGORY: IP
label | 8c1c6ef6-b24b-5d94-a94a-07b434e9fa07 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 21b32fca-8eba-5d89-8933-54c5e1fbc898 |  | note | VERIFYING DOCUMENTS: This ITP
date | c1510746-e393-5fee-ae0f-f83e9bdb0b34 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 As-built Survey
label | ba18835b-6782-5a83-84c2-a5e7dc9f33c5 |  | note | REFERENCE: IFC Drawings MRP-BEC-TRANS-000131-091-CRG, 703.15
label | b8af119f-4998-54f3-95a1-5d6e8923dfe4 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | e06d94e0-1b05-51d6-af2a-9aa28b613bb0 |  | note | ○ Departure from RL = ±10mm
label | 85bac33e-2633-5f7b-a0d5-3d5daf80ac4d |  | note | ○ Departure from alignment = ±10mm
label | ea7bc43c-0e98-5754-b8d9-ed191522a383 |  | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
label | a2447aa3-7b10-530c-9804-0f6256aaf52c |  | note | ○ Irregularities in alignment = 5mm in 3m
label | 6055e5b1-d575-5976-a237-d12525792989 |  | note | ○ Section dimensions = ±5mm
label | 286a090c-1a6a-5355-abd4-13011a6a957e |  | note | ○ Section dimensions (less than 25mm) = ±3mm
label | 14b9b6e6-fe87-5dc7-a3f6-b76f95e115ce |  | note | ○ Width of pavement = -5mm, +15mm
label | cd6d0576-feb2-545f-869d-089a44daacc1 |  | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
label | 62abe951-1199-52c8-b561-9630fa316249 |  | note | Attach: Survey As-builts / Survey Report
label | f073bf9a-c0cb-55c6-ab9a-278f6c12fc51 |  | note | METHOD: Document Review
label | 65634999-508f-5be5-8f5b-9636cec2db79 |  | note | FREQUENCY: Each lot
label | 31045f43-b94f-5c52-b3b8-6ac7f001fbf0 |  | note | CATEGORY: IP
label | 7dc6d0ec-7f3c-5cc6-a278-497cce67e624 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 47534e5b-e4bc-5d18-a399-55bb057916e3 |  | note | VERIFYING DOCUMENTS: This ITP
date | bfc98a56-10ea-52fb-9e05-fbd516bc10a2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Non-conformance Report (NCR) Closure
label | 26fbfc30-51fe-5077-a439-610a238f45a5 |  | note | REFERENCE: MRPA Quality Management Plan
label | 480a0648-ac1b-5c2a-b9b8-b8c7dea54bb4 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 53c41841-6afc-5a84-b653-f1823486ba90 |  | note | METHOD: Document Review
label | 8c4075ca-daea-5c03-8d11-0d7b3008ce07 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 51a4141a-6fbb-54e8-b8aa-55ee1cb08b91 |  | note | CATEGORY: HP*
label | 4950726d-0c8d-5afe-9d44-4d9ffdd91cd3 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 92b199bc-40e8-5f05-a7e1-43c53f765334 |  | note | VERIFYING DOCUMENTS: This ITP
date | 4a2c931d-d685-53ef-a3f3-66e4b52a5f4f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 211ea329-8dd6-5591-ba80-206e853c55f7 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | ac80d955-7b75-528a-a09f-03451ebc45fd |  | textbox | Name:
text | d7e42e08-e351-5f1d-8750-ba0a7dee0be4 |  | textbox | Position:
date | cbab8dc8-7f87-586f-a693-aefc1acdbc10 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-081-STR-PSDS-Bored Piling | itp |  |  |  | Yes | ITP-081-STR-PSDS-Bored Piling Rev 0 | c2c09775-4839-4e2b-8cb4-bbe36522d05b
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | f326ddb1-4792-54d0-ba31-cf7b86b25b48 |  | note | Document Title: ITP-081-STR-PSDS-Bored Piling
label | 93dd001b-4332-52c7-9ec6-7771fb765776 |  | note | ITP Description: PSDS-Bored Piling
label | 8d3c26e6-c501-5daf-a411-cb64f9e30cfa |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 2a5ad82d-b9d7-521c-8ede-9939d8174138 |  | note | Discipline (e.g. CIV/STR/RAIL): 081-STR
label | a53bbbc5-02cd-56ab-9d8f-e2784169b6d1 |  | note | Revision Number: 0
label | 48c990fd-ab84-561f-a450-c0ada065505b |  | note | Revision Date: 7/12/2021
label | 14bf47d3-4ca6-52d8-9ccb-634e169bacb4 |  | note | ITP created by: Mathew Velcek
label | 34c58b80-46f7-55ce-b2de-15279b0b33ef |  | note | ITP approved for use by: VM
label | 94a1dc9d-c92e-5556-8e57-9c4c8688f55f |  | note | 1.1 Non Dependent
label | f0865b7b-b478-563d-b6b1-c7f44d47f1e4 |  | note | Reference: VicRoads Section 606 July 2017
label | 449db959-4367-5731-b00e-50dd2ef7a7ce |  | note | 1.2 Non Dependent
label | 650b3a57-e9b9-530b-a0ee-2a1b5e6bef4c |  | note | Reference: VicRoads Section 610 Feb 2020
label | ec91a4d7-6905-58e0-95ac-e12699c941b6 |  | note | 1.3 Non Dependent
label | b9481284-bf61-51ab-a2b5-15e2cfccef66 |  | note | Reference: VicRoads Section 611 November 2018
label | 472ef902-18ef-54ff-91a3-4a17658ec531 |  | note | 1.4 Non Dependent
label | db480f1c-ef99-5526-b732-2c25ba5d25da |  | note | Reference: AS2159-2009
label | 1bce4b83-4cf1-5341-a540-1f27d774c2a3 |  | note | 1.5 Non Dependent
label | 21034320-ccf7-51b2-b1d6-3ad6b95fb205 |  | note | Reference: AS3810.1 2018
label | bf8e0e88-e499-509c-866f-d7a1135c6bcc |  | note | 1.6 Non Dependent
label | 087ec198-e6bb-5b2c-9d75-c2d838867e67 |  | note | Reference: AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 82678dbf-ab85-5475-b2f1-b730830b0419 |  | note | REFERENCE: 610.07 Table 610.071
label | 657d8f62-b731-5d9f-a670-75ecd5c02119 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | a3ee4bd1-6b54-571d-aba2-10f0f5f1cdd9 |  | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | d14c6d8a-3f5c-5cb5-88d4-26e2fc8ec385 |  | textbox | Enter: Teambinder Material Approval number
label | c73cadd2-303e-5e91-abe0-2c8df6aa792a |  | note | METHOD: Document Review
label | b9a920af-7d03-5a4b-8b50-ae5eea953211 |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | e6d52e13-7264-5277-99ff-3a6833ef2320 |  | note | CATEGORY: HP
label | a57062ee-db59-50ad-843d-d8512edf2890 |  | note | RESPONSIBILITY: Nominated Authority
label | aa00c048-1820-5fdb-aa66-bd00430aba71 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 5149354d-8155-538d-a6ab-a2b35e46d827 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | f75194de-5b83-5301-98a2-63667b253e98 |  | note | REFERENCE: 611.05 (a)
label | 7b2f4671-38e7-557d-9ea0-12fdb7b76b86 |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | 27aad95c-cee6-536b-803c-e755fb93db6a |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | db64d243-76ab-5f33-adcb-8a559679df97 |  | textbox | Enter: Teambinder Material Approval number
label | 478df3ae-294e-5f53-b55e-76277771a827 |  | note | METHOD: Document Review
label | 99b98f88-bd85-5dcf-a8c4-916093448cd4 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | 2c3b8f4f-7f1a-53d2-a864-e1e4c7d7633f |  | note | CATEGORY: HP
label | 44fe3b88-6b3f-570f-819b-d178afbd23ad |  | note | RESPONSIBILITY: Nominated Authority
label | 12249fa8-b3c7-5668-a13b-4478ff422f0e |  | note | VERIFYING DOCUMENTS: This ITP
date | 9107f57b-b5b9-55e9-ac0b-d063304f81d2 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
label | 48353566-d1ea-5ead-b8d5-b7f31734636c |  | note | REFERENCE: 610.26 (a)
label | 4bae30bf-219e-5642-b57c-c63bc699b541 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
label | cb41ea81-5f99-5711-b6fb-9b6cdc95a719 |  | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | a25afb7f-934b-5db9-a695-bc8b2d2c912a |  | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | fb4c1f08-f307-5c60-9abb-e7d75ec14b24 |  | textbox | Enter: Teambinder Material Approval number
label | 45c115b2-b18f-5c12-997b-b781e058e731 |  | note | METHOD: Document Review
label | e8e33c27-c9cf-5ffe-adcd-4db454b2bb0d |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 1ac17c1a-15ed-5582-8d90-4013c247ecf0 |  | note | CATEGORY: HP
label | 1275826b-5005-5083-a53d-24326058c8a5 |  | note | RESPONSIBILITY: Nominated Authority
label | 7dcbd13a-2143-5753-ab4a-f06079a6bb34 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5fbad56b-6caa-50d8-9130-5de5abb3c823 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Working Platform certification
label | 7744db66-00fc-5b1b-8f5b-471978d4ef25 |  | note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement
label | ba941438-487d-5577-b095-338486a968fc |  | note | METHOD: Document Review
label | cbbc55f0-46d0-5abb-b6b8-cd8c1c0ebf6c |  | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | 4d135f49-557a-54ae-8150-0fe511febcf7 |  | note | CATEGORY: HP
label | df9890fa-09d8-5640-a181-27de3a28b1d5 |  | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | ed5d7bf7-97f0-5040-a122-70eb35d46bb6 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0757e3f8-4be1-56b8-a442-99a9b20fae6d |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Piling Operations Work Procedure
label | aa48faff-59bb-5b4d-809d-2a87719821a3 |  | note | REFERENCE: 606.03 (a)
label | 32b79a1d-3094-5198-9896-c5c2b52f0067 |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | d6b2b9c4-52ea-5c5c-b742-3bfe19952a64 |  | textbox | Enter: Teambinder Approval number
label | 6c0dd415-7138-512a-aacf-5de1228302f8 |  | note | METHOD: Document Review
label | f0ba6001-a576-5093-9fd0-6bde9e0156a6 |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | 132a54e1-ec1a-504b-9359-a83fd72b6bfc |  | note | CATEGORY: HP
label | 0c563ecc-5bcd-5331-8a75-d1225c97baf8 |  | note | RESPONSIBILITY: Nominated Authority
label | 9e7a93ed-321a-53ea-89d3-f79b77de2a39 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 33eb915a-8655-5888-8102-158abd0ece8d |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Temporary Steel Casings
label | 8cd584d2-403f-518c-b09a-8ce518451601 |  | note | REFERENCE: 606.03 (b)
label | 38697f73-c1c5-5f18-b66f-3d5749f3411c |  | note | ACCEPTANCE CRITERIA: Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | 54466cce-663c-5dfc-a03a-0b4aba32d253 |  | note | ○ Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | 7b5aacdd-73da-5fa9-bc45-64a165e1a309 |  | note | ○ The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
text | 3252a745-900d-5740-9df1-38983dace3e3 |  | textbox | Enter: Teambinder Approval number
label | b1875357-1120-50f4-aeae-31dce7f50210 |  | note | METHOD: Document Review
label | 5efa2bee-ff4d-5547-b5ef-f254c71c55fe |  | note | FREQUENCY: Where applicable, once, prior to use
label | 0e05d688-fb3e-5324-9566-baeea8cda2fe |  | note | CATEGORY: HP
label | 4960618c-5c88-51e4-bd56-150ef164f0d6 |  | note | RESPONSIBILITY: Nominated Authority
label | a02e0b1a-aa97-5d87-9ba6-43e38556d194 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8d0549f7-ae75-59be-94ea-c562f8ef9813 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Casting Under Water Procedure
label | 8e3b80e7-4c61-5b85-94b0-31f0aca3e49e |  | note | REFERENCE: 606.06 (a)
label | f7c0d83b-0197-5d06-af3f-555d07fafefd |  | note | ACCEPTANCE CRITERIA: Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
text | 0e6bc281-eedb-521b-8a05-b5a3fe2ec5b3 |  | textbox | Enter: Teambinder Approval number
label | 3a367a99-00a4-5504-ac3e-e173a793d562 |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 9c127f07-0b37-5ad0-8ecf-00681e6b47cb |  | note | METHOD: Document Review
label | 7d4bc386-4cbd-50c2-8600-9fdcafd5e708 |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | 691ca531-1168-574e-92b7-5cf006fefe2c |  | note | CATEGORY: HP
label | 757ca6bd-b6ae-5e75-b3bd-2fd56395f114 |  | note | RESPONSIBILITY: Nominated Authority
label | cf2bc7d7-667d-5688-8312-571cee818575 |  | note | VERIFYING DOCUMENTS: This ITP
date | 80b9daba-a833-559d-b5bd-3df779ed53a8 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Boring With Bentonite or Polymer Fluids
label | 1d885dba-5211-54a9-b37a-9a423b636891 |  | note | REFERENCE: 606.03 (c)
label | 64b397b6-c1f2-5ba9-835e-c2f1c2b18769 |  | note | ACCEPTANCE CRITERIA: Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
text | 057aca05-cc1a-53af-b208-5eb5e1e4b4a6 |  | textbox | Enter: Teambinder Approval number
label | 7aef41e1-5887-596b-8e36-f46209189226 |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | e2ed7f50-ff43-5b9a-976e-a167a17e1ff6 |  | note | METHOD: Document Review
label | 62527ce2-483e-57d2-9a4f-2644974962eb |  | note | FREQUENCY: Where applicable, once, prior to commencement of boring
label | f9c85ff2-4871-584a-8951-018223536bf4 |  | note | CATEGORY: HP
label | 7ddd2017-5a38-57ba-bf19-b82ff32b1230 |  | note | RESPONSIBILITY: Nominated Authority
label | 6cc70316-85c7-5005-88f3-035916a96647 |  | note | VERIFYING DOCUMENTS: This ITP
date | f99bd3b7-e7c2-5170-a1a8-369ee29146a8 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Dynamic Pile Testing Procedure
label | 27443ea4-867a-5bc2-80ed-1d2f622c25d1 |  | note | REFERENCE: 606.07 (c)
label | ef3ff52b-9e51-5c97-aeda-810232d0983a |  | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | 7dc07aef-4ee7-500d-a7ce-d389e7dfa849 |  | textbox | Enter: Teambinder Approval number
label | ca09eaf5-c926-5ca9-956f-c59374f30819 |  | note | METHOD: Document Review
label | a4c35d64-179b-5ab2-b351-d1f584b44c50 |  | note | FREQUENCY: Once, prior to testing
label | 7ea67c41-7c5b-5825-a01e-da3a4b2a2440 |  | note | CATEGORY: HP
label | a1426721-8b4e-5d38-b4a8-128b98fddd8a |  | note | RESPONSIBILITY: Nominated Authority
label | 7ddf1563-88cc-54ed-9f0f-3d5ccabb9971 |  | note | VERIFYING DOCUMENTS: This ITP
date | 70e765b0-f3a3-510b-873e-4fe86441c21a |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Pre-qualified Pile Testing Consultant
label | c46a8e19-e45c-5869-9c35-388203f1cdf5 |  | note | REFERENCE: 606.07
label | fd47a797-3d5e-58d3-9c7b-25df5d1d93e6 |  | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | 0bc90919-0b28-5433-abd6-689ced1c8663 |  | note | ○ Details of the consultant to be submitted for review to the Nominated Authority.
text | db722084-b21e-5314-a18f-6e5c9c7936c8 |  | textbox | Enter: Teambinder Approval number
label | e741b5e1-3f6d-527b-aaf2-24c5718ac441 |  | note | METHOD: Document Review
label | b6de5653-6172-54fc-8dc8-239c99e8b38f |  | note | FREQUENCY: Once, two weeks prior to testing
label | 828c06e2-8752-5391-9cb6-6287fdcceb3e |  | note | CATEGORY: HP
label | 5cdc2f28-eb2d-5819-be9e-5b68125cae5d |  | note | RESPONSIBILITY: Nominated Authority
label | 8a0ae626-ba00-5680-86b9-a033b329fbdf |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 4147cf34-01bb-5728-92ef-d7102c67e599 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 Reinforcement Welding Specifications & Qualifications
label | 772bd7d4-b513-5622-b23d-4a54a5f0fc8e |  | note | REFERENCE: 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
label | a35ed773-c46f-55ed-b306-2363ee871a1a |  | note | ACCEPTANCE CRITERIA: Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
text | 29663543-a2a4-5e0f-b80f-a3fcc4465822 |  | textbox | Enter: Teambinder Approval number
label | d0da2f48-3e0f-5720-a2f8-1ad6ed9f1e61 |  | note | METHOD: Document Review
label | 3efb9e61-c4bd-5542-81b9-88bb085e37c7 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | 93496a8e-3d4f-5376-860a-1bd69b939336 |  | note | CATEGORY: HP
label | cab223d4-bd75-56ed-9f48-eac29a813431 |  | note | RESPONSIBILITY: Nominated Authority
label | 706ca335-ced9-5d50-a67c-4e7a13a160eb |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 10b05633-5762-5cce-b8d1-5ce20ce62c81 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | d96364c2-871b-5ed3-8cfb-f3486557b281 |  | note | REFERENCE: MRPA Quality Management Plan
label | a594099b-e63b-5ac9-be02-511a5a5daa42 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | b9de2857-63c8-5e40-bdc9-fe307bfb4a96 |  | note | METHOD: Document Review
label | 4f7b7f23-3afd-512b-b479-f18b38a0fe47 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 6bd6c086-9b9d-56a8-b97c-1acc3a770b06 |  | note | CATEGORY: HP*
label | 6c2e8731-f488-595e-acef-5e3abe9ee621 |  | note | RESPONSIBILITY: All
label | 9592842f-c65e-5f34-83cb-6f4e428ffe20 |  | note | VERIFYING DOCUMENTS: This ITP
date | 728af4b2-29f3-5f10-af54-7274cdc2ef03 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | a3207bf1-e9a8-5aea-be68-46363ad1924b |  | note | REFERENCE: IFC Drawings 606.08 (a - c)
label | f1fe569a-cb4d-5339-a480-b02eb855677a |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | b14944dc-5b04-5b83-b241-f9b507321e72 |  | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | 725620b2-4885-5a38-af88-e016ba66887e |  | note | METHOD: Measure, Visual
label | 5c0125e8-4398-5fc8-809a-22c3f2149460 |  | note | FREQUENCY: Each pile
label | e5181657-d31e-52a8-af72-4a8a3cdcb72e |  | note | CATEGORY: IP
label | f9a16679-d99f-594e-b3d9-4046a1459336 |  | note | RESPONSIBILITY: Surveyor, SE
label | 97d54947-d385-5f92-9b54-b214e89b90d6 |  | note | VERIFYING DOCUMENTS: This ITP
date | dad3c509-1aef-5884-ae13-e467052e2f3c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | 6e3e94df-460c-58f7-8696-1bb1691a47b4 |  | note | REFERENCE: 606.04
label | adee33fe-90c3-5c50-af6b-435b479f3303 |  | note | ACCEPTANCE CRITERIA: Pile construction shall not:
label | 0a8ebb80-f8b5-52ab-8278-3dc48d468faf |  | note | i. result in damage to adjacent newly cast piles due to ground vibration.
label | 8b2fea53-31ff-55d8-a659-ffff3a1a40c8 |  | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
label | 5d18f1a9-037c-53c0-bffa-8c6a5a110748 |  | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | 6988391c-4483-5eb3-bb79-842437d54edd |  | note | METHOD: Measure, Visual
label | b4b54985-e36d-5b59-a987-95223fabe34b |  | note | FREQUENCY: Each pile
label | c1f06a99-9130-512f-87e2-33726c3026f8 |  | note | CATEGORY: HP*
label | 2840bef0-31ed-538a-9859-2b6b11063187 |  | note | RESPONSIBILITY: SPE/PE
label | ef8fba63-f847-5852-95e2-9b8d346a6f5a |  | note | VERIFYING DOCUMENTS: This ITP
date | 11f17f0f-e73f-55f7-812f-4b5716e70395 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Boring Operations
label | 2270728e-c812-5a07-812c-cb8f0f1f3b29 |  | note | REFERENCE: IFC Drawings 606.03 (a)
label | 12fd69b4-b536-564a-a0e6-b734412b7c96 |  | note | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | 587f6e68-784a-538e-85e2-7ee02ea495ec |  | note | ○ Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | 462acc74-809c-5a4e-a92a-a3586db05be5 |  | note | ○ Excavation clean and de-watered (where applicable) for inspection.
label | f57e5441-32be-5bbb-b850-523bba6d86ae |  | note | ○ Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
label | e78b7950-f9bf-5645-bced-23c7ba803c0e |  | note | ○ Excavated material to be disposed of as appropriate to maintain a clean site.
label | 144c0c75-4644-5bae-ad92-3a2e409e0e64 |  | note | METHOD: Measure, Visual
label | e956eca6-a83b-594a-a7a7-068908792320 |  | note | FREQUENCY: Each pile
label | df2e1df7-45e2-5fb7-97ab-2d23ebfc13e2 |  | note | CATEGORY: IP
label | 3e45adc9-6ecd-5f50-9708-d87dc4722654 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 24b16ed5-c1da-50eb-959b-baf09cf88418 |  | note | VERIFYING DOCUMENTS: This ITP
date | 531134d3-c58e-51c4-a5d8-b02cc8d643fc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Extension
label | 2daa278c-51ba-510e-9a38-35f41600aba5 |  | note | REFERENCE: IFC Drawings
label | 01aff162-0ee1-5b49-839c-62606d16394a |  | note | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
label | e12327d7-72ff-55ab-9b00-6ab21293d953 |  | note | METHOD: Measure, Visual
label | 4a856d57-fb59-5ce2-a5e1-5fa2aad41f6b |  | note | FREQUENCY: Where applicable, each pile
label | 70c4d11f-6f9e-5b75-b22a-82761a699174 |  | note | CATEGORY: IP
label | 7508389f-962b-5e39-8280-d9c832434b8c |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | e2c5eb3a-15a2-5546-bd21-253095b81d40 |  | note | VERIFYING DOCUMENTS: This ITP
date | b216e0ca-d42b-5b09-8586-72617a0ae831 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Inspection of Pile Excavation
label | 5cd3c8f4-f2ca-5c1f-9200-372ca5388c7d |  | note | REFERENCE: 606.05
label | 419e63e4-cb67-51e9-818b-31174c9e8d7f |  | note | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | 6327e892-7366-5fb4-86c6-2e493020dce7 |  | note | Attach: Geotechnical Field Sheet or Report
label | bb2eb868-8080-5a2e-9b21-de3197247be8 |  | note | METHOD: Measure, Visual
label | c8433d71-dffc-55b9-a496-a28b8f752b94 |  | note | FREQUENCY: Each pile
label | 6be27d44-1316-5a31-9628-251ec80cba10 |  | note | CATEGORY: HP
label | 6b420364-5ed8-5bca-ba16-4d2ac4549eff |  | note | RESPONSIBILITY: Geotechnical Engineer
label | 5b8fe170-6a30-59ec-8770-d9720da9e764 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | f073e05e-9f61-52fa-9798-fd5a448b165e |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Reinforcement - Placement
label | 451f57ec-e641-57fd-b949-e1c604d74b6d |  | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12, 606.06 (a)
label | 8cd7f5d9-dae6-51d4-aee2-dd3fe6b5e052 |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 43803fc4-166f-564c-bdc3-d954144dd84b |  | note | ○ Projecting reinforcement is the correct length and location.
label | 987b341a-e714-51c1-99ab-21343c0c971d |  | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | f9c7ce27-589d-5af3-a4c0-d7aeefd8911d |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ebe4a2a2-ffd7-56d7-840e-64d900528514 |  | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 62ba4ef5-9cee-5c7d-a73b-de88cb43133a |  | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 97208176-362d-5e84-af31-f1353fdd76dc |  | note | METHOD: Measure, Visual
label | af62d5da-3275-5377-83e2-416b92aefac4 |  | note | FREQUENCY: Each pile
label | d5afecbb-e208-5198-9764-8c99860cebfe |  | note | CATEGORY: IP
label | ae84ca09-fa3c-551e-90dc-4cb950ee85b3 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 8b4a87ec-fd4f-57fb-bc47-0281a945bf00 |  | note | VERIFYING DOCUMENTS: This ITP
date | d766edf9-cb9b-5756-bd3c-795ddf3e7d96 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement - Electrical Continuity
label | 8a2f7572-799b-55cb-9854-7e6b2c689cd1 |  | note | REFERENCE: IFC Drawings 610.29 (d), 610.43
label | 6505e994-9643-511d-bccf-e7127d92ec8f |  | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
label | a6efc339-530b-52b2-9b47-268bbbd8dda6 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 3d69fa71-7f57-5d1d-a9e3-8da2316e43fa |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | e552ff4a-4286-5aab-b75f-fae66b76dd5c |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | f2bb27f6-6227-5ac5-877a-ce77f2bed94c |  | note | Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | a9e34c88-2c9f-5901-9e3c-e75669bec05f |  | note | Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | cae3c22c-5fd3-50a8-81e9-93cf073f5e17 |  | note | METHOD: Measure, Visual
label | dc3a0fd3-890d-5fef-8b39-5d7702cc8916 |  | note | FREQUENCY: Where applicable, each pile
label | ede5e1ac-f2db-52c9-8178-9da7029455b5 |  | note | CATEGORY: IP
label | 947c5288-28a3-5b6b-a1d2-e3de8a04d1e1 |  | note | RESPONSIBILITY: Earthing Engineer, SE/PE/SPE
label | 31793175-5a30-58c2-b33b-c3be1ae38810 |  | note | VERIFYING DOCUMENTS: This ITP
date | 93a3b0cc-dc28-558b-b49a-17237ceea546 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | e256df11-37ab-514f-bec3-dd4c2f850c80 |  | note | REFERENCE: IFC Drawings 610.46 (a) Table 610.462, 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
label | 0b6f8a5b-1753-5b87-a41f-fb2579727ff3 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | d5678c3e-c6b9-5c4a-831e-2c1727043e0c |  | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 056f245f-3cd2-50c8-bd5c-bbdd7c896297 |  | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | c4d0a5a2-fe9b-529f-8bcf-54a3e67a8ac4 |  | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 2ea4d951-5a14-5172-819a-afba6773ca33 |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | ad8be45d-375f-507b-aefd-ae31c879ca03 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 14617339-0ee5-579e-af53-f78f02933541 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | eb9d5054-4cd7-52ae-b509-821813e2d26d |  | note | iii. Ducts and conduit location = ±12mm
label | 9c7fb907-3503-5cc4-a0cf-a9ce2f33c122 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 6a97b748-5d1a-5ea0-8739-a8bf3d2dcb3c |  | note | METHOD: Measure, Visual
label | 11b31d9d-c9c1-5022-b386-f8656e31b0cd |  | note | FREQUENCY: Where applicable, each pile
label | dea0d236-c5aa-579c-bfb6-864e3c39437a |  | note | CATEGORY: IP
label | 3016c6c5-8315-5ab4-b360-f504369a8623 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | c6b7d356-ea42-53ed-afeb-2d9b59712bc6 |  | note | VERIFYING DOCUMENTS: This ITP
date | a383da06-cdf6-5f22-b7ca-03509b82a57d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pre-pour Inspection
label | 2559bda8-cd1a-5dd2-b20c-114a7ef4cbf9 |  | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
label | 8816c2f1-ab6b-5f2e-8e80-b041f308f893 |  | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 77eb3055-c4de-556c-a9f7-186c45583f10 |  | note | ○ All foreign material has been completely removed from the excavation.
label | 7a822bf3-340f-5550-8e20-95c348912cc7 |  | note | METHOD: Measure, Visual
label | 3bd439b8-7034-5192-b03b-fba994f16581 |  | note | FREQUENCY: Each pile
label | 56fca8fb-f97e-5a9e-b4a7-4bdfdd9efed7 |  | note | CATEGORY: HP
label | b6cd2ccd-ee35-5a34-9562-0760b0e749bb |  | note | RESPONSIBILITY: Nominated Authority
label | 0690b574-55e8-55a0-80b1-0eaacf6d1d71 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 283b7315-5abd-5590-b5ec-d0cbdc76481b |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Weather Conditions & Evaporation Limits
label | 09d36b95-dc69-5a44-8978-82abe9910005 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | ddbcb0c1-132f-50b6-821a-ced79b16a416 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | ffc87719-808b-58a5-b415-a3176878ad38 |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | bc315877-ab6a-5a5b-92da-100f049f5ecd |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | dab41219-8c4b-5b5e-9328-ba7e507aeed9 |  | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 5d76e5bb-ecb6-5bed-acff-5fe341454167 |  | note | Record: Required information on the Concrete Pour Record.
label | e954c18f-c6f8-5da6-9f9e-9dd6e557ec3b |  | note | METHOD: Measure, Visual
label | 9df3e87c-be0d-5b78-909c-68ba133c9d1f |  | note | FREQUENCY: Each pile
label | 939241fe-73cb-549d-b9c5-f5eeec0d8695 |  | note | CATEGORY: IP
label | fe4c5a97-3df7-5b32-8703-6e2f6dd1a71b |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | eaccba3e-5e0b-539c-9e76-5b76dc8e8383 |  | note | VERIFYING DOCUMENTS: This ITP
date | 94ab64b2-d047-5515-bcde-b03401a1863c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Sampling Frequency
label | f7c0e158-8602-54ad-a61d-7b1fb8b49ab0 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b) Table 610.161
label | 1a5d7799-d675-543e-9721-3aec50e7bc6a |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 5e8355b5-18f3-50e1-8feb-8eebc62f7193 |  | note | 0m³ to 10m³ = 1 sample
label | 546f921b-654c-54be-8d13-038841d1be2e |  | note | 10m³ to 25m³ = 2 samples
label | ec83ac58-dd20-5522-9832-947889ef0cfc |  | note | 25m³ to 50m³ = 3 samples
label | 28dc1cce-652e-519e-8b49-483fa5669992 |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | fda1e5f6-2a41-57cd-8400-28bd658fa7de |  | note | ○ For each additional 50m³ and additional sample shall be taken.
label | 91b7c070-d50b-5b84-a84e-013ae3fa1d23 |  | note | ○ where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | 05293a22-07b4-5c0e-b6b7-e2679ba46fb5 |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 513a2cb9-a5a2-5ee4-b235-078c488061f4 |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 5d9754b1-21fa-5f59-b18f-8f8ed4b03e25 |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 6153f30a-f868-529c-bb85-3506382a2bf7 |  | note | Record: Required information on the Concrete Pour Record.
label | 9ffb957c-ec7e-5b75-b7d3-ae2f40ea9103 |  | note | METHOD: Test
label | 7f496865-2d2b-5b36-b8d9-ef1f5089918a |  | note | FREQUENCY: Each pile
label | 0de2bc4e-b2a4-5c24-a68c-690c25f42624 |  | note | CATEGORY: IP
label | cd366c9b-a06f-5443-aa48-aec6f7e63f15 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | db6553ee-e595-5237-9455-4f07f7b685c9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 01127d29-8a90-568b-88bd-3b1bbb60aa7d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
label | 9717e5af-0616-5c3b-a404-d770e2a2758e |  | note | REFERENCE: 610.13 (b)
label | bdf10e67-53d2-560d-9f2b-8245eb6c9108 |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | 9ab529e4-fbdb-51d2-9f44-cef8001357e3 |  | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | ded3da3f-55fc-5608-93da-02f209b0f6c7 |  | note | ○ Passability = ≤10mm (aggregate height differential)
label | 95c3bab1-e29a-57f4-95f1-405ef0eef587 |  | note | Record: Required information on the Concrete Pour Record.
label | a5756e7c-c483-58e6-850d-0fd4900bae2e |  | note | METHOD: Test
label | 69cabe36-8d5a-5288-8d6b-65615dc13037 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | c1330993-72ef-54ad-9451-d9c6cc3e2ada |  | note | CATEGORY: IP
label | b587bcb3-a118-513c-9101-cfa21b2e572a |  | note | RESPONSIBILITY: Concrete Tester
label | 839f03d6-f146-5ac4-8ee2-d3001cfeca53 |  | note | VERIFYING DOCUMENTS: This ITP
date | 13a45fb4-1a4f-57de-ac6a-3f7337133274 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
label | 14dfa034-4b61-5c93-a22b-f0e5452fc115 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16
label | 960654de-d4e6-510b-b1c4-8e7405f04281 |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | d8429a5e-b0c2-59d8-abae-6dd54380dcec |  | note | Record: Required information on the Concrete Pour Record.
label | 2fb0ddcf-3f45-52b3-bfe4-194db169b65a |  | note | METHOD: Test
label | b4036952-acfd-570f-a04b-edb85c4c1dce |  | note | FREQUENCY: Each sample
label | c5a452e4-4f38-5878-8252-c740ec2cc2a8 |  | note | CATEGORY: IP
label | 326794e8-68af-55ce-8b75-d009898902ac |  | note | RESPONSIBILITY: Concrete Tester
label | 1a25bbbe-f252-5bbb-893c-73151cd1ea75 |  | note | VERIFYING DOCUMENTS: This ITP
date | 81912e31-b4a6-5f08-9950-fc79c85fd2d9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
label | b38e4860-0ea4-5d49-91d0-955e1b3620b0 |  | note | REFERENCE: Piling Quality Procedure 610.18 (a) & (b), 610.18 (d) (i), 606.06 (a & b)
label | fcfe4fea-5c53-5423-b8df-f3d6726a341d |  | note | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | f3e3abca-eb99-5bcb-8eee-4ab21cf70906 |  | note | ○ All concrete batches are traceable.
label | 2a19af8d-dacc-55d1-81fc-e76f7aa71e15 |  | note | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | 21082d24-cadb-54ca-858e-e7fc86e88d05 |  | note | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | afd5c334-86c8-57ae-a162-22f28eca6666 |  | note | ○ The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | a5737527-6007-5c45-b7ff-62b78ce87625 |  | note | ○ Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | 3e2c083d-1394-5432-9adc-ff99a9c17b58 |  | note | ○ Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | 474912b6-892e-5a4f-ae93-47c9a236d2b5 |  | note | Record: Required information on the Concrete Pour Record.
label | 4deb65c5-f1d1-5130-a06b-ff8d4141dcd9 |  | note | Attach: Concrete Pour Record
label | 66e81d02-0074-50e8-b6a9-57cba6ef2287 |  | note | Attach: Concrete Dockets
label | 1de19c9c-af93-5d0d-a3c5-8d53f393268c |  | note | METHOD: Visual
label | b55b5756-89f8-540f-88b2-d04ab7282545 |  | note | FREQUENCY: Each load
label | ab06549e-badb-56ea-9e63-2e5b304d5a2a |  | note | CATEGORY: SP
label | d6b3a27a-6a26-573b-9eff-61f737cd6192 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
date | b39518e0-f702-5bf8-90ef-3a362657e279 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes
label | b80cc77b-f475-5df5-b8ab-d985e947e77f |  | note | REFERENCE: IFC Drawings 610.31, 610.20
label | 9569bf39-7f89-5e17-ae58-bc748653bc7e |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | d4635bc6-bcd3-5207-927a-183f89ebb3e4 |  | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 907447d0-6f45-5ae1-adaf-6fa5f5588c97 |  | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 3c0cb462-8b38-53ae-a0be-4814a7823c2b |  | note | METHOD: Visual
label | 49027dce-c153-52f6-9ea1-1c576a7a1a3d |  | note | FREQUENCY: Each pile
label | ed84d3a7-ae5b-5b90-96a9-b7c5c39f4ebf |  | note | CATEGORY: IP
label | 5d046493-982f-56b2-9524-8891f0c35d08 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | d0307dbe-371d-553f-8494-cab2144c68b2 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6628bac5-02d6-5dcf-a685-bfca24e8e389 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | 1f5e83ce-63d7-5b65-9985-530e3e87ab14 |  | note | REFERENCE: IFC Drawings AS2159 Clause 7.2.2 - 3, 606.06 (a & b)
label | 72c492a6-15b9-5bb3-8846-a094e196594e |  | note | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | be91a28d-d1bd-507a-b655-5618260ccc50 |  | note | ○ Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | cf0c018d-a203-5c3b-bcab-ca8990e4ab16 |  | note | ○ Any weak or damaged concrete shall be removed back to sound concrete.
label | 5274eb6c-ecb1-5f77-84db-f49044110b2d |  | note | METHOD: Measure, Visual
label | 08dbda93-8be9-5587-b63b-1030062ec733 |  | note | FREQUENCY: Where applicable, each pile
label | 1f39d61f-8297-5eb9-ae87-5b2357c65420 |  | note | CATEGORY: IP
label | 89e17810-136b-5e61-b6ac-8cc859ab13fb |  | note | RESPONSIBILITY: SE/PE/SPE
label | 87063104-25d4-525d-8ae5-c3d5ceb44317 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9b7f46fe-ff6d-5487-bea7-e6fda5605edd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | a4b3d289-8a57-55dd-9bff-bae2e3d505b1 |  | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
label | adb80a7a-7918-535b-8670-e4c434f15288 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | f086bcd4-7bf6-5190-8df6-642cf918c0c3 |  | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 48a7eee6-15e0-5c8b-96a6-42561d2fd310 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | a3cf1abd-253e-5d8e-a6e7-3594d84e8c7d |  | note | Attach: Compressive Strength Test Results
label | 983e1d9c-dda5-56fc-b1c2-609712e50dca |  | note | METHOD: Document Review
label | 20aa5e45-9ed6-574f-bd73-26e65fec30cf |  | note | FREQUENCY: Each cylinder
label | e4778b40-f5de-5932-80d2-a51e6df19033 |  | note | CATEGORY: IP
label | 67e304d7-62cb-51b7-a88d-f54bb21482ac |  | note | RESPONSIBILITY: SE/PE/SPE
label | 42e094b7-921e-5bfe-82d4-1e5cbadc81c3 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3fd8283a-fbfe-5860-9d0c-79686e85fcc6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 94db05cd-c982-5262-b41f-042b1b6f0bfa |  | note | REFERENCE: 606.07 (a, d & e) AS2159 Clause 8.8
label | d6de77cf-45a2-5f57-b710-e7c6ca230000 |  | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | 6cb23655-1e08-59c7-9ba5-2404225741f6 |  | note | ○ Cross-sectional area = ≥95%
label | 4ffa1241-a68f-54c2-8844-e90227c574d3 |  | note | ○ If any test fails, all piles shall be tested.
label | 4e262d49-2a09-5194-8641-33d89d7e99b5 |  | note | Attach: Pile Integrity Test Report
label | ffd5025a-fcf9-54f9-ba6b-5411da9f73b7 |  | note | METHOD: Document Review
label | c6f799f3-8537-5058-9d64-c8f83b8eca02 |  | note | FREQUENCY: Piles #1 - #6.
label | ab184c6c-4383-5316-92c9-5309666a09ae |  | note | ○ Reduced to 1 test per 3 piles if the first 6 tests pass
label | d6fb1087-e0ab-5671-83ab-28c2bf4a6d39 |  | note | CATEGORY: IP
label | deae3f0a-71cd-5948-a5b5-c054130f3b64 |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 6781f3b6-6eee-5f0e-9877-a5819a140a59 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0e64d149-c17c-5bc8-8957-283eed0478ef |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Static Load Testing
label | 50492801-6045-5fb6-8a8e-6b670730a8f1 |  | note | REFERENCE: IFC Drawings 606.07 (b, d & e), AS2159 Clause 8.4
label | d6c3eb3c-ffdf-5fb1-9c6b-87c593deb1f8 |  | note | ACCEPTANCE CRITERIA: Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
label | f4e82e0c-e87d-5ece-aa5d-d32496f063eb |  | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
label | 79fd0dba-facb-5c6b-a28b-a49ce00c093d |  | note | ii. Creep rate = <2mm / log cycle of time at the test load
label | 1b1721c7-c888-56ce-bf43-43cbccfcf9f3 |  | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
label | d21cd3c1-0028-565e-94a8-ce30cd45162a |  | note | Attach: Static Load Test Report
label | aa89e497-5168-59bd-a9cd-1b0d3b5bfc1a |  | note | METHOD: Document Review
label | d3edf817-6406-5914-8aac-a72a597fba2e |  | note | FREQUENCY: Where applicable, as shown on the IFC Drawings
label | 1a60dda5-7612-58cb-ad1c-022793f2b2bd |  | note | CATEGORY: IP
label | 498fe558-082e-594a-a3b1-576b30b02378 |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | fbd9d725-a93b-542d-97c5-f318a47020c3 |  | note | VERIFYING DOCUMENTS: This ITP
date | f77738fd-b49c-528f-b3c2-663777f9e91d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Dynamic Pile Testing
label | dc08357e-847d-52c3-9d6f-3fcba5f3c3b4 |  | note | REFERENCE: 606.07 (c, d & e), AS2159 Clause 8.7
label | 7e17bfa6-7286-5c7d-895f-34ef43a5d6a5 |  | note | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | 37189798-8b28-514b-8cef-a5b4c2ae0c2c |  | note | ○ Measured Ultimate capacity = ≥ values on IFC drawings
label | df8e36d7-ceca-51c4-a5a5-f8bca887ab6f |  | note | Attach: Dynamic Pile Test Report
label | d785e235-47fd-5ab5-b3e8-d19a8f87ac9b |  | note | METHOD: Document Review
label | 81e14007-c823-5ded-ba2b-83a73a3d49a9 |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
label | 17661caa-d7fd-5105-b44a-88645b1d998f |  | note | ○ At least 1 test per 10 piles
label | 4f9f605c-c70b-5beb-a83b-82114ddea7ba |  | note | CATEGORY: IP
label | 91a8f50c-aa7f-51cc-bcc5-a440acd6e880 |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 61976b1d-bd2a-5476-8a25-0b7751079dfe |  | note | VERIFYING DOCUMENTS: This ITP
date | 8c8e6f15-bd4f-52c3-a22e-f0feb0b1e861 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 As-built Survey
label | ad29f10b-2ab6-5df8-af68-269645c0ff9b |  | note | REFERENCE: IFC Drawings 606.08 (a - c), AS2159 Clause 7.2.2
label | 7b02c025-9035-543b-8a14-13d7d89f1852 |  | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | 9318c57e-50bf-54a7-bf1d-f256815292fd |  | note | i. Pile head plan location = ±75mm
label | 77785c0a-5841-5d79-ae33-eeaf4c76236a |  | note | ii. Variance from vertical or rake = 1:100
label | 76e02fef-848b-56ef-96df-6f8a9ae9ff6d |  | note | iii. Irregularities in straightness = 1:100
label | 11f33dcb-ee1e-5297-9a52-c82ecac09529 |  | note | iv. RL = ±25mm
label | 37fa4614-dbd6-553a-97aa-6b6354fdb1f0 |  | note | Attach: Survey As-builts / Survey Report
label | 9d61e835-c8f9-52f6-b8a5-56dcde5d3fce |  | note | METHOD: Document Review
label | 276cca9d-90e3-56bb-896b-76c5ede469c2 |  | note | FREQUENCY: Each pile
label | 3dde48fa-08b6-5395-9094-ad17b98464ee |  | note | CATEGORY: IP
label | 86ac65c3-5b7c-5425-8398-6a3e79cf5c79 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | f85992bb-57db-5418-b6b1-60353a797478 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8a52ef6f-a1e0-5e17-a7a5-f7783bc73fe1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Non-conformance Report (NCR) Closure
label | 90a14310-9f38-54e6-9302-13bdb7a95beb |  | note | REFERENCE: MRPA Quality Management Plan
label | c05f8a5b-5124-5088-b373-88aadd279b39 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 3d3e40a1-51ad-5fe0-869d-045238a2fe08 |  | note | METHOD: Document Review
label | d7aced71-9a6b-5862-8754-dea2b0409ce8 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | c077ae9f-a429-5019-8819-54dddced5f5f |  | note | CATEGORY: HP*
label | 0ef65c01-7ee1-5c6f-bd27-4dc5ad9866d6 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a07997ff-29ee-5d5d-8379-d9e0228e9978 |  | note | VERIFYING DOCUMENTS: This ITP
date | d5db49aa-ff33-5255-b7be-71f6e2a9027b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 54b94864-4847-5111-9b1a-ee995b5b6da0 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 6867b7cb-683e-5cd2-838b-4f661720bd38 |  | textbox | Name:
text | 0b346b4b-87d3-58b0-a474-55920c864a96 |  | textbox | Position:
date | a8977d35-9736-5652-93a0-e60deb46d849 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-080-CIV-PSDS-Stormwater Drainage Supply & Installation | itp |  |  |  | Yes | ITP-080-CIV-PSDS-Stormwater Drainage Supply & Installation Rev 0 | d2268e3a-e814-48a3-9e21-a432edc88fa6
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 600c2332-b412-5fd7-b2f3-70f27e67fbba |  | note | Document Title: ITP-080-CIV-PSD-Stormwater Drainage Supply & Installation
label | d362aba9-4c79-5e3f-a516-aaa1d8de4e10 |  | note | ITP Description: PSD-Stormwater Drainage Supply & Installation
label | 9ac38935-e2d3-5217-a29c-a775e4f0e8c2 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | c70f1f63-3516-5874-8d70-64704ddda9a5 |  | note | Discipline (e.g. CIV/STR/RAIL): 080-CIV
label | 42283c48-dcff-59e2-9de2-bef5c4e091e6 |  | note | Revision Number: 0
label | 90e853be-7d07-53e3-8615-37c12d4df467 |  | note | Revision Date: 5/12/2023
label | 9e446fdf-be4c-50bf-9bf6-ab488827c709 |  | note | ITP created by: Victor Mira
label | ee8ddc47-b786-5167-ac0f-c7c9730080a1 |  | note | ITP approved for use by: Victor Mira
label | 8c623ed3-a667-56f0-b9ed-0432e62879ad |  | note | 1.1 Non Dependent
label | 6a93b4a5-491d-51e2-9e90-367b2d58e276 |  | note | Reference: VicRoads Section 701 (May 2020)
label | 0916ed94-2703-5264-aa9b-d100f4bd1fe0 |  | note | 1.2 Non Dependent
label | 2c5d66e8-a3cd-51cb-bc23-6de400310eec |  | note | Reference: VicRoads Section 705 (June 2021)
label | 9b7beb45-f68a-5c54-a1cc-8d78d97cfbbb |  | note | 1.3 Non Dependent
label | 18f8e8fb-6096-52da-9352-18c011edcec2 |  | note | Reference: IFC Drawings
label | c699c219-f237-5183-af39-880507346d57 |  | note | 1.4 Non Dependent
label | 0d16cd4f-0c37-5d04-8d65-a4137c47061b |  | note | Reference: CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
label | f82663dd-b80e-5e1b-a8a9-eb37e3cce4b7 |  | note | 1.5 Non Dependent
label | 5d29125a-6c99-53f5-a886-08c0cd81908f |  | note | Reference: CHK-002-CIV-Stormwater Drainage Pits Installation Rev 0
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Drainage Reinforced Concrete Pipes (RCP)
label | d7ae0d3d-24f7-53e9-bf1b-e66ca886557d |  | note | REFERENCE: Section 701.04, Section 701.05, Section 701.09
label | 25710082-d7ee-5d48-a16c-7dc4a3d5f81a |  | note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and Sections 701.05 & 701.09
label | e4bd7a22-e2b4-5d67-b6ec-5e800302c891 |  | note | ○ Precast reinforced concrete box culverts shall comply with the requirements of Section 701.04
label | 689dc06a-6647-54b1-8bae-2e6b5d0e29a5 |  | note | ○ Rubber ring joints shall comply with the requirements of AS 1646
text | eefc6907-5a3e-5660-bc34-871d0361b09c |  | textbox | Enter: Teambinder Material Approval number
label | 1f492c15-37ac-5770-91ec-037b6149c8ef |  | note | METHOD: Document Review
label | cc2e8367-ce73-59c6-a965-8d8b33c23a69 |  | note | FREQUENCY: Each lot
label | 163efa54-0b92-5674-ba35-b661bc945394 |  | note | CATEGORY: HP
label | ae847fc2-0fa0-5141-8ae5-c82109cbf3a8 |  | note | RESPONSIBILITY: Nominated Authority
label | b195a6b4-6a1a-5b91-a2ee-e72e7606e657 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | d5c5b447-f0ba-56fb-b2af-f6490e1506d3 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Drainage Flexible Pipes
label | 88481045-e553-531b-9b3c-d58a7a39d026 |  | note | REFERENCE: Section 701.08
label | ae5070c3-175b-57f4-9527-4ce453870078 |  | note | ACCEPTANCE CRITERIA: Flexible pipes shall be supplied in accordance with 701.08
text | c4969ba4-7d6b-5f59-9ce9-1640cb8a989e |  | textbox | Enter: Teambinder Material Approval number
label | 1099b183-df55-5ce9-96f7-8834077c0cfd |  | note | METHOD: Document Review
label | 612cb6cf-1287-5643-a25c-83d31d93c32f |  | note | FREQUENCY: Each lot
label | a69ac451-d166-5b35-81fa-54d929d980d1 |  | note | CATEGORY: HP
label | 7a212fd5-2ce5-5477-99e1-babee1ad100e |  | note | RESPONSIBILITY: Nominated Authority
label | e881ab87-bd6a-5460-af5f-5d4fa1a6388d |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 69bf56ec-0a34-5cd9-bb92-7ffe3bb76d3e |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Precast Drainage Pit
label | 966312e7-a515-57e8-a5d5-29095d4cedf8 |  | note | REFERENCE: Section 705.07, Section 705.04, Section 705.09
label | 819858a1-2ca2-544c-8568-6cb9cfa99108 |  | note | ACCEPTANCE CRITERIA: Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
label | 1e046086-2698-5ed2-8ee9-fccca3b1d5ff |  | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
text | 39edd419-85d0-5671-860f-3cd1343b6f48 |  | textbox | Enter: Teambinder Material Approval number
label | 39b0ca6c-38f4-5606-b981-a3f6fe291fda |  | note | METHOD: Document Review
label | 3bfc8c2e-b4eb-5555-8686-39a40ef0d448 |  | note | FREQUENCY: Each lot
label | 11fd2d47-d8e9-5f11-b7eb-90c720dc88e6 |  | note | CATEGORY: HP
label | 8421d591-efe5-5586-9709-1a5a6c6b8033 |  | note | RESPONSIBILITY: Nominated Authority
label | 98405887-1716-5e25-91c6-2cb7e5d7c22f |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | e7139071-ba45-53ed-a4f8-d513e8547ae1 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Cast in Place Drainage Pit
label | 0c3686e1-92de-5681-9c11-3960e0f3b26c |  | note | REFERENCE: Section 705.06 IFC Drawings
label | a5209a94-fcca-5530-8d12-efc3ccada8f4 |  | note | ACCEPTANCE CRITERIA: Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | c80b10e4-c298-52a5-9a23-fa5d805bdb29 |  | note | METHOD: Document Review
label | 5b871556-0895-5855-9e7f-4a29a2820fcc |  | note | FREQUENCY: Each lot
label | a251024f-e4dc-50f7-982f-ebc250cc7fbd |  | note | CATEGORY: HP
label | f9707f52-8bdf-5425-8407-a880cfe6a84a |  | note | RESPONSIBILITY: Nominated Authority
label | 2b178c73-fd08-5ec2-9100-06fecd26eccc |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 042347a1-a8de-5717-b104-34a491db63b4 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Drainage Pit - Step Irons
label | 7af73ace-45be-5815-af00-e2fe386e2f59 |  | note | REFERENCE: Section 705.04, Section 705.12
label | ba9a20de-beb3-5dfe-9655-0bcefd2acdd2 |  | note | ACCEPTANCE CRITERIA: Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | 0895ea75-8b5c-56af-9c9d-441942c06906 |  | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
text | 8720890f-c959-5436-89da-8f405be4fa41 |  | textbox | Enter: Teambinder Material Approval number
label | 821c79a9-9226-597b-b9e3-6d186bc95e9b |  | note | METHOD: Document Review
label | 59ed9799-0fb1-5b58-b1b1-28461c4f8209 |  | note | FREQUENCY: Each lot
label | c66d90b4-75e3-5a96-b988-1ab9baa4e7f1 |  | note | CATEGORY: HP
label | 37fef470-574b-58b5-aa6c-d4f293cf2700 |  | note | RESPONSIBILITY: Nominated Authority
label | 62a06a1f-4422-547f-b09e-167c2e19ef42 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | d250de2d-dbc6-5c6c-a8a4-ff7c86ec4e44 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 Drainage Bedding Material
label | 4cf4620c-e213-5269-a0cd-bf628fb0eb32 |  | note | REFERENCE: Section 701.09
label | edd5287b-ad8f-52f8-b25c-8ecc6b39e718 |  | note | ACCEPTANCE CRITERIA: Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | dde6ff40-7bf9-5979-8f7c-4b1005a66863 |  | textbox | Enter: Teambinder Material Approval number
label | 26e4dfa6-dd7b-5761-a8df-f0eee4b52097 |  | note | METHOD: Document Review
label | 594f9955-e4fd-5bb8-a8d6-2da792bc6eaa |  | note | FREQUENCY: Each lot
label | 87385f88-0759-535b-b607-45cc6b290175 |  | note | CATEGORY: HP
label | 17a581c2-4906-5ed9-9ef4-b03cbe346888 |  | note | RESPONSIBILITY: Nominated Authority
label | 0d678601-1699-5d7c-8313-5cbbc8ab6f4c |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 9be2a211-7601-5d6d-bccd-1cb9e79bf79c |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 Drainage Backfill Material
label | 0b00e8e8-5ab2-549f-8acd-004824cdf1df |  | note | REFERENCE: Section 701.09, Section 701.19
label | 007b8ebe-f976-5a90-9ca7-12a08458a549 |  | note | ACCEPTANCE CRITERIA: Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | 37b2ae3a-454c-5834-be83-e7a4f1f2e6e9 |  | note | Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
text | caf07ddb-a8f6-5e72-ba23-8d04ce9b5a76 |  | textbox | Enter: Teambinder Material Approval number
label | 8c6ffb7d-0cf8-55f9-a93c-8a642d2ef742 |  | note | METHOD: Document Review
label | e292d443-c59d-5c95-a849-ec3a5352ad5e |  | note | FREQUENCY: Each lot
label | 38bac9c6-f571-5a30-94fe-9fbdc31487ad |  | note | CATEGORY: HP
label | 7c05704a-84d3-580d-a9b2-222e01425424 |  | note | RESPONSIBILITY: Nominated Authority
label | b398498e-22d0-505c-bc38-d6bc26a40907 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 3fb3a8f5-791c-58e0-89f3-2640810e3bb2 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 Subcontractor ITP (where required)
label | 0d23b5a7-1694-5939-a78d-23f4abec61c1 |  | note | REFERENCE: Subcontractor ITP
label | 389c4bd0-0525-5d4c-b557-74ceaf34c434 |  | note | ACCEPTANCE CRITERIA: Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
label | 3d0c714f-e892-5092-a4fc-3a754029e6f6 |  | note | METHOD: Document Review
label | df24c44b-2e8f-5db0-911e-4fc12fba36e0 |  | note | FREQUENCY: Each Lot
label | 65de36ea-b993-535f-913b-8d7c44bc39f6 |  | note | CATEGORY: HP*
label | 74f3e0cb-33b6-569f-9463-f174a4a917cf |  | note | RESPONSIBILITY: PE
label | 1aed5a09-7f7f-59ac-bb5f-24dd9a04e793 |  | note | VERIFYING DOCUMENTS: Subcontractor ITP
date | 83088625-3de0-5371-84b8-addd54078551 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set Out - Pits & Pipes
label | 05fed162-5986-5e27-96cf-d33e6b85d7cd |  | note | REFERENCE: IFC Drawings Section 701.10
label | f53ee18a-cb41-5053-973c-6044b0edc34d |  | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | 343c1cd7-2808-5d21-bd86-e3e4bfdc61dc |  | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | 928cfb65-4d58-5fe6-8dc7-694fd90106a1 |  | note | METHOD: Survey
label | 287e8eae-b4bf-5d20-befa-1423f16de33b |  | note | FREQUENCY: Each Lot
label | b297cf43-22a2-519b-baba-e2e7411215c3 |  | note | CATEGORY: HP*
label | f182351c-b445-5f78-abb9-711902793962 |  | note | RESPONSIBILITY: PE
label | 0d35a704-5aa2-56db-ad52-f536a2f030bb |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation, CHK-002-CIV-Stormwater Drainage Pits Installation
date | 850b7c18-4673-5c57-bb31-77d657cc87c6 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Pits - Excavation
label | 6180b69b-e794-501d-959e-1a6939812772 |  | note | REFERENCE: IFC Drawings Section 705.05
label | d0da53f2-e061-50d9-a78d-afa34b1106c0 |  | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | 0534fb57-3346-5c71-b580-7f55b5b16496 |  | note | METHOD: Visual inspection, Measure
label | 4fe439a8-91f1-5427-a8d5-3850004a3aa8 |  | note | FREQUENCY: Each Lot
label | 70bb8ee7-0c09-5593-a43d-8f9a4708ab29 |  | note | CATEGORY: IP
label | 69906040-6eb8-58f8-8370-386dd1374874 |  | note | RESPONSIBILITY: SE
label | 12cc318a-fc51-5790-b056-58a15c34198c |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 29843405-ba20-5fcc-847d-7d629d9d13e7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pits - Placement of Bedding Material
label | 9852f554-ac42-5999-9551-8b07bc811b5a |  | note | REFERENCE: IFC Drawings Section 705.05
label | d7eaaf24-0036-557f-ba2e-481bdffad764 |  | note | ACCEPTANCE CRITERIA: Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | 80696860-a2d0-5a54-a57b-218045d7ca3c |  | note | > 80mm for clay foundations
label | c38ea44e-2a63-511f-8d0f-973406cefd74 |  | note | > 150mm for rock foundations
label | 09a32e87-3704-5d85-b155-b9b61db12b2f |  | note | METHOD: Visual inspection, Measure
label | 65455da0-9ffc-5479-b479-2fcac0405dfd |  | note | FREQUENCY: Each Lot
label | c3f407c2-03f8-5df9-894e-57d23d703b06 |  | note | CATEGORY: IP
label | 33deda73-139a-5773-bed2-e6f83623d007 |  | note | RESPONSIBILITY: SE
label | 6b3fcec9-6295-5e91-ac1c-a568765c6eb9 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 6110f313-a3f2-5de7-be6e-866b7ca760d7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Pits - Bedding Testting
label | c7d104bf-efad-5d1c-865e-3f7d017f5e53 |  | note | REFERENCE: IFC Drawings Section 701.20
label | 9ceed93a-45a7-5f51-a521-3e4f8e493329 |  | note | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | ca387ebd-6222-578f-85d6-3547d73f066d |  | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | f43600d4-99ba-5aa8-ac38-44901148ea2e |  | note | METHOD: Compaction Test
label | b8b52cbd-dc49-5bc1-a2f3-ea6398f072a1 |  | note | FREQUENCY: Each Lot
label | e1a12376-d5d0-5de5-aed1-d63a87309aa5 |  | note | CATEGORY: IP
label | 4ea523ae-3ed0-5964-b8e0-9bb0eba023cd |  | note | RESPONSIBILITY: SE
label | 78294686-7238-5529-8f3f-1a2dabb16a52 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 9420238a-d4ab-5ab0-b144-5eb43bd4181f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Pits - Placement of Precast Drainage Pit
label | 79abcd28-4853-5a38-bf18-a25fa3f6d4d6 |  | note | REFERENCE: IFC Drawings Section 701.10
label | 4a342cdf-9df7-5cf2-840c-8901bfc0bc6d |  | note | ACCEPTANCE CRITERIA: Survey pick-up to verify:
label | 9f227c38-ed23-587d-b2bd-490d30cd6f40 |  | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | 658ad066-466a-580d-8bd8-e28006648a1a |  | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | 8a9c1659-9b5e-5143-81b9-60e144b98bd2 |  | note | METHOD: Visual inspection, Measure
label | 33fcf54f-48a4-5725-bd41-177b70eb1f48 |  | note | FREQUENCY: Each Lot
label | 753bb8fe-3196-551f-b875-8d7fca190719 |  | note | CATEGORY: IP
label | c3ec03dc-dd7c-5e75-9928-14f248e5f98e |  | note | RESPONSIBILITY: SE
label | 06808838-ddeb-5b15-bbb6-203476218bed |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 60aa6399-6228-531c-b46d-cbaaec2ec2e3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Pits - Cast in Place Drainage Pit
label | 15922bcd-3857-5b0b-853f-d709f19c1c30 |  | note | REFERENCE: IFC Drawings Section 705.06, Section 610, Section 611
label | d47c70e8-d6c8-586f-ba26-df2c6106291b |  | note | ACCEPTANCE CRITERIA: Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
label | 42c53b71-f111-5762-b618-56d54599253d |  | note | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | 2a7d0a4f-c640-5c91-8cf0-5e5c2f6d7391 |  | note | METHOD: Survey, Measure
label | e34b75c9-7642-5845-99e9-9020788b87d5 |  | note | FREQUENCY: Each Lot
label | be98908b-1d45-5d56-866f-9eba653b3ecc |  | note | CATEGORY: IP
label | 1e531859-071f-524e-90a3-59bceb13b73d |  | note | RESPONSIBILITY: SE
label | 190fdf42-e90f-5d18-8f69-851c5bd509de |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 05a68788-fff9-58b5-a36b-77b4b806bc2e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Pits - Jointing & Drainage Connections
label | 100a91ea-511d-5378-af90-d82f2501a8a0 |  | note | REFERENCE: Section 705.11
label | feeb2c16-4f4e-5f7b-a85b-5e749de5f1e8 |  | note | ACCEPTANCE CRITERIA: All connections to drainage pits shall be neatly made in accordance with Section 705.11.
label | b67df2a8-a020-52ea-8e03-f9b0a1af1f86 |  | note | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | 4aeeec66-f089-59fc-a344-dbbae5381dfb |  | note | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | 87e4d03e-a26b-506a-9a18-f30f9ae90dcf |  | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | 0363d2d3-59d5-5133-af87-b0b26e4182a3 |  | note | METHOD: Visual inspection, Measure
label | 8b9003b1-b6b3-5ab8-88da-dfed4ef14cf3 |  | note | FREQUENCY: Each Lot
label | 975b9ad5-11fd-5b86-86e9-499fdae6d53c |  | note | CATEGORY: IP
label | bd47372f-5d06-584e-a653-9c85502f8ca2 |  | note | RESPONSIBILITY: SE
label | 18df06e8-1a1b-5965-99c6-f3793c8c2396 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | f9e09eb3-0947-501d-ae88-fb6cfe4ed37f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pits - Shaping of Floor
label | b7b78f1d-8385-513f-b0e3-a1bd7c79b5bd |  | note | REFERENCE: Section 705.13
label | dcff66d0-99f9-50ed-a1e8-620afd30617d |  | note | ACCEPTANCE CRITERIA: Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | f5a04665-72da-5951-9346-8b31323ccd78 |  | note | METHOD: Visual inspection, Measure
label | 403bcba3-e238-57f8-abc3-35910e609893 |  | note | FREQUENCY: Each Lot
label | f8a4aed1-1512-53eb-8552-f5ccca2b34f5 |  | note | CATEGORY: IP
label | acc2f5b5-1356-5caa-9ecf-a19b12001ab4 |  | note | RESPONSIBILITY: SE
label | 35b9e9b0-a229-5daf-a29a-c684b2c8bd6b |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 3b66eede-0889-5dcc-b173-54904c97d660 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pits - Step Irons
label | 3fffffa2-8249-584a-a4c3-f5c633cb14d2 |  | note | REFERENCE: IFC Drawings Section 705.12
label | 29ef4c4f-9861-5d95-9b30-6aa5d2af753d |  | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | 258e4457-3232-534f-af92-c1e2081b491f |  | note | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | 4cbf2eeb-e1dc-51de-9bbd-c843fcae166b |  | note | METHOD: Visual inspection, Measure
label | 07dcaea1-aa25-5eaf-a74e-8caa56da4004 |  | note | FREQUENCY: Each Lot
label | 7b6c2ad6-2491-5f31-91d6-a825287f7344 |  | note | CATEGORY: IP
label | dbfcd9ef-76c5-5f87-979a-17add77c9b29 |  | note | RESPONSIBILITY: SE
label | cddbdc90-c739-5388-9e01-8c51db231b70 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 244ed648-cbd6-5226-8666-d3b74709807c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Pits - Fitting of Covers
label | c13db66b-9930-50b4-aa9d-5b83ce59a776 |  | note | REFERENCE: IFC Drawings Section 705.17
label | 3e77fc39-03b1-56c7-9e88-26e3243b6a48 |  | note | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
label | 1e8a1877-d7b5-5334-a13a-dacfbe4c76a4 |  | note | ○ Height shall be within 10mm of the design level.
label | fb3e84f3-1d7d-54f0-9b72-29783d565dee |  | note | METHOD: Visual inspection, Measure
label | 012da919-01c9-55ec-9f68-6e34e1161a3d |  | note | FREQUENCY: Each Lot
label | b62908f6-6c63-58ff-9581-229ab3e5da74 |  | note | CATEGORY: IP
label | 30dffbbf-c11c-5973-8744-38d80320aaec |  | note | RESPONSIBILITY: SE
label | cd238386-fc21-5ca5-8062-3b0f16c250e7 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 66f4f92b-518d-52fc-af3b-c50be9d21969 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Pits - Pit Lids
label | acb61b99-48e0-51f2-aa10-9923c45fd240 |  | note | REFERENCE: IFC Drawings
label | 6c4d10ff-ecf4-5923-9ba3-af3f2bdd2f72 |  | note | ACCEPTANCE CRITERIA: All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | 6676001f-19e8-53b5-b24a-837949361182 |  | note | METHOD: Visual inspection
label | 402b0d35-507e-5183-a020-eb2e3545804d |  | note | FREQUENCY: Each Lot
label | a1acf8ae-6843-5e22-a629-e144a591994f |  | note | CATEGORY: IP
label | fe1e7d29-3023-5cd9-b8b3-4a8be664c8e8 |  | note | RESPONSIBILITY: SE
label | 681962b9-d186-57c9-a868-f0dd6d20da6a |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | 9fc9eeec-977e-59b4-862c-a492185e1742 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Pits - Backfilling Around Drainage Pits
label | c9ae1c7b-e628-5dbd-a8e6-2c2644c72576 |  | note | REFERENCE: Section 705.18
label | 73e799ac-5775-5ce7-9141-6484b47cc6d5 |  | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | 26d84730-2e83-50e2-a6f0-c872f64cb470 |  | note | METHOD: Visual inspection, Measure
label | 324b2d80-6d57-538a-aa1d-762b5090256e |  | note | FREQUENCY: Each Lot
label | ae7ac52e-0c95-5b29-806a-7760aa7118db |  | note | CATEGORY: IP
label | 89c5975e-dc2a-5b9b-8452-40c67f48f3d3 |  | note | RESPONSIBILITY: SE
label | 8d4d7c17-4e04-5f5c-b8f3-b2d749efb33c |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | a4764594-eb67-561d-9705-23edec740193 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Pipes - Trench Excavation
label | 8b30f105-2f55-5907-83c8-fef940607e8e |  | note | REFERENCE: IFC Drawings Section 701.15
label | 17988918-6f8e-55cf-8161-44244ce4317f |  | note | ACCEPTANCE CRITERIA: Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | f98b4d64-2567-599c-9369-2ca472fe3fa5 |  | note | > 300mm, < 600mm for RCP
label | 43dc62b3-e07b-58e9-a9d6-ed6f7ecd9ace |  | note | > 150mm for Flexible Pipe
label | 0f55565f-b191-5458-accb-4e6fd62681bb |  | note | ○ The base of the trench shall be compacted to refusal using mechanical plant.
label | dce0a5ea-b26e-53b7-ab39-3c57ea247c19 |  | note | METHOD: Visual inspection, Measure
label | af689f14-522a-5a48-94b5-608276fb9472 |  | note | FREQUENCY: Each Lot
label | 7c4383ca-2fe5-52f5-89c6-d2d6427b5c65 |  | note | CATEGORY: IP
label | 0ea67620-28f7-5a5a-a0ee-bcd6dba2bf37 |  | note | RESPONSIBILITY: SE
label | 12783c13-e71b-51f9-8b5d-53e0efa98d6a |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | b0ab98b9-1827-52b0-a7f2-4b05314ff080 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Pipes - Bedding Placement
label | a7a34bb9-0d3a-57d7-8a8e-b1ca5728d076 |  | note | REFERENCE: IFC Drawings Section 701.16
label | dcb02e76-f5cc-5d40-b613-8a091ca77f63 |  | note | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | 5534e307-a4b5-503f-98c5-c3a6d62cdfa1 |  | note | > 100mm where D<1500mm
label | 6bba818a-0424-591c-88c3-855380baaaf9 |  | note | > 200mmwhwere D≥1500mm
label | 327588b2-068f-5dcd-b1b2-ff5771273850 |  | note | ○ Bedding material shall be placed and compacted in layers <150mm loose thickness
label | 757c1c0b-a997-5603-9215-ce6d2c8e6e78 |  | note | METHOD: Visual inspection, Measure
label | c8fb6afe-6d42-51fb-83de-a4450bfc3aef |  | note | FREQUENCY: Each Lot
label | b3977e19-215a-5b60-a730-3028bb8678f7 |  | note | CATEGORY: IP
label | 43d4e213-34b3-5c40-b410-069d2bd61fdb |  | note | RESPONSIBILITY: SE
label | a8f5d2eb-def4-5440-b014-a5dfa9569ea4 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | a8bdf9c8-3ddc-5286-aedf-d82c1f795a71 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Pipes - Bedding Testting
label | b1910bdb-92d1-5614-b1c9-861b8f82411d |  | note | REFERENCE: IFC Drawings Section 701.20
label | 6a18981a-c974-580a-bc95-a2ca1e05afdb |  | note | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | c7cf0478-2669-5fd8-b3a5-2b57f06213e0 |  | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | d6763649-14c8-5b7f-86cc-a0aa0fe79141 |  | note | METHOD: Compaction Test
label | 4ddf459a-4a14-5cf8-b183-00539b6a660a |  | note | FREQUENCY: Each Lot
label | 9b474d17-7ee3-5f08-8868-ca07c0b6bb65 |  | note | CATEGORY: IP
label | dac0ae45-0eee-53cf-8e11-794dbc7af37b |  | note | RESPONSIBILITY: SE
label | ee525334-7f56-5ca6-b641-ad6797568452 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | 41f52620-2ddc-5f51-a055-d923989f02e3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Pipes - Placement of Pipe - RCP
label | 73f5c19d-6708-5ace-a1c5-4a5c02331287 |  | note | REFERENCE: IFC Drawings Section 701.17, Section 701.20
label | 4e4f889e-9fd3-5624-abf7-bf09eb2577fa |  | note | ACCEPTANCE CRITERIA: Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
label | 867ef1a9-9c54-57f5-807a-3eebb5a4c256 |  | note | ○ Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
label | f79b6800-7240-520d-9ca0-4ddb76899233 |  | note | ○ Gaps between spigot and socket are in accordance with the manufacturers specifications
label | 36bc6514-8169-5765-916c-060bd2fd1334 |  | note | ○ The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
label | a0d895fa-738a-50a1-b708-2db376a2ba18 |  | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | 7109be85-035e-519e-862f-14500dd9aa7d |  | note | ○ The spacing for multiple row culverts shall be as shown in Table 701.171
label | ca52d52d-0003-5520-957a-08c115b11fb9 |  | note | METHOD: Visual inspection, Measure
label | b36be2fd-78f4-5946-946f-c3a837cf1e3c |  | note | FREQUENCY: Each Lot
label | 44aeb80a-5188-529a-92bc-e4aae3d06464 |  | note | CATEGORY: IP
label | ae6a8fea-37f5-57c5-b00e-4d4db6648f07 |  | note | RESPONSIBILITY: SE
label | 7b4da0f9-7f61-5783-857f-e729c15540f7 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | f42c5889-11d3-5754-9c06-e34d309a225b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Pipes-Placement of Pipe - Flexible Pipe
label | 479fc994-cf49-54c2-9199-1e7b0c8083f9 |  | note | REFERENCE: IFC Drawings Section 701.17, Section 701.22
label | 852718a3-7626-5113-a6bd-ccd24713abbb |  | note | ACCEPTANCE CRITERIA: All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
label | 8ffe5395-1671-5937-a21b-746d2ef38687 |  | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | 44ccc78d-0c0d-55cf-9034-6b145bc500b2 |  | note | METHOD: Visual inspection
label | b2c37190-f39e-5923-a6ad-8a5186cc1679 |  | note | FREQUENCY: Each Lot
label | 34fdca1c-a978-5be2-89d8-f96e3858410c |  | note | CATEGORY: IP
label | 13957fc1-4ecd-53f7-b26a-caf2b7690632 |  | note | RESPONSIBILITY: SE
label | b868bcef-f94f-5851-a65d-7104a0f3c660 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | 112a1d7b-43aa-52ee-a466-8a128e6671fe |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Pipes - Lifting Holes
label | 2a1de408-d5c7-56cc-9a5c-2f2044fd18d3 |  | note | REFERENCE: Section 701.18
label | 3f4412e9-5bca-5c71-bf08-df798158d137 |  | note | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | 9833993a-66d8-507d-b33e-ddcd0ddbe6ea |  | note | METHOD: Visual inspection
label | 0d457fc5-24d3-57ce-b84c-f5d196f3dab6 |  | note | FREQUENCY: Each Lot
label | 89d0d04d-f097-52d8-b659-2608b349c58e |  | note | CATEGORY: IP
label | 5733b10c-2e2b-56ac-bff9-81a48f523b8c |  | note | RESPONSIBILITY: SE
label | c9d904b8-1030-5815-a31f-d35159484f26 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | 03dd1387-c459-55f3-996b-9887acb1ebfd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Pipes - As-built survey pick-up
label | fa3425a7-98db-515d-9260-ec4ccb8e3cc5 |  | note | REFERENCE: IFC Drawings Section 710.10
label | 921cf323-bf47-5fca-986d-5232221d3022 |  | note | ACCEPTANCE CRITERIA: Each run of underground drainage shall be Survey verified prior to backfilling.
label | a6d78408-8a15-5109-8f31-2fe7230f0f14 |  | note | – Offset pits to kerb +/- 20mm
label | 2d10cb31-7bde-5635-8e75-38e9e092f792 |  | note | – Plan location pits not adjacent to kerb +/- 100mm
label | c779f1ac-47e9-57b0-a01b-91018269f9a4 |  | note | – Invert level of pipes at pits +/- 50mm
label | 4dfbd7b7-9a6f-5713-8ff9-8e372d1d5e47 |  | note | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
label | 3e3de48f-d691-5997-b42c-77b84a1784e7 |  | note | METHOD: Survey
label | 109745b1-c91e-5ea4-8c4a-e03e3b6cd6c2 |  | note | FREQUENCY: Each Lot
label | e1d5c005-3075-5011-9916-ce185375ccef |  | note | CATEGORY: IP
label | 7ed5f41a-217b-594f-bcea-536a78ec638e |  | note | RESPONSIBILITY: SE
label | 4f640641-0548-5e3d-846f-5889d44e85f9 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | 60b7d6d0-7e6c-5dee-92d7-88309482adb0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 Pipes - Backfill Placement
label | 62ac3769-d08b-550c-b0dc-0f5c5f98118b |  | note | REFERENCE: IFC Drawings Section 701.16
label | 3fc201a6-eb2b-533e-a350-e6ef01f76e4d |  | note | ACCEPTANCE CRITERIA: Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | e7a7e578-fcd2-5a19-acf3-c72fe59b7cd6 |  | note | ○ Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
label | 62170fa0-67de-5850-9fb6-037765d24a54 |  | note | METHOD: Visual inspection, Measure
label | 866d1f88-058b-5084-b5fa-88eb349ef223 |  | note | FREQUENCY: Each Lot
label | 028773e3-c8ca-5429-8b99-1e9baefb2aab |  | note | CATEGORY: IP
label | d694c9da-2f0e-5712-9641-14b0b0342d69 |  | note | RESPONSIBILITY: SE
label | f2d0f130-e0c5-5bb8-9a72-8aa9dcb391a4 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | ce232754-6088-509d-b7df-10832b2641ec |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 Pipes - Backfill Testing
label | 245e99c7-65e2-593f-89e5-8c94825062e4 |  | note | REFERENCE: IFC Drawings Section 701.20, Section 701.29
label | 3a711691-3321-5751-b6cc-e7f97819d13f |  | note | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | c32e5ee2-3741-5cf3-8d1e-026ed9b18b75 |  | note | ○ Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 9f419473-c36b-52a7-ac1a-d19dcbbb322b |  | note | METHOD: Visual inspection
label | 30f45d80-8fcd-5fe9-9805-ffaa7f17ba80 |  | note | FREQUENCY: Each Lot
label | 74101bb7-f5a1-5fd7-b92a-9452506e1ca1 |  | note | CATEGORY: HP*
label | 1cbe4d49-e2ff-575a-85dd-0cc2fba4e493 |  | note | RESPONSIBILITY: PE
label | c27f306e-b19b-5fa6-a61a-6779f4d1eb0f |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | a2eea4ec-4f7c-542f-89db-25c5c6799ea9 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Flushing & CCTV
label | bdae0840-7e5b-5898-93ae-2d8b8bbc86ad |  | note | REFERENCE: Section 701.28, Section 701.30
label | 859bd84d-6969-5998-bb27-4d8b3101b69d |  | note | ACCEPTANCE CRITERIA: All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | 7ce55413-4b29-5756-9723-2fb08f14bc77 |  | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | c94933d5-dad7-5696-9bf6-c41a9770af62 |  | note | METHOD: Record Review
label | 9850f3c1-6e7e-50b0-bc89-227e5ae1ed5c |  | note | FREQUENCY: Each lot
label | a83dbb4b-5bec-5145-94f4-77cf385e684b |  | note | CATEGORY: HP
label | 06fa9d69-03ca-5c4f-b1de-ce9d0168f828 |  | note | RESPONSIBILITY: Nominated Authority
label | 16ab72e4-ade3-5104-866b-c4eaed3b2ea7 |  | note | VERIFYING DOCUMENTS: This ITP, CCTV Reports
date | 625e0772-0668-59fa-aa15-af0566016b96 |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 As Built Survey
label | 97df07a8-192b-532b-b4a4-425463913559 |  | note | REFERENCE: Section 701.10
label | 8121313b-1395-5e27-afc8-9ef4bf8e89cd |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | 35a8e7f1-991b-5cc1-9e4c-c90915ece1b9 |  | note | METHOD: Document Review
label | e9d81887-a271-5840-bfd1-f89a65640188 |  | note | FREQUENCY: Each lot
label | 785da560-d9b9-5e6e-950e-0e5b96b9e6c3 |  | note | CATEGORY: IP
label | c4da27be-23c3-5ae6-9f0a-ff27202776da |  | note | RESPONSIBILITY: SE
label | ca30db6c-0d42-5f01-a031-9c1d4e799237 |  | note | VERIFYING DOCUMENTS: This ITP, As Built Survey Report
date | 4a5e3f08-75a1-5ae2-b2e4-c1cc205b906f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Repairs to Damaged Pipes
label | 4108422a-8e64-5c2f-aab3-b8b60da10997 |  | note | REFERENCE: Section 701.31
label | dab07ac0-1512-510a-989c-28ed374aafe1 |  | note | ACCEPTANCE CRITERIA: Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | 72936ca4-0e69-52de-ae29-96fa70332abe |  | note | ○ cracks wider than 0.5 mm
label | fd9a433f-46a8-590c-aa40-076cdcb2cd33 |  | note | ○ spalling of concrete
label | ad60de67-6d15-563a-b7cb-f177ff858ee8 |  | note | ○ exposed reinforcement
label | 054bd3b0-e691-553a-ad10-4499c3121e92 |  | note | ○ joints that are not fully engaged.
label | 5de4b956-6912-52e7-8f0b-930b0257e650 |  | note | Any pipes with defects greater than the following limits shall be removed and replaced:
label | 6a50a2e0-ce04-5b1c-ba98-b9e30f7c71cc |  | note | ○ longitudinal cracks greater than 2 mm
label | 849c430a-5fe9-5913-8f50-b1fbbb919a99 |  | note | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | 035b0762-7dd8-5485-8809-265ab9e3934d |  | note | ○ circumferential cracks around part of the circumference with width greater than 4 mm
label | e24a01f8-8783-56da-b325-ebee7825abb8 |  | note | ○ penetrations with area greater than 400 mm2
label | b10f2199-2e14-5acd-ba5d-01a21748c10b |  | note | ○ pipe joints that are separated.
label | b3d27302-be44-582b-9ac8-2819bd008b15 |  | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | 836e9fd0-20b3-59c2-8b55-ed8fc3a45544 |  | note | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | ffe79127-3fd6-5994-b44c-cd7f3bbd8b68 |  | note | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | 3b35302a-3b53-5218-8222-a335942abaf9 |  | note | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | 0dff35d8-9997-5415-90fa-3ec9eb160a49 |  | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | 59064655-9b99-50e2-bad0-db1f1f7b8d9a |  | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | 3d570150-972f-5b06-a40d-74033371161d |  | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | 2410fa6b-c062-59ad-a04e-f561d9c52aeb |  | note | METHOD: Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
label | fe7867cf-1546-5f4f-b7cd-b415313b95b1 |  | note | FREQUENCY: Each lot
label | dff3f1d0-31a3-53eb-803f-5c5f0eefb258 |  | note | CATEGORY: HP
label | f5c1bae4-ccc8-50d9-ac93-742291d3915b |  | note | RESPONSIBILITY: Nominated Authority
label | 8f2aeba1-03b0-5b20-b5d7-8268cfaee634 |  | note | VERIFYING DOCUMENTS: This ITP, Approved Repair Procedure, Post Repair CCTV Report
date | 39ea62eb-a8bf-5d92-8947-fe9a158870ff |  | date | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | 4a7737d3-dd65-54e1-a601-34b604d5104f |  | note | REFERENCE: MRPA Quality Management Plan
label | e3d35e2d-5ac4-5663-af00-c2a407946e2d |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | 141a5e92-e839-5b1b-ae16-6d5605cd577e |  | note | METHOD: Document Review
label | 4abd3fa9-43ec-5837-ab09-fcaa24ddd7f4 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 99bb9803-cdce-5fe0-a505-f16a42c1a34f |  | note | CATEGORY: HP*
label | 32a9836a-9d20-5c3c-8a7e-a1fb88db331f |  | note | RESPONSIBILITY: PE
label | 247e7ecf-67a3-5b8a-9a08-ed97630052a4 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5e3e94b6-fa21-5ce1-aa7c-1f60bf58e612 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 30f2f451-6f2e-5c2e-9357-7f8edadd7438 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 21fdb08a-adbd-5d82-9198-994ac4d013b0 |  | textbox | Name:
text | b44ae525-1888-58b3-a591-bbecf37797b8 |  | textbox | Position:
date | 29c63d2e-9fdf-5653-9c65-70577800ddc1 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-003-Civil-Material Delivery Inspection-Precast Pits and RCPs | itp |  |  |  | Yes | CHK-003-Civil-Material Delivery Inspection-Precast Pits and RCPs Rev 0 | eda3aa5c-306f-477e-83a4-0bf807433b49
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | be1d4509-9d47-52f8-a5bc-e306a7d036a2 |  | note | Document Title: CHK-003-Civil-Material delivery inspection-Precast Pits and RCPs
label | 9d7351df-1c63-528c-9bfd-026800063515 |  | note | ITP Description: Material delivery inspection-Precast Pits and RCPs
label | b8414883-3e40-5e40-ae14-95abd319ebcd |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | f7134f6e-6cc7-57e7-8723-7816f23f3097 |  | note | Discipline (e.g. CIV/STR/RAIL): 003-Civil
label | fe011665-f134-544d-b6a5-fa908ed75af0 |  | note | Revision Number: 0
label | a24cd612-4bf9-576c-9adf-37c2068bee10 |  | note | Revision Date: 6/12/2023
label | b092acb1-f660-5211-b39e-fd5498c318d3 |  | note | ITP created by: Victor Mira
label | 3050289a-d891-5dc9-9dc1-16afe0868239 |  | note | ITP approved for use by: Victor Mira
checkpoint-status |  |  | checkpoint | 1 - Delivery Details
label | bf888bbb-e426-5780-bec0-226074aa7290 |  | note | ACCEPTANCE CRITERIA:
text | cf42f3f7-5145-581e-9aab-b2d514a47cc7 |  | textbox | Enter: Delivery Docket Number:
text | e9b709c1-d152-563a-a29f-d8d90aa16cdf |  | textbox | Enter: Delivery Date:
text | f908076d-14b2-5c45-89f5-9f6066b261ae |  | textbox | Enter: Element ID (s):
label | 16099a67-b219-535e-89b7-55484b0fa252 |  | note | Attach: Delivery Docket and packaging Slip
label | 15dce400-7cd7-590e-9bbe-f327798c6000 |  | note | METHOD: Document Review, Visual
label | 989992d8-6171-552b-91a0-86680d655213 |  | note | FREQUENCY: Each Delivery
label | d7f55c53-d549-59b8-9f51-05d79ce1b62c |  | note | CATEGORY: IP
label | 3f6af3b3-a2ce-5d85-815f-49fefefcad64 |  | note | RESPONSIBILITY: PE/SE
label | 9c2b40cf-8ba1-564e-8184-26fdad1f2f1e |  | note | VERIFYING DOCUMENTS: This Checklist
date | 0a28494c-c4f2-56d0-8f5a-e8269f51897a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Packaging Inspection-Quantity
label | edf91b52-bfd8-56b6-a8cb-f369295f1ca9 |  | note | ACCEPTANCE CRITERIA: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
label | e6814c1d-0ccd-5844-922e-ad0c22032eb9 |  | note | METHOD: Visual
label | 2dd37412-9696-58ba-a74a-8e2de1777840 |  | note | FREQUENCY: Each Delivery
label | cefc7dc9-7514-564d-8d54-b475ccbd2914 |  | note | CATEGORY: IP
label | 9256d912-2787-5f75-b387-c9453af8a9dc |  | note | RESPONSIBILITY: PE/SE
label | 48744d8c-99cd-5018-b8f6-f02ef154a058 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 74e014a8-7bcc-5001-9a53-737b55d2610f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Packaging Inspection-Delivery Contents
label | 4df401f9-8960-53a9-b469-cfadbbf71442 |  | note | ACCEPTANCE CRITERIA: Do the contents of the delivery match the freight list/packaging slip?
label | 683761b7-bdd2-58c8-a5f0-53f1c4b8b400 |  | note | METHOD: Document Review, Visual
label | 14051d1a-d59e-52c2-a1c9-17d7c3740061 |  | note | FREQUENCY: Each Delivery
label | 044adf34-e7df-5e12-ae93-356e75457ad4 |  | note | CATEGORY: IP
label | 90831b46-8024-5c73-baf1-73d37c8ece26 |  | note | RESPONSIBILITY: PE/SE
label | ff65b49e-55b7-5966-86d4-e95d698ca4c2 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 7cedf3fc-73dd-5ca7-bd8e-f877172119d1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Packaging Inspection-Birth Certificate
label | 7b932e97-9bcb-558c-8074-b05238f8c041 |  | note | ACCEPTANCE CRITERIA: Is the delivery accompanied by Precast items Birth Certificates?
label | 571f1a5a-7274-5ee9-be22-e8d919d5b0f2 |  | note | ○ Precast components are to be marked on the birth certificate.
label | a7254cb3-9175-5f4b-8787-a05b9a157427 |  | note | ○ Cast date and lot are to be marked on the birth certificate.
label | 0b34de6d-f367-5673-ba80-beb461d4c1a0 |  | note | METHOD: Document Review
label | 727ad533-3b07-54ef-9354-8878be0feac0 |  | note | FREQUENCY: Each Delivery
label | da27e886-6cf8-5835-a21c-3943c6592696 |  | note | CATEGORY: IP
label | f685850b-b13c-52d2-8d69-1c93af1e47a2 |  | note | RESPONSIBILITY: PE/SE
label | d37c9f15-b3fb-53ea-8df1-a5e9f811007d |  | note | VERIFYING DOCUMENTS: This Checklist
date | a1ab8964-1b48-54a9-8292-f2a1b3641cd1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Packaging Inspection-Transport
label | 7e51c573-2cc0-5c5f-a5d0-835e18b4ca36 |  | note | ACCEPTANCE CRITERIA: Is the condition of packaging acceptable.
label | 1456bc17-a3a7-56f1-b0d4-50a42bf5662c |  | note | ○ Precast items are protected from damage during the transport
label | f3d08b9a-e04d-5536-935b-a3a2039d8981 |  | note | METHOD: Visual
label | 09357f07-661d-563b-af17-f91428e2bc06 |  | note | FREQUENCY: Each Delivery
label | b27f52f4-9226-5d42-a08b-e444d30b4d5f |  | note | CATEGORY: IP
label | 4e8bd3ee-db82-5dff-97fe-727bf939a7b0 |  | note | RESPONSIBILITY: PE/SE
label | 9afa5f25-ef47-5f51-aac4-69e53cf42780 |  | note | VERIFYING DOCUMENTS: This Checklist
date | d9d6399b-58ff-57ed-b01b-9db2a578b1d2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Fault IDs:
label | 22b2e01b-ec08-518b-92eb-0b17e09f21c0 |  | note | ACCEPTANCE CRITERIA: For each precast type delivered, check for the following:
label | f126b8cf-1cdb-5f6f-87db-ad7176ad91e4 |  | note | 1 - Identification markings match the Precast type
label | 00ddcecd-3021-5e05-94f5-f7c62370ebd3 |  | note | 2 - Precast Pit fabricated as per drawings - inverts size.
label | b1981768-527a-5aee-85fd-3f860f1866a9 |  | note | 3 - Precast Pit Fabricated as per drawings - Inverts position (Distance from the bottom and edges).
label | 9906b2b4-0433-50d1-910e-342b13beb0eb |  | note | 4 - Precast Pit Fabricated as per Drawings - Invers Position - Correct Wall (orientation).
label | 5c56ded8-1bb2-5b5b-83ea-17d9d7c35d2a |  | note | 5 - Precast Pits - Inverts coliding.
label | e675c9b2-c6e5-5deb-896e-59af67524f72 |  | note | 6 - Precast Pits and RCPs - Inspect for Cracks.
label | 0ded8a6f-1b3a-5ba8-a045-44641a438a5d |  | note | 7 - Precast Pits and RCPs - Inspect for Spalling/Damage to concrete surface.
label | a987a1ea-c7e1-5860-aa2b-059058606ef6 |  | note | 8 - Precast Pits and RCPs - Inspect for Exposed Reinforcement.
label | 2d24bfbf-5aa8-53b3-b589-02361ad7f004 |  | note | 9 - Precast Pits and RCPs - Inspect for correct Lifting mechanism.
label | 2bf78551-2c7b-58fd-b557-253bdd486c99 |  | note | 10 - RCPs - Inspect rubber rings
label | 3ede2c37-e263-5f0a-81f7-8aba6ff2be9d |  | note | 11 - Precast Pits and RCPs - Inspect for other fabrication defects (specify on the following lines)
label | 61b265a2-7741-5162-9de1-17c3a31e3f54 |  | note | METHOD: Visual, Measure
label | 038a0460-ad96-5bdd-a6c3-718a98ae15b8 |  | note | FREQUENCY: Each Delivery
label | 06a8196d-3e45-51a2-b644-6ee5d9904362 |  | note | CATEGORY: IP
label | f2dc4bac-3807-5a2d-9ad6-97095c90ab43 |  | note | RESPONSIBILITY: PE/SE
label | db5045c7-69dd-51a7-b942-6e10f4ddca33 |  | note | VERIFYING DOCUMENTS: This Checklist
date | f6470be4-0736-5aa9-a3d3-c3c1ce7d6b3e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 1
label | 56edcacb-0a28-5257-aa27-d5996d999a22 |  | note | REFERENCE: Item 6 on this Checklist
label | 231c30c2-0fd8-5a61-a11f-ef5282cdb046 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | 09c3ad32-59c4-5a42-9e65-28c2470e2df6 |  | textbox | Enter: Panel Identification
text | a828bf58-8825-5ffe-95ee-8e6c6d7c3a9f |  | textbox | Enter: Quantity
text | 89b25c3c-6e73-5b0b-84de-3134d7ae80a2 |  | textbox | Enter: Fault ID if any
label | 8c93cba5-6e79-5434-9142-c2ae0248fe39 |  | note | METHOD: Visual, Measure
label | a4e3c3fe-0f61-5485-be25-194317f316f5 |  | note | FREQUENCY: Each precast type delivered
label | f49cf2c7-1eed-546e-9271-ba023a9200cc |  | note | CATEGORY: IP
label | dc7167fb-9692-5811-9462-afd03f08f06c |  | note | RESPONSIBILITY: PE/SE
label | 7705db87-a5ed-5263-92c1-69ccc1a0c55f |  | note | VERIFYING DOCUMENTS: This Checklist
date | 99ee7cd6-b843-5d7a-b2b2-6d8537e694ce |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 2
label | 47f275bc-3cd0-56de-bf33-4bc7b85eaf57 |  | note | REFERENCE: Item 6 on this Checklist
label | 2cb7f630-6401-5870-b568-6fd6d9d0d394 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | 358d7608-8d3d-594b-8c6f-31bdf9d6a977 |  | textbox | Enter: Panel Identification
text | 43a32293-12c9-549f-ad8e-f5edb713d99d |  | textbox | Enter: Quantity
text | d68e7110-4d3a-52d6-a524-1f5b4b667acb |  | textbox | Enter: Fault ID if any
label | a425ad1c-f646-50fd-bca4-548030b43ff1 |  | note | METHOD: Visual, Measure
label | f5e0870b-e2a4-540e-a705-d6adb13bb7b5 |  | note | FREQUENCY: Each precast type delivered
label | 512f4bb4-b902-5144-9ec7-2ff11a425500 |  | note | CATEGORY: IP
label | e0f525a8-f6b1-5368-9561-b868fb1a213e |  | note | RESPONSIBILITY: PE/SE
label | ebc50cb4-6282-500e-99ed-e6db236359f6 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 4d14a96b-26b2-5acf-a90a-f50f02e565d3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 3
label | 7163d552-e551-5af3-9007-4f8742973eb9 |  | note | REFERENCE: Item 6 on this Checklist
label | 33c43c0a-b93d-5de2-884d-2ee098649cc2 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | a0d67bfb-7128-50c3-8e6d-aeb88d737d34 |  | textbox | Enter: Panel Identification
text | c4ee366e-33d7-5175-b0d7-8bcd33b8185e |  | textbox | Enter: Quantity
text | 21508273-52d4-5bca-9466-78b32de7af26 |  | textbox | Enter: Fault ID if any
label | ac393090-b4a4-5625-97bc-ea56faa58761 |  | note | METHOD: Visual, Measure
label | 79cc5455-a250-59c5-aad6-111960ab6e43 |  | note | FREQUENCY: Each precast type delivered
label | 28acaffb-44ef-52af-a2a5-a562e1bfb031 |  | note | CATEGORY: IP
label | 53d7016f-2ad0-58e4-8ba9-019c6a5bf7c1 |  | note | RESPONSIBILITY: PE/SE
label | f36e0fd1-66f0-52dd-90b3-fe061ddf657b |  | note | VERIFYING DOCUMENTS: This Checklist
date | 95b238d6-7f99-5e7f-bb78-de075e3cf2db |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 4
label | bea9c3f5-001d-5720-8faf-950cfa706c60 |  | note | REFERENCE: Item 6 on this Checklist
label | 025d3f75-4f7c-5bf4-9fd7-f8ed22329df4 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | 25943a12-755f-594d-99c4-a4b079cd1ad4 |  | textbox | Enter: Panel Identification
text | 69b308c9-551e-5c93-a2e2-9dfaa0d3cce8 |  | textbox | Enter: Quantity
text | 10b55baa-3869-53de-9a85-2ccbe33a609e |  | textbox | Enter: Fault ID if any
label | b9374a20-2d84-55cf-9207-237304f8c070 |  | note | METHOD: Visual, Measure
label | e3cd5376-9a2c-5e18-bbd9-c86f76cb0080 |  | note | FREQUENCY: Each precast type delivered
label | be1bf93b-f9cc-56f1-bad0-f13e15f54df0 |  | note | CATEGORY: IP
label | 7dd498d1-967b-5258-ad14-a85ebd3c4986 |  | note | RESPONSIBILITY: PE/SE
label | 3fdaf2bc-6ee5-569f-b514-60ca25f0a59c |  | note | VERIFYING DOCUMENTS: This Checklist
date | d7fb09fa-5120-51e5-8538-5d758f53d66c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 5
label | fef9a71a-21db-5bcf-9054-1d0c7ce60314 |  | note | REFERENCE: Item 6 on this Checklist
label | dcfc25cd-bae7-5d2d-9d8b-e47871235bd9 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | fb4d79c9-03fb-5f18-8e7b-211f3e0165b4 |  | textbox | Enter: Panel Identification
text | 3e32db60-486e-5e21-8a5f-d9bbda8cc2db |  | textbox | Enter: Quantity
text | d043088a-4bbf-56e8-824b-8c88a68bc1ae |  | textbox | Enter: Fault ID if any
label | 5f47be41-175d-5e85-b8d2-545df0d7d973 |  | note | METHOD: Visual, Measure
label | 28354ba6-9979-5873-9242-4f35ff608ca8 |  | note | FREQUENCY: Each precast type delivered
label | 8ed74d92-226a-5076-a13d-f12ce3bb8282 |  | note | CATEGORY: IP
label | d3c1c813-73e7-5373-ae62-e87f4a66ac7a |  | note | RESPONSIBILITY: PE/SE
label | 12308c40-7d4e-5592-aa7a-a51d0175f098 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 144b4a25-1154-5db2-aa48-cc4fa2aab5b1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 252ea524-ef47-509e-905d-d5ffb40a63e9 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | de981dee-ce50-528a-872e-7f0f689299f4 |  | textbox | Name:
text | 5ca4ecfa-e261-54b0-bf76-d6abb9e0cfda |  | textbox | Position:
date | 271c363c-d9b7-5746-a79d-46ea54b89f2d |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP