## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-150-CIV-PSDS-Rock Beaching | itp |  |  |  |  | ITP-150-CIV-PSDS-Rock Beaching Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-150-CIV-PSDS-Rock Beaching
label | ITP Description: PSDS-Rock Beaching
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 150-CIV
label | Revision Number: 0
label | Revision Date: 17/04/2024
label | ITP created by: Jonathan Kogan
label | ITP approved for use by: Victor Mira
label | 1.1 VicRoads Specification and Melbourne Water approval
label | Reference: VicRoads Section 713 April 2017
section | Preliminaries - Materials
checkpoint | 2.1 Beaching Material
label | REFERENCE: 713.03 Section 713.03(a) IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CBR-5613
label | ACCEPTANCE CRITERIA: All rock beaching materials shall:
label | ○ comply with the material requirements for ‘sound’ rock in Section 801 and
label | ○ the Los Angeles Value (LAV) requirements of Table 801.033. and
label | ○ The rock shall have a minimum apparent particle density of 2.5 t/m3 and
label | ○ the rock beaching shall have a minimum wet strength of 100 kN and a wet/dry strength variation not exceeding 45%
label | ○ The rock beaching material shall be Type 5 - Melbourne Water waterway beaching and comply with criteria set out in IFC Drawings
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Prior to each use unless previously approved
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Bedding Material
label | REFERENCE: 713.03 Section 713.03(b)
label | ACCEPTANCE CRITERIA: The rock used for the granular filter layer is to be well graded and where a granular bedding is required, limited to 0-100 mm in size.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Prior to each use unless previously approved
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Beaching Placement Approval
label | REFERENCE: 713.05 Sect (a)
label | ACCEPTANCE CRITERIA: Prior to commencement of any work where placement of rock beaching is proposed, a detailed job safety assessment shall be undertaken by a suitably qualified and experienced professional and a suitable Safe Work Method Statement developed to cover all necessary elements.
label | ○ The completed job safety assessment and the Safe Work Method Statement shall be submitted to the Superintendent for review.
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: Site Safety manager
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
section | Pre-construction Activities
checkpoint | 4.1 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | METHOD: Document Review
label | FREQUENCY: Prior to starting Works and at regular intervals
label | CATEGORY: HP*
label | RESPONSIBILITY: All
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Confirmation of rock sizing
label | REFERENCE: Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613)
label | ACCEPTANCE CRITERIA: Ensure rocks being used are Type 5 with a minimum D50 of 400mm.
label | METHOD: Document Review, Measure
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Supervisor
label | VERIFYING DOCUMENTS: Delivery Dockets and test reports to be attached to this ITP
date | Date Completed:
checkpoint | 4.3 Confirmation of rock sizing
label | REFERENCE: Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613)
label | ACCEPTANCE CRITERIA: Toe rocks to be Type 5 with a 1m minimum diameter.
label | METHOD: Measure
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Supervisor
label | VERIFYING DOCUMENTS: Delivery Dockets and test reports to be attached to this ITP
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Preparation of Underlying Surface
label | REFERENCE: 713.04
label | ACCEPTANCE CRITERIA: Areas on which beaching is to be placed shall be compacted and trimmed as required to provide a finished surface level of beaching in accordance with the drawings. Any scours or hollows in the surface shall be filled with compacted Class 4 crushed rock.
label | ○ Trimmed material shall be removed from the site.
label | ○ For treatment of scours and hollows on or near Melbourne Water assets, contact Melbourne Water for the necessary treatment.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Toe Rock embedment
label | REFERENCE: 713.07 Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613)
label | ACCEPTANCE CRITERIA: Perimeter and toe edge rocks shall be trenched into in situ ground before bedding placement. Such rocks shall have 2/3 of the rock diameter embedded.
label | METHOD: Visual, Measure
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Bedding Placement
label | REFERENCE: 713.03 (b) IFC (MRP-091-C-BEC-DRG-00-DNG-CBR-5613)
label | ACCEPTANCE CRITERIA: Bedding to be placed as specified in IFC Drawings: – PSDS: 150 mm
label | METHOD: Measure
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Beaching Placement-Thichness
label | REFERENCE: Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613)
label | ACCEPTANCE CRITERIA: Thickness of placement to be 2 x D50. Rocks have min D50 of 400mm
label | METHOD: Measure
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Beaching Placement-embedment
label | REFERENCE: 713.05 Sect (a)
label | ACCEPTANCE CRITERIA: Beaching materials shall be firmly bedded on the prepared embankment and/or bedding if required and laid in courses commencing from the bottom of any slope.
label | ○ Un-grouted beaching and armour stone when placed shall form a tight ‘interlocking grid’, which shall prevent the removal of individual rocks.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Supervisor
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Type 5 Rock Beaching Placement-Surronding
label | REFERENCE: 713.05 Sect (f)
label | ACCEPTANCE CRITERIA: Rocks shall be placed to
label | ○ allow for the formation of a tightly interlocked rock mass in which the larger rocks are not free to move.
label | ○ All voids are to be sealed with smaller graded rock for stability and sufficient for water to flow over the top and not within or underneath the beaching.
label | ○ All leading and edge rocks shall finish flush with the surrounding ground level.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Type 5 Rock Beaching Placement-Surface
label | REFERENCE: 713.05 Sect (a)
label | ACCEPTANCE CRITERIA: The general surface of the finished beaching shall not vary from a 3 metre straight edge laid across the surface of the beaching by more than:
label | ○ 75 mm for Type 5 Beaching (unless otherwise specified by Melbourne Water Authority)
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Cleaning
label | REFERENCE: 713.09
label | ACCEPTANCE CRITERIA: On completion of the work, the beaching shall be cleaned to remove all foreign materials and discolouration from the beaching surface.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP