## Sheet1
FiberTite warm roof to CLT mechanically fixed and adhered
Tab | Tick Box
pre start | Area accessible
Edge protection and safety installed
Visual inspection of substrate ready for SWP
QA document received from previous trade from main contractor
CLT Substrate | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
installation of SA primer
Vapor control layer | Substrate clean, dry, free of debris
Z flashing installed
Install VCL over primer
VCL lapped with a minimum of 100mm side and end laps
Installation of SA primer
Insulation | VCL clean, dry, free of debris prior to install
VCL has been checked for damages and repaired
Closure flashings installed correctly
Install board adhesive in specified pattern
Specified insualtion board installed
Insulation board mechanically fixed with specified ficing patter
Boards tightly butted
Tapered EPS | Insulation boards clean and dry. Free from dirt/debris ready for adhesive
Install board adhesive in specified pattern
EPS board installed into adhesive
ILD system installed | ILD System installed as per specs
ILD test plate installed
HDP board | PIR clean, dry, free of debris prior to install
install board adhesive in specified pattern
HDP board installed in brick pattern where possible
FiberTite | Prime substrate where required
Adhesive installed to substrate
Laying of membrane into adhesive
Broom/rolling of membrane
Wipe and clean laps prior to welding
Test weld with welding machine
Probe of seam with QA hook
Sumps | Sealant installed to dropper flange under membrane
Membrane dressed in to outlets
Clamp/rings/basket installed
Flood test
ILD report | ILD report
Fiberclad flashing | Installed correctly according to specifications ( right way around )
Fixing and welding done according to specifications and details
Probe of seam with QA hook
Pressure bar installed | Installed correctly according to specifications ( right way around )
Fixings done according to specifications and details
Prime of Substrate where required
Sealant installed
Over flashings | Over flashings has a separation barrier
Fixings done according to specifications and details
Primer of Substrate
Sealant installed
Review and sign off | Area left clean and tidy
All installation work completed, checked and reviewed as per specifications
Client/main contractor sign off