## Sheet1
- | VERIFICATION ACTIVITY: | METHODS OR REFERENCE: | FREQUENCY: | ACCEPTANCE CRITERIA: | HOLD POINT: | RECORDS: | - | 2 | Pre-Construction Sign Offs | H | Sub-Contract and Supplier Agreements | Prior to commencement. | Document Review | Sub-Contract and Supplier Agreements to be agreed and signed | Subcontract and Supplier Agreements | 2 - Pre-Construction Sign Offs | ACTION (Hold, Monitor, Witness): H | DETAIL: Sub-Contract and Supplier Agreements | FREQUENCY: Prior to commencement. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed | RECORDS: Subcontract and Supplier Agreements | 2 - Pre-Construction Sign Offs | 2 | Survey Setout | Survey | Setout Kerb Alignment required to construct to design | Prior to commencement. | Survey | As per Construction Drawings HOLD POINT | Survey Receipt. | Site Engineer | 2 - Survey Setout | VERIFICATION ACTIVITY: Survey | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design | FREQUENCY: Prior to commencement. | ACCEPTANCE CRITERIA: Survey | HOLD POINT: As per Construction Drawings HOLD POINT | RECORDS: Survey Receipt. | ONSITE RESPONSIBILITY: Site Engineer | 2 - Survey Setout
[7 empty] | VERIFICATION ACTIVITY: | 3 | Design | H | Design is approved and Drawings are of the latest revision. | Prior to commencement. | Document Review | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Drawing Register. | 3 - Design | ACTION (Hold, Monitor, Witness): H | DETAIL: Design is approved and Drawings are of the latest revision. | FREQUENCY: Prior to commencement. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | RECORDS: Drawing Register. | ACTION (Hold, Monitor, Witness): H | 3 | Concrete Island | QA FORM | TDM Technical Standards - IS0001 and IS0002 | Each Site | Kerbs to be haunced with 20MPa Concrete | Inprocess Inspection | Photos | Site Engineer | 3 - Concrete Island | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - IS0001 and IS0002 | FREQUENCY: Each Site | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete | HOLD POINT: Inprocess Inspection | RECORDS: Photos | ONSITE RESPONSIBILITY: Site Engineer | VERIFICATION ACTIVITY: Survey
[7 empty] | METHODS OR REFERENCE: | 4 | Survey Setout | H | Setout Pipe Alignment and Service Locations with inlet CHAR(AMP) outlet points and inverts as required to construct to design | Prior to commencement. | Survey | As per Drawings: T18092 - R1-001 CHAR(AMP) Setout files | Survey Receipt. | 4 - Survey Setout | ACTION (Hold, Monitor, Witness): H | DETAIL: Setout Pipe Alignment and Service Locations with inlet CHAR(AMP) outlet points and inverts as required to construct to design | FREQUENCY: Prior to commencement. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey | CONFORMANCE CRITERIA: As per Drawings: T18092 - R1-001 CHAR(AMP) Setout files | RECORDS: Survey Receipt. | DETAIL: Sub-Contract and Supplier Agreements |  |  | QA FORM | TDM Technical Standards - IS0001 and IS0003 | Each Site | Basecourse to be 150mm min thickness of GAP65 | Inprocess Inspection | Photos | Site Engineer | - | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - IS0001 and IS0003 | FREQUENCY: Each Site | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65 | HOLD POINT: Inprocess Inspection | RECORDS: Photos | ONSITE RESPONSIBILITY: Site Engineer | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
[7 empty] | FREQUENCY: | 5 | Pipe and Manhole Material Compliance | H | Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards | Prior to commencement. | Document Review, Visual Inspection | Pipe shall be Check for freshyly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards CHAR(AMP) AC COP | Manufacturers Data Sheets, Delivery Dockets | 5 - Pipe and Manhole Material Compliance | ACTION (Hold, Monitor, Witness): H | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards | FREQUENCY: Prior to commencement. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection | CONFORMANCE CRITERIA: Pipe shall be Check for freshyly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards CHAR(AMP) AC COP | RECORDS: Manufacturers Data Sheets, Delivery Dockets | FREQUENCY: Prior to commencement. | 4 | Concrete Infill | QA FORM | TDM Technical Standards - IS0001 and IS0002 | Each Site | 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer | 4 - Concrete Infill | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - IS0001 and IS0002 | FREQUENCY: Each Site | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm | HOLD POINT: Inprocess Inspection | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record | ONSITE RESPONSIBILITY: Site Engineer | FREQUENCY: Prior to commencement.
[7 empty] | ACCEPTANCE CRITERIA: | 6 | Locate Existing Services by Hand Digging / Hydro Vac | H | Ensure all services conflicting with the line of trench have been exposed by hand digging. | Prior to commencement. | Potholing / Survey | All conflicts have been located. New services and / or conflicts to be advised to Project Manager. | GPR report Photos | 6 - Locate Existing Services by Hand Digging / Hydro Vac | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging. | FREQUENCY: Prior to commencement. | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager. | RECORDS: GPR report Photos | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review | [17 empty] | ACCEPTANCE CRITERIA: Survey
[7 empty] | HOLD POINT: | [15 empty] | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed | [17 empty] | HOLD POINT: As per Construction Drawings HOLD POINT
[7 empty] | RECORDS: | [15 empty] | RECORDS: Subcontract and Supplier Agreements | [17 empty] | RECORDS: Survey Receipt.
[23 empty] | 3 - Design | [17 empty] | ONSITE RESPONSIBILITY: Site Engineer
[23 empty] | ACTION (Hold, Monitor, Witness): H | [17 empty] | 3 - Concrete Island
[23 empty] | DETAIL: Design is approved and Drawings are of the latest revision. | [17 empty] | VERIFICATION ACTIVITY: QA FORM
[23 empty] | FREQUENCY: Prior to commencement. | [17 empty] | METHODS OR REFERENCE: TDM Technical Standards - IS0001 and IS0002
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review | [17 empty] | FREQUENCY: Each Site
[23 empty] | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | [17 empty] | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
[23 empty] | RECORDS: Drawing Register. | [17 empty] | HOLD POINT: Inprocess Inspection
[23 empty] | 4 - Survey Setout | [17 empty] | RECORDS: Photos
[23 empty] | ACTION (Hold, Monitor, Witness): H | [17 empty] | ONSITE RESPONSIBILITY: Site Engineer
[23 empty] | DETAIL: Setout Pipe Alignment and Service Locations with inlet CHAR(AMP) outlet points and inverts as required to construct to design | [17 empty] | -
[23 empty] | FREQUENCY: Prior to commencement. | [17 empty] | VERIFICATION ACTIVITY: QA FORM
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey | [17 empty] | METHODS OR REFERENCE: TDM Technical Standards - IS0001 and IS0003
[23 empty] | CONFORMANCE CRITERIA: As per Drawings: T18092 - R1-001 CHAR(AMP) Setout files | [17 empty] | FREQUENCY: Each Site
[23 empty] | RECORDS: Survey Receipt. | [17 empty] | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
[23 empty] | 5 - Pipe and Manhole Material Compliance | [17 empty] | HOLD POINT: Inprocess Inspection
[23 empty] | ACTION (Hold, Monitor, Witness): H | [17 empty] | RECORDS: Photos
[23 empty] | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards | [17 empty] | ONSITE RESPONSIBILITY: Site Engineer
[23 empty] | FREQUENCY: Prior to commencement. | [17 empty] | 4 - Concrete Infill
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection | [17 empty] | VERIFICATION ACTIVITY: QA FORM
[23 empty] | CONFORMANCE CRITERIA: Pipe shall be Check for freshyly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards CHAR(AMP) AC COP | [17 empty] | METHODS OR REFERENCE: TDM Technical Standards - IS0001 and IS0002
[23 empty] | RECORDS: Manufacturers Data Sheets, Delivery Dockets | [17 empty] | FREQUENCY: Each Site
[23 empty] | 6 - Locate Existing Services by Hand Digging / Hydro Vac | [17 empty] | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm
[23 empty] | ACTION (Hold, Monitor, Witness): H | [17 empty] | HOLD POINT: Inprocess Inspection
[23 empty] | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging. | [17 empty] | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
[23 empty] | FREQUENCY: Prior to commencement. | [17 empty] | ONSITE RESPONSIBILITY: Site Engineer
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
RECORDS: GPR report Photos