## ITP-025
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-049
[11 empty] | Revision : 001 | Date : 10/11/2021
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: New Preston Depot |  |  |  | Shear Stud Welding |  | Name:Aaron Hatch |  | Name: Charles Bate |  |  | Name:
Project No: 8B4000 |  |  |  | Specifications: AS/NZS 1554 Part 1&2 & AS4100, Contract Specifications
|  |  |  | Structure / Component: Bondek & Structural Beams |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Attach Lot Map |  | 2022-11-10 |  | Date : | 2022-11-10 |  | Date : | 2022-11-10
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and contractors are using the most current and complete set of drawings | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP Ensure that all employees and contractors involved in the welding process have been inducted onto the relevant Hotworks permit | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Materials Check |  | Prior to commencing any activity | Ensure the materials and equipment gathered are for the correct type (19mm thick, 95mm long) and steel grade (380) | Contract Drawings, AS4100 | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Welding Procedure Qualification |  | Each Welding Process | Ensure that the proposed welding procedure has been developed in accordance with the Contract Specifiactions and AS standard and is approved by the superintedent. Documentary evidence of the results of testing and an approved Welding Procedure Specification for each of the weld procedures to be used in the welding of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of welding. | Contract Specifications AS1554 Part 1&2 | Visual inspection | This ITP signed off | HP | Fulton Hogan Engineer Superintendent |  |  | N/A
2.2 | Setout | ` | Each Welds | Setout shall occur such that each shear stud is installed at the nominated spacings in the drawings | Contract Drawings | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Preparation |  | Each Weld | Each weld position shall be flat, sound clean metal and accepted by the stud contractor. Each weld position through bondek shall be flat betweem the bondek and the parent material ie. No air between the three surfaces | Contract Specification Welding Procedure | Visual inspection | This ITP signed off | IP | Fulton Hogan Engineer Subcontractor | N/A
2.4 | Welding |  | Each Lot & Crew | Ensure each weld is completed within the constraints of AS1554 and a daily welding checklist is completed and made available by the subcontractor stating all welding parameters. Bondek preparation shall coincide with recommendations outlined in the installation manual | Daily Weld Sheets Bondek Installation Guide | Verify | This ITP signed off | IP | Fulton Hogan Engineer Subcontractor | N/A |  | N/A
3 | Testing
3.1 | Weld Review & Testing |  | Each lot | Ensure weld is inspected and that a quality connection has been made. All welds shall be inspected by the stud contractor in the presence of a Fulton Hogan engineer and/or client representative once cooled to ambient temperature the following procedure: - 2 studs of a days production shall be bent to 30o - 100% of welds shall be visually scanned - 100% of welds shall give a clear ring when struck with a 1kg hammer in two opposite directions - Welds that do not give a clear ring shall be subject to the 10o bend test (stud shall be bent to 10o in one direction) Any studs proven to fail the above testing shall be removed and a new stud welded next to the failed area | Contract Specification | Visual & Audio Inspection | This ITP signed off, documented photos of testing | TP | Fulton Hogan Engineer Subcontractor Superintendent | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.