## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-049 - Shear Stud Welding | itp |  |  |  |  | ITP-049 - Shear Stud Welding
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | • Ensure that all employees and contractors involved in the welding process have been inducted onto the relevant Hotworks permit
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.3 Materials Check
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure the materials and equipment gathered are for the correct type (19mm thick, 95mm long) and steel grade (380)
label | REFERENCE DOCUMENTS: Contract Drawings, AS4100
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
section | Construction Works
checkpoint | 2.1 Welding Procedure Qualification
label | FREQUENCY: Each Welding Process
label | ACCEPTANCE CRITERIA: Ensure that the proposed welding procedure has been developed in accordance with the Contract Specifiactions and AS standard and is approved by the superintedent.
label | • Documentary evidence of the results of testing and an approved Welding Procedure Specification for each of the weld procedures to be used in the welding of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of welding.
label | REFERENCE DOCUMENTS: Contract Specifications AS1554 Part 1&2
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer, Superintendent
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Setout
label | FREQUENCY: Each Welds
label | ACCEPTANCE CRITERIA: Setout shall occur such that each shear stud is installed at the nominated spacings in the drawings
label | REFERENCE DOCUMENTS: Contract Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 2.3 Preparation
label | FREQUENCY: Each Weld
label | ACCEPTANCE CRITERIA: Each weld position shall be flat, sound clean metal and accepted by the stud contractor. Each weld position through bondek shall be flat betweem the bondek and the parent material ie. No air between the three surfaces
label | REFERENCE DOCUMENTS: Contract Specification Welding Procedure
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer, Subcontractor
text | Date Completed:
checkpoint | 2.4 Welding
label | FREQUENCY: Each Lot & Crew
label | ACCEPTANCE CRITERIA: Ensure each weld is completed within the constraints of AS1554 and a daily welding checklist is completed and made available by the subcontractor stating all welding parameters.
label | • Bondek preparation shall coincide with recommendations outlined in the installation manual
label | REFERENCE DOCUMENTS: Daily Weld Sheets, Bondek Installation Guide
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer, Subcontractor
text | Date Completed:
section | Testing
checkpoint | 3.1 Weld Review & Testing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure weld is inspected and that a quality connection has been made. All welds shall be inspected by the stud contractor in the presence of a Fulton Hogan engineer and/or client representative once cooled to ambient temperature the following procedure:
label | – 2 studs of a days production shall be bent to 30o
label | – 100% of welds shall be visually scanned
label | – 100% of welds shall give a clear ring when struck with a 1kg hammer in two opposite directions
label | – Welds that do not give a clear ring shall be subject to the 10o bend test (stud shall be bent to 10o in one direction)
label | • Any studs proven to fail the above testing shall be removed and a new stud welded next to the failed area
label | REFERENCE DOCUMENTS: Contract Specification
label | INSPECTION/TEST METHOD: Visual & Audio Inspection
label | RECORD OF CONFORMITY: This ITP signed off, documented photos of testing
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer, Subcontractor, Superintendent
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: